## Sheet1
| ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | project_name
4 | 0 | Telecom System Agnes | 2011-05-18 08:00 | 2011-07-15 17:00 | 43d |  |  | 72478.8701 |  |  | 180485.2701 |  | 53d | [5 empty] | 180485.2701 |  | 1 |  | 180485.2701 | 180485.2701 | C2011-05 Telecom System Agnes.xlsx
5 | 1 | order license | 2011-05-18 08:00 | 2011-05-20 17:00 | 3d | project leader | 2400 | 0 | 0 | 0 | 2400 | 2011-05-18 08:00 | 3d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 1 | Finished | 2400 | 2400 | C2011-05 Telecom System Agnes.xlsx
6 | 2 | final order | 2011-05-23 08:00 | 2011-05-23 17:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-05-23 08:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 1 | Finished | 800 | 800 | C2011-05 Telecom System Agnes.xlsx
7 | 3 | ordering equipment | 2011-05-24 08:00 | 2011-05-24 17:00 | 1d | procurement manager | 440 | 0 | 0 | 0 | 440 | 2011-05-24 08:00 | 1d | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 1 | Finished | 440 | 440 | C2011-05 Telecom System Agnes.xlsx
8 | 4 | discussion list | 2011-06-10 10:00 | 2011-06-13 10:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-06-10 10:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 1 | Finished | 800 | 800 | C2011-05 Telecom System Agnes.xlsx
9 | 5 | final discussion list | 2011-06-24 10:00 | 2011-06-27 10:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-06-24 10:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 1 | Finished | 800 | 800 | C2011-05 Telecom System Agnes.xlsx
10 | 6 | key technical area | 2011-05-24 09:00 | 2011-05-24 10:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-05-24 09:00 | 1h | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2011-05 Telecom System Agnes.xlsx
11 | 7 | technische ruimte klaar and DECT meting | 2011-05-24 10:00 | 2011-05-24 15:00 | 4h | technician[2.00 #3] | 368 | 9517.6396 | 0 | 0 | 9885.6396 | 2011-05-24 10:00 | 4h | 9885.6396 | 0 | 0 | 0 | 0 | 9885.6396 | 0 | 1 | Finished | 9885.6396 | 9885.6396 | C2011-05 Telecom System Agnes.xlsx
12 | 8 | installing 19" cabinets | 2011-05-25 08:00 | 2011-05-25 17:00 | 1d | technician[3.00 #3] | 1104 | 7722.6001 | 0 | 0 | 8826.6001 | 2011-05-25 08:00 | 1d | 8826.6001 | 0 | 0 | 0 | 0 | 8826.6001 | 0 | 1 | Finished | 8826.6001 | 8826.6001 | C2011-05 Telecom System Agnes.xlsx
13 | 9 | delivering and installing glassfiber | 2011-05-26 08:00 | 2011-06-20 17:00 | 18d | technician[3.00 #3] | 19872 | 878.05 | 0 | 0 | 20750.05 | 2011-05-26 08:00 | 18d | 20750.05 | 0 | 0 | 0 | 0 | 20750.05 | 0 | 1 | Finished | 20750.05 | 20750.05 | C2011-05 Telecom System Agnes.xlsx
14 | 10 | putting 69 UTP cables in resident rooms | 2011-05-31 08:00 | 2011-06-09 17:00 | 8d | subcontracted technicians[3.00 #9] | 10598.4 | 414 | 0 | 0 | 11012.4 | 2011-05-31 08:00 | 8d | 11012.4 | 0 | 0 | 0 | 0 | 11012.4 | 0 | 1 | Finished | 11012.4 | 11012.4 | C2011-05 Telecom System Agnes.xlsx
15 | 11 | putting UTP cables with DECT and MIVA toilet | 2011-06-01 13:00 | 2011-06-08 12:00 | 5d | subcontracted technicians[3.00 #9] | 6624 | 36 | 0 | 0 | 6660 | 2011-06-01 13:00 | 5d | 6660 | 0 | 0 | 0 | 0 | 6660 | 0 | 1 | Finished | 6660 | 6660 | C2011-05 Telecom System Agnes.xlsx
16 | 12 | delivering and installing I55 PABX | 2011-06-21 08:00 | 2011-06-27 17:00 | 5d | steeplejack;technician[3.00 #3] | 5720 | 8307.2803 | 0 | 0 | 14027.2803 | 2011-07-05 08:00 | 5d | 14027.2803 | 0 | 0 | 0 | 0 | 14027.2803 | 0 | 1 | Finished | 14027.2803 | 14027.2803 | C2011-05 Telecom System Agnes.xlsx
17 | 13 | programming telephone exchange (PABX) | 2011-06-28 08:00 | 2011-07-04 17:00 | 5d | programmer | 3200 | 1350 | 0 | 0 | 4550 | 2011-07-12 08:00 | 5d | 4550 | 0 | 0 | 0 | 0 | 4550 | 0 | 1 | Finished | 4550 | 4550 | C2011-05 Telecom System Agnes.xlsx
18 | 14 | delivering and installing NOVAbox, IMS, alarmconverter | 2011-06-10 08:00 | 2011-06-16 17:00 | 5d | subcontracted technicians[3.00 #9] | 6624 | 9201 | 0 | 0 | 15825 | 2011-06-10 08:00 | 5d | 15825 | 0 | 0 | 0 | 0 | 15825 | 0 | 1 | Finished | 15825 | 15825 | C2011-05 Telecom System Agnes.xlsx
19 | 15 | assemble nurse call units 69 pieces | 2011-06-17 08:00 | 2011-07-07 17:00 | 15d | subcontracted technicians[3.00 #9] | 19872 | 22770 | 0 | 0 | 42642 | 2011-06-17 08:00 | 15d | 42642 | 0 | 0 | 0 | 0 | 42642 | 0 | 1 | Finished | 42642 | 42642 | C2011-05 Telecom System Agnes.xlsx
20 | 16 | assembly and installation other components regarding nurse call units | 2011-06-17 08:00 | 2011-07-07 17:00 | 15d | subcontracted technicians[3.00 #9] | 19872 | 9888 | 0 | 0 | 29760 | 2011-06-17 08:00 | 15d | 29760 | 0 | 0 | 0 | 0 | 29760 | 0 | 1 | Finished | 29760 | 29760 | C2011-05 Telecom System Agnes.xlsx
21 | 17 | installing control location OSPC | 2011-07-08 08:00 | 2011-07-11 17:00 | 2d | programmer;technician[3.00 #3] | 3488 | 2393.3 | 0 | 0 | 5881.3 | 2011-07-22 08:00 | 2d | 5881.3 | 0 | 0 | 0 | 0 | 5881.3 | 0 | 1 | Finished | 5881.3 | 5881.3 | C2011-05 Telecom System Agnes.xlsx
22 | 18 | testing control location OSPC | 2011-07-12 08:00 | 2011-07-12 17:00 | 1d | programmer;technician | 1008 | 0 | 0 | 0 | 1008 | 2011-07-26 08:00 | 1d | 1008 | 0 | 0 | 0 | 0 | 1008 | 0 | 1 | Finished | 1008 | 1008 | C2011-05 Telecom System Agnes.xlsx
23 | 19 | nurses training 2 days | 2011-07-13 08:00 | 2011-07-14 17:00 | 2d | programmer | 1280 | 0 | 0 | 0 | 1280 | 2011-07-27 08:00 | 2d | 1280 | 0 | 0 | 0 | 0 | 1280 | 0 | 1 | Finished | 1280 | 1280 | C2011-05 Telecom System Agnes.xlsx
24 | 20 | prepare delivery | 2011-07-13 08:00 | 2011-07-14 17:00 | 2d | project leader;technician | 2336 | 0 | 0 | 0 | 2336 | 2011-07-27 09:00 | 2d | 2336 | 0 | 0 | 0 | 0 | 2336 | 0 | 1 | Finished | 2336 | 2336 | C2011-05 Telecom System Agnes.xlsx
25 | 21 | final delivery | 2011-07-15 08:00 | 2011-07-15 17:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-07-29 08:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 1 | Finished | 800 | 800 | C2011-05 Telecom System Agnes.xlsx
4 | 0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 444d | [5 empty] | 191065.06 |  | 1 |  | 180759.44 | 180759.44 | C2011-07 Patient Transport System.xlsx
5 | 50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 1 |  | 5512.64 | 5512.64 | C2011-07 Patient Transport System.xlsx
6 | 1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 1 | Finished | 125.12 | 125.12 | C2011-07 Patient Transport System.xlsx
7 | 2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 1 | Finished | 5137.28 | 5137.28 | C2011-07 Patient Transport System.xlsx
8 | 3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 1 | Finished | 250.24 | 250.24 | C2011-07 Patient Transport System.xlsx
9 | 51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 1 |  | 2478.88 | 2478.88 | C2011-07 Patient Transport System.xlsx
10 | 4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 1 | Finished | 2416.32 | 2416.32 | C2011-07 Patient Transport System.xlsx
11 | 5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 1 | Finished | 62.56 | 62.56 | C2011-07 Patient Transport System.xlsx
12 | 52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 1 |  | 2193.6 | 2193.6 | C2011-07 Patient Transport System.xlsx
13 | 6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 1 | Finished | 942.4 | 942.4 | C2011-07 Patient Transport System.xlsx
14 | 7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 1 | Finished | 500.48 | 500.48 | C2011-07 Patient Transport System.xlsx
15 | 8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 1 | Finished | 750.72 | 750.72 | C2011-07 Patient Transport System.xlsx
16 | 53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 1 |  | 3225.6 | 3225.6 | C2011-07 Patient Transport System.xlsx
17 | 9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 1 | Finished | 750.72 | 750.72 | C2011-07 Patient Transport System.xlsx
18 | 10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 1 | Finished | 1974.4 | 1974.4 | C2011-07 Patient Transport System.xlsx
19 | 11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 1 | Finished | 500.48 | 500.48 | C2011-07 Patient Transport System.xlsx
20 | 54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 72d | [5 empty] | 6834.56 |  | 1 |  | 6334.08 | 6334.08 | C2011-07 Patient Transport System.xlsx
21 | 12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 1 | Finished | 750.72 | 750.72 | C2011-07 Patient Transport System.xlsx
22 | 13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 1 | Finished | 4832.64 | 4832.64 | C2011-07 Patient Transport System.xlsx
23 | 14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 1 | Finished | 250.24 | 250.24 | C2011-07 Patient Transport System.xlsx
24 | 15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-09-15 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 1 | Finished | 500.48 | 500.48 | C2011-07 Patient Transport System.xlsx
25 | 55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 74d | [5 empty] | 3115.12 |  | 1 |  | 3115.12 | 3115.12 | C2011-07 Patient Transport System.xlsx
26 | 16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-09-17 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 1 | Finished | 750.72 | 750.72 | C2011-07 Patient Transport System.xlsx
27 | 17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 | 2010-11-15 13:00 | 4h | 1863.92 | 0 | 0 | 0 | 0 | 1863.92 | 0 | 1 | Finished | 1863.92 | 1863.92 | C2011-07 Patient Transport System.xlsx
28 | 18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-12-28 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 1 | Finished | 500.48 | 500.48 | C2011-07 Patient Transport System.xlsx
29 | 56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 4h | [5 empty] | 55373.52 |  | 1 |  | 55373.52 | 55373.52 | C2011-07 Patient Transport System.xlsx
30 | 19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 | 2011-01-05 08:00 | 4h | 55373.52 | 0 | 0 | 0 | 0 | 55373.52 | 0 | 1 | Finished | 55373.52 | 55373.52 | C2011-07 Patient Transport System.xlsx
31 | 57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 1 |  | 3460.8 | 3460.8 | C2011-07 Patient Transport System.xlsx
32 | 20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 1 | Finished | 2710.08 | 2710.08 | C2011-07 Patient Transport System.xlsx
33 | 21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 1 | Finished | 750.72 | 750.72 | C2011-07 Patient Transport System.xlsx
34 | 58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 48d 4h | [5 empty] | 2235.08 |  | 1 |  | 2235.08 | 2235.08 | C2011-07 Patient Transport System.xlsx
35 | 22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-11-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 1 | Finished | 500.48 | 500.48 | C2011-07 Patient Transport System.xlsx
36 | 23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2010-11-17 08:00 | 2h | 931.96 | 0 | 0 | 0 | 0 | 931.96 | 0 | 1 | Finished | 931.96 | 931.96 | C2011-07 Patient Transport System.xlsx
37 | 24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 | 2010-11-22 08:00 | 4h | 677.52 | 0 | 0 | 0 | 0 | 677.52 | 0 | 1 | Finished | 677.52 | 677.52 | C2011-07 Patient Transport System.xlsx
38 | 25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2011-01-10 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 1 | Finished | 125.12 | 125.12 | C2011-07 Patient Transport System.xlsx
39 | 59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 4h | [5 empty] | 18493.52 |  | 1 |  | 18493.52 | 18493.52 | C2011-07 Patient Transport System.xlsx
40 | 26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 | 2011-01-17 08:00 | 4h | 18493.52 | 0 | 0 | 0 | 0 | 18493.52 | 0 | 1 | Finished | 18493.52 | 18493.52 | C2011-07 Patient Transport System.xlsx
41 | 60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 1d | [5 empty] | 6408 |  | 1 |  | 6408 | 6408 | C2011-07 Patient Transport System.xlsx
42 | 27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 | 2011-01-20 08:00 | 2h | 1208.16 | 0 | 0 | 0 | 0 | 1208.16 | 0 | 1 | Finished | 1208.16 | 1208.16 | C2011-07 Patient Transport System.xlsx
43 | 28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 | 2011-01-20 15:00 | 2h | 5199.84 | 0 | 0 | 0 | 0 | 5199.84 | 0 | 1 | Finished | 5199.84 | 5199.84 | C2011-07 Patient Transport System.xlsx
44 | 61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 51d | [5 empty] | 7070.72 |  | 1 |  | 5303.04 | 5303.04 | C2011-07 Patient Transport System.xlsx
45 | 29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-01-21 08:00 | 6d | 2651.52 | 0 | 0 | 0 | 0 | 2651.52 | 0 | 1 | Finished | 2651.52 | 2651.52 | C2011-07 Patient Transport System.xlsx
46 | 30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-03-21 08:00 | 10d | 4419.2 | 0 | 0 | 0 | 0 | 4419.2 | 0 | 1 | Finished | 2651.52 | 2651.52 | C2011-07 Patient Transport System.xlsx
47 | 62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 161d | [5 empty] | 3250.72 |  | 1 |  | 3250.72 | 3250.72 | C2011-07 Patient Transport System.xlsx
48 | 31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-24 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 1 | Finished | 1250.24 | 1250.24 | C2011-07 Patient Transport System.xlsx
49 | 32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-27 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 1 | Finished | 1250.24 | 1250.24 | C2011-07 Patient Transport System.xlsx
50 | 33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 | 2011-09-05 08:00 | 1d | 750.24 | 0 | 0 | 0 | 0 | 750.24 | 0 | 1 | Finished | 750.24 | 750.24 | C2011-07 Patient Transport System.xlsx
51 | 63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 37d | [5 empty] | 10009.92 |  | 1 |  | 5476.16 | 5476.16 | C2011-07 Patient Transport System.xlsx
52 | 34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 | 2011-01-24 08:00 | 2d | 9067.52 | 0 | 0 | 0 | 0 | 9067.52 | 0 | 1 | Finished | 4533.76 | 4533.76 | C2011-07 Patient Transport System.xlsx
53 | 35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2011-03-14 08:00 | 2d | 942.4 | 0 | 0 | 0 | 0 | 942.4 | 0 | 1 | Finished | 942.4 | 942.4 | C2011-07 Patient Transport System.xlsx
54 | 64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 29d | [5 empty] | 3002.88 |  | 1 |  | 2502.4 | 2502.4 | C2011-07 Patient Transport System.xlsx
55 | 36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 | 2011-03-21 08:00 | 5d | 1251.2 | 0 | 0 | 0 | 0 | 1251.2 | 0 | 1 | Finished | 1000.96 | 1000.96 | C2011-07 Patient Transport System.xlsx
56 | 37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 | 2011-04-20 08:00 | 7d | 1751.68 | 0 | 0 | 0 | 0 | 1751.68 | 0 | 1 | Finished | 1501.44 | 1501.44 | C2011-07 Patient Transport System.xlsx
57 | 65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 12d | [5 empty] | 44101.12 |  | 1 |  | 44101.12 | 44101.12 | C2011-07 Patient Transport System.xlsx
58 | 38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 2011-05-02 08:00 | 2d | 4784 | 0 | 0 | 0 | 0 | 4784 | 0 | 1 | Finished | 4784 | 4784 | C2011-07 Patient Transport System.xlsx
59 | 39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 2011-05-04 08:00 | 2d | 4784 | 0 | 0 | 0 | 0 | 4784 | 0 | 1 | Finished | 4784 | 4784 | C2011-07 Patient Transport System.xlsx
60 | 40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 | 2011-05-06 08:00 | 2d | 9008.64 | 0 | 0 | 0 | 0 | 9008.64 | 0 | 1 | Finished | 9008.64 | 9008.64 | C2011-07 Patient Transport System.xlsx
61 | 41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-10 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 1 | Finished | 8508.16 | 8508.16 | C2011-07 Patient Transport System.xlsx
62 | 42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-12 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 1 | Finished | 8508.16 | 8508.16 | C2011-07 Patient Transport System.xlsx
63 | 43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-16 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 1 | Finished | 8508.16 | 8508.16 | C2011-07 Patient Transport System.xlsx
64 | 66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 16d | [5 empty] | 1355.04 |  | 1 |  | 1355.04 | 1355.04 | C2011-07 Patient Transport System.xlsx
65 | 44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2011-05-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 1 | Finished | 250.24 | 250.24 | C2011-07 Patient Transport System.xlsx
66 | 45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 | 2011-05-23 08:00 | 1d | 1104.8 | 0 | 0 | 0 | 0 | 1104.8 | 0 | 1 | Finished | 1104.8 | 1104.8 | C2011-07 Patient Transport System.xlsx
67 | 67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 71d | [5 empty] | 500 |  | 1 |  | 500 | 500 | C2011-07 Patient Transport System.xlsx
68 | 46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 | 2011-05-24 08:00 | 71d | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 1 | Finished | 500 | 500 | C2011-07 Patient Transport System.xlsx
69 | 68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 7d | [5 empty] | 11721.9 |  | 1 |  | 9440.12 | 9440.12 | C2011-07 Patient Transport System.xlsx
70 | 47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2011-09-06 08:00 | 5h | 2329.9 | 0 | 0 | 0 | 0 | 2329.9 | 0 | 1 | Finished | 931.96 | 931.96 | C2011-07 Patient Transport System.xlsx
71 | 48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 | 2011-09-13 08:00 | 4h | 8257.92 | 0 | 0 | 500 | 0 | 8757.92 | 0 | 1 | Finished | 8257.92 | 8257.92 | C2011-07 Patient Transport System.xlsx
72 | 49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2011-09-14 08:00 | 1d | 250.24 | 0 | 0 | 383.84 | 0 | 634.08 | 0 | 1 | Finished | 250.24 | 250.24 | C2011-07 Patient Transport System.xlsx
4 | 0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 202d 7h | [5 empty] | 494947.7125 |  | 1 |  | 484398.4125 | 484398.4125 | C2011-10 Building a House.xlsx
5 | 33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-10 Building a House.xlsx
6 | 1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 1 | Finished | 37032.6699 | 37032.6699 | C2011-10 Building a House.xlsx
7 | 2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 1 | Finished | 14744 | 14744 | C2011-10 Building a House.xlsx
8 | 3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 1 | Finished | 118606.9531 | 118606.9531 | C2011-10 Building a House.xlsx
9 | 4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 1 | Finished | 24205.5 | 24205.5 | C2011-10 Building a House.xlsx
10 | 5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 1 | Finished | 2420.55 | 2420.55 | C2011-10 Building a House.xlsx
11 | 6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 1 | Finished | 33575.2793 | 33575.2793 | C2011-10 Building a House.xlsx
12 | 7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 1 | Finished | 31715.5801 | 31715.5801 | C2011-10 Building a House.xlsx
13 | 8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 1 | Finished | 30520.5996 | 30520.5996 | C2011-10 Building a House.xlsx
14 | 9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 1 | Finished | 7630.1499 | 7630.1499 | C2011-10 Building a House.xlsx
15 | 10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 4d 1h | 12391.4102 | 0 | 0 | 0 | 0 | 12391.4102 | 0 | 1 | Finished | 12716.9102 | 12716.9102 | C2011-10 Building a House.xlsx
16 | 11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 2012-03-06 13:00 | 3d 5h | 10034.0303 | 0 | 0 | 0 | 0 | 10034.0303 | 0 | 1 | Finished | 10173.5303 | 10173.5303 | C2011-10 Building a House.xlsx
17 | 12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 1 | Finished | 7039.1001 | 7039.1001 | C2011-10 Building a House.xlsx
18 | 13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 10d 1h | 27213.5898 | 0 | 0 | 0 | 0 | 27213.5898 | 0 | 1 | Finished | 26748.5898 | 26748.5898 | C2011-10 Building a House.xlsx
19 | 14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 12d 6h | 4444 | 0 | 0 | 0 | 0 | 4444 | 0 | 1 | Finished | 3762 | 3762 | C2011-10 Building a House.xlsx
20 | 15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 2012-03-06 13:00 | 14d | 14123.2402 | 0 | 0 | 0 | 0 | 14123.2402 | 0 | 1 | Finished | 15983.2402 | 15983.2402 | C2011-10 Building a House.xlsx
21 | 16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 | 2012-03-14 13:00 | 20d 6h | 30692.5098 | 0 | 0 | 0 | 0 | 30692.5098 | 0 | 1 | Finished | 29669.5098 | 29669.5098 | C2011-10 Building a House.xlsx
22 | 17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 | 2012-04-20 10:00 | 5d 2h | 12715.0596 | 0 | 0 | 0 | 0 | 12715.0596 | 0 | 1 | Finished | 12622.0596 | 12622.0596 | C2011-10 Building a House.xlsx
23 | 18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 | 2012-04-27 13:00 | 2d 5h | 10185.9902 | 0 | 0 | 0 | 0 | 10185.9902 | 0 | 1 | Finished | 10371.9902 | 10371.9902 | C2011-10 Building a House.xlsx
24 | 19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 | 2012-05-04 09:00 | 7h | 2481.4 | 0 | 0 | 0 | 0 | 2481.4 | 0 | 1 | Finished | 2593 | 2593 | C2011-10 Building a House.xlsx
25 | 20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 | 2012-05-04 09:00 | 9d 1h | 8271.3544 | 0 | 0 | 0 | 0 | 8271.3544 | 0 | 1 | Finished | 8191.6402 | 8191.6402 | C2011-10 Building a House.xlsx
26 | 21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 | 2012-05-04 09:00 | 12d 3h | 4976.6916 | 0 | 0 | 0 | 0 | 4976.6916 | 0 | 1 | Finished | 4206.1201 | 4206.1201 | C2011-10 Building a House.xlsx
27 | 22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-04 09:00 | 4d 4h | 1278.7143 | 0 | 0 | 0 | 0 | 1278.7143 | 0 | 1 | Finished | 1881.0001 | 1881.0001 | C2011-10 Building a House.xlsx
28 | 23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 | 2012-05-24 13:00 | 6d 5h | 3364.8 | 0 | 0 | 0 | 0 | 3364.8 | 0 | 1 | Finished | 3876.3 | 3876.3 | C2011-10 Building a House.xlsx
29 | 24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 | 2012-06-05 09:00 | 1d 4h | 671.48 | 0 | 0 | 0 | 0 | 671.48 | 0 | 1 | Finished | 969.08 | 969.08 | C2011-10 Building a House.xlsx
30 | 25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 | 2012-05-21 10:00 | 17d 1h | 13770.9156 | 0 | 0 | 0 | 0 | 13770.9156 | 0 | 1 | Finished | 13106.6299 | 13106.6299 | C2011-10 Building a House.xlsx
31 | 26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 | 2012-05-24 13:00 | 4d | 6729.79 | 0 | 0 | 0 | 0 | 6729.79 | 0 | 1 | Finished | 6729.79 | 6729.79 | C2011-10 Building a House.xlsx
32 | 27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-10 14:00 | 13d | 2483.2858 | 0 | 0 | 0 | 0 | 2483.2858 | 0 | 1 | Finished | 1881.0001 | 1881.0001 | C2011-10 Building a House.xlsx
33 | 28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 | 2012-06-14 11:00 | 1d | 1638.33 | 0 | 0 | 0 | 0 | 1638.33 | 0 | 1 | Finished | 1638.33 | 1638.33 | C2011-10 Building a House.xlsx
34 | 29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 | 2012-05-31 13:00 | 6h | 841.22 | 0 | 0 | 0 | 0 | 841.22 | 0 | 1 | Finished | 841.22 | 841.22 | C2011-10 Building a House.xlsx
35 | 30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 | 2012-06-14 11:00 | 2d 4h | 2340.6801 | 0 | 0 | 0 | 0 | 2340.6801 | 0 | 1 | Finished | 2836.6801 | 2836.6801 | C2011-10 Building a House.xlsx
36 | 31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 | 2012-06-18 16:00 | 1d | 810.48 | 0 | 0 | 0 | 0 | 810.48 | 0 | 1 | Finished | 810.48 | 810.48 | C2011-10 Building a House.xlsx
37 | 32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 | 2012-06-18 16:00 | 4d | 4430.9299 | 0 | 0 | 0 | 0 | 4430.9299 | 0 | 1 | Finished | 5298.9299 | 5298.9299 | C2011-10 Building a House.xlsx
38 | 34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-06-22 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-10 Building a House.xlsx
4 | 0 | Claeys-Verhelst Premises | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.3057 |  |  | 3027133.1861 |  | 453d | [5 empty] | 3102395.9061 |  | 1 |  | 3027133.1861 | 3027133.1861 | C2011-12 Claeys-Verhelst Premises.xlsx
5 | 46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9701 |  |  | 253804.5701 |  | 214d | [5 empty] | 283418.6501 |  | 1 |  | 253804.5701 | 253804.5701 | C2011-12 Claeys-Verhelst Premises.xlsx
6 | 2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 75 | 75 | C2011-12 Claeys-Verhelst Premises.xlsx
7 | 3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 1 | Finished | 210000 | 210000 | C2011-12 Claeys-Verhelst Premises.xlsx
8 | 4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 1 | Finished | 3765.3101 | 3765.3101 | C2011-12 Claeys-Verhelst Premises.xlsx
9 | 5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 1 | Finished | 1876.54 | 1876.54 | C2011-12 Claeys-Verhelst Premises.xlsx
10 | 16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.01 | 0.01 | C2011-12 Claeys-Verhelst Premises.xlsx
11 | 6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.00 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 67701.79 | 0 | 0 | 0 | 0 | 67701.79 | 0 | 1 | Finished | 38087.71 | 38087.71 | C2011-12 Claeys-Verhelst Premises.xlsx
12 | 47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.894 |  |  | 401436.374 |  | 36d | [5 empty] | 402361.814 |  | 1 |  | 401436.374 | 401436.374 | C2011-12 Claeys-Verhelst Premises.xlsx
13 | 17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 29084.8 | 0 | 0 | 0 | 0 | 29084.8 | 0 | 1 | Finished | 30318.72 | 30318.72 | C2011-12 Claeys-Verhelst Premises.xlsx
14 | 69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.76 | 0 | 0 | 0 | 0 | 5701.76 | 0 | 1 | Finished | 2616.96 | 2616.96 | C2011-12 Claeys-Verhelst Premises.xlsx
15 | 18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4066 | 0 | 0 | 0 | 0 | 118883.4066 | 0 | 1 | Finished | 121659.7266 | 121659.7266 | C2011-12 Claeys-Verhelst Premises.xlsx
16 | 21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.00 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 12330.01 | 0 | 0 | 0 | 0 | 12330.01 | 0 | 1 | Finished | 10479.13 | 10479.13 | C2011-12 Claeys-Verhelst Premises.xlsx
17 | 23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.00 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 236361.8375 | 0 | 0 | 0 | 0 | 236361.8375 | 0 | 1 | Finished | 236361.8375 | 236361.8375 | C2011-12 Claeys-Verhelst Premises.xlsx
18 | 48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4531 |  |  | 542212.4531 |  | 45d | [5 empty] | 523703.6531 |  | 1 |  | 542212.4531 | 542212.4531 | C2011-12 Claeys-Verhelst Premises.xlsx
19 | 19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.00 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 137501.3078 | 0 | 0 | 0 | 0 | 137501.3078 | 0 | 1 | Finished | 143670.9078 | 143670.9078 | C2011-12 Claeys-Verhelst Premises.xlsx
20 | 20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.00 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 123579.3188 | 0 | 0 | 0 | 0 | 123579.3188 | 0 | 1 | Finished | 129748.9187 | 129748.9187 | C2011-12 Claeys-Verhelst Premises.xlsx
21 | 22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.00 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 132874.1078 | 0 | 0 | 0 | 0 | 132874.1078 | 0 | 1 | Finished | 132874.1078 | 132874.1078 | C2011-12 Claeys-Verhelst Premises.xlsx
22 | 24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.00 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 129748.9187 | 0 | 0 | 0 | 0 | 129748.9187 | 0 | 1 | Finished | 135918.5187 | 135918.5187 | C2011-12 Claeys-Verhelst Premises.xlsx
23 | 50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1641 |  |  | 597047.364 |  | 112d | [5 empty] | 671831.364 |  | 1 |  | 597047.364 | 597047.364 | C2011-12 Claeys-Verhelst Premises.xlsx
24 | 25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.00 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2007-06-04 08:00 | 20d | 351653.2 | 0 | 0 | 0 | 0 | 351653.2 | 0 | 1 | Finished | 351653.2 | 351653.2 | C2011-12 Claeys-Verhelst Premises.xlsx
25 | 26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 234654.5938 | 0 | 0 | 0 | 0 | 234654.5938 | 0 | 1 | Finished | 159870.5938 | 159870.5938 | C2011-12 Claeys-Verhelst Premises.xlsx
26 | 49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.00 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2007-06-04 08:00 | 10d | 85523.5703 | 0 | 0 | 0 | 0 | 85523.5703 | 0 | 1 | Finished | 85523.5703 | 85523.5703 | C2011-12 Claeys-Verhelst Premises.xlsx
27 | 62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9609 |  |  | 301814.5611 |  | 65d | [5 empty] | 291542.5611 |  | 1 |  | 301814.5611 | 301814.5611 | C2011-12 Claeys-Verhelst Premises.xlsx
28 | 28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.00 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2007-07-25 08:00 | 5d | 142112 | 0 | 0 | 0 | 0 | 142112 | 0 | 1 | Finished | 149824 | 149824 | C2011-12 Claeys-Verhelst Premises.xlsx
29 | 30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 1 | Finished | 7673 | 7673 | C2011-12 Claeys-Verhelst Premises.xlsx
30 | 27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 37704.9611 | 0 | 0 | 0 | 0 | 37704.9611 | 0 | 1 | Finished | 37704.9611 | 37704.9611 | C2011-12 Claeys-Verhelst Premises.xlsx
31 | 59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2007-08-29 08:00 | 20d | 18563 | 0 | 0 | 0 | 0 | 18563 | 0 | 1 | Finished | 18563 | 18563 | C2011-12 Claeys-Verhelst Premises.xlsx
32 | 29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-02 08:00 | 15d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 1 | Finished | 6400 | 6400 | C2011-12 Claeys-Verhelst Premises.xlsx
33 | 35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2007-09-26 08:00 | 20d | 81649.6 | 0 | 0 | 0 | 0 | 81649.6 | 0 | 1 | Finished | 81649.6 | 81649.6 | C2011-12 Claeys-Verhelst Premises.xlsx
34 | 66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 |  | 10d | [5 empty] | 0.01 |  | 1 |  | 0.01 | 0.01 | C2011-12 Claeys-Verhelst Premises.xlsx
35 | 31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-08-08 08:00 | 10d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.01 | 0.01 | C2011-12 Claeys-Verhelst Premises.xlsx
36 | 63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9709 |  |  | 262542.5712 |  | 45d | [5 empty] | 262542.5712 |  | 1 |  | 262542.5712 | 262542.5712 | C2011-12 Claeys-Verhelst Premises.xlsx
37 | 52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 1 | Finished | 7673 | 7673 | C2011-12 Claeys-Verhelst Premises.xlsx
38 | 45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 37704.9611 | 0 | 0 | 0 | 0 | 37704.9611 | 0 | 1 | Finished | 37704.9611 | 37704.9611 | C2011-12 Claeys-Verhelst Premises.xlsx
39 | 34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.00 #3] | 0 | 106140 | 0 | 0 | 106140 | 2007-08-29 08:00 | 15d | 106140 | 0 | 0 | 0 | 0 | 106140 | 0 | 1 | Finished | 106140 | 106140 | C2011-12 Claeys-Verhelst Premises.xlsx
40 | 60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2007-08-29 08:00 | 20d | 25475.0001 | 0 | 0 | 0 | 0 | 25475.0001 | 0 | 1 | Finished | 25475.0001 | 25475.0001 | C2011-12 Claeys-Verhelst Premises.xlsx
41 | 51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 25d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 1 | Finished | 6400 | 6400 | C2011-12 Claeys-Verhelst Premises.xlsx
42 | 67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.01 | 0.01 | C2011-12 Claeys-Verhelst Premises.xlsx
43 | 57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2007-10-03 08:00 | 20d | 79149.6 | 0 | 0 | 0 | 0 | 79149.6 | 0 | 1 | Finished | 79149.6 | 79149.6 | C2011-12 Claeys-Verhelst Premises.xlsx
44 | 64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9709 |  |  | 149562.5709 |  | 40d | [5 empty] | 148282.5709 |  | 1 |  | 149562.5709 | 149562.5709 | C2011-12 Claeys-Verhelst Premises.xlsx
45 | 53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 1 | Finished | 7673 | 7673 | C2011-12 Claeys-Verhelst Premises.xlsx
46 | 55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2007-08-29 08:00 | 10d | 34452.9609 | 0 | 0 | 0 | 0 | 34452.9609 | 0 | 1 | Finished | 34452.9609 | 34452.9609 | C2011-12 Claeys-Verhelst Premises.xlsx
47 | 56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2007-08-29 08:00 | 15d | 46116 | 0 | 0 | 0 | 0 | 46116 | 0 | 1 | Finished | 46116 | 46116 | C2011-12 Claeys-Verhelst Premises.xlsx
48 | 61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2007-08-29 08:00 | 20d | 16771 | 0 | 0 | 0 | 0 | 16771 | 0 | 1 | Finished | 16771 | 16771 | C2011-12 Claeys-Verhelst Premises.xlsx
49 | 54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 20d | 5120 | 0 | 0 | 0 | 0 | 5120 | 0 | 1 | Finished | 6400 | 6400 | C2011-12 Claeys-Verhelst Premises.xlsx
50 | 68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.01 | 0.01 | C2011-12 Claeys-Verhelst Premises.xlsx
51 | 58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2007-09-26 08:00 | 20d | 38149.6 | 0 | 0 | 0 | 0 | 38149.6 | 0 | 1 | Finished | 38149.6 | 38149.6 | C2011-12 Claeys-Verhelst Premises.xlsx
52 | 65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9116 |  |  | 518712.7116 |  | 48d | [5 empty] | 518712.7116 |  | 1 |  | 518712.7116 | 518712.7116 | C2011-12 Claeys-Verhelst Premises.xlsx
53 | 32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.00 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2007-11-05 08:00 | 15d | 23538.8 | 0 | 0 | 0 | 0 | 23538.8 | 0 | 1 | Finished | 23538.8 | 23538.8 | C2011-12 Claeys-Verhelst Premises.xlsx
54 | 36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2007-11-05 08:00 | 25d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 1 | Finished | 48000 | 48000 | C2011-12 Claeys-Verhelst Premises.xlsx
55 | 41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2007-11-26 08:00 | 20d | 87000 | 0 | 0 | 0 | 0 | 87000 | 0 | 1 | Finished | 87000 | 87000 | C2011-12 Claeys-Verhelst Premises.xlsx
56 | 37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2007-11-26 08:00 | 15d | 2156.0601 | 0 | 0 | 0 | 0 | 2156.0601 | 0 | 1 | Finished | 2156.0601 | 2156.0601 | C2011-12 Claeys-Verhelst Premises.xlsx
57 | 44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2007-12-10 08:00 | 10d | 33000 | 0 | 0 | 0 | 0 | 33000 | 0 | 1 | Finished | 33000 | 33000 | C2011-12 Claeys-Verhelst Premises.xlsx
58 | 42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2007-12-10 08:00 | 10d | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 | 1 | Finished | 16000 | 16000 | C2011-12 Claeys-Verhelst Premises.xlsx
59 | 43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2007-12-10 08:00 | 5d | 38817.8516 | 0 | 0 | 0 | 0 | 38817.8516 | 0 | 1 | Finished | 38817.8516 | 38817.8516 | C2011-12 Claeys-Verhelst Premises.xlsx
60 | 38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2007-12-10 08:00 | 5d | 32000 | 0 | 0 | 0 | 0 | 32000 | 0 | 1 | Finished | 32000 | 32000 | C2011-12 Claeys-Verhelst Premises.xlsx
61 | 39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.00 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2007-12-17 08:00 | 15d | 99800 | 0 | 0 | 0 | 0 | 99800 | 0 | 1 | Finished | 99800 | 99800 | C2011-12 Claeys-Verhelst Premises.xlsx
62 | 40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.00 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2008-01-03 08:00 | 5d | 138400 | 0 | 0 | 0 | 0 | 138400 | 0 | 1 | Finished | 138400 | 138400 | C2011-12 Claeys-Verhelst Premises.xlsx
4 | 0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 600d | [5 empty] | 26077764.7403 |  | 1 |  | 21369835.5102 | 21369835.5102 | C2011-13 Wind Farm.xlsx
5 | 1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 600d | [5 empty] | 26077764.7403 |  | 1 |  | 21369835.5102 | 21369835.5102 | C2011-13 Wind Farm.xlsx
6 | 2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2011-13 Wind Farm.xlsx
7 | 3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started | 0 | 0 | C2011-13 Wind Farm.xlsx
8 | 4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started | 0 | 0 | C2011-13 Wind Farm.xlsx
9 | 5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started | 0 | 0 | C2011-13 Wind Farm.xlsx
10 | 6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 1 |  | 309795.0755 | 309795.0755 | C2011-13 Wind Farm.xlsx
11 | 7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 1 |  | 30387.9796 | 30387.9796 | C2011-13 Wind Farm.xlsx
12 | 8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 1 | Finished | 6365.2998 | 6365.2998 | C2011-13 Wind Farm.xlsx
13 | 9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 1 | Finished | 15511.0999 | 15511.0999 | C2011-13 Wind Farm.xlsx
14 | 10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 1 | Finished | 8511.58 | 8511.58 | C2011-13 Wind Farm.xlsx
15 | 11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 1 |  | 147808.2721 | 147808.2721 | C2011-13 Wind Farm.xlsx
16 | 12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 1 | Finished | 61333.6209 | 61333.6209 | C2011-13 Wind Farm.xlsx
17 | 13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 1 | Finished | 53284.4719 | 53284.4719 | C2011-13 Wind Farm.xlsx
18 | 14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 1 | Finished | 33190.1793 | 33190.1793 | C2011-13 Wind Farm.xlsx
19 | 15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 1 |  | 131598.8237 | 131598.8237 | C2011-13 Wind Farm.xlsx
20 | 16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 1 | Finished | 16511.74 | 16511.74 | C2011-13 Wind Farm.xlsx
21 | 17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 1 | Finished | 16511.74 | 16511.74 | C2011-13 Wind Farm.xlsx
22 | 18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 1 | Finished | 98575.3438 | 98575.3438 | C2011-13 Wind Farm.xlsx
23 | 19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 1 |  | 1216717.082 | 1216717.082 | C2011-13 Wind Farm.xlsx
24 | 20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 1 | Finished | 1111351.7812 | 1111351.7812 | C2011-13 Wind Farm.xlsx
25 | 21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 1 | Finished | 52682.6504 | 52682.6504 | C2011-13 Wind Farm.xlsx
26 | 22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 1 | Finished | 52682.6504 | 52682.6504 | C2011-13 Wind Farm.xlsx
27 | 23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 1 |  | 1546009.5554 | 1546009.5554 | C2011-13 Wind Farm.xlsx
28 | 24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 1 | Finished | 2682.6499 | 2682.6499 | C2011-13 Wind Farm.xlsx
29 | 25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 1 |  | 508182.6572 | 508182.6572 | C2011-13 Wind Farm.xlsx
30 | 26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 1 | Finished | 72597.5225 | 72597.5225 | C2011-13 Wind Farm.xlsx
31 | 27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 1 | Finished | 72597.5225 | 72597.5225 | C2011-13 Wind Farm.xlsx
32 | 28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 1 | Finished | 72597.5225 | 72597.5225 | C2011-13 Wind Farm.xlsx
33 | 29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 1 | Finished | 72597.5225 | 72597.5225 | C2011-13 Wind Farm.xlsx
34 | 30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 1 | Finished | 72597.5225 | 72597.5225 | C2011-13 Wind Farm.xlsx
35 | 31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 1 | Finished | 72597.5225 | 72597.5225 | C2011-13 Wind Farm.xlsx
36 | 32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 1 | Finished | 72597.5225 | 72597.5225 | C2011-13 Wind Farm.xlsx
37 | 33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 1 |  | 1035144.1782 | 1035144.1782 | C2011-13 Wind Farm.xlsx
38 | 34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 1 | Finished | 147877.7397 | 147877.7397 | C2011-13 Wind Farm.xlsx
39 | 35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 1 | Finished | 147877.7397 | 147877.7397 | C2011-13 Wind Farm.xlsx
40 | 36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 1 | Finished | 147877.7397 | 147877.7397 | C2011-13 Wind Farm.xlsx
41 | 37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 1 | Finished | 147877.7397 | 147877.7397 | C2011-13 Wind Farm.xlsx
42 | 38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 1 | Finished | 147877.7397 | 147877.7397 | C2011-13 Wind Farm.xlsx
43 | 39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 1 | Finished | 147877.7397 | 147877.7397 | C2011-13 Wind Farm.xlsx
44 | 40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 1 | Finished | 147877.7397 | 147877.7397 | C2011-13 Wind Farm.xlsx
45 | 41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 1 |  | 0.07 | 0.07 | C2011-13 Wind Farm.xlsx
46 | 42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.01 | 0.01 | C2011-13 Wind Farm.xlsx
47 | 43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.01 | 0.01 | C2011-13 Wind Farm.xlsx
48 | 44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.01 | 0.01 | C2011-13 Wind Farm.xlsx
49 | 45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.01 | 0.01 | C2011-13 Wind Farm.xlsx
50 | 46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.01 | 0.01 | C2011-13 Wind Farm.xlsx
51 | 47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.01 | 0.01 | C2011-13 Wind Farm.xlsx
52 | 48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.01 | 0.01 | C2011-13 Wind Farm.xlsx
53 | 49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 161d | [5 empty] | 19215679.6007 |  | 1 |  | 16784528.0629 | 16784528.0629 | C2011-13 Wind Farm.xlsx
54 | 50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 1 |  | 7401145.5 | 7401145.5 | C2011-13 Wind Farm.xlsx
55 | 51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 1 |  | 1057306.5 | 1057306.5 | C2011-13 Wind Farm.xlsx
56 | 52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
57 | 53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 1 | Finished | 660816.5742 | 660816.5742 | C2011-13 Wind Farm.xlsx
58 | 54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
59 | 55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
60 | 56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
61 | 57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 1 |  | 1057306.5 | 1057306.5 | C2011-13 Wind Farm.xlsx
62 | 58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
63 | 59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 1 | Finished | 660816.5742 | 660816.5742 | C2011-13 Wind Farm.xlsx
64 | 60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
65 | 61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
66 | 62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
67 | 63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 1 |  | 1057306.5 | 1057306.5 | C2011-13 Wind Farm.xlsx
68 | 64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
69 | 65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 1 | Finished | 660816.5742 | 660816.5742 | C2011-13 Wind Farm.xlsx
70 | 66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
71 | 67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
72 | 68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
73 | 69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 1 |  | 1057306.5 | 1057306.5 | C2011-13 Wind Farm.xlsx
74 | 70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
75 | 71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 1 | Finished | 660816.5742 | 660816.5742 | C2011-13 Wind Farm.xlsx
76 | 72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
77 | 73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
78 | 74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
79 | 75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 1 |  | 1057306.5 | 1057306.5 | C2011-13 Wind Farm.xlsx
80 | 76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
81 | 77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 1 | Finished | 660816.5742 | 660816.5742 | C2011-13 Wind Farm.xlsx
82 | 78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
83 | 79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
84 | 80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
85 | 81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 1 |  | 1057306.5 | 1057306.5 | C2011-13 Wind Farm.xlsx
86 | 82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
87 | 83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 1 | Finished | 660816.5742 | 660816.5742 | C2011-13 Wind Farm.xlsx
88 | 84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
89 | 85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
90 | 86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
91 | 87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 1 |  | 1057306.5 | 1057306.5 | C2011-13 Wind Farm.xlsx
92 | 88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
93 | 89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 1 | Finished | 660816.5742 | 660816.5742 | C2011-13 Wind Farm.xlsx
94 | 90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
95 | 91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
96 | 92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 1 | Finished | 132163.3086 | 132163.3086 | C2011-13 Wind Farm.xlsx
97 | 93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 70d | [5 empty] | 10853878.2461 |  | 1 |  | 8828045.3242 | 8828045.3242 | C2011-13 Wind Farm.xlsx
98 | 94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 1 | Finished | 1261149.332 | 1261149.332 | C2011-13 Wind Farm.xlsx
99 | 95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 1 | Finished | 1261149.332 | 1261149.332 | C2011-13 Wind Farm.xlsx
100 | 96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 1 | Finished | 1261149.332 | 1261149.332 | C2011-13 Wind Farm.xlsx
101 | 97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 1 | Finished | 1261149.332 | 1261149.332 | C2011-13 Wind Farm.xlsx
102 | 98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 1 | Finished | 1261149.332 | 1261149.332 | C2011-13 Wind Farm.xlsx
103 | 99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-01 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 1 | Finished | 1261149.332 | 1261149.332 | C2011-13 Wind Farm.xlsx
104 | 100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-15 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 1 | Finished | 1261149.332 | 1261149.332 | C2011-13 Wind Farm.xlsx
105 | 101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 21d | [5 empty] | 180995.9948 |  | 1 |  | 174401.0146 | 174401.0146 | C2011-13 Wind Farm.xlsx
106 | 102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-22 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 1 | Finished | 24914.4307 | 24914.4307 | C2011-13 Wind Farm.xlsx
107 | 103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-25 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 1 | Finished | 24914.4307 | 24914.4307 | C2011-13 Wind Farm.xlsx
108 | 104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-30 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 1 | Finished | 24914.4307 | 24914.4307 | C2011-13 Wind Farm.xlsx
109 | 105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-03 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 1 | Finished | 24914.4307 | 24914.4307 | C2011-13 Wind Farm.xlsx
110 | 106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-08 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 1 | Finished | 24914.4307 | 24914.4307 | C2011-13 Wind Farm.xlsx
111 | 107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-13 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 1 | Finished | 24914.4307 | 24914.4307 | C2011-13 Wind Farm.xlsx
112 | 108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-16 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 1 | Finished | 24914.4307 | 24914.4307 | C2011-13 Wind Farm.xlsx
113 | 109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 28d | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2011-13 Wind Farm.xlsx
114 | 110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-25 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
115 | 111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
116 | 112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
117 | 113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
118 | 114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
119 | 115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
120 | 116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
121 | 117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 33d | [5 empty] | 278728.7237 |  | 1 |  | 167933.8461 | 167933.8461 | C2011-13 Wind Farm.xlsx
122 | 118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-25 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 1 | Finished | 23990.5494 | 23990.5494 | C2011-13 Wind Farm.xlsx
123 | 119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-30 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 1 | Finished | 23990.5494 | 23990.5494 | C2011-13 Wind Farm.xlsx
124 | 120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-03 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 1 | Finished | 23990.5494 | 23990.5494 | C2011-13 Wind Farm.xlsx
125 | 121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-08 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 1 | Finished | 23990.5494 | 23990.5494 | C2011-13 Wind Farm.xlsx
126 | 122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-13 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 1 | Finished | 23990.5494 | 23990.5494 | C2011-13 Wind Farm.xlsx
127 | 123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-16 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 1 | Finished | 23990.5494 | 23990.5494 | C2011-13 Wind Farm.xlsx
128 | 124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2011-01-04 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 1 | Finished | 23990.5494 | 23990.5494 | C2011-13 Wind Farm.xlsx
129 | 125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 41d | [5 empty] | 50670.551 |  | 1 |  | 48824.231 | 48824.231 | C2011-13 Wind Farm.xlsx
130 | 126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-02 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 1 | Finished | 6974.8901 | 6974.8901 | C2011-13 Wind Farm.xlsx
131 | 127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-07 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 1 | Finished | 6974.8901 | 6974.8901 | C2011-13 Wind Farm.xlsx
132 | 128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-10 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 1 | Finished | 6974.8901 | 6974.8901 | C2011-13 Wind Farm.xlsx
133 | 129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-15 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 1 | Finished | 6974.8901 | 6974.8901 | C2011-13 Wind Farm.xlsx
134 | 130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-03 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 1 | Finished | 6974.8901 | 6974.8901 | C2011-13 Wind Farm.xlsx
135 | 131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-06 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 1 | Finished | 6974.8901 | 6974.8901 | C2011-13 Wind Farm.xlsx
136 | 132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-11 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 1 | Finished | 6974.8901 | 6974.8901 | C2011-13 Wind Farm.xlsx
137 | 133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 20d | [5 empty] | 170386.5168 |  | 1 |  | 164178.147 | 164178.147 | C2011-13 Wind Farm.xlsx
138 | 134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-04 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 1 | Finished | 23454.021 | 23454.021 | C2011-13 Wind Farm.xlsx
139 | 135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-07 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 1 | Finished | 23454.021 | 23454.021 | C2011-13 Wind Farm.xlsx
140 | 136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-12 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 1 | Finished | 23454.021 | 23454.021 | C2011-13 Wind Farm.xlsx
141 | 137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-17 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 1 | Finished | 23454.021 | 23454.021 | C2011-13 Wind Farm.xlsx
142 | 138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-20 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 1 | Finished | 23454.021 | 23454.021 | C2011-13 Wind Farm.xlsx
143 | 139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-25 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 1 | Finished | 23454.021 | 23454.021 | C2011-13 Wind Farm.xlsx
144 | 140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-28 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 1 | Finished | 23454.021 | 23454.021 | C2011-13 Wind Farm.xlsx
145 | 141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2011-13 Wind Farm.xlsx
146 | 142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
147 | 143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
148 | 144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
149 | 145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
150 | 146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
151 | 147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
152 | 148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
153 | 149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 1 |  | 650046.796 | 650046.796 | C2011-13 Wind Farm.xlsx
154 | 150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 1 |  | 650046.796 | 650046.796 | C2011-13 Wind Farm.xlsx
155 | 151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 1 | Finished | 49073.0586 | 49073.0586 | C2011-13 Wind Farm.xlsx
156 | 152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
157 | 153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 1 | Finished | 100536.5312 | 100536.5312 | C2011-13 Wind Farm.xlsx
158 | 154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 1 | Finished | 115511.8975 | 115511.8975 | C2011-13 Wind Farm.xlsx
159 | 155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 1 | Finished | 223511.8994 | 223511.8994 | C2011-13 Wind Farm.xlsx
160 | 156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 2010-11-01 08:00 | 5d | 48047.9502 | 0 | 0 | 0 | 0 | 48047.9502 | 0 | 1 | Finished | 48047.9502 | 48047.9502 | C2011-13 Wind Farm.xlsx
161 | 157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 | 2010-11-08 08:00 | 3d | 73609.59 | 0 | 0 | 0 | 0 | 73609.59 | 0 | 1 | Finished | 73609.59 | 73609.59 | C2011-13 Wind Farm.xlsx
162 | 158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 | 2010-11-11 08:00 | 7d | 39755.8691 | 0 | 0 | -18000 | 0 | 21755.8691 | 0 | 1 | Finished | 39755.8691 | 39755.8691 | C2011-13 Wind Farm.xlsx
163 | 159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
164 | 160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 1 |  | 862738.9385 | 862738.9385 | C2011-13 Wind Farm.xlsx
165 | 161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 1 |  | 862738.9385 | 862738.9385 | C2011-13 Wind Farm.xlsx
166 | 162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
167 | 163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 1 | Finished | 295627.5957 | 295627.5957 | C2011-13 Wind Farm.xlsx
168 | 164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 1 | Finished | 284896.9961 | 284896.9961 | C2011-13 Wind Farm.xlsx
169 | 165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 1 | Finished | 282214.3467 | 282214.3467 | C2011-13 Wind Farm.xlsx
170 | 166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2011-13 Wind Farm.xlsx
4 | 0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 140d | [5 empty] | 350511.3094 |  | 1 |  | 336410.1494 | 336410.1494 | C2012-13 Pumping Station Jabbeke.xlsx
5 | 1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 1 | Finished | 3600 | 3600 | C2012-13 Pumping Station Jabbeke.xlsx
6 | 2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 1 | Finished | 10800 | 10800 | C2012-13 Pumping Station Jabbeke.xlsx
7 | 3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 1 | Finished | 18200 | 18200 | C2012-13 Pumping Station Jabbeke.xlsx
8 | 4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 1 | Finished | 15950 | 15950 | C2012-13 Pumping Station Jabbeke.xlsx
9 | 5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 1 | Finished | 5175 | 5175 | C2012-13 Pumping Station Jabbeke.xlsx
10 | 6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 1 | Finished | 22250 | 22250 | C2012-13 Pumping Station Jabbeke.xlsx
11 | 7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 1 | Finished | 1032 | 1032 | C2012-13 Pumping Station Jabbeke.xlsx
12 | 8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 1 | Finished | 750 | 750 | C2012-13 Pumping Station Jabbeke.xlsx
13 | 9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 1 | Finished | 790 | 790 | C2012-13 Pumping Station Jabbeke.xlsx
14 | 10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 1 | Finished | 1860 | 1860 | C2012-13 Pumping Station Jabbeke.xlsx
15 | 11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 1 | Finished | 4809 | 4809 | C2012-13 Pumping Station Jabbeke.xlsx
16 | 12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 1 | Finished | 8943.52 | 8943.52 | C2012-13 Pumping Station Jabbeke.xlsx
17 | 13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 1 | Finished | 5341 | 5341 | C2012-13 Pumping Station Jabbeke.xlsx
18 | 14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 1 | Finished | 4865 | 4865 | C2012-13 Pumping Station Jabbeke.xlsx
19 | 15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 1 | Finished | 14536 | 14536 | C2012-13 Pumping Station Jabbeke.xlsx
20 | 16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 1 | Finished | 5634 | 5634 | C2012-13 Pumping Station Jabbeke.xlsx
21 | 17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 1 | Finished | 9216 | 9216 | C2012-13 Pumping Station Jabbeke.xlsx
22 | 18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 1 | Finished | 1042 | 1042 | C2012-13 Pumping Station Jabbeke.xlsx
23 | 19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 1 | Finished | 4567 | 4567 | C2012-13 Pumping Station Jabbeke.xlsx
24 | 20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 1 | Finished | 6589 | 6589 | C2012-13 Pumping Station Jabbeke.xlsx
25 | 21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 1 | Finished | 2265 | 2265 | C2012-13 Pumping Station Jabbeke.xlsx
26 | 22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 1 | Finished | 4247.29 | 4247.29 | C2012-13 Pumping Station Jabbeke.xlsx
27 | 23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 1 | Finished | 5247.29 | 5247.29 | C2012-13 Pumping Station Jabbeke.xlsx
28 | 24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 1 | Finished | 5247.29 | 5247.29 | C2012-13 Pumping Station Jabbeke.xlsx
29 | 25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 1 | Finished | 45454.7891 | 45454.7891 | C2012-13 Pumping Station Jabbeke.xlsx
30 | 26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 1 | Finished | 5247.29 | 5247.29 | C2012-13 Pumping Station Jabbeke.xlsx
31 | 27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 1 | Finished | 3358 | 3358 | C2012-13 Pumping Station Jabbeke.xlsx
32 | 28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 1 | Finished | 5189 | 5189 | C2012-13 Pumping Station Jabbeke.xlsx
33 | 29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 1 | Finished | 1186.3 | 1186.3 | C2012-13 Pumping Station Jabbeke.xlsx
34 | 30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 1 | Finished | 1059 | 1059 | C2012-13 Pumping Station Jabbeke.xlsx
35 | 31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 1 | Finished | 1293 | 1293 | C2012-13 Pumping Station Jabbeke.xlsx
36 | 32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 1 | Finished | 1562.7 | 1562.7 | C2012-13 Pumping Station Jabbeke.xlsx
37 | 33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 1 | Finished | 2045 | 2045 | C2012-13 Pumping Station Jabbeke.xlsx
38 | 34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 1 | Finished | 1358 | 1358 | C2012-13 Pumping Station Jabbeke.xlsx
39 | 35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 1 | Finished | 1482 | 1482 | C2012-13 Pumping Station Jabbeke.xlsx
40 | 36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 1 | Finished | 1069 | 1069 | C2012-13 Pumping Station Jabbeke.xlsx
41 | 37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 1 | Finished | 1540 | 1540 | C2012-13 Pumping Station Jabbeke.xlsx
42 | 38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 1 | Finished | 1163.8 | 1163.8 | C2012-13 Pumping Station Jabbeke.xlsx
43 | 39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 1 | Finished | 750 | 750 | C2012-13 Pumping Station Jabbeke.xlsx
44 | 40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 1 | Finished | 1123 | 1123 | C2012-13 Pumping Station Jabbeke.xlsx
45 | 41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 | 2012-04-16 08:00 | 5d | 7655.6001 | 0 | 0 | 344.4 | 0 | 8000.0001 | 0 | 1 | Finished | 7655.6001 | 7655.6001 | C2012-13 Pumping Station Jabbeke.xlsx
46 | 42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 1 | Finished | 1564 | 1564 | C2012-13 Pumping Station Jabbeke.xlsx
47 | 43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-23 08:00 | 1d | 1160.35 | 0 | 0 | 239.65 | 0 | 1400 | 0 | 1 | Finished | 1160.35 | 1160.35 | C2012-13 Pumping Station Jabbeke.xlsx
48 | 44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-24 08:00 | 1d | 1160.35 | 0 | 0 | 375 | 0 | 1535.35 | 0 | 1 | Finished | 1160.35 | 1160.35 | C2012-13 Pumping Station Jabbeke.xlsx
49 | 45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-25 08:00 | 1d | 1160.35 | 0 | 0 | 0 | 0 | 1160.35 | 0 | 1 | Finished | 1160.35 | 1160.35 | C2012-13 Pumping Station Jabbeke.xlsx
50 | 46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 | 2012-04-25 08:00 | 1d | 1098 | 0 | 0 | 12 | 0 | 1110 | 0 | 1 | Finished | 1098 | 1098 | C2012-13 Pumping Station Jabbeke.xlsx
51 | 47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 | 2012-04-27 08:00 | 1d | 1090 | 0 | 0 | 10 | 0 | 1100 | 0 | 1 | Finished | 1090 | 1090 | C2012-13 Pumping Station Jabbeke.xlsx
52 | 48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-05-03 08:00 | 2d | 2418 | 0 | 0 | -218 | 0 | 2200 | 0 | 1 | Finished | 1293 | 1293 | C2012-13 Pumping Station Jabbeke.xlsx
53 | 49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 | 2012-05-07 08:00 | 1d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 1 | Finished | 1125 | 1125 | C2012-13 Pumping Station Jabbeke.xlsx
54 | 50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 | 2012-05-08 08:00 | 1d | 1043 | 0 | 0 | 157 | 0 | 1200 | 0 | 1 | Finished | 1043 | 1043 | C2012-13 Pumping Station Jabbeke.xlsx
55 | 51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-09 08:00 | 1d | 1235 | 0 | 0 | 375 | 0 | 1610 | 0 | 1 | Finished | 1235 | 1235 | C2012-13 Pumping Station Jabbeke.xlsx
56 | 52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 | 2012-05-10 08:00 | 1d | 1085 | 0 | 0 | 415 | 0 | 1500 | 0 | 1 | Finished | 1085 | 1085 | C2012-13 Pumping Station Jabbeke.xlsx
57 | 53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 | 2012-04-23 08:00 | 5d | 5273 | 0 | 0 | -373 | 0 | 4900 | 0 | 1 | Finished | 4523 | 4523 | C2012-13 Pumping Station Jabbeke.xlsx
58 | 54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-05-11 08:00 | 1d | 1123 | 0 | 0 | -123 | 0 | 1000 | 0 | 1 | Finished | 1123 | 1123 | C2012-13 Pumping Station Jabbeke.xlsx
59 | 55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-29 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 1 | Finished | 1235 | 1235 | C2012-13 Pumping Station Jabbeke.xlsx
60 | 56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-30 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 1 | Finished | 1235 | 1235 | C2012-13 Pumping Station Jabbeke.xlsx
61 | 57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-31 08:00 | 2d | 1985 | 0 | 0 | -385 | 0 | 1600 | 0 | 1 | Finished | 1235 | 1235 | C2012-13 Pumping Station Jabbeke.xlsx
62 | 58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 | 2012-07-02 08:00 | 4d | 4314 | 0 | 0 | 1986 | 0 | 6300 | 0 | 1 | Finished | 3564 | 3564 | C2012-13 Pumping Station Jabbeke.xlsx
63 | 59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 | 2012-07-06 08:00 | 1d | 1839.71 | 0 | 0 | 1250 | 0 | 3089.71 | 0 | 1 | Finished | 1839.71 | 1839.71 | C2012-13 Pumping Station Jabbeke.xlsx
64 | 60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 | 2012-05-14 08:00 | 4d | 4241 | 0 | 0 | 0 | 0 | 4241 | 0 | 1 | Finished | 4241 | 4241 | C2012-13 Pumping Station Jabbeke.xlsx
65 | 61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 | 2012-06-18 08:00 | 1d | 1667 | 0 | 0 | 0 | 0 | 1667 | 0 | 1 | Finished | 1292 | 1292 | C2012-13 Pumping Station Jabbeke.xlsx
66 | 62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 | 2012-05-22 08:00 | 4d | 4478 | 0 | 0 | 222 | 0 | 4700 | 0 | 1 | Finished | 5228 | 5228 | C2012-13 Pumping Station Jabbeke.xlsx
67 | 63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 | 2012-06-19 08:00 | 1d | 1827 | 0 | 0 | 0 | 0 | 1827 | 0 | 1 | Finished | 1452 | 1452 | C2012-13 Pumping Station Jabbeke.xlsx
68 | 64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 | 2012-06-20 08:00 | 1d | 1230 | 0 | 0 | 170 | 0 | 1400 | 0 | 1 | Finished | 1230 | 1230 | C2012-13 Pumping Station Jabbeke.xlsx
69 | 65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 | 2012-06-21 08:00 | 1d | 1156 | 0 | 0 | 0 | 0 | 1156 | 0 | 1 | Finished | 1156 | 1156 | C2012-13 Pumping Station Jabbeke.xlsx
70 | 66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 | 2012-06-22 08:00 | 1d | 1095 | 0 | 0 | 0 | 0 | 1095 | 0 | 1 | Finished | 1095 | 1095 | C2012-13 Pumping Station Jabbeke.xlsx
71 | 67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-07-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 1 | Finished | 1123 | 1123 | C2012-13 Pumping Station Jabbeke.xlsx
72 | 68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 | 2012-06-04 08:00 | 5d | 5479.63 | 0 | 0 | 0 | 0 | 5479.63 | 0 | 1 | Finished | 5479.63 | 5479.63 | C2012-13 Pumping Station Jabbeke.xlsx
73 | 69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 | 2012-06-11 08:00 | 5d | 6148 | 0 | 0 | 852 | 0 | 7000 | 0 | 1 | Finished | 8398 | 8398 | C2012-13 Pumping Station Jabbeke.xlsx
74 | 70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 | 2012-06-25 08:00 | 1d | 1170 | 0 | 0 | 0 | 0 | 1170 | 0 | 1 | Finished | 1170 | 1170 | C2012-13 Pumping Station Jabbeke.xlsx
75 | 71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 | 2012-06-26 08:00 | 2d | 5578 | 0 | 0 | 0 | 0 | 5578 | 0 | 1 | Finished | 5578 | 5578 | C2012-13 Pumping Station Jabbeke.xlsx
76 | 72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 | 2012-06-28 08:00 | 2d | 3278.5 | 0 | 0 | 0 | 0 | 3278.5 | 0 | 1 | Finished | 3278.5 | 3278.5 | C2012-13 Pumping Station Jabbeke.xlsx
77 | 73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 | 2012-07-03 08:00 | 9d | 10440.46 | 0 | 0 | 0 | 0 | 10440.46 | 0 | 1 | Finished | 10440.46 | 10440.46 | C2012-13 Pumping Station Jabbeke.xlsx
78 | 74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 | 2012-07-09 08:00 | 5d | 8986.9302 | 0 | 0 | 3513.0701 | 0 | 12500.0002 | 0 | 1 | Finished | 11986.9302 | 11986.9302 | C2012-13 Pumping Station Jabbeke.xlsx
4 | 0 | The Master Project | 2012-10-29 08:00 | 2012-12-14 20:00 | 32d |  |  | 180000 |  |  | 185472.45 |  | 32d | [5 empty] | 185113.1 |  | 1 |  | 185472.45 | 185472.45 | C2012-15 The Master Project.xlsx
5 | 1 | X Course strategic management | 2012-10-29 09:00 | 2012-10-29 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-10-29 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 1 | Finished | 60 | 60 | C2012-15 The Master Project.xlsx
6 | 2 | A Course Marketing communications | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-10-29 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 1 | Finished | 56.25 | 56.25 | C2012-15 The Master Project.xlsx
7 | 3 | X Groupwork strategic management | 2012-10-29 19:00 | 2012-10-30 10:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-10-29 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 1 | Finished | 10021.6 | 10021.6 | C2012-15 The Master Project.xlsx
8 | 4 | S Groupwork FEC | 2012-10-29 14:00 | 2012-10-29 16:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 08:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 1 | Finished | 10 | 10 | C2012-15 The Master Project.xlsx
9 | 6 | E Course B2B | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Eline | 0 | 0 | 140 | 420 | 420 | 2012-10-29 14:00 | 2h | 280 | 0 | 0 | 0 | 0 | 280 | 0 | 1 | Finished | 420 | 420 | C2012-15 The Master Project.xlsx
10 | 7 | X Groupwork Projectmanagement | 2012-10-30 18:00 | 2012-10-31 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 08:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 1 | Finished | 18.75 | 18.75 | C2012-15 The Master Project.xlsx
11 | 8 | E Course CRM | 2012-10-30 14:00 | 2012-10-30 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-10-30 14:00 | 5h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 120 | 120 | C2012-15 The Master Project.xlsx
12 | 9 | E Groupwork B2B | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-29 08:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 1 | Finished | 18 | 18 | C2012-15 The Master Project.xlsx
13 | 10 | A Groupwork Research Methods | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-29 08:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 1 | Finished | 64 | 64 | C2012-15 The Master Project.xlsx
14 | 11 | X Course Projectmanagement | 2012-10-31 14:00 | 2012-10-31 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-10-31 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 75 | 75 | C2012-15 The Master Project.xlsx
15 | 12 | A Course research methods | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-10-31 18:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 1 | Finished | 9.24 | 9.24 | C2012-15 The Master Project.xlsx
16 | 13 | E Groupwork Service Management | 2012-11-07 15:00 | 2012-11-07 19:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 08:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 1 | Finished | 27.84 | 27.84 | C2012-15 The Master Project.xlsx
17 | 14 | S Course FEC | 2012-10-31 09:00 | 2012-10-31 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-10-31 09:00 | 2h | 22.86 | 0 | 0 | 0 | 0 | 22.86 | 0 | 1 | Finished | 45.72 | 45.72 | C2012-15 The Master Project.xlsx
18 | 15 | X Deadline 1 Strategic management | 2012-10-31 20:00 | 2012-10-31 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2012-15 The Master Project.xlsx
19 | 16 | X Course strategic management | 2012-11-05 09:00 | 2012-11-05 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-05 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 1 | Finished | 60 | 60 | C2012-15 The Master Project.xlsx
20 | 17 | A Course Marketing Communications | 2012-11-05 14:00 | 2012-11-05 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-05 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 1 | Finished | 56.25 | 56.25 | C2012-15 The Master Project.xlsx
21 | 18 | S Course B2B | 2012-11-05 14:00 | 2012-11-05 15:00 | 1h | Sanne | 0 | 0 | 105 | 105 | 105 | 2012-11-05 14:00 | 1h | 105 | 0 | 0 | 0 | 0 | 105 | 0 | 1 | Finished | 105 | 105 | C2012-15 The Master Project.xlsx
22 | 19 | A Course Research methods | 2012-11-06 11:00 | 2012-11-06 13:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-11-06 11:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 1 | Finished | 9.24 | 9.24 | C2012-15 The Master Project.xlsx
23 | 20 | A Groupwork Research methods | 2012-11-07 09:00 | 2012-11-07 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 12:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 1 | Finished | 48 | 48 | C2012-15 The Master Project.xlsx
24 | 21 | E Exam CRM | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-11-06 14:00 | 4h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2012-15 The Master Project.xlsx
25 | 22 | X Groupwork Strategic management | 2012-11-05 17:00 | 2012-11-05 20:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-05 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 1 | Finished | 10021.6 | 10021.6 | C2012-15 The Master Project.xlsx
26 | 23 | S Groupwork FEC | 2012-10-29 16:00 | 2012-10-29 18:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 11:00 | 1h | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 1 | Finished | 10 | 10 | C2012-15 The Master Project.xlsx
27 | 24 | A Groupwork research methods | 2012-11-07 12:00 | 2012-11-07 16:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 17:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 1 | Finished | 48 | 48 | C2012-15 The Master Project.xlsx
28 | 25 | X Groupwork Project management | 2012-11-06 08:00 | 2012-11-06 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 10:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 1 | Finished | 18.75 | 18.75 | C2012-15 The Master Project.xlsx
29 | 26 | E Groupwork Service management | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 11:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 1 | Finished | 27.84 | 27.84 | C2012-15 The Master Project.xlsx
30 | 28 | S Course FEC | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-07 09:00 | 4h | 45.72 | 0 | 0 | 0 | 0 | 45.72 | 0 | 1 | Finished | 45.72 | 45.72 | C2012-15 The Master Project.xlsx
31 | 29 | X Deadline 2 Strategic management | 2012-11-07 20:00 | 2012-11-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2012-15 The Master Project.xlsx
32 | 30 | A Course Research Methods | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-08 09:00 | 4h | 18.48 | 0 | 0 | 0 | 0 | 18.48 | 0 | 1 | Finished | 18.48 | 18.48 | C2012-15 The Master Project.xlsx
33 | 31 | E+S Course systeemdynamica | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-08 09:00 | 2h | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 1 | Finished | 100 | 100 | C2012-15 The Master Project.xlsx
34 | 32 | E Course Service Management | 2012-11-08 16:00 | 2012-11-08 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 | 2012-11-08 16:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 1 | Finished | 60 | 60 | C2012-15 The Master Project.xlsx
35 | 33 | E Groupwork B2B | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-29 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | Finished | 12 | 12 | C2012-15 The Master Project.xlsx
36 | 34 | X Group work strategisch management | 2012-11-08 18:00 | 2012-11-09 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-08 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 1 | Finished | 10021.6 | 10021.6 | C2012-15 The Master Project.xlsx
37 | 36 | E Group work B2B | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-29 14:00 | 6h | 36 | 0 | 0 | 0 | 0 | 36 | 0 | 1 | Finished | 24 | 24 | C2012-15 The Master Project.xlsx
38 | 37 | S Group work B2B | 2012-11-06 11:00 | 2012-11-06 16:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 08:00 | 4h | 34.28 | 0 | 0 | 0 | 0 | 34.28 | 0 | 1 | Finished | 34.28 | 34.28 | C2012-15 The Master Project.xlsx
39 | 38 | X Course Strategisch management | 2012-11-12 09:00 | 2012-11-12 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-12 09:00 | 3h | 45 | 0 | 0 | 0 | 0 | 45 | 0 | 1 | Finished | 60 | 60 | C2012-15 The Master Project.xlsx
40 | 39 | A Course research methods | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-12 14:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 1 | Finished | 18.48 | 18.48 | C2012-15 The Master Project.xlsx
41 | 40 | E Groupwork B2B | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-30 08:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | Finished | 12 | 12 | C2012-15 The Master Project.xlsx
42 | 41 | X Deadline 3 | 2012-11-12 20:00 | 2012-11-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2012-15 The Master Project.xlsx
43 | 42 | A Groupwork Marketing Communications | 2012-10-29 08:00 | 2012-10-29 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 08:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 1 | Finished | 30 | 30 | C2012-15 The Master Project.xlsx
44 | 43 | X Groupwork Project Management | 2012-11-06 18:00 | 2012-11-07 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 14:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 1 | Finished | 18.75 | 18.75 | C2012-15 The Master Project.xlsx
45 | 44 | X Groupwork Strategic Management | 2012-11-13 08:00 | 2012-11-13 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-11-13 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 1 | Finished | 10007.2 | 10007.2 | C2012-15 The Master Project.xlsx
46 | 45 | E Course CRM | 2012-11-13 14:00 | 2012-11-13 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-13 14:00 | 5h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 120 | 120 | C2012-15 The Master Project.xlsx
47 | 46 | X Deadline 4 | 2012-11-13 20:00 | 2012-11-13 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2012-15 The Master Project.xlsx
48 | 47 | S Groupwork FEC | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 12:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 1 | Finished | 15 | 15 | C2012-15 The Master Project.xlsx
49 | 48 | X Course Project Management | 2012-11-14 14:00 | 2012-11-14 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-11-14 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 1 | Finished | 75 | 75 | C2012-15 The Master Project.xlsx
50 | 49 | X Group Work Strategic Management | 2012-11-14 18:00 | 2012-11-14 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-11-14 08:00 | 2h | 10014.4 | 0 | 0 | 0 | 0 | 10014.4 | 0 | 1 | Finished | 10014.4 | 10014.4 | C2012-15 The Master Project.xlsx
51 | 50 | E Group Work Service Management | 2012-11-12 17:00 | 2012-11-12 20:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 08:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 1 | Finished | 20.88 | 20.88 | C2012-15 The Master Project.xlsx
52 | 51 | S Course FEC | 2012-11-14 09:00 | 2012-11-14 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-14 09:00 | 6h | 68.58 | 0 | 0 | 0 | 0 | 68.58 | 0 | 1 | Finished | 45.72 | 45.72 | C2012-15 The Master Project.xlsx
53 | 52 | X Deadline 5 | 2012-11-14 20:00 | 2012-11-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2012-15 The Master Project.xlsx
54 | 53 | E Group Work B2B | 2012-11-13 18:00 | 2012-11-14 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 10:00 | 4h | 24 | 0 | 0 | 0 | 0 | 24 | 0 | 1 | Finished | 24 | 24 | C2012-15 The Master Project.xlsx
55 | 54 | X Group Work Project Management | 2012-11-16 11:00 | 2012-11-16 17:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 16:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 1 | Finished | 31.25 | 31.25 | C2012-15 The Master Project.xlsx
56 | 55 | X Course Strategic Management | 2012-11-19 09:00 | 2012-11-19 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-19 09:00 | 4h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 1 | Finished | 60 | 60 | C2012-15 The Master Project.xlsx
57 | 56 | A Course Marketing Communications | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-19 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 56.25 | 56.25 | C2012-15 The Master Project.xlsx
58 | 57 | X Group Work Strategic Management | 2012-11-16 08:00 | 2012-11-16 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-16 08:00 | 3h | 10021.6 | 0 | 0 | 0 | 0 | 10021.6 | 0 | 1 | Finished | 10021.6 | 10021.6 | C2012-15 The Master Project.xlsx
59 | 58 | S Course B2B | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Sanne | 0 | 0 | 105 | 315 | 315 | 2012-11-19 14:00 | 2h | 210 | 0 | 0 | 0 | 0 | 210 | 0 | 1 | Finished | 315 | 315 | C2012-15 The Master Project.xlsx
60 | 59 | X Group Work Project Management | 2012-11-19 17:00 | 2012-11-20 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 19:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 1 | Finished | 31.25 | 31.25 | C2012-15 The Master Project.xlsx
61 | 60 | E Course CRM | 2012-11-20 14:00 | 2012-11-20 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-20 14:00 | 4h | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 1 | Finished | 120 | 120 | C2012-15 The Master Project.xlsx
62 | 61 | X Course Project Management | 2012-11-21 14:00 | 2012-11-21 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-11-21 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 1 | Finished | 75 | 75 | C2012-15 The Master Project.xlsx
63 | 62 | A Group Work Marketing Communications | 2012-10-30 10:00 | 2012-10-30 12:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 09:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 1 | Finished | 60 | 60 | C2012-15 The Master Project.xlsx
64 | 63 | E Group Work Service Management | 2012-11-09 14:00 | 2012-11-09 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 14:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 1 | Finished | 20.88 | 20.88 | C2012-15 The Master Project.xlsx
65 | 64 | Deadline 6 | 2012-11-21 20:00 | 2012-11-21 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2012-15 The Master Project.xlsx
66 | 65 | S Course FEC | 2012-11-21 09:00 | 2012-11-21 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-21 09:00 | 2h | 22.86 | 0 | 0 | 0 | 0 | 22.86 | 0 | 1 | Finished | 45.72 | 45.72 | C2012-15 The Master Project.xlsx
67 | 66 | A Course Research Methods | 2012-11-22 10:00 | 2012-11-22 12:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-11-22 10:00 | 2h | 9.24 | 0 | 0 | 0 | 0 | 9.24 | 0 | 1 | Finished | 9.24 | 9.24 | C2012-15 The Master Project.xlsx
68 | 67 | E+S Course Systeemdynamica | 2012-11-22 09:00 | 2012-11-22 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-22 09:00 | 3h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 100 | 100 | C2012-15 The Master Project.xlsx
69 | 68 | E Group Work Service Management | 2012-11-09 17:00 | 2012-11-09 19:00 | 2h | Eline | 0 | 0 | 6.96 | 13.92 | 13.92 | 2012-10-29 17:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 1 | Finished | 13.92 | 13.92 | C2012-15 The Master Project.xlsx
70 | 69 | X Group Work Project Management | 2012-11-20 10:00 | 2012-11-20 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 10:00 | 1h | 6.25 | 0 | 0 | 0 | 0 | 6.25 | 0 | 1 | Finished | 12.5 | 12.5 | C2012-15 The Master Project.xlsx
71 | 70 | A Group Work Research Methods | 2012-11-07 16:00 | 2012-11-07 19:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 09:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 1 | Finished | 48 | 48 | C2012-15 The Master Project.xlsx
72 | 71 | E Group Work B2B | 2012-11-16 17:00 | 2012-11-19 09:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 15:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 1 | Finished | 24 | 24 | C2012-15 The Master Project.xlsx
73 | 72 | X Group Work Project Management | 2012-11-20 18:00 | 2012-11-20 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 11:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 1 | Finished | 12.5 | 12.5 | C2012-15 The Master Project.xlsx
74 | 73 | S Group Work FEC | 2012-10-30 14:00 | 2012-10-30 17:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 16:00 | 4h | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | Finished | 15 | 15 | C2012-15 The Master Project.xlsx
75 | 74 | S Group Work B2B | 2012-11-07 14:00 | 2012-11-07 17:00 | 3h | Sanne | 0 | 0 | 8.57 | 25.71 | 25.71 | 2012-10-29 12:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 1 | Finished | 25.71 | 25.71 | C2012-15 The Master Project.xlsx
76 | 75 | X Course Strategic Management | 2012-11-26 09:00 | 2012-11-26 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-26 09:00 | 6h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 1 | Finished | 60 | 60 | C2012-15 The Master Project.xlsx
77 | 77 | A Group Work Marketing Communications | 2012-10-30 12:00 | 2012-10-30 15:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 11:00 | 3h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 1 | Finished | 60 | 60 | C2012-15 The Master Project.xlsx
78 | 79 | A Course Marketing Communications | 2012-11-26 14:00 | 2012-11-26 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-26 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 1 | Finished | 56.25 | 56.25 | C2012-15 The Master Project.xlsx
79 | 80 | X Group Work Strategic Management | 2012-11-22 14:00 | 2012-11-22 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-11-22 08:00 | 3h | 10021.6 | 0 | 0 | 0 | 0 | 10021.6 | 0 | 1 | Finished | 10014.4 | 10014.4 | C2012-15 The Master Project.xlsx
80 | 81 | E Course CRM | 2012-11-27 14:00 | 2012-11-27 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-27 14:00 | 4h | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 1 | Finished | 120 | 120 | C2012-15 The Master Project.xlsx
81 | 82 | S Group Work FEC | 2012-11-09 14:00 | 2012-11-09 20:00 | 6h | Sanne | 0 | 0 | 5 | 30 | 30 | 2012-10-30 08:00 | 7h | 35 | 0 | 0 | 0 | 0 | 35 | 0 | 1 | Finished | 30 | 30 | C2012-15 The Master Project.xlsx
82 | 83 | S Course FEC | 2012-11-28 09:00 | 2012-11-28 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-28 09:00 | 4h | 45.72 | 0 | 0 | 0 | 0 | 45.72 | 0 | 1 | Finished | 45.72 | 45.72 | C2012-15 The Master Project.xlsx
83 | 84 | X Group Work Project Management | 2012-11-22 16:00 | 2012-11-23 10:00 | 6h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 37.5 | 37.5 | 2012-10-30 14:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 1 | Finished | 37.5 | 37.5 | C2012-15 The Master Project.xlsx
84 | 85 | X Deadline 7 | 2012-11-28 20:00 | 2012-11-28 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2012-15 The Master Project.xlsx
85 | 86 | A Course Research Methods | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-29 09:00 | 4h | 18.48 | 0 | 0 | 0 | 0 | 18.48 | 0 | 1 | Finished | 18.48 | 18.48 | C2012-15 The Master Project.xlsx
86 | 87 | A Group Work Research Methods | 2012-11-08 14:00 | 2012-11-08 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-30 14:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 1 | Finished | 64 | 64 | C2012-15 The Master Project.xlsx
87 | 88 | E+S Course Systeemdynamica | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-29 09:00 | 6h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 100 | 100 | C2012-15 The Master Project.xlsx
88 | 89 | E Course Service Management | 2012-11-29 16:00 | 2012-11-29 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 | 2012-11-29 16:00 | 3h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 1 | Finished | 60 | 60 | C2012-15 The Master Project.xlsx
89 | 91 | X Group Work Project Management | 2012-11-23 10:00 | 2012-11-23 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 17:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 1 | Finished | 12.5 | 12.5 | C2012-15 The Master Project.xlsx
90 | 92 | E Group Work Service Management | 2012-11-12 14:00 | 2012-11-12 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-30 08:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 1 | Finished | 20.88 | 20.88 | C2012-15 The Master Project.xlsx
91 | 93 | E Group Work B2B | 2012-11-21 08:00 | 2012-11-21 12:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 18:00 | 5h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 1 | Finished | 24 | 24 | C2012-15 The Master Project.xlsx
92 | 94 | S Group Work B2B | 2012-11-07 17:00 | 2012-11-08 09:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 15:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 1 | Finished | 34.28 | 34.28 | C2012-15 The Master Project.xlsx
93 | 95 | X Course Strategic Management | 2012-12-03 09:00 | 2012-12-03 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-12-03 09:00 | 4h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 1 | Finished | 60 | 60 | C2012-15 The Master Project.xlsx
94 | 96 | A Course Marketing Communications | 2012-12-03 14:00 | 2012-12-03 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-12-03 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 1 | Finished | 56.25 | 56.25 | C2012-15 The Master Project.xlsx
95 | 97 | A Group Work Marketing Communications | 2012-10-30 15:00 | 2012-10-30 17:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 15:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 1 | Finished | 60 | 60 | C2012-15 The Master Project.xlsx
96 | 98 | E Group Work B2B | 2012-11-27 18:00 | 2012-11-28 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-31 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | Finished | 24 | 24 | C2012-15 The Master Project.xlsx
97 | 99 | S Group Work B2B | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 17:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 1 | Finished | 34.28 | 34.28 | C2012-15 The Master Project.xlsx
98 | 100 | A Group Work Research Methods | 2012-11-09 09:00 | 2012-11-09 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 19:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 1 | Finished | 48 | 48 | C2012-15 The Master Project.xlsx
99 | 101 | X Group Work Project Management | 2012-11-23 12:00 | 2012-11-23 17:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-30 19:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 1 | Finished | 25 | 25 | C2012-15 The Master Project.xlsx
100 | 102 | X Group Work Strategic Management | 2012-11-29 14:00 | 2012-11-29 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-11-29 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 1 | Finished | 10014.4 | 10014.4 | C2012-15 The Master Project.xlsx
101 | 103 | E Exam SAS | 2012-12-04 16:00 | 2012-12-04 18:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-12-04 16:00 | 2h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2012-15 The Master Project.xlsx
102 | 104 | X Deadline 8 | 2012-12-04 20:00 | 2012-12-04 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2012-15 The Master Project.xlsx
103 | 105 | X Course Project Management | 2012-12-05 14:00 | 2012-12-05 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-12-05 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 75 | 75 | C2012-15 The Master Project.xlsx
104 | 106 | E Group Work Service Management | 2012-11-13 09:00 | 2012-11-13 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-30 12:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 1 | Finished | 27.84 | 27.84 | C2012-15 The Master Project.xlsx
105 | 107 | S Course FEC | 2012-12-05 09:00 | 2012-12-05 13:00 | 4h | Sanne | 0 | 0 | 5 | 20 | 20 | 2012-12-05 09:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 1 | Finished | 20 | 20 | C2012-15 The Master Project.xlsx
106 | 108 | A Course Research Methods | 2012-12-06 09:00 | 2012-12-06 11:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-12-06 09:00 | 1h | 4.62 | 0 | 0 | 0 | 0 | 4.62 | 0 | 1 | Finished | 9.24 | 9.24 | C2012-15 The Master Project.xlsx
107 | 109 | E+S Course Systeemdynamica | 2012-12-06 09:00 | 2012-12-06 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-12-06 09:00 | 5h | 125 | 0 | 0 | 0 | 0 | 125 | 0 | 1 | Finished | 100 | 100 | C2012-15 The Master Project.xlsx
108 | 110 | E Course Service Management | 2012-12-06 16:00 | 2012-12-06 20:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-12-06 16:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 1 | Finished | 120 | 120 | C2012-15 The Master Project.xlsx
109 | 111 | A Group Work Research Methods | 2012-11-09 12:00 | 2012-11-09 17:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-31 10:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 1 | Finished | 64 | 64 | C2012-15 The Master Project.xlsx
110 | 112 | X Group Work Project Management | 2012-11-23 17:00 | 2012-11-26 09:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-31 11:00 | 5h | 31.25 | 0 | 0 | 0 | 0 | 31.25 | 0 | 1 | Finished | 25 | 25 | C2012-15 The Master Project.xlsx
111 | 113 | A Group Work Marketing Communications | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 17:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 1 | Finished | 60 | 60 | C2012-15 The Master Project.xlsx
112 | 114 | X Group Work Strategic Management | 2012-12-05 18:00 | 2012-12-05 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-12-05 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 1 | Finished | 10014.4 | 10014.4 | C2012-15 The Master Project.xlsx
113 | 115 | S Group Work B2B | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 19:00 | 3h | 25.71 | 0 | 0 | 0 | 0 | 25.71 | 0 | 1 | Finished | 34.28 | 34.28 | C2012-15 The Master Project.xlsx
114 | 116 | X Deadline 9 | 2012-12-07 20:00 | 2012-12-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2012-15 The Master Project.xlsx
115 | 117 | X Course Strategic Management | 2012-12-10 09:00 | 2012-12-10 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-12-10 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 1 | Finished | 60 | 60 | C2012-15 The Master Project.xlsx
116 | 118 | A Course Marketing Communications | 2012-12-10 14:00 | 2012-12-10 15:00 | 1h | Ann-Sophie | 0 | 0 | 18.75 | 18.75 | 18.75 | 2012-12-10 14:00 | 1h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 1 | Finished | 18.75 | 18.75 | C2012-15 The Master Project.xlsx
117 | 119 | X Group Work Strategic Management | 2012-12-10 08:00 | 2012-12-10 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-12-10 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 1 | Finished | 10007.2 | 10007.2 | C2012-15 The Master Project.xlsx
118 | 120 | X Group Work Project Management | 2012-11-26 17:00 | 2012-11-27 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-31 17:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 1 | Finished | 31.25 | 31.25 | C2012-15 The Master Project.xlsx
119 | 121 | X Deadline 10 | 2012-12-10 20:00 | 2012-12-10 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-11 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2012-15 The Master Project.xlsx
120 | 122 | E Course CRM | 2012-12-11 14:00 | 2012-12-11 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-12-11 14:00 | 6h | 180 | 0 | 0 | 0 | 0 | 180 | 0 | 1 | Finished | 120 | 120 | C2012-15 The Master Project.xlsx
121 | 123 | X Group Work Strategic Management | 2012-12-11 08:00 | 2012-12-11 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-12-11 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 1 | Finished | 10007.2 | 10007.2 | C2012-15 The Master Project.xlsx
122 | 124 | X Group Work Project Management | 2012-11-28 14:00 | 2012-11-28 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-11-05 09:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 1 | Finished | 25 | 25 | C2012-15 The Master Project.xlsx
123 | 125 | A Group Work Marketing Communications | 2012-11-12 08:00 | 2012-11-12 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 19:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 1 | Finished | 30 | 30 | C2012-15 The Master Project.xlsx
124 | 126 | A Group Work Research Methods | 2012-11-09 17:00 | 2012-11-09 20:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 16:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 1 | Finished | 48 | 48 | C2012-15 The Master Project.xlsx
125 | 127 | S Group Work B2B | 2012-11-12 18:00 | 2012-11-12 20:00 | 2h | Sanne | 0 | 0 | 8.57 | 17.14 | 17.14 | 2012-10-30 10:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 1 | Finished | 17.14 | 17.14 | C2012-15 The Master Project.xlsx
126 | 128 | X Deadline 11 | 2012-12-11 20:00 | 2012-12-11 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2012-15 The Master Project.xlsx
127 | 129 | S Course FEC | 2012-12-12 09:00 | 2012-12-12 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-12-12 09:00 | 4h | 45.72 | 0 | 0 | 0 | 0 | 45.72 | 0 | 1 | Finished | 45.72 | 45.72 | C2012-15 The Master Project.xlsx
128 | 130 | A Group Work Research Methods | 2012-11-13 09:00 | 2012-11-13 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 19:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 1 | Finished | 48 | 48 | C2012-15 The Master Project.xlsx
129 | 131 | X Group Work Strategic Management | 2012-12-12 08:00 | 2012-12-12 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-12-12 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 1 | Finished | 10007.2 | 10007.2 | C2012-15 The Master Project.xlsx
130 | 132 | X Deadline 12 | 2012-12-12 20:00 | 2012-12-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2012-15 The Master Project.xlsx
131 | 133 | X Presentation Project Management | 2012-12-12 15:00 | 2012-12-12 16:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-12-12 15:00 | 1h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2012-15 The Master Project.xlsx
132 | 134 | A Course Research Methods | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-12-13 09:00 | 4h | 18.48 | 0 | 0 | 0 | 0 | 18.48 | 0 | 1 | Finished | 18.48 | 18.48 | C2012-15 The Master Project.xlsx
133 | 135 | E+S Course Systeemdynamica | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-12-13 09:00 | 4h | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 1 | Finished | 100 | 100 | C2012-15 The Master Project.xlsx
134 | 136 | E Presentation Service Management | 2012-12-13 14:00 | 2012-12-13 16:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-12-13 14:00 | 3h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2012-15 The Master Project.xlsx
135 | 137 | E Group Work B2B | 2012-11-28 10:00 | 2012-11-28 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-31 14:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 1 | Finished | 18 | 18 | C2012-15 The Master Project.xlsx
136 | 138 | E Exam CRM | 2012-12-14 09:00 | 2012-12-14 13:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-12-14 09:00 | 4h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2012-15 The Master Project.xlsx
137 | 139 | X Group Work Strategic Management | 2012-12-13 16:00 | 2012-12-13 18:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-12-13 08:00 | 3h | 10021.6 | 0 | 0 | 0 | 0 | 10021.6 | 0 | 1 | Finished | 10014.4 | 10014.4 | C2012-15 The Master Project.xlsx
138 | 140 | X Deadline 13 | 2012-12-14 20:00 | 2012-12-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2012-15 The Master Project.xlsx
4 | 0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 204d 3h | [5 empty] | 314856.144 |  | 1 |  | 241015.0007 | 241015.0007 | C2012-17 Building a Dream.xlsx
5 | 1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 1 | Finished | 850 | 850 | C2012-17 Building a Dream.xlsx
6 | 2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 1 | Finished | 1210 | 1210 | C2012-17 Building a Dream.xlsx
7 | 3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 1 | Finished | 1640 | 1640 | C2012-17 Building a Dream.xlsx
8 | 4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 1 | Finished | 11800.0002 | 11800.0002 | C2012-17 Building a Dream.xlsx
9 | 5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 1 | Finished | 5280 | 5280 | C2012-17 Building a Dream.xlsx
10 | 6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 1 | Finished | 23920 | 23920 | C2012-17 Building a Dream.xlsx
11 | 7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 1 | Finished | 24920 | 24920 | C2012-17 Building a Dream.xlsx
12 | 8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 180 | 180 | C2012-17 Building a Dream.xlsx
13 | 9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 1 | Finished | 2180 | 2180 | C2012-17 Building a Dream.xlsx
14 | 10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 1 | Finished | 5400.0001 | 5400.0001 | C2012-17 Building a Dream.xlsx
15 | 11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 1 | Finished | 1210 | 1210 | C2012-17 Building a Dream.xlsx
16 | 12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 1 | Finished | 5760.0002 | 5760.0002 | C2012-17 Building a Dream.xlsx
17 | 13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 1 | Finished | 42440 | 42440 | C2012-17 Building a Dream.xlsx
18 | 14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 1 | Finished | 2650 | 2650 | C2012-17 Building a Dream.xlsx
19 | 15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 1 | Finished | 7700 | 7700 | C2012-17 Building a Dream.xlsx
20 | 16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 1 | Finished | 5160.0001 | 5160.0001 | C2012-17 Building a Dream.xlsx
21 | 17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 1 | Finished | 3780.0001 | 3780.0001 | C2012-17 Building a Dream.xlsx
22 | 18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 1 | Finished | 6600 | 6600 | C2012-17 Building a Dream.xlsx
23 | 19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 1 | Finished | 200 | 200 | C2012-17 Building a Dream.xlsx
24 | 20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 17d 6h | 8620 | 0 | 0 | 0 | 0 | 8620 | 0 | 1 | Finished | 7300 | 7300 | C2012-17 Building a Dream.xlsx
25 | 21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 | 2013-09-19 09:00 | 14d 5h | 8277 | 0 | 0 | 0 | 0 | 8277 | 0 | 1 | Finished | 4857 | 4857 | C2012-17 Building a Dream.xlsx
26 | 22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 | 2013-10-10 15:00 | 7d 1h | 3648.0001 | 0 | 0 | 0 | 0 | 3648.0001 | 0 | 1 | Finished | 1920 | 1920 | C2012-17 Building a Dream.xlsx
27 | 23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 | 2013-10-21 16:00 | 17d 3h | 16680 | 0 | 0 | 0 | 0 | 16680 | 0 | 1 | Finished | 9600 | 9600 | C2012-17 Building a Dream.xlsx
28 | 24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 | 2013-11-14 10:00 | 2d 3h | 6460 | 0 | 0 | 0 | 0 | 6460 | 0 | 1 | Finished | 5440 | 5440 | C2012-17 Building a Dream.xlsx
29 | 25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 | 2013-11-18 14:00 | 3d 5h | 19000 | 0 | 0 | 0 | 0 | 19000 | 0 | 1 | Finished | 19000 | 19000 | C2012-17 Building a Dream.xlsx
30 | 26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 | 2013-11-18 14:00 | 3d 1h | 8000 | 0 | 0 | 0 | 0 | 8000 | 0 | 1 | Finished | 8000 | 8000 | C2012-17 Building a Dream.xlsx
31 | 27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 | 2013-11-22 10:00 | 2d 6h | 1131.4286 | 0 | 0 | 0 | 0 | 1131.4286 | 0 | 1 | Finished | 720 | 720 | C2012-17 Building a Dream.xlsx
32 | 28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 | 2013-11-14 10:00 | 3d 4h | 12000 | 0 | 0 | 0 | 0 | 12000 | 0 | 1 | Finished | 12000 | 12000 | C2012-17 Building a Dream.xlsx
33 | 29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 | 2013-11-27 08:00 | 3d 3h | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2012-17 Building a Dream.xlsx
34 | 30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 | 2013-12-02 11:00 | 7d 6h | 6500 | 0 | 0 | 0 | 0 | 6500 | 0 | 1 | Finished | 6500 | 6500 | C2012-17 Building a Dream.xlsx
35 | 31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 | 2013-12-02 11:00 | 5d 2h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2012-17 Building a Dream.xlsx
36 | 32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 | 2013-11-27 08:00 | 2d | 198 | 0 | 0 | 0 | 0 | 198 | 0 | 1 | Finished | 198 | 198 | C2012-17 Building a Dream.xlsx
37 | 33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 2013-12-12 09:00 | 1d 2h | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 1 | Finished | 100 | 100 | C2012-17 Building a Dream.xlsx
4 | 0 | Wiedauwkaai Fenders | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 253122.0964 |  |  | 1069532.4154 |  | 152d | [5 empty] | 1314584.5815 |  | 1 |  | 1069532.4154 | 1069532.4154 | C2013-01 Wiedauwkaai Fenders.xlsx
5 | 1 | Contractuele uitvoeringstermijn | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  | 0 | 19349.6992 | 0 | 0 | 19349.6992 | 2007-02-01 08:00 | 150d | 19349.6992 | 0 | 0 | 492.45 | 0 | 19842.1492 | 0 | 1 | Finished | 19349.6992 | 19349.6992 | C2013-01 Wiedauwkaai Fenders.xlsx
6 | 2 | Totaal Project | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 233772.3972 |  |  | 1050182.7162 |  | 152d | [5 empty] | 1294742.4322 |  | 1 |  | 1050182.7162 | 1050182.7162 | C2013-01 Wiedauwkaai Fenders.xlsx
7 | 3 | Tijdelijke scheepvaartseinen plaatsen | 2007-02-19 08:00 | 2007-02-21 17:00 | 3d |  | 0 | 2378.3999 | 0 | 0 | 2378.3999 | 2007-02-19 08:00 | 3d | 2378.3999 | 0 | 0 | 0 | 0 | 2378.3999 | 0 | 1 | Finished | 2378.3999 | 2378.3999 | C2013-01 Wiedauwkaai Fenders.xlsx
8 | 4 | Bestaande scheepvaartseinen wegnemen | 2007-02-21 08:00 | 2007-02-23 17:00 | 3d |  | 0 | 1500.85 | 0 | 0 | 1500.85 | 2007-02-21 08:00 | 3d | 1500.85 | 0 | 0 | 0 | 0 | 1500.85 | 0 | 1 | Finished | 1500.85 | 1500.85 | C2013-01 Wiedauwkaai Fenders.xlsx
9 | 5 | Staketsel, dukdalven, scheepvaartseinen | 2007-02-01 08:00 | 2007-08-30 17:00 | 151d |  |  | 58790.45 |  |  | 721026.8496 |  | 151d | [5 empty] | 879483.8495 |  | 1 |  | 721026.8496 | 721026.8496 | C2013-01 Wiedauwkaai Fenders.xlsx
10 | 6 | Stalen onderbouw en azobé: prefab | 2007-02-01 08:00 | 2007-06-20 17:00 | 100d |  | 0 | 3770.5801 | 117.68 | 94144.0002 | 97914.5803 | 2007-02-01 08:00 | 104d | 101680.3403 | 0 | 0 | 28975.2598 | 0 | 130655.6001 | 0 | 1 | Finished | 97914.5803 | 97914.5803 | C2013-01 Wiedauwkaai Fenders.xlsx
11 | 7 | Afbraak stak afw kant TL & DD IV | 2007-02-26 08:00 | 2007-03-02 17:00 | 5d |  | 0 | 116.25 | 178.93 | 7157.1997 | 7273.4497 | 2007-02-26 08:00 | 5d | 7273.4497 | 0 | 0 | -120 | 0 | 7153.4497 | 0 | 1 | Finished | 7273.4497 | 7273.4497 | C2013-01 Wiedauwkaai Fenders.xlsx
12 | 8 | Heien buispalen stak afw kant TL, DD IV & SS A1 (9 st) | 2007-03-05 08:00 | 2007-03-09 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 2007-03-05 08:00 | 5d | 34466.001 | 0 | 0 | 16547.8906 | 0 | 51013.8916 | 0 | 1 | Finished | 34466.001 | 34466.001 | C2013-01 Wiedauwkaai Fenders.xlsx
13 | 9 | Montage stak afw kant TL & DD IV | 2007-03-22 08:00 | 2007-03-27 17:00 | 4d |  | 0 | 0 | 1119.11 | 35811.5195 | 35811.5195 | 2007-03-22 08:00 | 4d | 35811.5195 | 0 | 0 | 3975 | 0 | 39786.5195 | 0 | 1 | Finished | 35811.5195 | 35811.5195 | C2013-01 Wiedauwkaai Fenders.xlsx
14 | 10 | Afbraak stak afw kant WK & DD V | 2007-03-28 08:00 | 2007-04-03 17:00 | 5d |  | 0 | 0 | 178.93 | 7157.1997 | 7157.1997 | 2007-03-28 08:00 | 5d | 7157.1997 | 0 | 0 | 0 | 0 | 7157.1997 | 0 | 1 | Finished | 7157.1997 | 7157.1997 | C2013-01 Wiedauwkaai Fenders.xlsx
15 | 11 | Heien buispalen stak afw kant WK, DD V & SS A4 (10 st) | 2007-04-04 08:00 | 2007-04-10 17:00 | 5d |  | 0 | 0 | 957.39 | 38295.6006 | 38295.6006 | 2007-04-04 08:00 | 5d | 38295.6006 | 0 | 0 | 18386.5391 | 0 | 56682.1396 | 0 | 1 | Finished | 38295.6006 | 38295.6006 | C2013-01 Wiedauwkaai Fenders.xlsx
16 | 12 | Montage stak afw kant WK met verbindingen, & DD V | 2007-04-18 08:00 | 2007-04-25 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 | 2007-04-18 08:00 | 6d | 53717.2793 | 0 | 0 | 5960.3799 | 0 | 59677.6592 | 0 | 1 | Finished | 53717.2793 | 53717.2793 | C2013-01 Wiedauwkaai Fenders.xlsx
17 | 13 | Heien buispalen stak afw: kop (7 st) | 2007-04-26 08:00 | 2007-05-01 17:00 | 4d |  | 0 | 0 | 837.71 | 26806.7207 | 26806.7207 | 2007-04-26 08:00 | 3d | 20105.0405 | 0 | 0 | 19572.4297 | 0 | 39677.4702 | 0 | 1 | Finished | 26806.7207 | 26806.7207 | C2013-01 Wiedauwkaai Fenders.xlsx
18 | 14 | Montage stak afw kop | 2007-05-04 08:00 | 2007-05-10 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 | 2007-05-04 08:00 | 5d | 44764.3994 | 0 | 0 | 4966.9902 | 0 | 49731.3896 | 0 | 1 | Finished | 44764.3994 | 44764.3994 | C2013-01 Wiedauwkaai Fenders.xlsx
19 | 15 | Afbraak stak opw kant WK, DD II + III & helft gasleiding | 2007-05-11 08:00 | 2007-05-22 17:00 | 8d |  | 0 | 0 | 178.93 | 11451.5195 | 11451.5195 | 2007-05-11 08:00 | 8d | 11451.5195 | 0 | 0 | 0 | 0 | 11451.5195 | 0 | 1 | Finished | 11451.5195 | 11451.5195 | C2013-01 Wiedauwkaai Fenders.xlsx
20 | 16 | Heien buispalen stak opw kant WK, DD II & SS O4 (9 st) | 2007-05-25 08:00 | 2007-05-31 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 2007-05-25 08:00 | 5d | 34466.001 | 0 | 0 | 23441.0898 | 0 | 57907.0908 | 0 | 1 | Finished | 34466.001 | 34466.001 | C2013-01 Wiedauwkaai Fenders.xlsx
21 | 17 | Montage stak opw kant WK & DD II | 2007-06-04 08:00 | 2007-06-11 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 | 2007-06-04 08:00 | 6d | 53717.2793 | 0 | 0 | 5960.3799 | 0 | 59677.6592 | 0 | 1 | Finished | 53717.2793 | 53717.2793 | C2013-01 Wiedauwkaai Fenders.xlsx
22 | 18 | Afbraak stak opw kant TL, DD I & helft gasleiding | 2007-06-12 08:00 | 2007-06-21 17:00 | 8d |  | 0 | 116.25 | 178.93 | 11451.5195 | 11567.7695 | 2007-06-12 08:00 | 8d | 11567.7695 | 0 | 0 | -116.37 | 0 | 11451.3995 | 0 | 1 | Finished | 11567.7695 | 11567.7695 | C2013-01 Wiedauwkaai Fenders.xlsx
23 | 19 | Heien buispalen stak opw kant TL, DD I & SS O1(9 st) | 2007-06-22 08:00 | 2007-06-28 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 2007-06-22 08:00 | 5d | 34466.001 | 0 | 0 | 16547.8906 | 0 | 51013.8916 | 0 | 1 | Finished | 34466.001 | 34466.001 | C2013-01 Wiedauwkaai Fenders.xlsx
24 | 20 | Montage stak opw kant TL met verbindingen, & DD I | 2007-06-29 08:00 | 2007-07-10 17:00 | 8d |  | 0 | 0 | 1119.11 | 71623.0391 | 71623.0391 | 2007-08-01 08:00 | 8d | 71623.0391 | 0 | 0 | 7947.1802 | 0 | 79570.2192 | 0 | 1 | Finished | 71623.0391 | 71623.0391 | C2013-01 Wiedauwkaai Fenders.xlsx
25 | 21 | Heien buispalen stak opw: kop (7 st) | 2007-07-11 08:00 | 2007-07-16 17:00 | 4d |  | 0 | 1966.2 | 837.71 | 26806.7207 | 28772.9207 | 2007-07-11 08:00 | 4d | 28772.9207 | 0 | 0 | 12870.8301 | 0 | 41643.7507 | 0 | 1 | Finished | 28772.9207 | 28772.9207 | C2013-01 Wiedauwkaai Fenders.xlsx
26 | 22 | Montage stak opw kop | 2007-08-07 08:00 | 2007-08-13 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 | 2007-08-07 08:00 | 5d | 44764.3994 | 0 | 0 | 4966.9902 | 0 | 49731.3896 | 0 | 1 | Finished | 44764.3994 | 44764.3994 | C2013-01 Wiedauwkaai Fenders.xlsx
27 | 23 | Roosters | 2007-08-14 08:00 | 2007-08-20 17:00 | 5d |  | 0 | 0 | 779.25 | 31170 | 31170 | 2007-08-14 08:00 | 5d | 31170 | 0 | 0 | -21705.4805 | 0 | 9464.5195 | 0 | 1 | Finished | 31170 | 31170 | C2013-01 Wiedauwkaai Fenders.xlsx
28 | 24 | Scheepvaartseinen | 2007-08-22 08:00 | 2007-08-27 17:00 | 4d |  | 0 | 33154.6094 | 0 | 0 | 33154.6094 | 2007-08-22 08:00 | 4d | 33154.6094 | 0 | 0 | -1586.98 | 0 | 31567.6294 | 0 | 1 | Finished | 33154.6094 | 33154.6094 | C2013-01 Wiedauwkaai Fenders.xlsx
29 | 25 | Kabels voedingen | 2007-08-28 08:00 | 2007-08-30 17:00 | 3d |  | 0 | 19666.5605 | 0 | 0 | 19666.5605 | 2007-08-28 08:00 | 3d | 19666.5605 | 0 | 0 | 14802.9004 | 0 | 34469.4609 | 0 | 1 | Finished | 19666.5605 | 19666.5605 | C2013-01 Wiedauwkaai Fenders.xlsx
30 | 26 | Gestuurde boring | 2007-03-12 08:00 | 2007-03-23 17:00 | 10d |  |  | 29855.1895 |  |  | 54887.1091 |  | 10d | [5 empty] | 54887.1091 |  | 1 |  | 54887.1091 | 54887.1091 | C2013-01 Wiedauwkaai Fenders.xlsx
31 | 27 | Gestuurde boring | 2007-03-12 08:00 | 2007-03-20 17:00 | 7d |  | 0 | 25079.0195 | 378.62 | 21202.7197 | 46281.7393 | 2007-03-12 08:00 | 7d | 46281.7393 | 0 | 0 | 0 | 0 | 46281.7393 | 0 | 1 | Finished | 46281.7393 | 46281.7393 | C2013-01 Wiedauwkaai Fenders.xlsx
32 | 28 | Heien buispaal tbv boring | 2007-03-21 08:00 | 2007-03-21 17:00 | 1d |  | 0 | 0 | 478.65 | 3829.2 | 3829.2 | 2007-03-21 08:00 | 1d | 3829.2 | 0 | 0 | 0 | 0 | 3829.2 | 0 | 1 | Finished | 3829.2 | 3829.2 | C2013-01 Wiedauwkaai Fenders.xlsx
33 | 29 | Trekontlastingen, borden | 2007-03-22 08:00 | 2007-03-23 17:00 | 2d |  | 0 | 4776.1699 | 0 | 0 | 4776.1699 | 2007-03-22 08:00 | 2d | 4776.1699 | 0 | 0 | 0 | 0 | 4776.1699 | 0 | 1 | Finished | 4776.1699 | 4776.1699 | C2013-01 Wiedauwkaai Fenders.xlsx
34 | 30 | Kabelwerken | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  |  | 5963.3999 |  |  | 24123.3999 |  | 54d | [5 empty] | 50598.7983 |  | 1 |  | 24123.3999 | 24123.3999 | C2013-01 Wiedauwkaai Fenders.xlsx
35 | 31 | Fase 4: kabels door ingebaggerde buizen | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  | 0 | 5963.3999 | 227 | 18160 | 24123.3999 | 2007-03-22 08:00 | 54d | 104027.3999 | 0 | 0 | -53428.6016 | 0 | 50598.7983 | 0 | 1 | Finished | 24123.3999 | 24123.3999 | C2013-01 Wiedauwkaai Fenders.xlsx
36 | 32 | Dukdalven | 2007-06-29 08:00 | 2007-08-24 17:00 | 41d |  |  | 52913.5192 |  |  | 114453.359 |  | 46d | [5 empty] | 146330.3575 |  | 1 |  | 114453.359 | 114453.359 | C2013-01 Wiedauwkaai Fenders.xlsx
37 | 33 | Stalen brugjes | 2007-06-29 08:00 | 2007-07-20 17:00 | 16d |  | 0 | 902.15 | 480.78 | 61539.8398 | 62441.9899 | 2007-06-29 08:00 | 46d | 177829.1896 | 0 | 0 | -98313.1016 | 0 | 79516.088 | 0 | 1 | Finished | 62441.9899 | 62441.9899 | C2013-01 Wiedauwkaai Fenders.xlsx
38 | 34 | Scheepvaartseinen | 2007-08-13 08:00 | 2007-08-17 17:00 | 5d |  | 0 | 30008.4395 | 0 | 0 | 30008.4395 | 2007-08-13 08:00 | 5d | 30008.4395 | 0 | 0 | 0 | 0 | 30008.4395 | 0 | 1 | Finished | 30008.4395 | 30008.4395 | C2013-01 Wiedauwkaai Fenders.xlsx
39 | 35 | Kabels voedingen | 2007-08-21 08:00 | 2007-08-24 17:00 | 4d |  | 0 | 22002.9297 | 0 | 0 | 22002.9297 | 2007-08-21 08:00 | 4d | 22002.9297 | 0 | 0 | 14802.9004 | 0 | 36805.8301 | 0 | 1 | Finished | 22002.9297 | 22002.9297 | C2013-01 Wiedauwkaai Fenders.xlsx
40 | 36 | Stabilisatie landhoofd | 2007-03-22 08:00 | 2007-05-11 17:00 | 37d |  |  | 78594.2688 |  |  | 128036.4286 |  | 53d | [5 empty] | 155786.7478 |  | 1 |  | 128036.4286 | 128036.4286 | C2013-01 Wiedauwkaai Fenders.xlsx
41 | 37 | Opzoeken leidingen in vaargeul | 2007-03-22 08:00 | 2007-03-22 17:00 | 1d |  | 0 | 1127.6899 | 0 | 0 | 1127.6899 | 2007-02-28 08:00 | 1d | 1127.6899 | 0 | 0 | 0 | 0 | 1127.6899 | 0 | 1 | Finished | 1127.6899 | 1127.6899 | C2013-01 Wiedauwkaai Fenders.xlsx
42 | 38 | Peiling 1 | 2007-03-23 08:00 | 2007-03-23 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-02-28 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 1 | Finished | 1281.47 | 1281.47 | C2013-01 Wiedauwkaai Fenders.xlsx
43 | 39 | Onderwater grondbanketten aanbrengen | 2007-03-26 08:00 | 2007-03-29 17:00 | 4d |  | 0 | 0 | 778.38 | 24908.1602 | 24908.1602 | 2007-03-26 08:00 | 6d | 37362.2402 | 0 | 0 | -16004.9404 | 0 | 21357.2998 | 0 | 1 | Finished | 24908.1602 | 24908.1602 | C2013-01 Wiedauwkaai Fenders.xlsx
44 | 40 | Peiling 2 | 2007-03-30 08:00 | 2007-03-30 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-04-02 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 1 | Finished | 1281.47 | 1281.47 | C2013-01 Wiedauwkaai Fenders.xlsx
45 | 41 | Aanvoer boorinstallatie | 2007-04-02 08:00 | 2007-04-03 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 | 2007-03-28 08:00 | 2d | 5125.8599 | 0 | 0 | 0 | 0 | 5125.8599 | 0 | 1 | Finished | 5125.8599 | 5125.8599 | C2013-01 Wiedauwkaai Fenders.xlsx
46 | 42 | Groutinjecties | 2007-04-04 08:00 | 2007-04-24 17:00 | 15d |  | 0 | 63370.4492 | 204.45 | 24533.9996 | 87904.4489 | 2007-03-28 08:00 | 20d | 96082.4487 | 0 | 0 | 23123.1797 | 0 | 119205.6284 | 0 | 1 | Finished | 87904.4489 | 87904.4489 | C2013-01 Wiedauwkaai Fenders.xlsx
47 | 43 | Buitendienststellingsweekend 1 | 2007-04-27 17:00 | 2007-04-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2007-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-01 Wiedauwkaai Fenders.xlsx
48 | 44 | Buitendienststellingsweekend 2 | 2007-05-04 17:00 | 2007-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2007-05-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-01 Wiedauwkaai Fenders.xlsx
49 | 45 | Buitendienststellingsweekend 3 | 2007-05-11 17:00 | 2007-05-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2007-05-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-01 Wiedauwkaai Fenders.xlsx
50 | 46 | Peiling 3 | 2007-05-04 08:00 | 2007-05-04 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-05-04 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 1 | Finished | 1281.47 | 1281.47 | C2013-01 Wiedauwkaai Fenders.xlsx
51 | 47 | Afvoer boorinstallatie | 2007-05-07 08:00 | 2007-05-08 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 | 2007-05-07 08:00 | 2d | 5125.8599 | 0 | 0 | 0 | 0 | 5125.8599 | 0 | 1 | Finished | 5125.8599 | 5125.8599 | C2013-01 Wiedauwkaai Fenders.xlsx
52 | 48 | Opkuis werf | 2007-08-27 08:00 | 2007-08-31 17:00 | 5d |  | 0 | 3776.3201 | 0 | 0 | 3776.3201 | 2007-08-27 08:00 | 5d | 3776.3201 | 0 | 0 | 0 | 0 | 3776.3201 | 0 | 1 | Finished | 3776.3201 | 3776.3201 | C2013-01 Wiedauwkaai Fenders.xlsx
4 | 0 | Sewage Plant Hove | 2004-04-28 08:00 | 2005-11-11 17:00 | 403d |  |  | 58 |  |  | 1236603.6638 |  | 408d | [5 empty] | 1146444.3809 |  | 1 |  | 1236603.6638 | 1236603.6638 | C2013-02 Sewage Plant Hove.xlsx
5 | 1 | RWZI-HOVE | 2004-04-28 08:00 | 2004-04-28 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2004-04-28 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
6 | 2 | P1-P2-P3 | 2004-05-03 08:00 | 2005-11-11 17:00 | 400d |  | 0 | 0 | 69.19 | 221408.0078 | 221408.0078 | 2004-05-03 08:00 | 400d | 221408.0078 | 0 | 0 | 0 | 0 | 221408.0078 | 0 | 1 | Finished | 221408.0078 | 221408.0078 | C2013-02 Sewage Plant Hove.xlsx
7 | 3 | werfinstallatie | 2004-05-03 08:00 | 2004-06-09 17:00 | 28d |  |  | 0 |  |  | 84728.159 |  | 39d | [5 empty] | 74999.2654 |  | 1 |  | 84728.159 | 84728.159 | C2013-02 Sewage Plant Hove.xlsx
8 | 4 | installatie werfketen | 2004-05-03 08:00 | 2004-05-07 17:00 | 5d |  | 0 | 0 | 35.45 | 1418 | 1418 | 2004-05-03 08:00 | 5d | 1418 | 0 | 0 | 0 | 0 | 1418 | 0 | 1 | Finished | 1418 | 1418 | C2013-02 Sewage Plant Hove.xlsx
9 | 5 | sonderingen | 2004-05-03 08:00 | 2004-05-07 17:00 | 5d |  | 0 | 0 | 311.75 | 12470 | 12470 | 2004-05-03 08:00 | 5d | 12470 | 0 | 0 | 0 | 0 | 12470 | 0 | 1 | Finished | 12470 | 12470 | C2013-02 Sewage Plant Hove.xlsx
10 | 6 | afbraak slibverwerkingsgebouw | 2004-05-17 08:00 | 2004-05-28 17:00 | 10d |  | 0 | 0 | 375 | 30000 | 30000 | 2004-05-26 08:00 | 10d | 30000 | 0 | 0 | 0 | 0 | 30000 | 0 | 1 | Finished | 30000 | 30000 | C2013-02 Sewage Plant Hove.xlsx
11 | 7 | opbreken gedeelte terrein riolering | 2004-05-10 08:00 | 2004-05-14 17:00 | 5d |  | 0 | 0 | 309.175 | 12366.9995 | 12366.9995 | 2004-06-03 08:00 | 5d | 12366.9995 | 0 | 0 | 0 | 0 | 12366.9995 | 0 | 1 | Finished | 12366.9995 | 12366.9995 | C2013-02 Sewage Plant Hove.xlsx
12 | 8 | opbreken gedeelte bestaande wegenis | 2004-05-10 08:00 | 2004-05-14 17:00 | 5d |  | 0 | 0 | 41.5 | 1660 | 1660 | 2004-06-03 08:00 | 5d | 1660 | 0 | 0 | 0 | 0 | 1660 | 0 | 1 | Finished | 1660 | 1660 | C2013-02 Sewage Plant Hove.xlsx
13 | 9 | afgraven teelaarde | 2004-05-17 08:00 | 2004-05-19 17:00 | 3d |  | 0 | 0 | 41.67 | 1000.08 | 1000.08 | 2004-05-19 08:00 | 3d | 1000.08 | 0 | 0 | 0 | 0 | 1000.08 | 0 | 1 | Finished | 1000.08 | 1000.08 | C2013-02 Sewage Plant Hove.xlsx
14 | 10 | voorbereidende grondwerken | 2004-05-24 08:00 | 2004-05-26 17:00 | 3d |  | 0 | 0 | 41.67 | 1000.08 | 1000.08 | 2004-05-26 08:00 | 7d | 2333.5199 | 0 | 0 | -1000 | 0 | 1333.5199 | 0 | 1 | Finished | 1000.08 | 1000.08 | C2013-02 Sewage Plant Hove.xlsx
15 | 11 | plaatsen bemaling | 2004-05-27 08:00 | 2004-05-31 17:00 | 3d |  | 0 | 0 | 617.2083 | 14812.9995 | 14812.9995 | 2004-06-07 08:00 | 4d | 19750.666 | 0 | 0 | -15000 | 0 | 4750.666 | 0 | 1 | Finished | 14812.9995 | 14812.9995 | C2013-02 Sewage Plant Hove.xlsx
16 | 12 | inbuizen van de beek en opvangen van drains (grasland) | 2004-05-27 08:00 | 2004-06-09 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2004-06-11 08:00 | 10d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2013-02 Sewage Plant Hove.xlsx
17 | 13 | effluentmeting en lozingskonstruktie (deelwerk 2) | 2004-06-02 08:00 | 2004-11-08 17:00 | 114d |  |  | 1 |  |  | 5430.9152 |  | 178d | [5 empty] | 5780.8088 |  | 1 |  | 5430.9152 | 5430.9152 | C2013-02 Sewage Plant Hove.xlsx
18 | 14 | grondwerk | 2004-06-02 08:00 | 2004-06-04 17:00 | 3d |  | 0 | 0 | 20.8333 | 499.9992 | 499.9992 | 2004-06-11 08:00 | 3d | 499.9992 | 0 | 0 | 0 | 0 | 499.9992 | 0 | 1 | Finished | 499.9992 | 499.9992 | C2013-02 Sewage Plant Hove.xlsx
19 | 15 | betonwerken | 2004-06-07 08:00 | 2004-06-29 17:00 | 17d |  |  | 0 |  |  | 1999.9192 |  | 18d | [5 empty] | 2349.8128 |  | 1 |  | 1999.9192 | 1999.9192 | C2013-02 Sewage Plant Hove.xlsx
20 | 16 | zuiverheidsbeton | 2004-06-07 08:00 | 2004-06-07 17:00 | 1d |  | 0 | 0 | 62.5 | 500 | 500 | 2004-06-16 08:00 | 1d | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 1 | Finished | 500 | 500 | C2013-02 Sewage Plant Hove.xlsx
21 | 17 | vloerplaat | 2004-06-08 08:00 | 2004-06-10 17:00 | 3d |  | 0 | 0 | 20.8333 | 499.9992 | 499.9992 | 2004-06-17 08:00 | 2d | 333.3328 | 0 | 0 | 0 | 0 | 333.3328 | 0 | 1 | Finished | 499.9992 | 499.9992 | C2013-02 Sewage Plant Hove.xlsx
22 | 18 | wanden | 2004-06-11 08:00 | 2004-06-24 17:00 | 10d |  | 0 | 0 | 6.25 | 500 | 500 | 2004-06-21 08:00 | 7d | 350 | 0 | 0 | 0 | 0 | 350 | 0 | 1 | Finished | 500 | 500 | C2013-02 Sewage Plant Hove.xlsx
23 | 19 | waterdichtheidsproef | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 0 | 20.83 | 499.92 | 499.92 | 2004-07-01 08:00 | 7d | 1166.48 | 0 | 0 | 0 | 0 | 1166.48 | 0 | 1 | Finished | 499.92 | 499.92 | C2013-02 Sewage Plant Hove.xlsx
24 | 20 | plaatsen stortbuizen (omlegging effluentwater) | 2004-06-25 08:00 | 2004-07-05 17:00 | 7d |  | 0 | 0 | 17.8571 | 999.9976 | 999.9976 | 2004-06-21 08:00 | 7d | 999.9976 | 0 | 0 | 0 | 0 | 999.9976 | 0 | 1 | Finished | 999.9976 | 999.9976 | C2013-02 Sewage Plant Hove.xlsx
25 | 21 | aansluiting op bestaande effluentkoker NBT1/2 | 2004-07-06 08:00 | 2004-07-06 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 | 2004-06-30 08:00 | 1d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 1 | Finished | 100 | 100 | C2013-02 Sewage Plant Hove.xlsx
26 | 22 | opbraak gedeelte van bestaande effluentafvoerkoker | 2004-07-07 08:00 | 2004-07-08 17:00 | 2d |  | 0 | 0 | 31.25 | 500 | 500 | 2004-07-01 08:00 | 2d | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 1 | Finished | 500 | 500 | C2013-02 Sewage Plant Hove.xlsx
27 | 23 | plaatsen nieuwe effluentkoker en aansluiting kopmuur | 2004-11-02 08:00 | 2004-11-08 17:00 | 5d |  | 0 | 0 | 12.5 | 500 | 500 | 2004-12-07 08:00 | 5d | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 1 | Finished | 500 | 500 | C2013-02 Sewage Plant Hove.xlsx
28 | 24 | aanleg lekwaterleiding dia 150 | 2004-07-07 08:00 | 2004-07-09 17:00 | 3d |  | 0 | 0 | 34.5833 | 829.9992 | 829.9992 | 2004-12-14 08:00 | 3d | 829.9992 | 0 | 0 | 0 | 0 | 829.9992 | 0 | 1 | Finished | 829.9992 | 829.9992 | C2013-02 Sewage Plant Hove.xlsx
29 | 25 | looproosters, deksels, ladder,.. | 2004-07-09 08:00 | 2004-08-12 17:00 | 25d |  | 0 | 1 | 0 | 0 | 1 | 2005-02-02 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
30 | 26 | werken EM (lotII) | 2004-06-30 08:00 | 2004-07-08 17:00 | 7d |  |  | 4 |  |  | 4 |  | 152d | [5 empty] | 4 |  | 1 |  | 4 | 4 | C2013-02 Sewage Plant Hove.xlsx
31 | 27 | leveren en plaatsen : 2 manuele wandafsluiters | 2004-06-30 08:00 | 2004-07-06 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2004-12-07 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
32 | 28 | leveren en plaatsen : leiding en debietsmeter dia 600 | 2004-06-30 08:00 | 2004-07-06 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2004-07-01 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
33 | 29 | leveren en plaatsen : lekwaterpompje | 2004-06-30 08:00 | 2004-07-06 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2004-12-07 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
34 | 30 | electriciteit : kabels en lokaalbord | 2004-06-30 08:00 | 2004-07-08 17:00 | 7d |  | 0 | 1 | 0 | 0 | 1 | 2005-01-20 08:00 | 7d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
35 | 31 | nabezinktank 3 en recirkulatiepompstation (deelwerk 3) | 2004-06-02 08:00 | 2004-11-15 17:00 | 119d |  |  | 0 |  |  | 359382.3605 |  | 330d | [5 empty] | 286337.7676 |  | 1 |  | 359382.3605 | 359382.3605 | C2013-02 Sewage Plant Hove.xlsx
36 | 32 | beschoeiing | 2004-06-02 08:00 | 2004-06-08 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 | 2004-06-11 08:00 | 5d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 1 | Finished | 15000 | 15000 | C2013-02 Sewage Plant Hove.xlsx
37 | 33 | grondwerk | 2004-06-09 08:00 | 2004-06-17 17:00 | 7d |  | 0 | 0 | 187.5 | 10500 | 10500 | 2004-06-17 08:00 | 10d | 15000 | 0 | 0 | -4500 | 0 | 10500 | 0 | 1 | Finished | 10500 | 10500 | C2013-02 Sewage Plant Hove.xlsx
38 | 34 | palen | 2004-06-18 08:00 | 2004-06-24 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2005-09-09 08:00 | 5d | 25000 | 0 | 0 | -25000 | 0 | 0 | 0 | 1 | Finished | 25000 | 25000 | C2013-02 Sewage Plant Hove.xlsx
39 | 35 | grondwerk rond de palen voor zuiverheidsbeton | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 0 | 604.1667 | 14500.0005 | 14500.0005 | 2004-07-05 08:00 | 5d | 24166.6675 | 0 | 0 | -10000 | 0 | 14166.6675 | 0 | 1 | Finished | 14500.0005 | 14500.0005 | C2013-02 Sewage Plant Hove.xlsx
40 | 36 | betonwerken | 2004-06-30 08:00 | 2004-10-14 17:00 | 77d |  |  | 0 |  |  | 233382.9995 |  | 99d | [5 empty] | 194869.4998 |  | 1 |  | 233382.9995 | 233382.9995 | C2013-02 Sewage Plant Hove.xlsx
41 | 37 | zuiverheidsbeton, incl afkappen van de palen | 2004-06-30 08:00 | 2004-07-02 17:00 | 3d |  | 0 | 0 | 522.0833 | 12529.9995 | 12529.9995 | 2004-08-03 08:00 | 3d | 12529.9995 | 0 | 0 | 0 | 0 | 12529.9995 | 0 | 1 | Finished | 12529.9995 | 12529.9995 | C2013-02 Sewage Plant Hove.xlsx
42 | 38 | leidingen | 2004-07-05 08:00 | 2004-07-09 17:00 | 5d |  | 0 | 0 | 515 | 20600 | 20600 | 2004-08-06 08:00 | 5d | 20600 | 0 | 0 | -10000 | 0 | 10600 | 0 | 1 | Finished | 20600 | 20600 | C2013-02 Sewage Plant Hove.xlsx
43 | 39 | kern | 2004-08-03 08:00 | 2004-08-05 17:00 | 3d |  | 0 | 0 | 833.3333 | 19999.9995 | 19999.9995 | 2004-08-20 08:00 | 3d | 19999.9995 | 0 | 0 | -10000 | 0 | 9999.9995 | 0 | 1 | Finished | 19999.9995 | 19999.9995 | C2013-02 Sewage Plant Hove.xlsx
44 | 40 | vloerplaat | 2004-08-06 08:00 | 2004-08-19 17:00 | 10d |  | 0 | 0 | 250 | 20000 | 20000 | 2004-08-26 08:00 | 15d | 30000 | 0 | 0 | -20000 | 0 | 10000 | 0 | 1 | Finished | 20000 | 20000 | C2013-02 Sewage Plant Hove.xlsx
45 | 41 | wanden | 2004-08-20 08:00 | 2004-09-16 17:00 | 20d |  | 0 | 0 | 375 | 60000 | 60000 | 2004-09-15 08:00 | 20d | 60000 | 0 | 0 | -15000 | 0 | 45000 | 0 | 1 | Finished | 60000 | 60000 | C2013-02 Sewage Plant Hove.xlsx
46 | 42 | putten | 2004-09-17 08:00 | 2004-09-30 17:00 | 10d |  | 0 | 0 | 412.1625 | 32973.0005 | 32973.0005 | 2004-09-29 08:00 | 15d | 49459.5007 | 0 | 0 | 0 | 0 | 49459.5007 | 0 | 1 | Finished | 32973.0005 | 32973.0005 | C2013-02 Sewage Plant Hove.xlsx
47 | 43 | kolommen en vloerplaten centraal | 2004-08-20 08:00 | 2004-09-02 17:00 | 10d |  | 0 | 0 | 250 | 20000 | 20000 | 2004-09-15 08:00 | 20d | 40000 | 0 | 0 | -20000 | 0 | 20000 | 0 | 1 | Finished | 20000 | 20000 | C2013-02 Sewage Plant Hove.xlsx
48 | 44 | inbetonneren leveringen lot II | 2004-10-01 08:00 | 2004-10-06 17:00 | 4d |  | 0 | 0 | 852.5 | 27280 | 27280 | 2004-10-20 08:00 | 4d | 27280 | 0 | 0 | -10000 | 0 | 17280 | 0 | 1 | Finished | 27280 | 27280 | C2013-02 Sewage Plant Hove.xlsx
49 | 45 | waterdichtheidsproeven | 2004-10-07 08:00 | 2004-10-13 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2004-12-13 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | Finished | 5000 | 5000 | C2013-02 Sewage Plant Hove.xlsx
50 | 46 | afwerking | 2004-10-01 08:00 | 2004-10-14 17:00 | 10d |  | 0 | 0 | 187.5 | 15000 | 15000 | 2004-10-20 08:00 | 10d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 1 | Finished | 15000 | 15000 | C2013-02 Sewage Plant Hove.xlsx
51 | 47 | leidingen buiten de konstruktie (toevoer, afvoer en rc-persleiding) | 2004-10-14 08:00 | 2004-10-22 17:00 | 7d |  | 0 | 0 | 107.14 | 5999.84 | 5999.84 | 2004-11-16 08:00 | 10d | 8571.2 | 0 | 0 | 0 | 0 | 8571.2 | 0 | 1 | Finished | 5999.84 | 5999.84 | C2013-02 Sewage Plant Hove.xlsx
52 | 48 | aanvullingen en wegnemen beschoeiing | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 | 2004-12-01 08:00 | 5d | 30000 | 0 | 0 | 0 | 0 | 30000 | 0 | 1 | Finished | 30000 | 30000 | C2013-02 Sewage Plant Hove.xlsx
53 | 49 | looproosters en leuningen | 2004-10-28 08:00 | 2004-11-15 17:00 | 13d |  | 0 | 0 | 240.38 | 24999.5205 | 24999.5205 | 2005-01-25 08:00 | 10d | 19230.4004 | 0 | 0 | -6000 | 0 | 13230.4004 | 0 | 1 | Finished | 24999.5205 | 24999.5205 | C2013-02 Sewage Plant Hove.xlsx
54 | 50 | werken EM (lot II) | 2004-10-14 08:00 | 2004-10-27 17:00 | 10d |  |  | 4 |  |  | 4 |  | 40d | [5 empty] | 4 |  | 1 |  | 4 | 4 | C2013-02 Sewage Plant Hove.xlsx
55 | 51 | leveren en plaatsen : ruimerbrug, overstortranden, drijflaagafvoer,.. | 2004-10-14 08:00 | 2004-10-27 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2004-12-01 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
56 | 52 | leveren en plaatsen : spuislibpompen, leidingen, appendages,.. | 2004-10-14 08:00 | 2004-10-27 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2004-11-02 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
57 | 53 | leveren en plaatsen : em-debietsmeting, appendages,isolatie en tracing | 2004-10-14 08:00 | 2004-10-27 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2004-12-01 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
58 | 54 | electriciteit : kabels en lokaal bord | 2004-10-14 08:00 | 2004-10-27 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2004-12-14 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
59 | 55 | verdeelkamer nabezinktank 1/2 & 3 (deelwerk 4) | 2004-08-20 08:00 | 2004-10-20 17:00 | 44d |  |  | 0 |  |  | 86162.6799 |  | 120d | [5 empty] | 86162.6799 |  | 1 |  | 86162.6799 | 86162.6799 | C2013-02 Sewage Plant Hove.xlsx
60 | 56 | afbreken trapstruktuur | 2004-08-20 08:00 | 2004-08-23 17:00 | 2d |  | 0 | 0 | 86.6875 | 1387 | 1387 | 2004-09-03 08:00 | 2d | 1387 | 0 | 0 | 0 | 0 | 1387 | 0 | 1 | Finished | 1387 | 1387 | C2013-02 Sewage Plant Hove.xlsx
61 | 57 | sonderen en traceren bestaande leidingen | 2004-08-24 08:00 | 2004-08-25 17:00 | 2d |  | 0 | 0 | 62.5 | 1000 | 1000 | 2004-09-21 08:00 | 2d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 1 | Finished | 1000 | 1000 | C2013-02 Sewage Plant Hove.xlsx
62 | 58 | grondwerken | 2004-08-26 08:00 | 2004-08-27 17:00 | 2d |  | 0 | 0 | 750.9375 | 12015 | 12015 | 2004-09-23 08:00 | 2d | 12015 | 0 | 0 | 0 | 0 | 12015 | 0 | 1 | Finished | 12015 | 12015 | C2013-02 Sewage Plant Hove.xlsx
63 | 59 | ondersteuning bestaande toevoerleiding NBT 1/2 | 2004-08-30 08:00 | 2004-09-01 17:00 | 3d |  | 0 | 0 | 83.33 | 1999.92 | 1999.92 | 2004-09-27 08:00 | 3d | 1999.92 | 0 | 0 | 0 | 0 | 1999.92 | 0 | 1 | Finished | 1999.92 | 1999.92 | C2013-02 Sewage Plant Hove.xlsx
64 | 60 | betonwerken | 2004-09-02 08:00 | 2004-09-29 17:00 | 20d |  |  | 0 |  |  | 48039.92 |  | 27d | [5 empty] | 48039.92 |  | 1 |  | 48039.92 | 48039.92 | C2013-02 Sewage Plant Hove.xlsx
65 | 61 | zuiverheidsbeton | 2004-09-02 08:00 | 2004-09-02 17:00 | 1d |  | 0 | 0 | 1250 | 10000 | 10000 | 2004-10-01 08:00 | 1d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2013-02 Sewage Plant Hove.xlsx
66 | 62 | vloerplaat | 2004-09-03 08:00 | 2004-09-08 17:00 | 4d |  | 0 | 0 | 312.5 | 10000 | 10000 | 2004-10-05 08:00 | 4d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2013-02 Sewage Plant Hove.xlsx
67 | 63 | wanden | 2004-09-09 08:00 | 2004-09-24 17:00 | 12d |  | 0 | 0 | 240 | 23040 | 23040 | 2004-10-14 08:00 | 12d | 23040 | 0 | 0 | 0 | 0 | 23040 | 0 | 1 | Finished | 23040 | 23040 | C2013-02 Sewage Plant Hove.xlsx
68 | 64 | waterdichtheidsproeven | 2004-09-27 08:00 | 2004-09-29 17:00 | 3d |  | 0 | 0 | 208.33 | 4999.92 | 4999.92 | 2004-11-04 08:00 | 3d | 4999.92 | 0 | 0 | 0 | 0 | 4999.92 | 0 | 1 | Finished | 4999.92 | 4999.92 | C2013-02 Sewage Plant Hove.xlsx
69 | 65 | ontmantelen bestaande verdeelput en leiding dia 900 | 2004-09-30 08:00 | 2004-10-04 17:00 | 3d |  | 0 | 0 | 208.33 | 4999.92 | 4999.92 | 2005-02-08 08:00 | 3d | 4999.92 | 0 | 0 | 0 | 0 | 4999.92 | 0 | 1 | Finished | 4999.92 | 4999.92 | C2013-02 Sewage Plant Hove.xlsx
70 | 66 | aansluiten nieuwe leidingen | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 0 | 312.5 | 5000 | 5000 | 2005-02-11 08:00 | 2d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | Finished | 5000 | 5000 | C2013-02 Sewage Plant Hove.xlsx
71 | 67 | aanvullen bouwput | 2004-10-07 08:00 | 2004-10-11 17:00 | 3d |  | 0 | 0 | 208.33 | 4999.92 | 4999.92 | 2005-02-15 08:00 | 3d | 4999.92 | 0 | 0 | 0 | 0 | 4999.92 | 0 | 1 | Finished | 4999.92 | 4999.92 | C2013-02 Sewage Plant Hove.xlsx
72 | 68 | leuningen trappen en roosters | 2004-10-07 08:00 | 2004-10-20 17:00 | 10d |  | 0 | 0 | 84.0125 | 6720.9998 | 6720.9998 | 2004-12-01 08:00 | 10d | 6720.9998 | 0 | 0 | 0 | 0 | 6720.9998 | 0 | 1 | Finished | 6720.9998 | 6720.9998 | C2013-02 Sewage Plant Hove.xlsx
73 | 69 | werken EM (lot II) | 2004-09-30 08:00 | 2004-10-06 17:00 | 5d |  |  | 1 |  |  | 1 |  | 5d | [5 empty] | 1 |  | 1 |  | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
74 | 70 | leveren en plaatsen manuelen overstortschuiven | 2004-09-30 08:00 | 2004-10-06 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2004-11-08 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
75 | 71 | interventie AQUAFIN | 2004-09-30 08:00 | 2004-10-06 17:00 | 5d |  |  | 1 |  |  | 1 |  | 5d | [5 empty] | 1 |  | 1 |  | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
76 | 72 | overpompen van beluchting naar verdeelkamer NBT3 | 2004-09-30 08:00 | 2004-10-06 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2005-02-08 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
77 | 73 | slibbuffertanks (deelwerk 5) | 2004-06-11 08:00 | 2004-10-07 17:00 | 85d |  |  | 0 |  |  | 136276.7585 |  | 115d | [5 empty] | 152490.679 |  | 1 |  | 136276.7585 | 136276.7585 | C2013-02 Sewage Plant Hove.xlsx
78 | 74 | grondwerk | 2004-06-11 08:00 | 2004-06-15 17:00 | 3d |  | 0 | 0 | 139 | 3336 | 3336 | 2004-06-28 08:00 | 3d | 3336 | 0 | 0 | 0 | 0 | 3336 | 0 | 1 | Finished | 3336 | 3336 | C2013-02 Sewage Plant Hove.xlsx
79 | 75 | palen | 2004-06-16 08:00 | 2004-06-17 17:00 | 2d |  | 0 | 0 | 833.3125 | 13333 | 13333 | 2004-07-01 08:00 | 2d | 13333 | 0 | 0 | 0 | 0 | 13333 | 0 | 1 | Finished | 13333 | 13333 | C2013-02 Sewage Plant Hove.xlsx
80 | 76 | grondwerk tussen de palen voor zuiverheidsbeton | 2004-06-18 08:00 | 2004-06-18 17:00 | 1d |  | 0 | 0 | 416.6 | 3332.8 | 3332.8 | 2004-07-05 08:00 | 1d | 3332.8 | 0 | 0 | 0 | 0 | 3332.8 | 0 | 1 | Finished | 3332.8 | 3332.8 | C2013-02 Sewage Plant Hove.xlsx
81 | 77 | betonwerken | 2004-06-21 08:00 | 2004-09-09 17:00 | 59d |  |  | 0 |  |  | 96074.9585 |  | 109d | [5 empty] | 112288.8789 |  | 1 |  | 96074.9585 | 96074.9585 | C2013-02 Sewage Plant Hove.xlsx
82 | 78 | zuiverheidsbeton, incl afkappen van de palen | 2004-06-21 08:00 | 2004-06-23 17:00 | 3d |  | 0 | 0 | 471.3 | 11311.1997 | 11311.1997 | 2004-07-06 08:00 | 4d | 15081.5996 | 0 | 0 | -4000 | 0 | 11081.5996 | 0 | 1 | Finished | 11311.1997 | 11311.1997 | C2013-02 Sewage Plant Hove.xlsx
83 | 79 | vloerplaten | 2004-06-24 08:00 | 2004-07-01 17:00 | 6d |  | 0 | 0 | 652.0833 | 31299.999 | 31299.999 | 2004-08-03 08:00 | 6d | 31299.999 | 0 | 0 | 0 | 0 | 31299.999 | 0 | 1 | Finished | 31299.999 | 31299.999 | C2013-02 Sewage Plant Hove.xlsx
84 | 80 | wanden | 2004-07-02 08:00 | 2004-07-27 17:00 | 18d |  | 0 | 0 | 159.72 | 22999.6802 | 22999.6802 | 2004-08-11 08:00 | 70d | 89443.2007 | 0 | 0 | -50000 | 0 | 39443.2007 | 0 | 1 | Finished | 22999.6802 | 22999.6802 | C2013-02 Sewage Plant Hove.xlsx
85 | 81 | uitvullingsbeton | 2004-08-19 08:00 | 2004-08-23 17:00 | 3d |  | 0 | 0 | 535.67 | 12856.0796 | 12856.0796 | 2004-11-22 08:00 | 3d | 12856.0796 | 0 | 0 | 0 | 0 | 12856.0796 | 0 | 1 | Finished | 12856.0796 | 12856.0796 | C2013-02 Sewage Plant Hove.xlsx
86 | 82 | waterdichtheidsproeven | 2004-08-24 08:00 | 2004-08-26 17:00 | 3d |  | 0 | 0 | 284.5 | 6828 | 6828 | 2004-11-25 08:00 | 3d | 6828 | 0 | 0 | 0 | 0 | 6828 | 0 | 1 | Finished | 6828 | 6828 | C2013-02 Sewage Plant Hove.xlsx
87 | 83 | afwerking | 2004-08-27 08:00 | 2004-09-09 17:00 | 10d |  | 0 | 0 | 134.75 | 10780 | 10780 | 2004-11-22 08:00 | 10d | 10780 | 0 | 0 | 0 | 0 | 10780 | 0 | 1 | Finished | 10780 | 10780 | C2013-02 Sewage Plant Hove.xlsx
88 | 84 | plaatsen persleiding voedingspompen | 2004-09-10 08:00 | 2004-09-15 17:00 | 4d |  | 0 | 0 | 318.75 | 10200 | 10200 | 2004-11-29 08:00 | 4d | 10200 | 0 | 0 | 0 | 0 | 10200 | 0 | 1 | Finished | 10200 | 10200 | C2013-02 Sewage Plant Hove.xlsx
89 | 85 | staalstruktuur met trap en bordessen | 2004-09-24 08:00 | 2004-10-07 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2004-11-22 08:00 | 10d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2013-02 Sewage Plant Hove.xlsx
90 | 86 | werken EM (lot II) | 2004-09-10 08:00 | 2004-09-23 17:00 | 10d |  |  | 3 |  |  | 3 |  | 10d | [5 empty] | 3 |  | 1 |  | 3 | 3 | C2013-02 Sewage Plant Hove.xlsx
91 | 87 | leveren en plaatsen mixers, meettoestellen,.. | 2004-09-10 08:00 | 2004-09-23 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2004-12-01 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
92 | 88 | leveren en plaatsen leidingen met appendages, isolatie en tracing | 2004-09-10 08:00 | 2004-09-23 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2004-12-01 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
93 | 89 | electriciteit : kabels en lokale borden | 2004-09-10 08:00 | 2004-09-23 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2004-12-01 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
94 | 90 | pompenkelder slibbehandeling (deelwerk 6) | 2004-08-27 08:00 | 2004-10-04 17:00 | 27d |  |  | 0 |  |  | 30360 |  | 30d | [5 empty] | 32660 |  | 1 |  | 30360 | 30360 | C2013-02 Sewage Plant Hove.xlsx
95 | 91 | opbreken bestaande sokkels in overleg met lot II | 2004-08-27 08:00 | 2004-09-09 17:00 | 10d |  | 0 | 0 | 75 | 6000 | 6000 | 2004-10-18 08:00 | 10d | 6000 | 0 | 0 | 2300 | 0 | 8300 | 0 | 1 | Finished | 6000 | 6000 | C2013-02 Sewage Plant Hove.xlsx
96 | 92 | afwerken vloeroppervlak | 2004-09-10 08:00 | 2004-09-16 17:00 | 5d |  | 0 | 0 | 137.5 | 5500 | 5500 | 2004-11-02 08:00 | 5d | 5500 | 0 | 0 | 0 | 0 | 5500 | 0 | 1 | Finished | 5500 | 5500 | C2013-02 Sewage Plant Hove.xlsx
97 | 93 | dichten van oude doorvoeropeningen (leidingen en kabels) | 2004-09-17 08:00 | 2004-09-22 17:00 | 4d |  | 0 | 0 | 171.875 | 5500 | 5500 | 2004-11-09 08:00 | 4d | 5500 | 0 | 0 | 0 | 0 | 5500 | 0 | 1 | Finished | 5500 | 5500 | C2013-02 Sewage Plant Hove.xlsx
98 | 94 | maken nieuwe doorvoeropeningen (leidingen en kabels) | 2004-09-23 08:00 | 2004-09-28 17:00 | 4d |  | 0 | 0 | 171.875 | 5500 | 5500 | 2004-11-17 08:00 | 4d | 5500 | 0 | 0 | 0 | 0 | 5500 | 0 | 1 | Finished | 5500 | 5500 | C2013-02 Sewage Plant Hove.xlsx
99 | 95 | betonwerken : sokkels (voedingspompen slibbuffertanks) | 2004-09-29 08:00 | 2004-10-04 17:00 | 4d |  | 0 | 0 | 245.625 | 7860 | 7860 | 2004-11-23 08:00 | 4d | 7860 | 0 | 0 | 0 | 0 | 7860 | 0 | 1 | Finished | 7860 | 7860 | C2013-02 Sewage Plant Hove.xlsx
100 | 96 | werken EM (lot II) | 2004-08-27 08:00 | 2004-11-16 17:00 | 58d |  |  | 6 |  |  | 6 |  | 50d | [5 empty] | 6 |  | 1 |  | 6 | 6 | C2013-02 Sewage Plant Hove.xlsx
101 | 97 | demonteren van oude voedingspompen (incl leidingen, kabels,..) | 2004-08-27 08:00 | 2004-09-09 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2004-11-15 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
102 | 98 | leveren en plaatsen nieuwe excenterwormpompen (incl leidingen,..) | 2004-10-05 08:00 | 2004-10-18 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2004-12-01 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
103 | 99 | electriciteit : kabels en lokale borden | 2004-10-19 08:00 | 2004-11-01 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2004-12-01 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
104 | 100 | aansluiten zuigleiding nieuwe pompen | 2004-10-19 08:00 | 2004-11-01 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2004-12-01 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
105 | 101 | demontage voedingspompen voormalige slibbuffertank (incl leidingen, kabels,..) | 2004-11-03 08:00 | 2004-11-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-01-10 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
106 | 102 | demontage oude voedingspompen indikker (incl leidingen, kabels,..) | 2004-11-03 08:00 | 2004-11-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-01-10 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
107 | 103 | interventie AQUAFIN | 2004-11-02 08:00 | 2004-11-02 17:00 | 1d |  |  | 1 |  |  | 1 |  | 1d | [5 empty] | 1 |  | 1 |  | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
108 | 104 | gedurende 8 uren niet spuien | 2004-11-02 08:00 | 2004-11-02 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2005-01-14 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
109 | 105 | voeding indikker (deelwerk 7) | 2004-10-05 08:00 | 2004-10-18 17:00 | 10d |  |  | 0 |  |  | 12000.08 |  | 9d | [5 empty] | 16000.08 |  | 1 |  | 12000.08 | 12000.08 | C2013-02 Sewage Plant Hove.xlsx
110 | 106 | verwijderen oude trappen en bordes over RC | 2004-10-05 08:00 | 2004-10-07 17:00 | 3d |  | 0 | 0 | 41.67 | 1000.08 | 1000.08 | 2005-02-01 08:00 | 3d | 1000.08 | 0 | 0 | 0 | 0 | 1000.08 | 0 | 1 | Finished | 1000.08 | 1000.08 | C2013-02 Sewage Plant Hove.xlsx
111 | 107 | maken leidingdoorvoer in wand RC (vijzelput) | 2004-10-08 08:00 | 2004-10-11 17:00 | 2d |  | 0 | 0 | 312.5 | 5000 | 5000 | 2005-02-03 08:00 | 2d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | Finished | 5000 | 5000 | C2013-02 Sewage Plant Hove.xlsx
112 | 108 | aanleg van persleiding in volle grond (dia 90) | 2004-10-12 08:00 | 2004-10-18 17:00 | 5d |  | 0 | 0 | 150 | 6000 | 6000 | 2005-02-07 08:00 | 5d | 6000 | 0 | 0 | 4000 | 0 | 10000 | 0 | 1 | Finished | 6000 | 6000 | C2013-02 Sewage Plant Hove.xlsx
113 | 109 | werken EM (lot II) | 2004-10-08 08:00 | 2004-11-15 17:00 | 27d |  |  | 4 |  |  | 4 |  | 38d | [5 empty] | 4 |  | 1 |  | 4 | 4 | C2013-02 Sewage Plant Hove.xlsx
114 | 110 | reviseren bestaande wandafsluiter | 2004-10-08 08:00 | 2004-10-08 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2004-12-01 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
115 | 111 | leveren en plaatsen van 2 dompelpompen | 2004-10-11 08:00 | 2004-10-15 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2004-12-01 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
116 | 112 | leveren en plaatsen leidingen, appendages, isolatie en tracing | 2004-10-18 08:00 | 2004-10-29 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-01-10 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
117 | 113 | electriciteit : kabels en lokale borden | 2004-11-02 08:00 | 2004-11-15 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-01-10 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
118 | 114 | interventie AQUAFIN | 2004-10-08 08:00 | 2004-10-08 17:00 | 1d |  |  | 1 |  |  | 1 |  | 1d | [5 empty] | 1 |  | 1 |  | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
119 | 115 | gedurende 8 uren de RC-vijzels niet opstarten | 2004-10-08 08:00 | 2004-10-08 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2005-01-14 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
120 | 116 | SWA-lijn (deelwerk 8) | 2004-09-17 08:00 | 2004-11-26 17:00 | 51d |  |  | 0 |  |  | 26829.9191 |  | 77d | [5 empty] | 32652.9191 |  | 1 |  | 26829.9191 | 26829.9191 | C2013-02 Sewage Plant Hove.xlsx
121 | 117 | verwijderen trap en bordes struktuur over roostergoten | 2004-09-17 08:00 | 2004-09-20 17:00 | 2d |  | 0 | 0 | 62.5 | 1000 | 1000 | 2004-11-04 08:00 | 2d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 1 | Finished | 1000 | 1000 | C2013-02 Sewage Plant Hove.xlsx
122 | 118 | grondwerken en eventuele beschoeiing | 2004-09-21 08:00 | 2004-09-24 17:00 | 4d |  | 0 | 0 | 31.25 | 1000 | 1000 | 2004-11-08 08:00 | 4d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 1 | Finished | 1000 | 1000 | C2013-02 Sewage Plant Hove.xlsx
123 | 119 | betonwerken | 2004-09-27 08:00 | 2004-10-21 17:00 | 19d |  |  | 0 |  |  | 14999.9191 |  | 19d | [5 empty] | 14999.9191 |  | 1 |  | 14999.9191 | 14999.9191 | C2013-02 Sewage Plant Hove.xlsx
124 | 120 | plaatsen bocht 90° dia 600 | 2004-09-27 08:00 | 2004-09-27 17:00 | 1d |  | 0 | 0 | 250 | 2000 | 2000 | 2004-11-16 08:00 | 1d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 1 | Finished | 2000 | 2000 | C2013-02 Sewage Plant Hove.xlsx
125 | 121 | zuiverheidsberton | 2004-09-28 08:00 | 2004-09-29 17:00 | 2d |  | 0 | 0 | 125 | 2000 | 2000 | 2004-11-17 08:00 | 2d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 1 | Finished | 2000 | 2000 | C2013-02 Sewage Plant Hove.xlsx
126 | 122 | vloerplaat | 2004-09-30 08:00 | 2004-10-04 17:00 | 3d |  | 0 | 0 | 208.33 | 4999.92 | 4999.92 | 2004-11-19 08:00 | 3d | 4999.92 | 0 | 0 | 0 | 0 | 4999.92 | 0 | 1 | Finished | 4999.92 | 4999.92 | C2013-02 Sewage Plant Hove.xlsx
127 | 123 | wanden | 2004-10-05 08:00 | 2004-10-13 17:00 | 7d |  | 0 | 0 | 89.2857 | 4999.9991 | 4999.9991 | 2004-11-24 08:00 | 7d | 4999.9991 | 0 | 0 | 0 | 0 | 4999.9991 | 0 | 1 | Finished | 4999.9991 | 4999.9991 | C2013-02 Sewage Plant Hove.xlsx
128 | 124 | aanvullen (herstellen van talud) | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 0 | 62.5 | 1000 | 1000 | 2004-12-09 08:00 | 2d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 1 | Finished | 1000 | 1000 | C2013-02 Sewage Plant Hove.xlsx
129 | 125 | creëren van de overstortopening in de roostergoten naar nieuwe put | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  | 0 | 0 | 62.5 | 2000 | 2000 | 2004-12-14 08:00 | 4d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 1 | Finished | 2000 | 2000 | C2013-02 Sewage Plant Hove.xlsx
130 | 126 | SWA-leiding tot aan de bestaande RWA-afvoergoot | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  | 0 | 0 | 31.25 | 1000 | 1000 | 2004-12-03 08:00 | 4d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 1 | Finished | 1000 | 1000 | C2013-02 Sewage Plant Hove.xlsx
131 | 127 | aansluiten nieuwe SWA-leiding in de wand van de bestaande RWA-goot | 2004-10-20 08:00 | 2004-10-22 17:00 | 3d |  | 0 | 0 | 76.25 | 1830 | 1830 | 2004-12-09 08:00 | 3d | 1830 | 0 | 0 | 5823 | 0 | 7653 | 0 | 1 | Finished | 1830 | 1830 | C2013-02 Sewage Plant Hove.xlsx
132 | 128 | nieuw bordes en tapstructuur | 2004-11-15 08:00 | 2004-11-26 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2005-02-07 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | Finished | 5000 | 5000 | C2013-02 Sewage Plant Hove.xlsx
133 | 129 | werken EM (lotII) | 2004-10-20 08:00 | 2004-11-09 17:00 | 15d |  |  | 2 |  |  | 2 |  | 59d | [5 empty] | 2 |  | 1 |  | 2 | 2 | C2013-02 Sewage Plant Hove.xlsx
134 | 130 | leveren en plaatsen van motorische overstortschuif | 2004-10-20 08:00 | 2004-10-26 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2004-12-01 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
135 | 131 | bekabeling en lokaal bord | 2004-10-27 08:00 | 2004-11-09 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-02-08 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
136 | 132 | interventie AQUAFIN | 2004-10-14 08:00 | 2004-10-22 17:00 | 7d |  |  | 1 |  |  | 1 |  | 7d | [5 empty] | 1 |  | 1 |  | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
137 | 133 | enkel de DWA-influentvijzels zijn in gebruik, de RWA-fractie verpompen | 2004-10-14 08:00 | 2004-10-22 17:00 | 7d |  | 0 | 1 | 0 | 0 | 1 | 2004-12-01 08:00 | 7d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
138 | 134 | beluchtingstank 1 (deelwerk 9) | 2005-01-10 08:00 | 2005-04-01 17:00 | 60d |  |  | 0 |  |  | 53672.0004 |  | 75d | [5 empty] | 48013.0004 |  | 1 |  | 53672.0004 | 53672.0004 | C2013-02 Sewage Plant Hove.xlsx
139 | 135 | maken doorvoering voor leiding dia 1200 | 2005-01-10 08:00 | 2005-01-21 17:00 | 10d |  | 0 | 0 | 84.81 | 6784.7998 | 6784.7998 | 2005-02-14 08:00 | 10d | 6784.7998 | 0 | 0 | 0 | 0 | 6784.7998 | 0 | 1 | Finished | 6784.7998 | 6784.7998 | C2013-02 Sewage Plant Hove.xlsx
140 | 136 | leiding dia 1200 naar bestaande RBT | 2005-01-24 08:00 | 2005-02-04 17:00 | 10d |  | 0 | 0 | 87.5 | 7000 | 7000 | 2005-02-14 08:00 | 10d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 1 | Finished | 7000 | 7000 | C2013-02 Sewage Plant Hove.xlsx
141 | 137 | betonwerken | 2005-02-07 08:00 | 2005-02-18 17:00 | 10d |  |  | 0 |  |  | 27808.0005 |  | 75d | [5 empty] | 27808.0005 |  | 1 |  | 27808.0005 | 27808.0005 | C2013-02 Sewage Plant Hove.xlsx
142 | 138 | sokkels voor blowers in pompenkelder | 2005-02-07 08:00 | 2005-02-18 17:00 | 10d |  | 0 | 0 | 181.3 | 14504.0002 | 14504.0002 | 2004-11-15 08:00 | 10d | 14504.0002 | 0 | 0 | 0 | 0 | 14504.0002 | 0 | 1 | Finished | 14504.0002 | 14504.0002 | C2013-02 Sewage Plant Hove.xlsx
143 | 139 | plaatsen waterdichte 'wand' (zie doorvoering beluchting 2) | 2005-02-07 08:00 | 2005-02-18 17:00 | 10d |  | 0 | 0 | 166.3 | 13304.0002 | 13304.0002 | 2005-02-14 08:00 | 10d | 13304.0002 | 0 | 0 | 0 | 0 | 13304.0002 | 0 | 1 | Finished | 13304.0002 | 13304.0002 | C2013-02 Sewage Plant Hove.xlsx
144 | 140 | blowerleiding (in volle grond) | 2005-02-21 08:00 | 2005-03-04 17:00 | 10d |  | 0 | 0 | 56.3 | 4503.9999 | 4503.9999 | 2005-02-14 08:00 | 10d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 1 | Finished | 4503.9999 | 4503.9999 | C2013-02 Sewage Plant Hove.xlsx
145 | 141 | leuningen | 2005-03-21 08:00 | 2005-04-01 17:00 | 10d |  | 0 | 0 | 94.69 | 7575.2002 | 7575.2002 | 2005-02-14 08:00 | 10d | 7575.2002 | 0 | 0 | -5659 | 0 | 1916.2002 | 0 | 1 | Finished | 7575.2002 | 7575.2002 | C2013-02 Sewage Plant Hove.xlsx
146 | 142 | werken EM (lot II) | 2005-01-10 08:00 | 2005-03-18 17:00 | 50d |  |  | 6 |  |  | 6 |  | 10d | [5 empty] | 6 |  | 1 |  | 6 | 6 | C2013-02 Sewage Plant Hove.xlsx
147 | 143 | verwijderen bestaande EM-uitrusting | 2005-01-10 08:00 | 2005-01-21 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-02-14 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
148 | 144 | leveren en plaatsen manuele wandafsluiter dia 1200 | 2005-02-07 08:00 | 2005-02-18 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-02-14 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
149 | 145 | leveren en plaatsen meng en meettoestellen | 2005-02-21 08:00 | 2005-03-04 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-02-14 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
150 | 146 | leveren en plaatsen van beluchtingssysteem (blowers, leidingen, schotels,..) | 2005-02-21 08:00 | 2005-03-04 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-02-14 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
151 | 147 | costrueren aanzuigkoker | 2005-02-21 08:00 | 2005-03-04 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-02-14 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
152 | 148 | electriciteit : kabels en lokale borden | 2005-03-07 08:00 | 2005-03-18 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-02-14 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
153 | 149 | influentgoot na zandvanger, selektortank en anoxische reactor 1 (deelwerk 10) | 2005-02-07 08:00 | 2005-08-05 17:00 | 130d |  |  | 7 |  |  | 44496.0002 |  | 46d | [5 empty] | 33955.6002 |  | 1 |  | 44496.0002 | 44496.0002 | C2013-02 Sewage Plant Hove.xlsx
154 | 150 | influentgoten | 2005-04-04 08:00 | 2005-04-29 17:00 | 20d |  |  | 0 |  |  | 17024.0002 |  | 33d | [5 empty] | 10342.4002 |  | 1 |  | 17024.0002 | 17024.0002 | C2013-02 Sewage Plant Hove.xlsx
155 | 151 | afbreken scheidingswand (l=7m), afwerken betonoppervlak | 2005-04-04 08:00 | 2005-04-15 17:00 | 10d |  | 0 | 0 | 53.2 | 4256.0001 | 4256.0001 | 2005-01-19 08:00 | 7d | 2979.2 | 0 | 0 | -2000 | 0 | 979.2 | 0 | 1 | Finished | 4256.0001 | 4256.0001 | C2013-02 Sewage Plant Hove.xlsx
156 | 152 | aanpassen beton thv instroom | 2005-04-18 08:00 | 2005-04-29 17:00 | 10d |  | 0 | 0 | 53.2 | 4256.0001 | 4256.0001 | 2005-01-28 08:00 | 10d | 4256.0001 | 0 | 0 | 0 | 0 | 4256.0001 | 0 | 1 | Finished | 4256.0001 | 4256.0001 | C2013-02 Sewage Plant Hove.xlsx
157 | 153 | vernieuwen trapstruktuur | 2005-04-04 08:00 | 2005-04-15 17:00 | 10d |  | 0 | 0 | 53.2 | 4256.0001 | 4256.0001 | 2005-02-17 08:00 | 10d | 4256.0001 | 0 | 0 | 0 | 0 | 4256.0001 | 0 | 1 | Finished | 4256.0001 | 4256.0001 | C2013-02 Sewage Plant Hove.xlsx
158 | 154 | plaatsen voorlopige afdichting in toevoergoot naar huidige RBT's | 2005-04-18 08:00 | 2005-04-29 17:00 | 10d |  | 0 | 0 | 53.2 | 4256.0001 | 4256.0001 | 2005-01-17 08:00 | 2d | 851.2 | 0 | 0 | 0 | 0 | 851.2 | 0 | 1 | Finished | 4256.0001 | 4256.0001 | C2013-02 Sewage Plant Hove.xlsx
159 | 155 | selektortank | 2005-02-07 08:00 | 2005-05-27 17:00 | 80d |  |  | 0 |  |  | 8133.9999 |  | 24d | [5 empty] | 6091.1999 |  | 1 |  | 8133.9999 | 8133.9999 | C2013-02 Sewage Plant Hove.xlsx
160 | 156 | verwijderen trappen en leuningen | 2005-02-07 08:00 | 2005-02-18 17:00 | 10d |  | 0 | 0 | 23.625 | 1890 | 1890 | 2005-01-19 08:00 | 9d | 1701 | 0 | 0 | -1000 | 0 | 701 | 0 | 1 | Finished | 1890 | 1890 | C2013-02 Sewage Plant Hove.xlsx
161 | 157 | uitbreken kopse wand | 2005-02-21 08:00 | 2005-03-04 17:00 | 10d |  | 0 | 0 | 25.2125 | 2017 | 2017 | 2005-01-24 08:00 | 14d | 2823.8 | 0 | 0 | -1000 | 0 | 1823.8 | 0 | 1 | Finished | 2017 | 2017 | C2013-02 Sewage Plant Hove.xlsx
162 | 158 | opvullen slibkuilen en aanpassen leeglaat | 2005-03-07 08:00 | 2005-03-18 17:00 | 10d |  | 0 | 0 | 32.1875 | 2575 | 2575 | 2005-01-24 08:00 | 14d | 3605 | 0 | 0 | -1000 | 0 | 2605 | 0 | 1 | Finished | 2575 | 2575 | C2013-02 Sewage Plant Hove.xlsx
163 | 159 | betonneren duikschotten en dichtstorten bestaande uitstroom | 2005-03-21 08:00 | 2005-04-01 17:00 | 10d |  | 0 | 0 | 7.1875 | 575 | 575 | 2005-01-24 08:00 | 21d | 1207.5 | 0 | 0 | -1000 | 0 | 207.5 | 0 | 1 | Finished | 575 | 575 | C2013-02 Sewage Plant Hove.xlsx
164 | 160 | plaatsen nieuwe loopbruggen, trappen, leuningen,.. | 2005-05-16 08:00 | 2005-05-27 17:00 | 10d |  | 0 | 0 | 13.4625 | 1077 | 1077 | 2005-02-11 08:00 | 7d | 753.9 | 0 | 0 | 0 | 0 | 753.9 | 0 | 1 | Finished | 1077 | 1077 | C2013-02 Sewage Plant Hove.xlsx
165 | 161 | werken EM | 2005-04-04 08:00 | 2005-05-13 17:00 | 30d |  |  | 3 |  |  | 3 |  | 27d | [5 empty] | 3 |  | 1 |  | 3 | 3 | C2013-02 Sewage Plant Hove.xlsx
166 | 162 | ombouwen ruimerbrug | 2005-04-04 08:00 | 2005-04-15 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-01-19 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
167 | 163 | leveren en plaatsen van mixers, wandafsluiters en meettoestellen | 2005-04-18 08:00 | 2005-04-29 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-02-11 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
168 | 164 | electriciteit: kabels en lokale borden | 2005-05-02 08:00 | 2005-05-13 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-02-11 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
169 | 165 | anoxisch bekken 1 | 2005-02-07 08:00 | 2005-06-10 17:00 | 90d |  |  | 0 |  |  | 19331.0001 |  | 27d | [5 empty] | 17515.0001 |  | 1 |  | 19331.0001 | 19331.0001 | C2013-02 Sewage Plant Hove.xlsx
170 | 166 | verwijderen trappen en leuningen | 2005-02-07 08:00 | 2005-02-18 17:00 | 10d |  | 0 | 0 | 28.375 | 2270 | 2270 | 2005-01-19 08:00 | 2d | 454 | 0 | 0 | 0 | 0 | 454 | 0 | 1 | Finished | 2270 | 2270 | C2013-02 Sewage Plant Hove.xlsx
171 | 167 | opvullen slibkuilen en aanpassen leeglaten | 2005-02-21 08:00 | 2005-03-04 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2005-02-11 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 1 | Finished | 2000 | 2000 | C2013-02 Sewage Plant Hove.xlsx
172 | 168 | afdichten toevoeropeningen | 2005-03-07 08:00 | 2005-03-18 17:00 | 10d |  | 0 | 0 | 7.1875 | 575 | 575 | 2005-01-24 08:00 | 10d | 575 | 0 | 0 | 0 | 0 | 575 | 0 | 1 | Finished | 575 | 575 | C2013-02 Sewage Plant Hove.xlsx
173 | 169 | creëren van doorvoeropening en geleidingswand | 2005-03-21 08:00 | 2005-04-01 17:00 | 10d |  | 0 | 0 | 7.1875 | 575 | 575 | 2005-01-24 08:00 | 10d | 575 | 0 | 0 | 0 | 0 | 575 | 0 | 1 | Finished | 575 | 575 | C2013-02 Sewage Plant Hove.xlsx
174 | 170 | aanbrengen van uitvullingsbeton en dichtstorten bestaande uitstroom | 2005-04-04 08:00 | 2005-04-15 17:00 | 10d |  | 0 | 0 | 53.2 | 4256.0001 | 4256.0001 | 2005-02-11 08:00 | 10d | 4256.0001 | 0 | 0 | 0 | 0 | 4256.0001 | 0 | 1 | Finished | 4256.0001 | 4256.0001 | C2013-02 Sewage Plant Hove.xlsx
175 | 171 | leuningen, loopbruggen en trappen | 2005-05-30 08:00 | 2005-06-10 17:00 | 10d |  | 0 | 0 | 120.6875 | 9655 | 9655 | 2005-02-11 08:00 | 10d | 9655 | 0 | 0 | 0 | 0 | 9655 | 0 | 1 | Finished | 9655 | 9655 | C2013-02 Sewage Plant Hove.xlsx
176 | 172 | werken EM | 2005-04-18 08:00 | 2005-05-27 17:00 | 30d |  |  | 3 |  |  | 3 |  | 27d | [5 empty] | 3 |  | 1 |  | 3 | 3 | C2013-02 Sewage Plant Hove.xlsx
177 | 173 | ombouwen ruimerbrug | 2005-04-18 08:00 | 2005-04-29 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-01-19 08:00 | 9d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
178 | 174 | leveren en plaatsen van schotbalken, mixers, wandafsluiters en meettoestellen | 2005-05-02 08:00 | 2005-05-13 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-02-11 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
179 | 175 | electriciteit: kabels en lokale borden | 2005-05-16 08:00 | 2005-05-27 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-02-11 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
180 | 176 | interventie AQUAFIN | 2005-04-04 08:00 | 2005-08-05 17:00 | 90d |  |  | 1 |  |  | 1 |  | 27d | [5 empty] | 1 |  | 1 |  | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
181 | 177 | RWA-vijzels: 250l/s via bestaande RBT1/2 (=VBT); 500l/s via nieuwe SWA-overstort | 2005-04-04 08:00 | 2005-08-05 17:00 | 90d |  | 0 | 1 | 0 | 0 | 1 | 2005-02-11 08:00 | 27d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
182 | 178 | anoxische reactor 2 (deelwerk 11) | 2005-08-08 08:00 | 2005-10-14 17:00 | 50d |  |  | 3 |  |  | 46602.408 |  | 39d | [5 empty] | 39653.2599 |  | 1 |  | 46602.408 | 46602.408 | C2013-02 Sewage Plant Hove.xlsx
183 | 179 | verwijderen trappen, leuningen, bordessen,.. | 2005-08-08 08:00 | 2005-08-19 17:00 | 10d |  | 0 | 0 | 97.0821 | 7766.568 | 7766.568 | 2005-04-04 08:00 | 10d | 7766.568 | 0 | 0 | 0 | 0 | 7766.568 | 0 | 1 | Finished | 7766.568 | 7766.568 | C2013-02 Sewage Plant Hove.xlsx
184 | 180 | opvullen slibkuilen en aanpassen leeglaten | 2005-08-22 08:00 | 2005-09-02 17:00 | 10d |  | 0 | 0 | 97.0821 | 7766.568 | 7766.568 | 2005-04-04 08:00 | 10d | 7766.568 | 0 | 0 | -6599 | 0 | 1167.568 | 0 | 1 | Finished | 7766.568 | 7766.568 | C2013-02 Sewage Plant Hove.xlsx
185 | 181 | maken van doorvoer leiding dia 1200 en geleidingswand (incl afwerken betonoppervlak) | 2005-09-05 08:00 | 2005-09-16 17:00 | 10d |  | 0 | 0 | 97.0821 | 7766.568 | 7766.568 | 2005-04-22 08:00 | 14d | 10873.1952 | 0 | 0 | -3000 | 0 | 7873.1952 | 0 | 1 | Finished | 7766.568 | 7766.568 | C2013-02 Sewage Plant Hove.xlsx
186 | 182 | uitvullingsbeton en dichtstorten bestaande uitstroom | 2005-09-19 08:00 | 2005-09-30 17:00 | 10d |  | 0 | 0 | 97.0821 | 7766.568 | 7766.568 | 2005-04-22 08:00 | 21d | 16309.7928 | 0 | 0 | -9000 | 0 | 7309.7928 | 0 | 1 | Finished | 7766.568 | 7766.568 | C2013-02 Sewage Plant Hove.xlsx
187 | 183 | creëren doorstroomopening (1 naar 2) | 2005-10-03 08:00 | 2005-10-14 17:00 | 10d |  | 0 | 0 | 97.0821 | 7766.568 | 7766.568 | 2005-05-13 08:00 | 10d | 7766.568 | 0 | 0 | 0 | 0 | 7766.568 | 0 | 1 | Finished | 7766.568 | 7766.568 | C2013-02 Sewage Plant Hove.xlsx
188 | 184 | loopbruggen, trappen en leuningen | 2005-10-03 08:00 | 2005-10-14 17:00 | 10d |  | 0 | 0 | 97.0821 | 7766.568 | 7766.568 | 2005-05-13 08:00 | 10d | 7766.568 | 0 | 0 | 0 | 0 | 7766.568 | 0 | 1 | Finished | 7766.568 | 7766.568 | C2013-02 Sewage Plant Hove.xlsx
189 | 185 | werken EM (lot II) | 2005-08-22 08:00 | 2005-09-30 17:00 | 30d |  |  | 3 |  |  | 3 |  | 39d | [5 empty] | 3 |  | 1 |  | 3 | 3 | C2013-02 Sewage Plant Hove.xlsx
190 | 186 | ombouwen ruimerbrug | 2005-08-22 08:00 | 2005-09-02 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-04-04 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
191 | 187 | leveren en plaatsen schotbalken, mixers, wandafsluiters en meettoestellen | 2005-09-05 08:00 | 2005-09-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-05-13 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
192 | 188 | electriciteit: kabels en lokale borden | 2005-09-19 08:00 | 2005-09-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-05-13 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
193 | 189 | beluchtingstank 2 en beluchtingsreactor 3 (deelwerk 12) | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  |  | 8 |  |  | 31780.3206 |  | 47d | [5 empty] | 27556.2581 |  | 1 |  | 31780.3206 | 31780.3206 | C2013-02 Sewage Plant Hove.xlsx
194 | 190 | verwijderen looproosters, bordessen, trappen en leuningen | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 0 | 39.7154 | 3177.2321 | 3177.2321 | 2005-06-21 08:00 | 3d | 953.1696 | 0 | 0 | 0 | 0 | 953.1696 | 0 | 1 | Finished | 3177.2321 | 3177.2321 | C2013-02 Sewage Plant Hove.xlsx
195 | 191 | maken doorstroomopening (1 naar 2) | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 0 | 39.7154 | 3177.2321 | 3177.2321 | 2005-06-21 08:00 | 7d | 2224.0624 | 0 | 0 | 0 | 0 | 2224.0624 | 0 | 1 | Finished | 3177.2321 | 3177.2321 | C2013-02 Sewage Plant Hove.xlsx
196 | 192 | afdichten bestaande verbindingsleiding (dia 400) | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 0 | 39.7154 | 3177.2321 | 3177.2321 | 2005-06-24 08:00 | 7d | 2224.0624 | 0 | 0 | 0 | 0 | 2224.0624 | 0 | 1 | Finished | 3177.2321 | 3177.2321 | C2013-02 Sewage Plant Hove.xlsx
197 | 193 | aanleggen procesleiding (dia 1200) (2 naar 3) | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 0 | 39.7154 | 3177.2321 | 3177.2321 | 2005-06-24 08:00 | 14d | 4448.1249 | 0 | 0 | -1000 | 0 | 3448.1249 | 0 | 1 | Finished | 3177.2321 | 3177.2321 | C2013-02 Sewage Plant Hove.xlsx
198 | 194 | creëren geleidingswanden in reactor 3 en doorvoeren interne recirculatie | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 0 | 39.7154 | 3177.2321 | 3177.2321 | 2005-06-21 08:00 | 21d | 6672.1873 | 0 | 0 | -3000 | 0 | 3672.1873 | 0 | 1 | Finished | 3177.2321 | 3177.2321 | C2013-02 Sewage Plant Hove.xlsx
199 | 195 | vullingsbeton | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 0 | 39.7154 | 3177.2321 | 3177.2321 | 2005-08-11 08:00 | 7d | 2224.0624 | 0 | 0 | 0 | 0 | 2224.0624 | 0 | 1 | Finished | 3177.2321 | 3177.2321 | C2013-02 Sewage Plant Hove.xlsx
200 | 196 | blowerleiding | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 0 | 39.7154 | 3177.2321 | 3177.2321 | 2005-08-05 08:00 | 14d | 4448.1249 | 0 | 0 | 0 | 0 | 4448.1249 | 0 | 1 | Finished | 3177.2321 | 3177.2321 | C2013-02 Sewage Plant Hove.xlsx
201 | 197 | sokkels voor blowergroep | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 0 | 39.7154 | 3177.2321 | 3177.2321 | 2005-08-05 08:00 | 7d | 2224.0624 | 0 | 0 | 0 | 0 | 2224.0624 | 0 | 1 | Finished | 3177.2321 | 3177.2321 | C2013-02 Sewage Plant Hove.xlsx
202 | 198 | nieuwe leuningen, loopbruggen en trappen | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 0 | 39.7154 | 3177.2321 | 3177.2321 | 2005-08-05 08:00 | 10d | 3177.2321 | 0 | 0 | 0 | 0 | 3177.2321 | 0 | 1 | Finished | 3177.2321 | 3177.2321 | C2013-02 Sewage Plant Hove.xlsx
203 | 199 | plaatsen waterdichte wand (beluchting 1en 2/ deelwerk 13) | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 0 | 39.7154 | 3177.2321 | 3177.2321 | 2005-08-11 08:00 | 3d | 953.1696 | 0 | 0 | 2000 | 0 | 2953.1696 | 0 | 1 | Finished | 3177.2321 | 3177.2321 | C2013-02 Sewage Plant Hove.xlsx
204 | 200 | werken EM | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  |  | 8 |  |  | 8 |  | 47d | [5 empty] | 8 |  | 1 |  | 8 | 8 | C2013-02 Sewage Plant Hove.xlsx
205 | 201 | demontage bestaande EM-uitrusting | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-06-21 08:00 | 8d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
206 | 202 | leveren en plaatsen(BB2): schotbalken, wandafsluiter,meng en meettoestellen, beluchtingssysteem,... | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-08-05 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
207 | 203 | leveren en plaatsen(BR3): voorstuwers,beluchtingssysteem | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-08-11 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
208 | 204 | meettoestellen | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-08-11 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
209 | 205 | optrekken overstortrand | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-08-11 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
210 | 206 | revisie steekschuiven | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-08-11 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
211 | 207 | FeCl³-doseerleiding | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-08-11 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
212 | 208 | electriciteit: kabels en lokale borden | 2005-10-17 08:00 | 2005-10-28 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-08-11 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
213 | 209 | interventie AQUAFIN | 2004-04-28 08:00 | 2004-05-11 17:00 | 10d |  |  | 1 |  |  | 1 |  | 8d | [5 empty] | 1 |  | 1 |  | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
214 | 210 | RWA-vijzels: 500l/s ;afvoer via de SWA-afvoergoot; DWA-vijzels: 250l/s ..(voorlopig vlottende puntbeluchters) | 2004-04-28 08:00 | 2004-05-11 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-06-21 08:00 | 8d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
215 | 211 | beluchtingsreactor 4 (deelwerk 13) | 2005-10-31 08:00 | 2005-10-31 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2005-09-09 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
216 | 212 | verwijderen looproosters | 2004-04-28 08:00 | 2004-05-11 17:00 | 10d |  | 0 | 0 | 26.4769 | 2118.152 | 2118.152 | 2005-09-09 08:00 | 10d | 2118.152 | 0 | 0 | 0 | 0 | 2118.152 | 0 | 1 | Finished | 2118.152 | 2118.152 | C2013-02 Sewage Plant Hove.xlsx
217 | 213 | maken doorstroomopening | 2004-04-28 08:00 | 2004-05-11 17:00 | 10d |  | 0 | 0 | 26.4769 | 2118.152 | 2118.152 | 2005-09-09 08:00 | 10d | 2118.152 | 0 | 0 | 0 | 0 | 2118.152 | 0 | 1 | Finished | 2118.152 | 2118.152 | C2013-02 Sewage Plant Hove.xlsx
218 | 214 | maken van geleidingswand | 2004-04-28 08:00 | 2004-05-11 17:00 | 10d |  | 0 | 0 | 26.4769 | 2118.152 | 2118.152 | 2005-09-09 08:00 | 10d | 2118.152 | 0 | 0 | 0 | 0 | 2118.152 | 0 | 1 | Finished | 2118.152 | 2118.152 | C2013-02 Sewage Plant Hove.xlsx
219 | 215 | vullingsbeton | 2004-04-28 08:00 | 2004-05-11 17:00 | 10d |  | 0 | 0 | 26.4769 | 2118.152 | 2118.152 | 2005-09-09 08:00 | 10d | 2118.152 | 0 | 0 | 0 | 0 | 2118.152 | 0 | 1 | Finished | 2118.152 | 2118.152 | C2013-02 Sewage Plant Hove.xlsx
220 | 216 | doorvoeren interne recirculatie leidingen | 2004-04-28 08:00 | 2004-05-11 17:00 | 10d |  | 0 | 0 | 26.4769 | 2118.152 | 2118.152 | 2005-09-09 08:00 | 10d | 2118.152 | 0 | 0 | 0 | 0 | 2118.152 | 0 | 1 | Finished | 2118.152 | 2118.152 | C2013-02 Sewage Plant Hove.xlsx
221 | 217 | plaatsen leuningen, looproosters en trappen | 2004-04-28 08:00 | 2004-05-11 17:00 | 10d |  | 0 | 0 | 26.4769 | 2118.152 | 2118.152 | 2005-09-09 08:00 | 10d | 2118.152 | 0 | 0 | 0 | 0 | 2118.152 | 0 | 1 | Finished | 2118.152 | 2118.152 | C2013-02 Sewage Plant Hove.xlsx
222 | 218 | werken EM | 2004-04-28 08:00 | 2004-05-11 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-10-10 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
223 | 219 | interventie AQUAFIN | 2004-04-28 08:00 | 2004-05-11 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2005-09-09 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-02 Sewage Plant Hove.xlsx
224 | 220 | Wegeniswerken en afwerking | 2005-07-25 08:00 | 2005-11-11 17:00 | 80d |  | 0 | 0 | 132.3846 | 84726.1426 | 84726.1426 | 2005-08-01 08:00 | 80d | 84726.1426 | 0 | 0 | -8700 | 0 | 76026.1426 | 0 | 1 | Finished | 84726.1426 | 84726.1426 | C2013-02 Sewage Plant Hove.xlsx
4 | 0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 426d | [5 empty] | 16338027.1975 |  | 1 |  | 15440865.8897 | 15440865.8897 | C2013-03 Brussels Finance Tower.xlsx
5 | 1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 426d | [5 empty] | 16338027.1975 |  | 1 |  | 15440865.8897 | 15440865.8897 | C2013-03 Brussels Finance Tower.xlsx
6 | 2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 385d | 1676166.8677 | 0 | 0 | 569033.3125 | 0 | 2245200.1802 | 0 | 1 | Finished | 1850314.0747 | 1850314.0747 | C2013-03 Brussels Finance Tower.xlsx
7 | 9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 184d | [5 empty] | 2838094.8889 |  | 1 |  | 2872078.2812 | 2872078.2812 | C2013-03 Brussels Finance Tower.xlsx
8 | 10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 1 | Finished | 255893.041 | 255893.041 | C2013-03 Brussels Finance Tower.xlsx
9 | 11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 1 | Finished | 255893.041 | 255893.041 | C2013-03 Brussels Finance Tower.xlsx
10 | 12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 1 | Finished | 255893.041 | 255893.041 | C2013-03 Brussels Finance Tower.xlsx
11 | 13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-11 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 1 | Finished | 255892.793 | 255892.793 | C2013-03 Brussels Finance Tower.xlsx
12 | 14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-26 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 1 | Finished | 255892.793 | 255892.793 | C2013-03 Brussels Finance Tower.xlsx
13 | 15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-10-11 08:00 | 15d 3h | 262290.1128 | 0 | 0 | -9400 | 0 | 252890.1128 | 0 | 1 | Finished | 255892.793 | 255892.793 | C2013-03 Brussels Finance Tower.xlsx
14 | 16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-01 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 1 | Finished | 191919.5947 | 191919.5947 | C2013-03 Brussels Finance Tower.xlsx
15 | 17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-20 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 1 | Finished | 191919.5947 | 191919.5947 | C2013-03 Brussels Finance Tower.xlsx
16 | 18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 1 | Finished | 255893.041 | 255893.041 | C2013-03 Brussels Finance Tower.xlsx
17 | 19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 1 | Finished | 255893.041 | 255893.041 | C2013-03 Brussels Finance Tower.xlsx
18 | 20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 1 | Finished | 383839.1895 | 383839.1895 | C2013-03 Brussels Finance Tower.xlsx
19 | 21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 | 2006-11-09 08:00 | 39d | 93041.5173 | 0 | 0 | -36462.3906 | 0 | 56579.1267 | 0 | 1 | Finished | 57256.3184 | 57256.3184 | C2013-03 Brussels Finance Tower.xlsx
20 | 765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 | 2006-12-01 08:00 | 179d | 3183436.3379 | 0 | 0 | -118755.7109 | 0 | 3064680.627 | 0 | 1 | Finished | 2756606.8848 | 2756606.8848 | C2013-03 Brussels Finance Tower.xlsx
21 | 764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 | 2007-04-11 08:00 | 19d | 376803.4355 | 0 | 0 | 42110 | 0 | 418913.4355 | 0 | 1 | Finished | 376803.4355 | 376803.4355 | C2013-03 Brussels Finance Tower.xlsx
22 | 45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 34d | [5 empty] | 139908.8843 |  | 1 |  | 141518.0015 | 141518.0015 | C2013-03 Brussels Finance Tower.xlsx
23 | 46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 | 2007-02-27 08:00 | 34d | 456114.084 | 0 | 0 | -323500 | 0 | 132614.084 | 0 | 1 | Finished | 134151.2012 | 134151.2012 | C2013-03 Brussels Finance Tower.xlsx
24 | 48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 | 2007-03-01 08:00 | 3d | 7366.8003 | 0 | 0 | -72 | 0 | 7294.8003 | 0 | 1 | Finished | 7366.8003 | 7366.8003 | C2013-03 Brussels Finance Tower.xlsx
25 | 49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 139d | [5 empty] | 128602.8896 |  | 1 |  | 130114.7993 | 130114.7993 | C2013-03 Brussels Finance Tower.xlsx
26 | 50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 | 2006-12-01 08:00 | 7d | 19697.4395 | 0 | 0 | -233 | 0 | 19464.4395 | 0 | 1 | Finished | 19697.4395 | 19697.4395 | C2013-03 Brussels Finance Tower.xlsx
27 | 51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 | 2007-03-27 08:00 | 5d | 7951.5997 | 0 | 0 | -100 | 0 | 7851.5997 | 0 | 1 | Finished | 7951.5997 | 7951.5997 | C2013-03 Brussels Finance Tower.xlsx
28 | 52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 | 2007-02-22 08:00 | 5d | 16671.2 | 0 | 0 | -197 | 0 | 16474.2 | 0 | 1 | Finished | 16671.2 | 16671.2 | C2013-03 Brussels Finance Tower.xlsx
29 | 53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 | 2007-01-18 08:00 | 18d | 39193.9189 | 0 | 0 | -464.15 | 0 | 38729.769 | 0 | 1 | Finished | 39193.9189 | 39193.9189 | C2013-03 Brussels Finance Tower.xlsx
30 | 54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 | 2007-02-14 08:00 | 15d | 22675.2008 | 0 | 0 | -268 | 0 | 22407.2008 | 0 | 1 | Finished | 22675.2008 | 22675.2008 | C2013-03 Brussels Finance Tower.xlsx
31 | 55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 | 2007-04-27 08:00 | 34d | 36975.6807 | 0 | 0 | -13300 | 0 | 23675.6807 | 0 | 1 | Finished | 23925.4404 | 23925.4404 | C2013-03 Brussels Finance Tower.xlsx
32 | 56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 | 2007-02-21 08:00 | 20d | 13667.1997 | 0 | 0 | -4000 | 0 | 9667.1997 | 0 | 1 | Finished | 13667.1997 | 13667.1997 | C2013-03 Brussels Finance Tower.xlsx
33 | 57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 | 2007-02-28 08:00 | 5d | 75157.2021 | 0 | 0 | -24000 | 0 | 51157.2021 | 0 | 1 | Finished | 75157.2021 | 75157.2021 | C2013-03 Brussels Finance Tower.xlsx
34 | 58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 | 2006-10-02 08:00 | 67d | 224701.9207 | 0 | 0 | -89000 | 0 | 135701.9207 | 0 | 1 | Finished | 134150.4004 | 134150.4004 | C2013-03 Brussels Finance Tower.xlsx
35 | 59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 | 2007-03-29 08:00 | 22d | 122781.1191 | 0 | 0 | -1200 | 0 | 121581.1191 | 0 | 1 | Finished | 122781.1191 | 122781.1191 | C2013-03 Brussels Finance Tower.xlsx
36 | 61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 | 2007-03-01 08:00 | 46d | 178170.8813 | 0 | 0 | -51870 | 0 | 126300.8813 | 0 | 1 | Finished | 127818.241 | 127818.241 | C2013-03 Brussels Finance Tower.xlsx
37 | 62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 | 2007-04-13 08:00 | 49d | 21857.9193 | 0 | 0 | -3780 | 0 | 18077.9193 | 0 | 1 | Finished | 17397.1195 | 17397.1195 | C2013-03 Brussels Finance Tower.xlsx
38 | 63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 | 2007-05-31 15:00 | 88d | 651650.5703 | 0 | 0 | -418485.1562 | 0 | 233165.4141 | 0 | 1 | Finished | 259179.2041 | 259179.2041 | C2013-03 Brussels Finance Tower.xlsx
39 | 64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 | 2007-06-12 08:00 | 79d | 204843.8369 | 0 | 0 | -3406.26 | 0 | 201437.5769 | 0 | 1 | Finished | 129647.998 | 129647.998 | C2013-03 Brussels Finance Tower.xlsx
40 | 65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 | 2007-09-17 08:00 | 33d | 7785.3599 | 0 | 0 | 942.17 | 0 | 8727.5299 | 0 | 1 | Finished | 8493.1199 | 8493.1199 | C2013-03 Brussels Finance Tower.xlsx
41 | 66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 | 2007-06-29 08:00 | 47d | 85791.9193 | 0 | 0 | -40700 | 0 | 45091.9193 | 0 | 1 | Finished | 45633.9996 | 45633.9996 | C2013-03 Brussels Finance Tower.xlsx
42 | 67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 | 2007-05-31 16:00 | 88d | 290526.7148 | 0 | 0 | -160033.9844 | 0 | 130492.7305 | 0 | 1 | Finished | 132057.5977 | 132057.5977 | C2013-03 Brussels Finance Tower.xlsx
43 | 68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2007-10-03 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-03 Brussels Finance Tower.xlsx
44 | 69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2007-10-18 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-03 Brussels Finance Tower.xlsx
45 | 752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 | 2006-11-13 08:00 | 121d | 207558.5582 | 0 | 0 | 216000 | 0 | 423558.5582 | 0 | 1 | Finished | 439132.1562 | 439132.1562 | C2013-03 Brussels Finance Tower.xlsx
46 | 753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 | 2006-12-01 08:00 | 130d | 225648.8013 | 0 | 0 | 198000 | 0 | 423648.8013 | 0 | 1 | Finished | 439147.2825 | 439147.2825 | C2013-03 Brussels Finance Tower.xlsx
47 | 754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 | 2006-12-18 08:00 | 125d | 219570.0073 | 0 | 0 | 204000 | 0 | 423570.0073 | 0 | 1 | Finished | 439140.0146 | 439140.0146 | C2013-03 Brussels Finance Tower.xlsx
48 | 755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 | 2007-01-01 08:00 | 169d | 300468.4874 | 0 | 0 | 123000 | 0 | 423468.4874 | 0 | 1 | Finished | 439146.2509 | 439146.2509 | C2013-03 Brussels Finance Tower.xlsx
49 | 756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 | 2007-02-01 08:00 | 128d | 230369.2812 | 0 | 0 | 193000 | 0 | 423369.2812 | 0 | 1 | Finished | 439141.4424 | 439141.4424 | C2013-03 Brussels Finance Tower.xlsx
50 | 757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 | 2007-03-01 08:00 | 123d | 224125.6842 | 0 | 0 | 199000 | 0 | 423125.6842 | 0 | 1 | Finished | 439140.5682 | 439140.5682 | C2013-03 Brussels Finance Tower.xlsx
51 | 758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 | 2007-03-12 08:00 | 129d | 241064.8762 | 0 | 0 | 182000 | 0 | 423064.8762 | 0 | 1 | Finished | 439149.1931 | 439149.1931 | C2013-03 Brussels Finance Tower.xlsx
52 | 759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 | 2007-05-01 08:00 | 110d | 208216.8005 | 0 | 0 | 215000 | 0 | 423216.8005 | 0 | 1 | Finished | 439148.1611 | 439148.1611 | C2013-03 Brussels Finance Tower.xlsx
53 | 760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 | 2007-03-01 08:00 | 86d | 364110.2266 | 0 | 0 | 0 | 0 | 364110.2266 | 0 | 1 | Finished | 368344.0664 | 368344.0664 | C2013-03 Brussels Finance Tower.xlsx
54 | 761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 | 2007-06-25 08:00 | 93d | 189072.7236 | 0 | 0 | 234566.6875 | 0 | 423639.4111 | 0 | 1 | Finished | 439136.6484 | 439136.6484 | C2013-03 Brussels Finance Tower.xlsx
55 | 762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 | 2007-08-01 08:00 | 66d | 134803.6787 | 0 | 0 | 288835.7188 | 0 | 423639.3975 | 0 | 1 | Finished | 439133.1958 | 439133.1958 | C2013-03 Brussels Finance Tower.xlsx
56 | 763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 | 2007-08-01 08:00 | 66d | 135437.2852 | 0 | 0 | 288202.125 | 0 | 423639.4102 | 0 | 1 | Finished | 439145.1367 | 439145.1367 | C2013-03 Brussels Finance Tower.xlsx
57 | 742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 218d | [5 empty] | 1399171.9373 |  | 1 |  | 1048541.095 | 1048541.095 | C2013-03 Brussels Finance Tower.xlsx
58 | 743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 211d | [5 empty] | 653548.6931 |  | 1 |  | 356500.4934 | 356500.4934 | C2013-03 Brussels Finance Tower.xlsx
59 | 744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 | 2007-01-10 08:00 | 75d | 163278.0029 | 0 | 0 | 44255.6211 | 0 | 207533.624 | 0 | 1 | Finished | 113206.082 | 113206.082 | C2013-03 Brussels Finance Tower.xlsx
60 | 745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 | 2007-08-01 08:00 | 66d | 136065.6064 | 0 | 0 | 302343.5625 | 0 | 438409.1689 | 0 | 1 | Finished | 239145.6113 | 239145.6113 | C2013-03 Brussels Finance Tower.xlsx
61 | 746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 | 2007-10-01 08:00 | 10d | 4148.8 | 0 | 0 | 3457.1001 | 0 | 7605.9001 | 0 | 1 | Finished | 4148.8 | 4148.8 | C2013-03 Brussels Finance Tower.xlsx
62 | 747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 175d | [5 empty] | 745623.2441 |  | 1 |  | 692040.6016 | 692040.6016 | C2013-03 Brussels Finance Tower.xlsx
63 | 748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-01-01 08:00 | 45d | 189889.1895 | 0 | 0 | -3000 | 0 | 186889.1895 | 0 | 1 | Finished | 173010.1504 | 173010.1504 | C2013-03 Brussels Finance Tower.xlsx
64 | 749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-02-01 08:00 | 42d | 177229.9102 | 0 | 0 | 9000 | 0 | 186229.9102 | 0 | 1 | Finished | 173010.1504 | 173010.1504 | C2013-03 Brussels Finance Tower.xlsx
65 | 750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-03-01 08:00 | 43d | 181449.6699 | 0 | 0 | 5000 | 0 | 186449.6699 | 0 | 1 | Finished | 173010.1504 | 173010.1504 | C2013-03 Brussels Finance Tower.xlsx
66 | 751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-08-01 08:00 | 23d | 97054.4746 | 0 | 0 | 89000 | 0 | 186054.4746 | 0 | 1 | Finished | 173010.1504 | 173010.1504 | C2013-03 Brussels Finance Tower.xlsx
4 | 0 | Kitchen Tower Anderlecht | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  |  | 1448084 |  |  | 2113684 |  | 453d | [5 empty] | 2512524 |  | 1 |  | 2113684 | 2113684 | C2013-04 Kitchen Tower Anderlecht.xlsx
5 | 1 | KEUKENTOREN IN WERKDAGEN (ADMIN BEDIENDEN) | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  | 0 | 0 | 50 | 133200 | 133200 | 2008-05-05 08:00 | 445d | 178000 | 0 | 0 | 5000 | 0 | 183000 | 0 | 1 | Finished | 133200 | 133200 | C2013-04 Kitchen Tower Anderlecht.xlsx
6 | 2 | UITZETTEN HOOFDASSEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 0 | 30 | 240 | 240 | 2008-05-05 08:00 | 1d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 1 | Finished | 240 | 240 | C2013-04 Kitchen Tower Anderlecht.xlsx
7 | 3 | AFGRAVEN TEELAARDE | 2008-05-06 08:00 | 2008-05-09 17:00 | 4d |  | 0 | 0 | 150 | 4800 | 4800 | 2008-05-05 08:00 | 4d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 1 | Finished | 4800 | 4800 | C2013-04 Kitchen Tower Anderlecht.xlsx
8 | 4 | AANLEGGEN RIOLERING EN WERFWEG | 2008-05-13 08:00 | 2008-05-16 17:00 | 4d |  | 0 | 20000 | 150 | 4800 | 24800 | 2008-05-05 08:00 | 4d | 24800 | 0 | 0 | 0 | 0 | 24800 | 0 | 1 | Finished | 24800 | 24800 | C2013-04 Kitchen Tower Anderlecht.xlsx
9 | 5 | WERFINRICHTING EN ELEKTR. AANSLUITING | 2008-05-19 08:00 | 2008-05-23 17:00 | 5d |  | 0 | 0 | 60 | 2400 | 2400 | 2008-05-05 08:00 | 5d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 1 | Finished | 2400 | 2400 | C2013-04 Kitchen Tower Anderlecht.xlsx
10 | 6 | INSTALLATIE SNELOPBOUWKRAAN/TORENKRAAN/WERFLIFT | 2008-06-12 08:00 | 2009-08-12 17:00 | 305d |  | 0 | 43000 | 20 | 48800 | 91800 | 2008-06-05 08:00 | 410d | 108600 | 0 | 0 | 12000 | 0 | 120600 | 0 | 1 | Finished | 91800 | 91800 | C2013-04 Kitchen Tower Anderlecht.xlsx
11 | 9 | TE ONTVANGEN PLANNEN GOED VOOR UITVOERING: $ | 2008-05-05 08:00 | 2009-02-09 17:00 | 201d |  |  | 8 |  |  | 8 |  | 80d | [5 empty] | 8 |  | 1 |  | 8 | 8 | C2013-04 Kitchen Tower Anderlecht.xlsx
12 | 10 | AANGEPASTE PLANNEN UITSPARINGEN VOOR TECHNIEKEN (coördinatie studie) | 2008-05-05 08:00 | 2008-05-09 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-04 Kitchen Tower Anderlecht.xlsx
13 | 11 | BETON EN WAPENING WANDEN KOKERS A tot F | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-04 Kitchen Tower Anderlecht.xlsx
14 | 12 | BETON EN WAPENING PREFABTRAPPEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-08 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-04 Kitchen Tower Anderlecht.xlsx
15 | 13 | BETON EN WAPENING FUNDERINGSZOLEN EN PLATEN + WACHTSTAVEN WANDEN | 2008-05-08 08:00 | 2008-05-08 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-07-11 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-04 Kitchen Tower Anderlecht.xlsx
16 | 14 | BETON EN WAPENING KELDER WANDEN + PLAAT BOVEN KELDER | 2008-05-06 08:00 | 2008-05-06 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-23 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-04 Kitchen Tower Anderlecht.xlsx
17 | 15 | BETON EN WAPENING PLAAT BOVEN GLVL , +1 ,+2, +3, +4 | 2008-07-04 08:00 | 2008-07-04 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-04 Kitchen Tower Anderlecht.xlsx
18 | 16 | BETON EN WAPENING PLAAT BOVEN GLVL , +5 ,+6, +7, +8 | 2008-10-14 08:00 | 2008-10-14 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-04 Kitchen Tower Anderlecht.xlsx
19 | 17 | BETON EN WAPENING PLAAT BOVEN GLVL , +9 ,+10, +11, +12, +13 , DAKPLAN | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-04 Kitchen Tower Anderlecht.xlsx
20 | 18 | RUWBOUW BETONWERKEN $$ | 2008-05-19 08:00 | 2009-08-12 17:00 | 323d |  |  | 1385076 |  |  | 1856436 |  | 449d | [5 empty] | 2176676 |  | 1 |  | 1856436 | 1856436 | C2013-04 Kitchen Tower Anderlecht.xlsx
21 | 19 | BETON KELDER | 2008-05-19 08:00 | 2009-01-27 17:00 | 182d |  |  | 329440 |  |  | 400000 |  | 286d | [5 empty] | 415040 |  | 1 |  | 400000 | 400000 | C2013-04 Kitchen Tower Anderlecht.xlsx
22 | 20 | BOREN SCHROEFPALEN GEBOUW + KRAANSOKKEL | 2008-05-19 08:00 | 2008-05-27 17:00 | 7d |  | 0 | 88510 | 0 | 0 | 88510 | 2008-05-09 08:00 | 7d | 88510 | 0 | 0 | 0 | 0 | 88510 | 0 | 1 | Finished | 88510 | 88510 | C2013-04 Kitchen Tower Anderlecht.xlsx
23 | 21 | INSTALLATIE BEMALING BOUWPUT | 2008-05-28 08:00 | 2008-05-29 17:00 | 2d |  | 0 | 3300 | 0 | 0 | 3300 | 2008-05-21 08:00 | 2d | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 1 | Finished | 3300 | 3300 | C2013-04 Kitchen Tower Anderlecht.xlsx
24 | 22 | BEMALING | 2008-05-30 08:00 | 2008-07-24 17:00 | 40d |  | 0 | 50642 | 90 | 28800 | 79442 | 2008-05-23 08:00 | 40d | 79442 | 0 | 0 | 0 | 0 | 79442 | 0 | 1 | Finished | 79442 | 79442 | C2013-04 Kitchen Tower Anderlecht.xlsx
25 | 23 | UITGRAVING KELDER EN ZOLEN | 2008-06-06 08:00 | 2008-06-10 17:00 | 3d |  | 0 | 0 | 150 | 3600 | 3600 | 2008-06-02 08:00 | 3d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 1 | Finished | 3600 | 3600 | C2013-04 Kitchen Tower Anderlecht.xlsx
26 | 24 | ZUIVERHEIDSBETON | 2008-06-11 08:00 | 2008-06-11 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-09 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 1 | Finished | 4760 | 4760 | C2013-04 Kitchen Tower Anderlecht.xlsx
27 | 25 | AFSCHIETEN PAALKOPPEN | 2008-06-16 08:00 | 2008-06-18 17:00 | 3d |  | 0 | 0 | 60 | 1440 | 1440 | 2008-06-13 08:00 | 3d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 1 | Finished | 1440 | 1440 | C2013-04 Kitchen Tower Anderlecht.xlsx
28 | 26 | BEKISTEN FUNDERINGSPLAAT KELDER + WATERKEERPLATEN | 2008-06-19 08:00 | 2008-06-24 17:00 | 4d |  | 0 | 180 | 150 | 4800 | 4980 | 2008-06-18 08:00 | 4d | 4980 | 0 | 0 | 0 | 0 | 4980 | 0 | 1 | Finished | 4980 | 4980 | C2013-04 Kitchen Tower Anderlecht.xlsx
29 | 27 | WAPENING FUNDERINGSPLAAT KELDER | 2008-06-24 08:00 | 2008-06-26 17:00 | 3d |  | 0 | 40000 | 120 | 2880 | 42880 | 2008-06-24 08:00 | 3d | 42880 | 0 | 0 | 16000 | 0 | 58880 | 0 | 1 | Finished | 42880 | 42880 | C2013-04 Kitchen Tower Anderlecht.xlsx
30 | 28 | RIOLERING IN FUNDERINGSPLAAT | 2008-06-25 08:00 | 2008-06-26 17:00 | 2d |  | 0 | 1000 | 90 | 1440 | 2440 | 2008-06-25 08:00 | 2d | 2440 | 0 | 0 | 0 | 0 | 2440 | 0 | 1 | Finished | 2440 | 2440 | C2013-04 Kitchen Tower Anderlecht.xlsx
31 | 29 | BETON FUNDERINGSPLAAT KELDER te vlinderen | 2008-06-27 08:00 | 2008-06-27 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-27 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 1 | Finished | 4760 | 4760 | C2013-04 Kitchen Tower Anderlecht.xlsx
32 | 30 | BETON KELDERWANDEN | 2008-07-01 08:00 | 2008-07-15 17:00 | 11d |  | 0 | 92470 | 120 | 10560 | 103030 | 2008-07-01 08:00 | 10d | 102070 | 0 | 0 | 0 | 0 | 102070 | 0 | 1 | Finished | 103030 | 103030 | C2013-04 Kitchen Tower Anderlecht.xlsx
33 | 31 | WATERDICHTE ROK OP KELDERWANDEN | 2008-08-06 08:00 | 2008-08-08 17:00 | 3d |  | 0 | 20000 | 60 | 1440 | 21440 | 2008-08-08 08:00 | 3d | 21440 | 0 | 0 | 0 | 0 | 21440 | 0 | 1 | Finished | 21440 | 21440 | C2013-04 Kitchen Tower Anderlecht.xlsx
34 | 32 | AANVULLING KELDER | 2008-08-14 08:00 | 2008-08-18 17:00 | 3d |  | 0 | 2000 | 90 | 2160 | 4160 | 2008-08-21 08:00 | 3d | 4160 | 0 | 0 | 0 | 0 | 4160 | 0 | 1 | Finished | 4160 | 4160 | C2013-04 Kitchen Tower Anderlecht.xlsx
35 | 33 | BETON BORDES KOKER A | 2008-08-06 08:00 | 2008-08-06 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-08-08 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 1 | Finished | 4760 | 4760 | C2013-04 Kitchen Tower Anderlecht.xlsx
36 | 34 | ZUIVERHEIDSBETON PLATEN EN ZOOL GLVL | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-26 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 1 | Finished | 6377 | 6377 | C2013-04 Kitchen Tower Anderlecht.xlsx
37 | 35 | BEKISTEN PLATEN EN ZOOL BOVEN KELDER+RIOLERINGSBUIZEN IN ZOOL | 2008-08-06 08:00 | 2008-08-12 17:00 | 5d |  | 0 | 5417 | 120 | 4800 | 10217 | 2008-08-08 08:00 | 5d | 10217 | 0 | 0 | 0 | 0 | 10217 | 0 | 1 | Finished | 10217 | 10217 | C2013-04 Kitchen Tower Anderlecht.xlsx
38 | 36 | WAPENING PLATEN EN ZOOL BOVEN KELDER | 2008-08-11 08:00 | 2008-08-14 17:00 | 4d |  | 0 | 3683 | 120 | 3840 | 7523 | 2008-08-18 08:00 | 4d | 7523 | 0 | 0 | 0 | 0 | 7523 | 0 | 1 | Finished | 7523 | 7523 | C2013-04 Kitchen Tower Anderlecht.xlsx
39 | 37 | BETON PLATEN EN ZOOL BOVEN KELDER | 2008-08-18 08:00 | 2008-08-18 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-22 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 1 | Finished | 6377 | 6377 | C2013-04 Kitchen Tower Anderlecht.xlsx
40 | 38 | PREFABBETON KOKERWANDEN | 2008-06-04 08:00 | 2009-01-27 17:00 | 170d |  |  | 4 |  |  | 4 |  | 176d | [5 empty] | 4 |  | 1 |  | 4 | 4 | C2013-04 Kitchen Tower Anderlecht.xlsx
41 | 39 | STUDIE EN PLANNEN VOORLEGGEN + VOORLEGGEN STALEN IN GETINTE BETON | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-10 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-04 Kitchen Tower Anderlecht.xlsx
42 | 40 | PRODUCTIE DEUVELKOPPELPLATEN | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-24 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-04 Kitchen Tower Anderlecht.xlsx
43 | 41 | PRODUCTIE PREFABWANDEN 11 dagen per verdiep (incl hydrofoberen) | 2008-06-25 08:00 | 2009-01-27 17:00 | 155d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 160d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-04 Kitchen Tower Anderlecht.xlsx
44 | 42 | KEURING EERSTE ELEMENTEN -WIT-ZWART-GRIJS | 2008-07-11 08:00 | 2008-07-11 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2013-04 Kitchen Tower Anderlecht.xlsx
45 | 43 | BETON GELIJKVLOERS | 2008-08-20 08:00 | 2008-09-08 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 32d | [5 empty] | 111400 |  | 1 |  | 100000 | 100000 | C2013-04 Kitchen Tower Anderlecht.xlsx
46 | 44 | WANDEN KOKER A | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-05 08:00 | 2d | 12400 | 0 | 0 | 0 | 0 | 12400 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
47 | 45 | WANDEN KOKER F | 2008-08-21 08:00 | 2008-08-21 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-03 08:00 | 1d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
48 | 46 | WANDEN KOKER B tot E | 2008-08-22 08:00 | 2008-08-25 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2008-12-01 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 1 | Finished | 22400 | 22400 | C2013-04 Kitchen Tower Anderlecht.xlsx
49 | 47 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
50 | 48 | BEKISTEN TUSSENBORDES KOKER F | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
51 | 49 | PL. WERKVLOEREN KOKERS B tot E | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
52 | 50 | BETON DRAAGWAND KOKER A en F | 2008-08-25 08:00 | 2008-08-26 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2008-12-10 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 1 | Finished | 4300 | 4300 | C2013-04 Kitchen Tower Anderlecht.xlsx
53 | 51 | BETON DRAAGWAND KOKER B tot E | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2008-12-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 1 | Finished | 3100 | 3100 | C2013-04 Kitchen Tower Anderlecht.xlsx
54 | 52 | BEKISTEN PLAAT KOKER A (zwart) | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
55 | 53 | BEKISTEN PLAAT KOKER F | 2008-08-28 08:00 | 2008-08-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
56 | 54 | BEKISTEN RANDBALK PLAAT | 2008-08-27 08:00 | 2008-08-29 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-12 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
57 | 55 | BEKISTEN PLAAT (met tafels) | 2008-08-29 08:00 | 2008-09-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-15 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
58 | 56 | WAPENING VLOERPLATEN | 2008-09-02 08:00 | 2008-09-04 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2008-12-17 08:00 | 2d | 12400 | 0 | 0 | 10000 | 0 | 22400 | 0 | 1 | Finished | 13600 | 13600 | C2013-04 Kitchen Tower Anderlecht.xlsx
59 | 57 | BETON VLOERPLATEN ( grof vlinderen) | 2008-09-05 08:00 | 2008-09-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
60 | 58 | PLAATSEN PREFABTRAPPEN + veiligheid $ | 2008-09-08 08:00 | 2008-09-08 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-01-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | Finished | 3800 | 3800 | C2013-04 Kitchen Tower Anderlecht.xlsx
61 | 59 | BETON EERSTE VERDIEPING | 2008-09-09 08:00 | 2008-09-26 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 15d | [5 empty] | 113800 |  | 1 |  | 100000 | 100000 | C2013-04 Kitchen Tower Anderlecht.xlsx
62 | 60 | WANDEN KOKER A | 2008-09-09 08:00 | 2008-09-09 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-15 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
63 | 61 | WANDEN KOKER F | 2008-09-10 08:00 | 2008-09-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
64 | 62 | WANDEN KOKER B tot E | 2008-09-11 08:00 | 2008-09-12 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-01-20 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 1 | Finished | 22400 | 22400 | C2013-04 Kitchen Tower Anderlecht.xlsx
65 | 63 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
66 | 64 | BEKISTEN TUSSENBORDES KOKER F | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
67 | 65 | PL. WERKVLOEREN KOKERS B tot E | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
68 | 66 | BETON DRAAGWAND KOKER A en F | 2008-09-12 08:00 | 2008-09-15 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-01-21 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 1 | Finished | 4300 | 4300 | C2013-04 Kitchen Tower Anderlecht.xlsx
69 | 67 | BETON DRAAGWAND KOKER B tot E | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-01-26 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 1 | Finished | 3100 | 3100 | C2013-04 Kitchen Tower Anderlecht.xlsx
70 | 68 | BEKISTEN PLAAT KOKER A (zwart) | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
71 | 69 | BEKISTEN PLAAT KOKER F | 2008-09-17 08:00 | 2008-09-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
72 | 70 | BEKISTEN RANDBALK PLAAT | 2008-09-16 08:00 | 2008-09-18 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
73 | 71 | BEKISTEN PLAAT (met tafels) | 2008-09-18 08:00 | 2008-09-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-28 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
74 | 72 | WAPENING VLOERPLATEN | 2008-09-22 08:00 | 2008-09-24 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-01-30 08:00 | 1d | 11200 | 0 | 0 | 11000 | 0 | 22200 | 0 | 1 | Finished | 13600 | 13600 | C2013-04 Kitchen Tower Anderlecht.xlsx
75 | 73 | BETON VLOERPLATEN (grof vlinderen) | 2008-09-25 08:00 | 2008-09-25 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
76 | 74 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-09-26 08:00 | 2008-09-26 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-04 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | Finished | 3800 | 3800 | C2013-04 Kitchen Tower Anderlecht.xlsx
77 | 75 | BETON TWEEDE VERDIEPING | 2008-09-29 08:00 | 2008-10-16 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 115800 |  | 1 |  | 100000 | 100000 | C2013-04 Kitchen Tower Anderlecht.xlsx
78 | 76 | WANDEN KOKER A | 2008-09-29 08:00 | 2008-09-29 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
79 | 77 | WANDEN KOKER F | 2008-09-30 08:00 | 2008-09-30 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
80 | 78 | WANDEN KOKER B tot E | 2008-10-01 08:00 | 2008-10-02 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-12 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 1 | Finished | 22400 | 22400 | C2013-04 Kitchen Tower Anderlecht.xlsx
81 | 79 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
82 | 80 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
83 | 81 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
84 | 82 | BETON DRAAGWAND KOKER A en F | 2008-10-02 08:00 | 2008-10-03 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-02-11 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 1 | Finished | 4300 | 4300 | C2013-04 Kitchen Tower Anderlecht.xlsx
85 | 83 | BETON DRAAGWAND KOKER B tot E | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-02-13 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 1 | Finished | 3100 | 3100 | C2013-04 Kitchen Tower Anderlecht.xlsx
86 | 84 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
87 | 85 | BEKISTEN PLAAT KOKER F | 2008-10-07 08:00 | 2008-10-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
88 | 86 | BEKISTEN RANDBALK PLAAT | 2008-10-06 08:00 | 2008-10-08 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
89 | 87 | BEKISTEN PLAAT (met tafels) | 2008-10-08 08:00 | 2008-10-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-17 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
90 | 88 | WAPENING VLOERPLATEN | 2008-10-10 08:00 | 2008-10-14 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-02-19 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 1 | Finished | 13600 | 13600 | C2013-04 Kitchen Tower Anderlecht.xlsx
91 | 89 | BETON VLOERPLATEN (grof vlinderen) | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
92 | 90 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | Finished | 3800 | 3800 | C2013-04 Kitchen Tower Anderlecht.xlsx
93 | 91 | BETON DERDE VERDIEPING | 2008-10-17 08:00 | 2008-11-06 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 1 |  | 100000 | 100000 | C2013-04 Kitchen Tower Anderlecht.xlsx
94 | 92 | WANDEN KOKER A | 2008-10-17 08:00 | 2008-10-17 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
95 | 93 | WANDEN KOKER F | 2008-10-20 08:00 | 2008-10-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
96 | 94 | WANDEN KOKER B tot E | 2008-10-21 08:00 | 2008-10-22 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 1 | Finished | 22400 | 22400 | C2013-04 Kitchen Tower Anderlecht.xlsx
97 | 95 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
98 | 96 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
99 | 97 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
100 | 98 | BETON DRAAGWAND KOKER A en F | 2008-10-22 08:00 | 2008-10-23 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-02 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 1 | Finished | 4300 | 4300 | C2013-04 Kitchen Tower Anderlecht.xlsx
101 | 99 | BETON DRAAGWAND KOKER B tot E | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 1 | Finished | 3100 | 3100 | C2013-04 Kitchen Tower Anderlecht.xlsx
102 | 100 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
103 | 101 | BEKISTEN PLAAT KOKER F | 2008-10-27 08:00 | 2008-10-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
104 | 102 | BEKISTEN RANDBALK PLAAT | 2008-10-24 08:00 | 2008-10-28 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
105 | 103 | BEKISTEN PLAAT (met tafels) | 2008-10-28 08:00 | 2008-10-30 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-06 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
106 | 104 | WAPENING VLOERPLATEN | 2008-10-30 08:00 | 2008-11-03 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-11 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 1 | Finished | 13600 | 13600 | C2013-04 Kitchen Tower Anderlecht.xlsx
107 | 105 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
108 | 106 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-03-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | Finished | 3800 | 3800 | C2013-04 Kitchen Tower Anderlecht.xlsx
109 | 107 | BETON VIERDE VERDIEPING | 2008-11-07 08:00 | 2008-11-28 17:00 | 16d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 1 |  | 100000 | 100000 | C2013-04 Kitchen Tower Anderlecht.xlsx
110 | 108 | WANDEN KOKER A | 2008-11-07 08:00 | 2008-11-07 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
111 | 109 | WANDEN KOKER F | 2008-11-12 08:00 | 2008-11-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-17 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
112 | 110 | WANDEN KOKER B tot E | 2008-11-13 08:00 | 2008-11-14 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-03-18 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 1 | Finished | 22400 | 22400 | C2013-04 Kitchen Tower Anderlecht.xlsx
113 | 111 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
114 | 112 | BEKISTEN TUSSENBORDES KOKER F | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
115 | 113 | PL. WERKVLOEREN KOKERS B tot E | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
116 | 114 | BETON DRAAGWAND KOKER A en F | 2008-11-14 08:00 | 2008-11-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-19 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 1 | Finished | 4300 | 4300 | C2013-04 Kitchen Tower Anderlecht.xlsx
117 | 115 | BETON DRAAGWAND KOKER B tot E | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-23 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 1 | Finished | 3100 | 3100 | C2013-04 Kitchen Tower Anderlecht.xlsx
118 | 116 | BEKISTEN PLAAT KOKER A (zwart) | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
119 | 117 | BEKISTEN PLAAT KOKER F | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
120 | 118 | BEKISTEN RANDBALK PLAAT | 2008-11-18 08:00 | 2008-11-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
121 | 119 | BEKISTEN PLAAT (met tafels) | 2008-11-20 08:00 | 2008-11-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
122 | 120 | WAPENING VLOERPLATEN | 2008-11-24 08:00 | 2008-11-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-31 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 1 | Finished | 13600 | 13600 | C2013-04 Kitchen Tower Anderlecht.xlsx
123 | 121 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-27 08:00 | 2008-11-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
124 | 122 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-28 08:00 | 2008-11-28 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-02 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | Finished | 3800 | 3800 | C2013-04 Kitchen Tower Anderlecht.xlsx
125 | 123 | BETON VIJFDE VERDIEPING | 2008-12-01 08:00 | 2008-12-18 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 17d | [5 empty] | 120800 |  | 1 |  | 100000 | 100000 | C2013-04 Kitchen Tower Anderlecht.xlsx
126 | 124 | WANDEN KOKER A | 2008-12-01 08:00 | 2008-12-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-03 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
127 | 125 | WANDEN KOKER F | 2008-12-02 08:00 | 2008-12-02 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
128 | 126 | WANDEN KOKER B tot E | 2008-12-03 08:00 | 2008-12-04 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-07 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 1 | Finished | 22400 | 22400 | C2013-04 Kitchen Tower Anderlecht.xlsx
129 | 127 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
130 | 128 | BEKISTEN TUSSENBORDES KOKER F | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
131 | 129 | PL. WERKVLOEREN KOKERS B tot E | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
132 | 130 | BETON DRAAGWAND KOKER A en F | 2008-12-04 08:00 | 2008-12-05 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-04-08 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 1 | Finished | 4300 | 4300 | C2013-04 Kitchen Tower Anderlecht.xlsx
133 | 131 | BETON DRAAGWAND KOKER B tot E | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-04-10 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 1 | Finished | 3100 | 3100 | C2013-04 Kitchen Tower Anderlecht.xlsx
134 | 132 | BEKISTEN PLAAT KOKER A (zwart) | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
135 | 133 | BEKISTEN PLAAT KOKER F | 2008-12-09 08:00 | 2008-12-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
136 | 134 | BEKISTEN RANDBALK PLAAT | 2008-12-08 08:00 | 2008-12-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
137 | 135 | BEKISTEN PLAAT (met tafels) | 2008-12-10 08:00 | 2008-12-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
138 | 136 | WAPENING VLOERPLATEN | 2008-12-12 08:00 | 2008-12-16 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-04-23 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 1 | Finished | 13600 | 13600 | C2013-04 Kitchen Tower Anderlecht.xlsx
139 | 137 | BETON VLOERPLATEN (grof vlinderen) | 2008-12-17 08:00 | 2008-12-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-24 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
140 | 138 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-12-18 08:00 | 2008-12-18 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-27 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | Finished | 3800 | 3800 | C2013-04 Kitchen Tower Anderlecht.xlsx
141 | 139 | BETON ZESDE VERDIEPING | 2008-12-19 08:00 | 2009-01-21 17:00 | 24d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 120800 |  | 1 |  | 100000 | 100000 | C2013-04 Kitchen Tower Anderlecht.xlsx
142 | 140 | WANDEN KOKER A | 2008-12-19 08:00 | 2008-12-19 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-27 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
143 | 141 | WANDEN KOKER F | 2009-01-05 08:00 | 2009-01-05 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-28 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
144 | 142 | WANDEN KOKER B tot E | 2009-01-06 08:00 | 2009-01-07 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-29 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 1 | Finished | 22400 | 22400 | C2013-04 Kitchen Tower Anderlecht.xlsx
145 | 143 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
146 | 144 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
147 | 145 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
148 | 146 | BETON DRAAGWAND KOKER A en F | 2009-01-07 08:00 | 2009-01-08 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-05-01 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 1 | Finished | 4300 | 4300 | C2013-04 Kitchen Tower Anderlecht.xlsx
149 | 147 | BETON DRAAGWAND KOKER B tot E | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-05-05 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 1 | Finished | 3100 | 3100 | C2013-04 Kitchen Tower Anderlecht.xlsx
150 | 148 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
151 | 149 | BEKISTEN PLAAT KOKER F | 2009-01-12 08:00 | 2009-01-12 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-06 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
152 | 150 | BEKISTEN RANDBALK PLAAT | 2009-01-09 08:00 | 2009-01-13 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
153 | 151 | BEKISTEN PLAAT (met tafels) | 2009-01-13 08:00 | 2009-01-15 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-07 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
154 | 152 | WAPENING VLOERPLATEN | 2009-01-15 08:00 | 2009-01-19 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-05-11 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 1 | Finished | 13600 | 13600 | C2013-04 Kitchen Tower Anderlecht.xlsx
155 | 153 | BETON VLOERPLATEN (grof vlinderen) | 2009-01-20 08:00 | 2009-01-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
156 | 154 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-01-21 08:00 | 2009-01-21 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-05-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | Finished | 3800 | 3800 | C2013-04 Kitchen Tower Anderlecht.xlsx
157 | 155 | BETON ZEVENDE VERDIEPING | 2009-01-22 08:00 | 2009-02-10 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 17d | [5 empty] | 128000 |  | 1 |  | 100000 | 100000 | C2013-04 Kitchen Tower Anderlecht.xlsx
158 | 156 | WANDEN KOKER A | 2009-01-22 08:00 | 2009-01-22 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-12 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
159 | 157 | WANDEN KOKER F | 2009-01-23 08:00 | 2009-01-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-13 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
160 | 158 | WANDEN KOKER B tot E | 2009-01-26 08:00 | 2009-01-27 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-05-14 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 1 | Finished | 22400 | 22400 | C2013-04 Kitchen Tower Anderlecht.xlsx
161 | 159 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
162 | 160 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
163 | 161 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
164 | 162 | BETON DRAAGWAND KOKER A en F | 2009-01-27 08:00 | 2009-01-28 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-05-15 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 1 | Finished | 4300 | 4300 | C2013-04 Kitchen Tower Anderlecht.xlsx
165 | 163 | BETON DRAAGWAND KOKER B tot E | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-05-19 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 1 | Finished | 3100 | 3100 | C2013-04 Kitchen Tower Anderlecht.xlsx
166 | 164 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
167 | 165 | BEKISTEN PLAAT KOKER F | 2009-01-30 08:00 | 2009-01-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
168 | 166 | BEKISTEN RANDBALK PLAAT | 2009-01-29 08:00 | 2009-02-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-19 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
169 | 167 | BEKISTEN PLAAT (met tafels) | 2009-02-02 08:00 | 2009-02-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-25 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
170 | 168 | WAPENING VLOERPLATEN | 2009-02-04 08:00 | 2009-02-06 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-05-27 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 1 | Finished | 13600 | 13600 | C2013-04 Kitchen Tower Anderlecht.xlsx
171 | 169 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
172 | 170 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-02-10 08:00 | 2009-02-10 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-06-03 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | Finished | 3800 | 3800 | C2013-04 Kitchen Tower Anderlecht.xlsx
173 | 171 | BETON ACHTSTE VERDIEPING | 2009-02-11 08:00 | 2009-03-02 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 128000 |  | 1 |  | 100000 | 100000 | C2013-04 Kitchen Tower Anderlecht.xlsx
174 | 172 | WANDEN KOKER A | 2009-02-11 08:00 | 2009-02-11 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-04 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
175 | 173 | WANDEN KOKER F | 2009-02-12 08:00 | 2009-02-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
176 | 174 | WANDEN KOKER B tot E | 2009-02-13 08:00 | 2009-02-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-06-08 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 1 | Finished | 22400 | 22400 | C2013-04 Kitchen Tower Anderlecht.xlsx
177 | 175 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
178 | 176 | BEKISTEN TUSSENBORDES KOKER F | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
179 | 177 | PL. WERKVLOEREN KOKERS B tot E | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
180 | 178 | BETON DRAAGWAND KOKER A en F | 2009-02-16 08:00 | 2009-02-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-06-09 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 1 | Finished | 4300 | 4300 | C2013-04 Kitchen Tower Anderlecht.xlsx
181 | 179 | BETON DRAAGWAND KOKER B tot E | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-06-11 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 1 | Finished | 3100 | 3100 | C2013-04 Kitchen Tower Anderlecht.xlsx
182 | 180 | BEKISTEN PLAAT KOKER A (zwart) | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
183 | 181 | BEKISTEN PLAAT KOKER F | 2009-02-19 08:00 | 2009-02-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
184 | 182 | BEKISTEN RANDBALK PLAAT | 2009-02-18 08:00 | 2009-02-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-06-11 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
185 | 183 | BEKISTEN PLAAT (met tafels) | 2009-02-20 08:00 | 2009-02-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-06-15 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
186 | 184 | WAPENING VLOERPLATEN | 2009-02-24 08:00 | 2009-02-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-06-17 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 1 | Finished | 13600 | 13600 | C2013-04 Kitchen Tower Anderlecht.xlsx
187 | 185 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-27 08:00 | 2009-02-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-22 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
188 | 186 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-02 08:00 | 2009-03-02 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-06-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | Finished | 3800 | 3800 | C2013-04 Kitchen Tower Anderlecht.xlsx
189 | 187 | BETON NEGENDE VERDIEPING | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 51d | [5 empty] | 128000 |  | 1 |  | 100000 | 100000 | C2013-04 Kitchen Tower Anderlecht.xlsx
190 | 188 | WANDEN KOKER A | 2009-03-03 08:00 | 2009-03-03 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
191 | 189 | WANDEN KOKER F | 2009-03-04 08:00 | 2009-03-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
192 | 190 | WANDEN KOKER B tot E | 2009-03-05 08:00 | 2009-03-06 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-06-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 1 | Finished | 22400 | 22400 | C2013-04 Kitchen Tower Anderlecht.xlsx
193 | 191 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
194 | 192 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
195 | 193 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
196 | 194 | BETON DRAAGWAND KOKER A en F | 2009-03-06 08:00 | 2009-03-09 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-06-29 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 1 | Finished | 4300 | 4300 | C2013-04 Kitchen Tower Anderlecht.xlsx
197 | 195 | BETON DRAAGWAND KOKER B tot E | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-07-01 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 1 | Finished | 3100 | 3100 | C2013-04 Kitchen Tower Anderlecht.xlsx
198 | 196 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
199 | 197 | BEKISTEN PLAAT KOKER F | 2009-03-11 08:00 | 2009-03-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
200 | 198 | BEKISTEN RANDBALK PLAAT | 2009-03-10 08:00 | 2009-03-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-07-01 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
201 | 199 | BEKISTEN PLAAT (met tafels) | 2009-03-12 08:00 | 2009-03-16 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-07-03 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
202 | 200 | WAPENING VLOERPLATEN | 2009-03-16 08:00 | 2009-03-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-07-07 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 1 | Finished | 13600 | 13600 | C2013-04 Kitchen Tower Anderlecht.xlsx
203 | 201 | BETON VLOERPLATEN (grof vlinderen) | 2009-03-19 08:00 | 2009-03-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
204 | 202 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-20 08:00 | 2009-03-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-08-03 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | Finished | 3800 | 3800 | C2013-04 Kitchen Tower Anderlecht.xlsx
205 | 203 | BETON TIENDE VERDIEPING | 2009-03-23 08:00 | 2009-04-09 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 25d | [5 empty] | 120000 |  | 1 |  | 100000 | 100000 | C2013-04 Kitchen Tower Anderlecht.xlsx
206 | 204 | WANDEN KOKER A | 2009-03-23 08:00 | 2009-03-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-08-04 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
207 | 205 | WANDEN KOKER F | 2009-03-24 08:00 | 2009-03-24 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-08-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
208 | 206 | WANDEN KOKER B tot E | 2009-03-25 08:00 | 2009-03-26 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-08-06 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 1 | Finished | 22400 | 22400 | C2013-04 Kitchen Tower Anderlecht.xlsx
209 | 207 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
210 | 208 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
211 | 209 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
212 | 210 | BETON DRAAGWAND KOKER A en F | 2009-03-26 08:00 | 2009-03-27 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-08-07 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 1 | Finished | 4300 | 4300 | C2013-04 Kitchen Tower Anderlecht.xlsx
213 | 211 | BETON DRAAGWAND KOKER B tot E | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-08-11 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 1 | Finished | 3100 | 3100 | C2013-04 Kitchen Tower Anderlecht.xlsx
214 | 212 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
215 | 213 | BEKISTEN PLAAT KOKER F | 2009-03-31 08:00 | 2009-03-31 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
216 | 214 | BEKISTEN RANDBALK PLAAT | 2009-03-30 08:00 | 2009-04-01 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-08-11 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
217 | 215 | BEKISTEN PLAAT (met tafels) | 2009-04-01 08:00 | 2009-04-03 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-08-13 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
218 | 216 | WAPENING VLOERPLATEN | 2009-04-03 08:00 | 2009-04-07 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-08-18 08:00 | 3d | 13600 | 0 | 0 | 10000 | 0 | 23600 | 0 | 1 | Finished | 13600 | 13600 | C2013-04 Kitchen Tower Anderlecht.xlsx
219 | 217 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-08 08:00 | 2009-04-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
220 | 218 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-09 08:00 | 2009-04-09 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-09-07 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | Finished | 3800 | 3800 | C2013-04 Kitchen Tower Anderlecht.xlsx
221 | 219 | BETON ELFDE VERDIEPING | 2009-04-10 08:00 | 2009-04-30 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 123000 |  | 1 |  | 100000 | 100000 | C2013-04 Kitchen Tower Anderlecht.xlsx
222 | 220 | WANDEN KOKER A | 2009-04-10 08:00 | 2009-04-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-08 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
223 | 221 | WANDEN KOKER F | 2009-04-14 08:00 | 2009-04-14 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-09 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
224 | 222 | WANDEN KOKER B tot E | 2009-04-15 08:00 | 2009-04-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-09-10 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 1 | Finished | 22400 | 22400 | C2013-04 Kitchen Tower Anderlecht.xlsx
225 | 223 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
226 | 224 | BEKISTEN TUSSENBORDES KOKER F | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
227 | 225 | PL. WERKVLOEREN KOKERS B tot E | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
228 | 226 | BETON DRAAGWAND KOKER A en F | 2009-04-16 08:00 | 2009-04-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-09-11 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 1 | Finished | 4300 | 4300 | C2013-04 Kitchen Tower Anderlecht.xlsx
229 | 227 | BETON DRAAGWAND KOKER B tot E | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-09-15 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 1 | Finished | 3100 | 3100 | C2013-04 Kitchen Tower Anderlecht.xlsx
230 | 228 | BEKISTEN PLAAT KOKER A (zwart) | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
231 | 229 | BEKISTEN PLAAT KOKER F | 2009-04-21 08:00 | 2009-04-21 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
232 | 230 | BEKISTEN RANDBALK PLAAT | 2009-04-20 08:00 | 2009-04-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-09-15 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
233 | 231 | BEKISTEN PLAAT (met tafels) | 2009-04-22 08:00 | 2009-04-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-09-17 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
234 | 232 | WAPENING VLOERPLATEN | 2009-04-24 08:00 | 2009-04-28 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-09-21 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 1 | Finished | 13600 | 13600 | C2013-04 Kitchen Tower Anderlecht.xlsx
235 | 233 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-29 08:00 | 2009-04-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-24 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
236 | 234 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-30 08:00 | 2009-04-30 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-09-25 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | Finished | 3800 | 3800 | C2013-04 Kitchen Tower Anderlecht.xlsx
237 | 235 | BETON TWAALFDE VERDIEPING | 2009-05-01 08:00 | 2009-05-20 17:00 | 14d |  |  | 72400 |  |  | 98800 |  | 16d | [5 empty] | 121800 |  | 1 |  | 98800 | 98800 | C2013-04 Kitchen Tower Anderlecht.xlsx
238 | 236 | WANDEN KOKER A | 2009-05-01 08:00 | 2009-05-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-28 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
239 | 237 | WANDEN KOKER F | 2009-05-04 08:00 | 2009-05-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-29 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
240 | 238 | WANDEN KOKER B tot E | 2009-05-05 08:00 | 2009-05-05 17:00 | 1d |  | 0 | 20000 | 150 | 1200 | 21200 | 2009-09-30 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 1 | Finished | 21200 | 21200 | C2013-04 Kitchen Tower Anderlecht.xlsx
241 | 239 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
242 | 240 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
243 | 241 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-06 08:00 | 2009-05-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
244 | 242 | BETON DRAAGWAND KOKER A en F | 2009-05-06 08:00 | 2009-05-07 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-10-01 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 1 | Finished | 4300 | 4300 | C2013-04 Kitchen Tower Anderlecht.xlsx
245 | 243 | BETON DRAAGWAND KOKER B tot E | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-10-02 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 1 | Finished | 3100 | 3100 | C2013-04 Kitchen Tower Anderlecht.xlsx
246 | 244 | BEKISTEN PLAAT KOKER A (zwart) | 2009-05-08 08:00 | 2009-05-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-07 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
247 | 245 | BEKISTEN PLAAT KOKER F | 2009-05-11 08:00 | 2009-05-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-08 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
248 | 246 | BEKISTEN RANDBALK PLAAT | 2009-05-08 08:00 | 2009-05-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-10-07 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
249 | 247 | BEKISTEN PLAAT (met tafels) | 2009-05-12 08:00 | 2009-05-14 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-10-09 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
250 | 248 | WAPENING VLOERPLATEN | 2009-05-14 08:00 | 2009-05-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-10-13 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 1 | Finished | 13600 | 13600 | C2013-04 Kitchen Tower Anderlecht.xlsx
251 | 249 | BETON VLOERPLATEN (grof vlinderen) | 2009-05-19 08:00 | 2009-05-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
252 | 250 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-05-20 08:00 | 2009-05-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-10-19 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | Finished | 3800 | 3800 | C2013-04 Kitchen Tower Anderlecht.xlsx
253 | 251 | BETON DERTIENDE VERDIEPING | 2009-05-25 08:00 | 2009-06-12 17:00 | 15d |  |  | 72400 |  |  | 101200 |  | 18d | [5 empty] | 116200 |  | 1 |  | 101200 | 101200 | C2013-04 Kitchen Tower Anderlecht.xlsx
254 | 252 | WANDEN KOKER A | 2009-05-25 08:00 | 2009-05-25 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-10-20 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
255 | 253 | WANDEN KOKER F | 2009-05-26 08:00 | 2009-05-26 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-10-21 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
256 | 254 | WANDEN KOKER B tot E | 2009-05-27 08:00 | 2009-05-28 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-10-22 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 1 | Finished | 22400 | 22400 | C2013-04 Kitchen Tower Anderlecht.xlsx
257 | 255 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
258 | 256 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
259 | 257 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
260 | 258 | BETON DRAAGWAND KOKER A en F | 2009-05-28 08:00 | 2009-05-29 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-10-23 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 1 | Finished | 4300 | 4300 | C2013-04 Kitchen Tower Anderlecht.xlsx
261 | 259 | BETON DRAAGWAND KOKER B tot E | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-10-27 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 1 | Finished | 3100 | 3100 | C2013-04 Kitchen Tower Anderlecht.xlsx
262 | 260 | BEKISTEN PLAAT KOKER A (zwart) | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
263 | 261 | BEKISTEN PLAAT KOKER F | 2009-06-03 08:00 | 2009-06-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-28 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
264 | 262 | BEKISTEN RANDBALK PLAAT | 2009-06-02 08:00 | 2009-06-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-10-27 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 1 | Finished | 5600 | 5600 | C2013-04 Kitchen Tower Anderlecht.xlsx
265 | 263 | BEKISTEN PLAAT (met tafels) deels met stelling 8m hoog | 2009-06-04 08:00 | 2009-06-09 17:00 | 4d |  | 0 | 2000 | 150 | 4800 | 6800 | 2009-10-29 08:00 | 4d | 6800 | 0 | 0 | 5000 | 0 | 11800 | 0 | 1 | Finished | 6800 | 6800 | C2013-04 Kitchen Tower Anderlecht.xlsx
266 | 264 | WAPENING VLOERPLATEN | 2009-06-08 08:00 | 2009-06-10 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-11-04 08:00 | 3d | 13600 | 0 | 0 | 0 | 0 | 13600 | 0 | 1 | Finished | 13600 | 13600 | C2013-04 Kitchen Tower Anderlecht.xlsx
267 | 265 | BETON VLOERPLATEN (grof vlinderen) | 2009-06-11 08:00 | 2009-06-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-11-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2013-04 Kitchen Tower Anderlecht.xlsx
268 | 266 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-06-12 08:00 | 2009-06-12 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-11-12 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | Finished | 3800 | 3800 | C2013-04 Kitchen Tower Anderlecht.xlsx
269 | 267 | BETON VEERTIENDE DAKVERDIEPING | 2009-06-15 08:00 | 2009-08-12 17:00 | 43d |  |  | 42036 |  |  | 56436 |  | 53d | [5 empty] | 72436 |  | 1 |  | 56436 | 56436 | C2013-04 Kitchen Tower Anderlecht.xlsx
270 | 268 | WANDEN KOKER A | 2009-06-15 08:00 | 2009-06-15 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-11-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
271 | 269 | WANDEN KOKER F | 2009-06-16 08:00 | 2009-06-16 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-11-17 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 1 | Finished | 11200 | 11200 | C2013-04 Kitchen Tower Anderlecht.xlsx
272 | 270 | BETON DRAAGWAND KOKER F | 2009-06-18 08:00 | 2009-06-19 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 | 2009-11-19 08:00 | 2d | 12400 | 0 | 0 | 5000 | 0 | 17400 | 0 | 1 | Finished | 12400 | 12400 | C2013-04 Kitchen Tower Anderlecht.xlsx
273 | 271 | BEKISTEN DAKPLAAT KOKER F | 2009-06-23 08:00 | 2009-06-24 17:00 | 2d |  | 0 | 1000 | 150 | 2400 | 3400 | 2009-12-01 08:00 | 2d | 3400 | 0 | 0 | 0 | 0 | 3400 | 0 | 1 | Finished | 3400 | 3400 | C2013-04 Kitchen Tower Anderlecht.xlsx
274 | 272 | HELLINGSBETON DAK enkel boven kokers | 2009-06-25 08:00 | 2009-06-26 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 | 2009-12-07 08:00 | 2d | 12400 | 0 | 0 | 0 | 0 | 12400 | 0 | 1 | Finished | 12400 | 12400 | C2013-04 Kitchen Tower Anderlecht.xlsx
275 | 273 | ONTKISTEN PLATEN 13de EN 14de VERDIEPING | 2009-08-07 08:00 | 2009-08-12 17:00 | 4d |  | 0 | 1036 | 150 | 4800 | 5836 | 2010-01-22 08:00 | 4d | 5836 | 0 | 0 | 6000 | 0 | 11836 | 0 | 1 | Finished | 5836 | 5836 | C2013-04 Kitchen Tower Anderlecht.xlsx
4 | 0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 632d | [5 empty] | 874554.2837 |  | 1 |  | 874554.2837 | 874554.2837 | C2013-05 PET Packaging.xlsx
5 | 6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 1 |  | 28353.9331 | 28353.9331 | C2013-05 PET Packaging.xlsx
6 | 1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 1 | Finished | 5670.7866 | 5670.7866 | C2013-05 PET Packaging.xlsx
7 | 2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 1 | Finished | 5670.7866 | 5670.7866 | C2013-05 PET Packaging.xlsx
8 | 3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 1 | Finished | 5670.7866 | 5670.7866 | C2013-05 PET Packaging.xlsx
9 | 4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 1 | Finished | 5670.7866 | 5670.7866 | C2013-05 PET Packaging.xlsx
10 | 5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 1 | Finished | 5670.7866 | 5670.7866 | C2013-05 PET Packaging.xlsx
11 | 11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 609d | [5 empty] | 161094.1533 |  | 1 |  | 161094.1533 | 161094.1533 | C2013-05 PET Packaging.xlsx
12 | 7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 1 | Finished | 76711.5 | 76711.5 | C2013-05 PET Packaging.xlsx
13 | 8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 218d | 46026.9023 | 0 | 0 | 0 | 0 | 46026.9023 | 0 | 1 | Finished | 46026.9023 | 46026.9023 | C2013-05 PET Packaging.xlsx
14 | 9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 | 2012-11-01 08:00 | 43d | 15342.2998 | 0 | 0 | 0 | 0 | 15342.2998 | 0 | 1 | Finished | 15342.2998 | 15342.2998 | C2013-05 PET Packaging.xlsx
15 | 10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 | 2013-04-01 08:00 | 65d | 23013.4512 | 0 | 0 | 0 | 0 | 23013.4512 | 0 | 1 | Finished | 23013.4512 | 23013.4512 | C2013-05 PET Packaging.xlsx
16 | 16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 1 |  | 127886.6816 | 127886.6816 | C2013-05 PET Packaging.xlsx
17 | 12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 1 | Finished | 21314.4473 | 21314.4473 | C2013-05 PET Packaging.xlsx
18 | 13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 1 | Finished | 42628.8945 | 42628.8945 | C2013-05 PET Packaging.xlsx
19 | 14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 1 | Finished | 31971.6699 | 31971.6699 | C2013-05 PET Packaging.xlsx
20 | 15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 1 | Finished | 31971.6699 | 31971.6699 | C2013-05 PET Packaging.xlsx
21 | 20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 262d | [5 empty] | 129698.0352 |  | 1 |  | 129698.0352 | 129698.0352 | C2013-05 PET Packaging.xlsx
22 | 17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 1 | Finished | 51879.2148 | 51879.2148 | C2013-05 PET Packaging.xlsx
23 | 18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 1 | Finished | 38909.4102 | 38909.4102 | C2013-05 PET Packaging.xlsx
24 | 19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 1 | Finished | 38909.4102 | 38909.4102 | C2013-05 PET Packaging.xlsx
25 | 24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 390d | [5 empty] | 217995.2734 |  | 1 |  | 217995.2734 | 217995.2734 | C2013-05 PET Packaging.xlsx
26 | 21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 283d | 124568.7266 | 0 | 0 | 0 | 0 | 124568.7266 | 0 | 1 | Finished | 124568.7266 | 124568.7266 | C2013-05 PET Packaging.xlsx
27 | 22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 64d | 46713.2734 | 0 | 0 | 0 | 0 | 46713.2734 | 0 | 1 | Finished | 46713.2734 | 46713.2734 | C2013-05 PET Packaging.xlsx
28 | 23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 64d | 46713.2734 | 0 | 0 | 0 | 0 | 46713.2734 | 0 | 1 | Finished | 46713.2734 | 46713.2734 | C2013-05 PET Packaging.xlsx
29 | 31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 218d | [5 empty] | 165125.8984 |  | 1 |  | 165125.8984 | 165125.8984 | C2013-05 PET Packaging.xlsx
30 | 25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 | 2012-10-01 08:00 | 218d | 40274.6094 | 0 | 0 | 0 | 0 | 40274.6094 | 0 | 1 | Finished | 40274.6094 | 40274.6094 | C2013-05 PET Packaging.xlsx
31 | 26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 | 2013-01-01 08:00 | 152d | 28192.2266 | 0 | 0 | 0 | 0 | 28192.2266 | 0 | 1 | Finished | 28192.2266 | 28192.2266 | C2013-05 PET Packaging.xlsx
32 | 27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 173d | 32219.6875 | 0 | 0 | 0 | 0 | 32219.6875 | 0 | 1 | Finished | 32219.6875 | 32219.6875 | C2013-05 PET Packaging.xlsx
33 | 28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 173d | 32219.6875 | 0 | 0 | 0 | 0 | 32219.6875 | 0 | 1 | Finished | 32219.6875 | 32219.6875 | C2013-05 PET Packaging.xlsx
34 | 29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 | 2012-12-03 08:00 | 64d | 12082.3828 | 0 | 0 | 0 | 0 | 12082.3828 | 0 | 1 | Finished | 12082.3828 | 12082.3828 | C2013-05 PET Packaging.xlsx
35 | 35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 | 2013-07-01 08:00 | 23d | 4027.4609 | 0 | 0 | 0 | 0 | 4027.4609 | 0 | 1 | Finished | 4027.4609 | 4027.4609 | C2013-05 PET Packaging.xlsx
36 | 30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 | 2012-12-03 08:00 | 85d | 16109.8438 | 0 | 0 | 0 | 0 | 16109.8438 | 0 | 1 | Finished | 16109.8438 | 16109.8438 | C2013-05 PET Packaging.xlsx
37 | 34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 523d | [5 empty] | 44400.3086 |  | 1 |  | 44400.3086 | 44400.3086 | C2013-05 PET Packaging.xlsx
38 | 32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 523d | 22200.1543 | 0 | 0 | 0 | 0 | 22200.1543 | 0 | 1 | Finished | 22200.1543 | 22200.1543 | C2013-05 PET Packaging.xlsx
39 | 33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 523d | 22200.1543 | 0 | 0 | 0 | 0 | 22200.1543 | 0 | 1 | Finished | 22200.1543 | 22200.1543 | C2013-05 PET Packaging.xlsx
4 | 0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 344d | [5 empty] | 21546846.1819 |  | 1 |  | 19429810.5132 | 19407310.5132 | C2013-06 Government Office Building.xlsx
5 | 456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 1 | Finished | 867102 | 867102 | C2013-06 Government Office Building.xlsx
6 | 468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 155d | [5 empty] | 545329.4824 |  | 1 |  | 533489.4428 | 533489.4428 | C2013-06 Government Office Building.xlsx
7 | 458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 1 | Finished | 907.58 | 907.58 | C2013-06 Government Office Building.xlsx
8 | 459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 150d | 27227.4199 | 0 | 0 | 5824.0298 | 0 | 33051.4497 | 0 | 1 | Finished | 27227.4199 | 27227.4199 | C2013-06 Government Office Building.xlsx
9 | 460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 1 | Finished | 104828.3281 | 104828.3281 | C2013-06 Government Office Building.xlsx
10 | 461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 1 | Finished | 9333.3301 | 9333.3301 | C2013-06 Government Office Building.xlsx
11 | 462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 1 | Finished | 9333.3301 | 9333.3301 | C2013-06 Government Office Building.xlsx
12 | 463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 1 | Finished | 241105.1562 | 241105.1562 | C2013-06 Government Office Building.xlsx
13 | 464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 1 | Finished | 4666.6699 | 4666.6699 | C2013-06 Government Office Building.xlsx
14 | 457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 1 | Finished | 4666.5698 | 4666.5698 | C2013-06 Government Office Building.xlsx
15 | 465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 1 | Finished | 20710.5293 | 20710.5293 | C2013-06 Government Office Building.xlsx
16 | 466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 1 | Finished | 90000 | 90000 | C2013-06 Government Office Building.xlsx
17 | 467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 1 | Finished | 20710.5293 | 20710.5293 | C2013-06 Government Office Building.xlsx
18 | 436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 176d | [5 empty] | 6199805.6499 |  | 1 |  | 5887941.9712 | 5887941.9712 | C2013-06 Government Office Building.xlsx
19 | 416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 62d | [5 empty] | 332131.6968 |  | 1 |  | 329571.4868 | 329571.4868 | C2013-06 Government Office Building.xlsx
20 | 1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 1 | Finished | 9394.7402 | 9394.7402 | C2013-06 Government Office Building.xlsx
21 | 2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 1 | Finished | 26178.6699 | 26178.6699 | C2013-06 Government Office Building.xlsx
22 | 3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 1 | Finished | 152015.2188 | 152015.2188 | C2013-06 Government Office Building.xlsx
23 | 4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 1 | Finished | 90000 | 90000 | C2013-06 Government Office Building.xlsx
24 | 5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 15d | 6710.5298 | 0 | 0 | 582.4 | 0 | 7292.9298 | 0 | 1 | Finished | 6710.5298 | 6710.5298 | C2013-06 Government Office Building.xlsx
25 | 6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 2009-04-06 08:00 | 5d | 45272.3281 | 0 | 0 | 194.13 | 0 | 45466.4581 | 0 | 1 | Finished | 45272.3281 | 45272.3281 | C2013-06 Government Office Building.xlsx
26 | 475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 53d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 1 | Finished | 378979.8125 | 378979.8125 | C2013-06 Government Office Building.xlsx
27 | 476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 28d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 1 | Finished | 505306.4062 | 505306.4062 | C2013-06 Government Office Building.xlsx
28 | 477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 56d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 1 | Finished | 378979.8125 | 378979.8125 | C2013-06 Government Office Building.xlsx
29 | 478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 42d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 1 | Finished | 505306.4062 | 505306.4062 | C2013-06 Government Office Building.xlsx
30 | 479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-04-08 08:00 | 21d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 1 | Finished | 252653.2031 | 252653.2031 | C2013-06 Government Office Building.xlsx
31 | 480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-05 08:00 | 14d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 1 | Finished | 252653.2031 | 252653.2031 | C2013-06 Government Office Building.xlsx
32 | 481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-19 08:00 | 10d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 1 | Finished | 252653.2031 | 252653.2031 | C2013-06 Government Office Building.xlsx
33 | 482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-05 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 1 | Finished | 252653.2031 | 252653.2031 | C2013-06 Government Office Building.xlsx
34 | 483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-17 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 1 | Finished | 252653.2031 | 252653.2031 | C2013-06 Government Office Building.xlsx
35 | 484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-29 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 1 | Finished | 252653.2031 | 252653.2031 | C2013-06 Government Office Building.xlsx
36 | 485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-09 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 1 | Finished | 252653.2031 | 252653.2031 | C2013-06 Government Office Building.xlsx
37 | 486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 1 | Finished | 252653.2031 | 252653.2031 | C2013-06 Government Office Building.xlsx
38 | 487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 1 | Finished | 252653.2031 | 252653.2031 | C2013-06 Government Office Building.xlsx
39 | 488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-12 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 1 | Finished | 252653.2031 | 252653.2031 | C2013-06 Government Office Building.xlsx
40 | 489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-25 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 1 | Finished | 252653.2031 | 252653.2031 | C2013-06 Government Office Building.xlsx
41 | 490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-04 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 1 | Finished | 252653.2031 | 252653.2031 | C2013-06 Government Office Building.xlsx
42 | 491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-16 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 1 | Finished | 252653.2031 | 252653.2031 | C2013-06 Government Office Building.xlsx
43 | 492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-28 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 1 | Finished | 252653.2031 | 252653.2031 | C2013-06 Government Office Building.xlsx
44 | 493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-10-08 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 1 | Finished | 252653.2031 | 252653.2031 | C2013-06 Government Office Building.xlsx
45 | 438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 104d | [5 empty] | 598869.7309 |  | 1 |  | 597815.1211 | 597815.1211 | C2013-06 Government Office Building.xlsx
46 | 437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 104d | [5 empty] | 598869.7309 |  | 1 |  | 597815.1211 | 597815.1211 | C2013-06 Government Office Building.xlsx
47 | 182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 | 2009-10-20 08:00 | 5d | 66991.6562 | 0 | 0 | 194.13 | 0 | 67185.7863 | 0 | 1 | Finished | 66991.6562 | 66991.6562 | C2013-06 Government Office Building.xlsx
48 | 183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 | 2009-10-07 08:00 | 10d | 46575.5195 | 0 | 0 | -639.21 | 0 | 45936.3095 | 0 | 1 | Finished | 46575.5195 | 46575.5195 | C2013-06 Government Office Building.xlsx
49 | 184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 | 2009-10-27 08:00 | 15d | 139726.5469 | 0 | 0 | -1917.63 | 0 | 137808.9169 | 0 | 1 | Finished | 139726.5469 | 139726.5469 | C2013-06 Government Office Building.xlsx
50 | 185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 | 2009-11-19 08:00 | 10d | 91163.3906 | 0 | 0 | 6225.1099 | 0 | 97388.5005 | 0 | 1 | Finished | 91163.3906 | 91163.3906 | C2013-06 Government Office Building.xlsx
51 | 186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 | 2009-06-16 08:00 | 20d | 232877.5781 | 0 | 0 | -3196.0601 | 0 | 229681.5181 | 0 | 1 | Finished | 232877.5781 | 232877.5781 | C2013-06 Government Office Building.xlsx
52 | 187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 | 2009-08-04 08:00 | 10d | 20480.4297 | 0 | 0 | 388.27 | 0 | 20868.6997 | 0 | 1 | Finished | 20480.4297 | 20480.4297 | C2013-06 Government Office Building.xlsx
53 | 440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 127d | [5 empty] | 3253773.5414 |  | 1 |  | 3310363.4299 | 3310363.4299 | C2013-06 Government Office Building.xlsx
54 | 439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 127d | [5 empty] | 3253773.5414 |  | 1 |  | 3310363.4299 | 3310363.4299 | C2013-06 Government Office Building.xlsx
55 | 188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 | 2009-06-29 08:00 | 10d | 2053.97 | 0 | 0 | 388.27 | 0 | 2442.24 | 0 | 1 | Finished | 2053.97 | 2053.97 | C2013-06 Government Office Building.xlsx
56 | 189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 | 2010-01-04 08:00 | 20d | 1071966 | 0 | 0 | -18668.2891 | 0 | 1053297.7109 | 0 | 1 | Finished | 1071966 | 1071966 | C2013-06 Government Office Building.xlsx
57 | 190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-08-03 09:00 | 42d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 1 | Finished | 491317.75 | 491317.75 | C2013-06 Government Office Building.xlsx
58 | 191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-10-01 08:00 | 22d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 1 | Finished | 491317.75 | 491317.75 | C2013-06 Government Office Building.xlsx
59 | 192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 | 2009-11-03 08:00 | 33d | 1250627 | 0 | 0 | -21779.6699 | 0 | 1228847.3301 | 0 | 1 | Finished | 1250627 | 1250627 | C2013-06 Government Office Building.xlsx
60 | 193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 | 2010-01-04 10:00 | 15d | 3080.96 | 0 | 0 | 582.4 | 0 | 3663.36 | 0 | 1 | Finished | 3080.96 | 3080.96 | C2013-06 Government Office Building.xlsx
61 | 441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 99d | [5 empty] | 1092383.8923 |  | 1 |  | 520800.3072 | 520800.3072 | C2013-06 Government Office Building.xlsx
62 | 274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-07 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 1 | Finished | 8611.6201 | 8611.6201 | C2013-06 Government Office Building.xlsx
63 | 275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-30 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 1 | Finished | 39378.6016 | 39378.6016 | C2013-06 Government Office Building.xlsx
64 | 276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-11-05 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 1 | Finished | 88472.6172 | 88472.6172 | C2013-06 Government Office Building.xlsx
65 | 277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-01 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 1 | Finished | 544.23 | 544.23 | C2013-06 Government Office Building.xlsx
66 | 278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-04 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 1 | Finished | 957.81 | 957.81 | C2013-06 Government Office Building.xlsx
67 | 279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 | 2010-02-10 08:00 | 5d | 26237.0293 | 0 | 0 | 589.25 | 0 | 26826.2793 | 0 | 1 | Finished | 26237.0293 | 26237.0293 | C2013-06 Government Office Building.xlsx
68 | 280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 | 2010-02-17 08:00 | 10d | 2554.8601 | 0 | 0 | 388.27 | 0 | 2943.1301 | 0 | 1 | Finished | 2554.8601 | 2554.8601 | C2013-06 Government Office Building.xlsx
69 | 281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-03-03 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 1 | Finished | 187631.6875 | 187631.6875 | C2013-06 Government Office Building.xlsx
70 | 282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 | 2010-03-17 08:00 | 10d | 9851.1602 | 0 | 0 | 1082.6899 | 0 | 10933.8501 | 0 | 1 | Finished | 9851.1602 | 9851.1602 | C2013-06 Government Office Building.xlsx
71 | 283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 1 | Finished | 4682.9302 | 4682.9302 | C2013-06 Government Office Building.xlsx
72 | 284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 1 | Finished | 24999.8008 | 24999.8008 | C2013-06 Government Office Building.xlsx
73 | 285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-05 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 1 | Finished | 1037.39 | 1037.39 | C2013-06 Government Office Building.xlsx
74 | 286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-02-08 08:00 | 4d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 1 | Finished | 37201.2891 | 37201.2891 | C2013-06 Government Office Building.xlsx
75 | 287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-24 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 1 | Finished | 20841.1602 | 20841.1602 | C2013-06 Government Office Building.xlsx
76 | 288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-26 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 1 | Finished | 11668.21 | 11668.21 | C2013-06 Government Office Building.xlsx
77 | 289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 | 2010-02-05 08:00 | 10d | 18002.3008 | 0 | 0 | 16267.6904 | 0 | 34269.9912 | 0 | 1 | Finished | 18002.3008 | 18002.3008 | C2013-06 Government Office Building.xlsx
78 | 290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-04 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 1 | Finished | 15626.6104 | 15626.6104 | C2013-06 Government Office Building.xlsx
79 | 291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 | 2009-11-12 08:00 | 80d | 1 | 0 | 0 | 530274.125 | 0 | 530275.125 | 0 | 1 | Finished | 1 | 1 | C2013-06 Government Office Building.xlsx
80 | 292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-18 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 1 | Finished | 22500 | 22500 | C2013-06 Government Office Building.xlsx
81 | 442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 99d | [5 empty] | 621482.7349 |  | 1 |  | 559972.2264 | 559972.2264 | C2013-06 Government Office Building.xlsx
82 | 258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-14 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 1 | Finished | 8611.6201 | 8611.6201 | C2013-06 Government Office Building.xlsx
83 | 259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-27 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 1 | Finished | 39378.6016 | 39378.6016 | C2013-06 Government Office Building.xlsx
84 | 260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 1 | Finished | 88472.6172 | 88472.6172 | C2013-06 Government Office Building.xlsx
85 | 261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-01 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 1 | Finished | 544.23 | 544.23 | C2013-06 Government Office Building.xlsx
86 | 262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-04 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 1 | Finished | 957.81 | 957.81 | C2013-06 Government Office Building.xlsx
87 | 263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-02-10 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 1 | Finished | 84509.5 | 84509.5 | C2013-06 Government Office Building.xlsx
88 | 264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-04 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 1 | Finished | 187631.6875 | 187631.6875 | C2013-06 Government Office Building.xlsx
89 | 265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 1 | Finished | 4682.9302 | 4682.9302 | C2013-06 Government Office Building.xlsx
90 | 266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 1 | Finished | 24999.8008 | 24999.8008 | C2013-06 Government Office Building.xlsx
91 | 267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-05 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 1 | Finished | 1037.39 | 1037.39 | C2013-06 Government Office Building.xlsx
92 | 268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-02-12 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 1 | Finished | 37201.2891 | 37201.2891 | C2013-06 Government Office Building.xlsx
93 | 269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-24 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 1 | Finished | 20841.1602 | 20841.1602 | C2013-06 Government Office Building.xlsx
94 | 270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-26 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 1 | Finished | 11668.21 | 11668.21 | C2013-06 Government Office Building.xlsx
95 | 271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-04 08:00 | 13d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 1 | Finished | 15626.6104 | 15626.6104 | C2013-06 Government Office Building.xlsx
96 | 272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-23 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 1 | Finished | 11308.7695 | 11308.7695 | C2013-06 Government Office Building.xlsx
97 | 273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-26 08:00 | 3d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 1 | Finished | 22500 | 22500 | C2013-06 Government Office Building.xlsx
98 | 443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 30d | [5 empty] | 55338.81 |  | 1 |  | 52785.1602 | 52785.1602 | C2013-06 Government Office Building.xlsx
99 | 414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 | 2009-10-21 08:00 | 10d | 14638.2695 | 0 | 0 | 388.27 | 0 | 15026.5395 | 0 | 1 | Finished | 14638.2695 | 14638.2695 | C2013-06 Government Office Building.xlsx
100 | 415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 | 2009-11-05 08:00 | 20d | 38146.8906 | 0 | 0 | 2165.3799 | 0 | 40312.2705 | 0 | 1 | Finished | 38146.8906 | 38146.8906 | C2013-06 Government Office Building.xlsx
101 | 444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 109d | [5 empty] | 621482.7349 |  | 1 |  | 559972.2264 | 559972.2264 | C2013-06 Government Office Building.xlsx
102 | 194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 1 | Finished | 8611.6201 | 8611.6201 | C2013-06 Government Office Building.xlsx
103 | 195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-11 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 1 | Finished | 39378.6016 | 39378.6016 | C2013-06 Government Office Building.xlsx
104 | 196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-14 08:00 | 25d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 1 | Finished | 88472.6172 | 88472.6172 | C2013-06 Government Office Building.xlsx
105 | 197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 1 | Finished | 544.23 | 544.23 | C2013-06 Government Office Building.xlsx
106 | 198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 1 | Finished | 957.81 | 957.81 | C2013-06 Government Office Building.xlsx
107 | 199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 1 | Finished | 84509.5 | 84509.5 | C2013-06 Government Office Building.xlsx
108 | 200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 1 | Finished | 187631.6875 | 187631.6875 | C2013-06 Government Office Building.xlsx
109 | 201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 1 | Finished | 4682.9302 | 4682.9302 | C2013-06 Government Office Building.xlsx
110 | 202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 1 | Finished | 24999.8008 | 24999.8008 | C2013-06 Government Office Building.xlsx
111 | 203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2009-12-09 08:00 | 4d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 1 | Finished | 1037.39 | 1037.39 | C2013-06 Government Office Building.xlsx
112 | 204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-09 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 1 | Finished | 37201.2891 | 37201.2891 | C2013-06 Government Office Building.xlsx
113 | 205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2009-12-15 08:00 | 4d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 1 | Finished | 20841.1602 | 20841.1602 | C2013-06 Government Office Building.xlsx
114 | 206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 1 | Finished | 11668.21 | 11668.21 | C2013-06 Government Office Building.xlsx
115 | 207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-04 08:00 | 10d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 1 | Finished | 15626.6104 | 15626.6104 | C2013-06 Government Office Building.xlsx
116 | 208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-01-18 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 1 | Finished | 11308.7695 | 11308.7695 | C2013-06 Government Office Building.xlsx
117 | 209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-01-21 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 1 | Finished | 22500 | 22500 | C2013-06 Government Office Building.xlsx
118 | 445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 116d | [5 empty] | 621482.7349 |  | 1 |  | 559972.2264 | 559972.2264 | C2013-06 Government Office Building.xlsx
119 | 210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 1 | Finished | 8611.6201 | 8611.6201 | C2013-06 Government Office Building.xlsx
120 | 211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-14 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 1 | Finished | 39378.6016 | 39378.6016 | C2013-06 Government Office Building.xlsx
121 | 212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-20 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 1 | Finished | 88472.6172 | 88472.6172 | C2013-06 Government Office Building.xlsx
122 | 213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 1 | Finished | 544.23 | 544.23 | C2013-06 Government Office Building.xlsx
123 | 214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 1 | Finished | 957.81 | 957.81 | C2013-06 Government Office Building.xlsx
124 | 215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 1 | Finished | 84509.5 | 84509.5 | C2013-06 Government Office Building.xlsx
125 | 216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 1 | Finished | 187631.6875 | 187631.6875 | C2013-06 Government Office Building.xlsx
126 | 217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 1 | Finished | 4682.9302 | 4682.9302 | C2013-06 Government Office Building.xlsx
127 | 218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 1 | Finished | 24999.8008 | 24999.8008 | C2013-06 Government Office Building.xlsx
128 | 219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2009-12-09 08:00 | 6d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 1 | Finished | 1037.39 | 1037.39 | C2013-06 Government Office Building.xlsx
129 | 220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-14 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 1 | Finished | 37201.2891 | 37201.2891 | C2013-06 Government Office Building.xlsx
130 | 221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2009-12-15 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 1 | Finished | 20841.1602 | 20841.1602 | C2013-06 Government Office Building.xlsx
131 | 222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 1 | Finished | 11668.21 | 11668.21 | C2013-06 Government Office Building.xlsx
132 | 223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-06 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 1 | Finished | 15626.6104 | 15626.6104 | C2013-06 Government Office Building.xlsx
133 | 224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-01-27 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 1 | Finished | 11308.7695 | 11308.7695 | C2013-06 Government Office Building.xlsx
134 | 225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-01 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 1 | Finished | 22500 | 22500 | C2013-06 Government Office Building.xlsx
135 | 446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 120d | [5 empty] | 621482.7349 |  | 1 |  | 559972.2264 | 559972.2264 | C2013-06 Government Office Building.xlsx
136 | 226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 1 | Finished | 8611.6201 | 8611.6201 | C2013-06 Government Office Building.xlsx
137 | 227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-20 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 1 | Finished | 39378.6016 | 39378.6016 | C2013-06 Government Office Building.xlsx
138 | 228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-25 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 1 | Finished | 88472.6172 | 88472.6172 | C2013-06 Government Office Building.xlsx
139 | 229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 1 | Finished | 544.23 | 544.23 | C2013-06 Government Office Building.xlsx
140 | 230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 1 | Finished | 957.81 | 957.81 | C2013-06 Government Office Building.xlsx
141 | 231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 1 | Finished | 84509.5 | 84509.5 | C2013-06 Government Office Building.xlsx
142 | 232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 1 | Finished | 187631.6875 | 187631.6875 | C2013-06 Government Office Building.xlsx
143 | 233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 1 | Finished | 4682.9302 | 4682.9302 | C2013-06 Government Office Building.xlsx
144 | 234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 1 | Finished | 24999.8008 | 24999.8008 | C2013-06 Government Office Building.xlsx
145 | 235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-17 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 1 | Finished | 37201.2891 | 37201.2891 | C2013-06 Government Office Building.xlsx
146 | 236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-04 08:00 | 6d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 1 | Finished | 1037.39 | 1037.39 | C2013-06 Government Office Building.xlsx
147 | 237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-12 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 1 | Finished | 20841.1602 | 20841.1602 | C2013-06 Government Office Building.xlsx
148 | 238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-12-09 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 1 | Finished | 11668.21 | 11668.21 | C2013-06 Government Office Building.xlsx
149 | 239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-20 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 1 | Finished | 15626.6104 | 15626.6104 | C2013-06 Government Office Building.xlsx
150 | 240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-10 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 1 | Finished | 11308.7695 | 11308.7695 | C2013-06 Government Office Building.xlsx
151 | 241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-15 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 1 | Finished | 22500 | 22500 | C2013-06 Government Office Building.xlsx
152 | 447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 120d | [5 empty] | 621482.7349 |  | 1 |  | 559972.2264 | 559972.2264 | C2013-06 Government Office Building.xlsx
153 | 242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 1 | Finished | 8611.6201 | 8611.6201 | C2013-06 Government Office Building.xlsx
154 | 243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 1 | Finished | 39378.6016 | 39378.6016 | C2013-06 Government Office Building.xlsx
155 | 244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-28 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 1 | Finished | 88472.6172 | 88472.6172 | C2013-06 Government Office Building.xlsx
156 | 245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 1 | Finished | 544.23 | 544.23 | C2013-06 Government Office Building.xlsx
157 | 246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 1 | Finished | 957.81 | 957.81 | C2013-06 Government Office Building.xlsx
158 | 247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 1 | Finished | 84509.5 | 84509.5 | C2013-06 Government Office Building.xlsx
159 | 248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 1 | Finished | 187631.6875 | 187631.6875 | C2013-06 Government Office Building.xlsx
160 | 249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 1 | Finished | 4682.9302 | 4682.9302 | C2013-06 Government Office Building.xlsx
161 | 250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 1 | Finished | 24999.8008 | 24999.8008 | C2013-06 Government Office Building.xlsx
162 | 251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-04 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 1 | Finished | 1037.39 | 1037.39 | C2013-06 Government Office Building.xlsx
163 | 252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-05 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 1 | Finished | 37201.2891 | 37201.2891 | C2013-06 Government Office Building.xlsx
164 | 253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-12 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 1 | Finished | 20841.1602 | 20841.1602 | C2013-06 Government Office Building.xlsx
165 | 254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-12-09 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 1 | Finished | 11668.21 | 11668.21 | C2013-06 Government Office Building.xlsx
166 | 255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-20 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 1 | Finished | 15626.6104 | 15626.6104 | C2013-06 Government Office Building.xlsx
167 | 256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-10 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 1 | Finished | 11308.7695 | 11308.7695 | C2013-06 Government Office Building.xlsx
168 | 257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-15 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 1 | Finished | 22500 | 22500 | C2013-06 Government Office Building.xlsx
169 | 448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 123d | [5 empty] | 621482.7249 |  | 1 |  | 559972.2264 | 559972.2264 | C2013-06 Government Office Building.xlsx
170 | 293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-03 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 1 | Finished | 8611.6201 | 8611.6201 | C2013-06 Government Office Building.xlsx
171 | 294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-28 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 1 | Finished | 39378.6016 | 39378.6016 | C2013-06 Government Office Building.xlsx
172 | 295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-02 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 1 | Finished | 88472.6172 | 88472.6172 | C2013-06 Government Office Building.xlsx
173 | 296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.36 | 0 | 178.87 | 0 | 1 | Finished | 544.23 | 544.23 | C2013-06 Government Office Building.xlsx
174 | 297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 1 | Finished | 957.81 | 957.81 | C2013-06 Government Office Building.xlsx
175 | 298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-12-11 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 1 | Finished | 84509.5 | 84509.5 | C2013-06 Government Office Building.xlsx
176 | 299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 1 | Finished | 187631.6875 | 187631.6875 | C2013-06 Government Office Building.xlsx
177 | 300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 1 | Finished | 4682.9302 | 4682.9302 | C2013-06 Government Office Building.xlsx
178 | 301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 1 | Finished | 24999.8008 | 24999.8008 | C2013-06 Government Office Building.xlsx
179 | 302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-08 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 1 | Finished | 37201.2891 | 37201.2891 | C2013-06 Government Office Building.xlsx
180 | 303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-14 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 1 | Finished | 1037.39 | 1037.39 | C2013-06 Government Office Building.xlsx
181 | 304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-25 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 1 | Finished | 20841.1602 | 20841.1602 | C2013-06 Government Office Building.xlsx
182 | 305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-04 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 1 | Finished | 11668.21 | 11668.21 | C2013-06 Government Office Building.xlsx
183 | 306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-02 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 1 | Finished | 15626.6104 | 15626.6104 | C2013-06 Government Office Building.xlsx
184 | 307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-23 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 1 | Finished | 11308.7695 | 11308.7695 | C2013-06 Government Office Building.xlsx
185 | 308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-26 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 1 | Finished | 22500 | 22500 | C2013-06 Government Office Building.xlsx
186 | 449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 123d | [5 empty] | 621482.7349 |  | 1 |  | 559972.2264 | 559972.2264 | C2013-06 Government Office Building.xlsx
187 | 309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-03 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 1 | Finished | 8611.6201 | 8611.6201 | C2013-06 Government Office Building.xlsx
188 | 310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-03 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 1 | Finished | 39378.6016 | 39378.6016 | C2013-06 Government Office Building.xlsx
189 | 311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-08 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 1 | Finished | 88472.6172 | 88472.6172 | C2013-06 Government Office Building.xlsx
190 | 312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 1 | Finished | 544.23 | 544.23 | C2013-06 Government Office Building.xlsx
191 | 313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 1 | Finished | 957.81 | 957.81 | C2013-06 Government Office Building.xlsx
192 | 314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-12-11 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 1 | Finished | 84509.5 | 84509.5 | C2013-06 Government Office Building.xlsx
193 | 315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 1 | Finished | 187631.6875 | 187631.6875 | C2013-06 Government Office Building.xlsx
194 | 316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 1 | Finished | 4682.9302 | 4682.9302 | C2013-06 Government Office Building.xlsx
195 | 317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 1 | Finished | 24999.8008 | 24999.8008 | C2013-06 Government Office Building.xlsx
196 | 318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-14 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 1 | Finished | 1037.39 | 1037.39 | C2013-06 Government Office Building.xlsx
197 | 319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-13 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 1 | Finished | 37201.2891 | 37201.2891 | C2013-06 Government Office Building.xlsx
198 | 320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-25 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 1 | Finished | 20841.1602 | 20841.1602 | C2013-06 Government Office Building.xlsx
199 | 321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-04 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 1 | Finished | 11668.21 | 11668.21 | C2013-06 Government Office Building.xlsx
200 | 322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-02 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 1 | Finished | 15626.6104 | 15626.6104 | C2013-06 Government Office Building.xlsx
201 | 323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-23 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 1 | Finished | 11308.7695 | 11308.7695 | C2013-06 Government Office Building.xlsx
202 | 324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-26 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 1 | Finished | 22500 | 22500 | C2013-06 Government Office Building.xlsx
203 | 450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 116d | [5 empty] | 621482.7349 |  | 1 |  | 559972.2264 | 559972.2264 | C2013-06 Government Office Building.xlsx
204 | 325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-10 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 1 | Finished | 8611.6201 | 8611.6201 | C2013-06 Government Office Building.xlsx
205 | 326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-15 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 1 | Finished | 39378.6016 | 39378.6016 | C2013-06 Government Office Building.xlsx
206 | 327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-18 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 1 | Finished | 88472.6172 | 88472.6172 | C2013-06 Government Office Building.xlsx
207 | 328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 1 | Finished | 544.23 | 544.23 | C2013-06 Government Office Building.xlsx
208 | 329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 1 | Finished | 957.81 | 957.81 | C2013-06 Government Office Building.xlsx
209 | 330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-01-08 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 1 | Finished | 84509.5 | 84509.5 | C2013-06 Government Office Building.xlsx
210 | 331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 1 | Finished | 187631.6875 | 187631.6875 | C2013-06 Government Office Building.xlsx
211 | 332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 1 | Finished | 4682.9302 | 4682.9302 | C2013-06 Government Office Building.xlsx
212 | 333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 1 | Finished | 24999.8008 | 24999.8008 | C2013-06 Government Office Building.xlsx
213 | 334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-18 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 1 | Finished | 37201.2891 | 37201.2891 | C2013-06 Government Office Building.xlsx
214 | 335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-26 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 1 | Finished | 1037.39 | 1037.39 | C2013-06 Government Office Building.xlsx
215 | 336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-04 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 1 | Finished | 20841.1602 | 20841.1602 | C2013-06 Government Office Building.xlsx
216 | 337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-14 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 1 | Finished | 11668.21 | 11668.21 | C2013-06 Government Office Building.xlsx
217 | 338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-12 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 1 | Finished | 15626.6104 | 15626.6104 | C2013-06 Government Office Building.xlsx
218 | 339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-05 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 1 | Finished | 11308.7695 | 11308.7695 | C2013-06 Government Office Building.xlsx
219 | 340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-05 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 1 | Finished | 22500 | 22500 | C2013-06 Government Office Building.xlsx
220 | 451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 119d | [5 empty] | 621482.7349 |  | 1 |  | 559972.2264 | 559972.2264 | C2013-06 Government Office Building.xlsx
221 | 341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-10 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 1 | Finished | 8611.6201 | 8611.6201 | C2013-06 Government Office Building.xlsx
222 | 342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 1 | Finished | 39378.6016 | 39378.6016 | C2013-06 Government Office Building.xlsx
223 | 343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 1 | Finished | 88472.6172 | 88472.6172 | C2013-06 Government Office Building.xlsx
224 | 344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 1 | Finished | 544.23 | 544.23 | C2013-06 Government Office Building.xlsx
225 | 345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 1 | Finished | 957.81 | 957.81 | C2013-06 Government Office Building.xlsx
226 | 346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-01-08 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 1 | Finished | 84509.5 | 84509.5 | C2013-06 Government Office Building.xlsx
227 | 347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 1 | Finished | 187631.6875 | 187631.6875 | C2013-06 Government Office Building.xlsx
228 | 348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 1 | Finished | 4682.9302 | 4682.9302 | C2013-06 Government Office Building.xlsx
229 | 349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 1 | Finished | 24999.8008 | 24999.8008 | C2013-06 Government Office Building.xlsx
230 | 350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-26 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 1 | Finished | 1037.39 | 1037.39 | C2013-06 Government Office Building.xlsx
231 | 351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-21 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 1 | Finished | 37201.2891 | 37201.2891 | C2013-06 Government Office Building.xlsx
232 | 352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-04 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 1 | Finished | 20841.1602 | 20841.1602 | C2013-06 Government Office Building.xlsx
233 | 353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-14 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 1 | Finished | 11668.21 | 11668.21 | C2013-06 Government Office Building.xlsx
234 | 354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-12 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 1 | Finished | 15626.6104 | 15626.6104 | C2013-06 Government Office Building.xlsx
235 | 355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-05 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 1 | Finished | 11308.7695 | 11308.7695 | C2013-06 Government Office Building.xlsx
236 | 356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-10 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 1 | Finished | 22500 | 22500 | C2013-06 Government Office Building.xlsx
237 | 452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 120d | [5 empty] | 621482.7349 |  | 1 |  | 559972.2264 | 559972.2264 | C2013-06 Government Office Building.xlsx
238 | 357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-17 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 1 | Finished | 8611.6201 | 8611.6201 | C2013-06 Government Office Building.xlsx
239 | 358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-07 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 1 | Finished | 39378.6016 | 39378.6016 | C2013-06 Government Office Building.xlsx
240 | 359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-12 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 1 | Finished | 88472.6172 | 88472.6172 | C2013-06 Government Office Building.xlsx
241 | 360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-04 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 1 | Finished | 544.23 | 544.23 | C2013-06 Government Office Building.xlsx
242 | 361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-09 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 1 | Finished | 957.81 | 957.81 | C2013-06 Government Office Building.xlsx
243 | 362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-02-15 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 1 | Finished | 84509.5 | 84509.5 | C2013-06 Government Office Building.xlsx
244 | 363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-09 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 1 | Finished | 187631.6875 | 187631.6875 | C2013-06 Government Office Building.xlsx
245 | 364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 1 | Finished | 4682.9302 | 4682.9302 | C2013-06 Government Office Building.xlsx
246 | 365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 1 | Finished | 24999.8008 | 24999.8008 | C2013-06 Government Office Building.xlsx
247 | 366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-26 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 1 | Finished | 37201.2891 | 37201.2891 | C2013-06 Government Office Building.xlsx
248 | 367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-17 08:00 | 8d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 1 | Finished | 1037.39 | 1037.39 | C2013-06 Government Office Building.xlsx
249 | 368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-03-01 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 1 | Finished | 20841.1602 | 20841.1602 | C2013-06 Government Office Building.xlsx
250 | 369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-02-05 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 1 | Finished | 11668.21 | 11668.21 | C2013-06 Government Office Building.xlsx
251 | 370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-09 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 1 | Finished | 15626.6104 | 15626.6104 | C2013-06 Government Office Building.xlsx
252 | 371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-30 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 1 | Finished | 11308.7695 | 11308.7695 | C2013-06 Government Office Building.xlsx
253 | 372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-04-02 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 1 | Finished | 22500 | 22500 | C2013-06 Government Office Building.xlsx
254 | 453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 129d | [5 empty] | 621482.7349 |  | 1 |  | 559972.2264 | 559972.2264 | C2013-06 Government Office Building.xlsx
255 | 373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-17 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 1 | Finished | 8611.6201 | 8611.6201 | C2013-06 Government Office Building.xlsx
256 | 374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-19 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 1 | Finished | 39378.6016 | 39378.6016 | C2013-06 Government Office Building.xlsx
257 | 375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-22 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 1 | Finished | 88472.6172 | 88472.6172 | C2013-06 Government Office Building.xlsx
258 | 376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-04 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 1 | Finished | 544.23 | 544.23 | C2013-06 Government Office Building.xlsx
259 | 377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-09 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 1 | Finished | 957.81 | 957.81 | C2013-06 Government Office Building.xlsx
260 | 378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-02-24 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 1 | Finished | 84509.5 | 84509.5 | C2013-06 Government Office Building.xlsx
261 | 379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-09 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 1 | Finished | 187631.6875 | 187631.6875 | C2013-06 Government Office Building.xlsx
262 | 380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 1 | Finished | 4682.9302 | 4682.9302 | C2013-06 Government Office Building.xlsx
263 | 381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 1 | Finished | 24999.8008 | 24999.8008 | C2013-06 Government Office Building.xlsx
264 | 382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-17 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 1 | Finished | 1037.39 | 1037.39 | C2013-06 Government Office Building.xlsx
265 | 383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-29 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 1 | Finished | 37201.2891 | 37201.2891 | C2013-06 Government Office Building.xlsx
266 | 384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-03-10 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 1 | Finished | 20841.1602 | 20841.1602 | C2013-06 Government Office Building.xlsx
267 | 385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-02-05 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 1 | Finished | 11668.21 | 11668.21 | C2013-06 Government Office Building.xlsx
268 | 386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-18 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 1 | Finished | 15626.6104 | 15626.6104 | C2013-06 Government Office Building.xlsx
269 | 387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-04-12 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 1 | Finished | 11308.7695 | 11308.7695 | C2013-06 Government Office Building.xlsx
270 | 388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-04-15 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 1 | Finished | 22500 | 22500 | C2013-06 Government Office Building.xlsx
271 | 454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 134d | [5 empty] | 639265.5943 |  | 1 |  | 559973.2264 | 537473.2264 | C2013-06 Government Office Building.xlsx
272 | 389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-07 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 1 | Finished | 8611.6201 | 8611.6201 | C2013-06 Government Office Building.xlsx
273 | 390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-22 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 1 | Finished | 39378.6016 | 39378.6016 | C2013-06 Government Office Building.xlsx
274 | 391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-27 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 1 | Finished | 88472.6172 | 88472.6172 | C2013-06 Government Office Building.xlsx
275 | 392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-09 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 1 | Finished | 544.23 | 544.23 | C2013-06 Government Office Building.xlsx
276 | 393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 1 | Finished | 957.81 | 957.81 | C2013-06 Government Office Building.xlsx
277 | 394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-03-01 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 1 | Finished | 84509.5 | 84509.5 | C2013-06 Government Office Building.xlsx
278 | 395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 1 | Finished | 187631.6875 | 187631.6875 | C2013-06 Government Office Building.xlsx
279 | 396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-22 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 1 | Finished | 4682.9302 | 4682.9302 | C2013-06 Government Office Building.xlsx
280 | 397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-22 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 1 | Finished | 24999.8008 | 24999.8008 | C2013-06 Government Office Building.xlsx
281 | 398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-02-03 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 1 | Finished | 37201.2891 | 37201.2891 | C2013-06 Government Office Building.xlsx
282 | 399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-03-01 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 1 | Finished | 1037.39 | 1037.39 | C2013-06 Government Office Building.xlsx
283 | 400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-03-15 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 1 | Finished | 20841.1602 | 20841.1602 | C2013-06 Government Office Building.xlsx
284 | 401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-02-17 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 1 | Finished | 11668.21 | 11668.21 | C2013-06 Government Office Building.xlsx
285 | 402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-23 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 1 | Finished | 15626.6104 | 15626.6104 | C2013-06 Government Office Building.xlsx
286 | 403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-04-15 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 1 | Finished | 11308.7695 | 11308.7695 | C2013-06 Government Office Building.xlsx
287 | 404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 | 2010-04-20 08:00 | 13d | 1 | 0 | 0 | 17781.8594 | 0 | 17782.8594 | 0 | 1 | Finished | 1 | 1 | C2013-06 Government Office Building.xlsx
288 | 405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-05-07 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 1 | Finished | 22500 | 0 | C2013-06 Government Office Building.xlsx
289 | 455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 122d | [5 empty] | 353439.4188 |  | 1 |  | 322737.5283 | 322737.5283 | C2013-06 Government Office Building.xlsx
290 | 406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 | 2009-10-20 08:00 | 15d | 68850 | 0 | 0 | 582.38 | 0 | 69432.38 | 0 | 1 | Finished | 68850 | 68850 | C2013-06 Government Office Building.xlsx
291 | 407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 | 2009-11-12 08:00 | 5d | 64694.3984 | 0 | 0 | 194.13 | 0 | 64888.5284 | 0 | 1 | Finished | 64694.3984 | 64694.3984 | C2013-06 Government Office Building.xlsx
292 | 408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 | 2009-11-19 08:00 | 10d | 52474.0508 | 0 | 0 | 755.3 | 0 | 53229.3508 | 0 | 1 | Finished | 52474.0508 | 52474.0508 | C2013-06 Government Office Building.xlsx
293 | 409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2009-12-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-06 Government Office Building.xlsx
294 | 410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-12-03 08:00 | 15d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 1 | Finished | 24999.8008 | 24999.8008 | C2013-06 Government Office Building.xlsx
295 | 411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 | 2009-12-03 08:00 | 45d | 75251.5078 | 0 | 0 | 12770.25 | 0 | 88021.7578 | 0 | 1 | Finished | 75251.5078 | 75251.5078 | C2013-06 Government Office Building.xlsx
296 | 412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-18 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 1 | Finished | 20841.1602 | 20841.1602 | C2013-06 Government Office Building.xlsx
297 | 413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-04-12 08:00 | 10d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 1 | Finished | 15626.6104 | 15626.6104 | C2013-06 Government Office Building.xlsx
298 | 469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 | 2010-02-26 08:00 | 50d | 194720.8281 | 0 | 0 | 133669.8125 | 0 | 328390.6406 | 0 | 1 | Finished | 194720.8281 | 194720.8281 | C2013-06 Government Office Building.xlsx
299 | 474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 71d | [5 empty] | 681431.1211 |  | 1 |  | 422387.0078 | 422387.0078 | C2013-06 Government Office Building.xlsx
300 | 470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 | 2010-02-17 08:00 | 20d | 99385.1797 | 0 | 0 | 56565.8711 | 0 | 155951.0508 | 0 | 1 | Finished | 99385.1797 | 99385.1797 | C2013-06 Government Office Building.xlsx
301 | 471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 | 2010-03-03 08:00 | 20d | 99385.1797 | 0 | 0 | 64849.9414 | 0 | 164235.1211 | 0 | 1 | Finished | 99385.1797 | 99385.1797 | C2013-06 Government Office Building.xlsx
302 | 472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 | 2010-04-15 08:00 | 20d | 99385.1797 | 0 | 0 | 56565.8711 | 0 | 155951.0508 | 0 | 1 | Finished | 99385.1797 | 99385.1797 | C2013-06 Government Office Building.xlsx
303 | 473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 | 2010-04-22 08:00 | 25d | 124231.4688 | 0 | 0 | 81062.4297 | 0 | 205293.8984 | 0 | 1 | Finished | 124231.4688 | 124231.4688 | C2013-06 Government Office Building.xlsx
4 | 0 | Family Residence | 2006-04-06 08:00 | 2007-01-17 17:00 | 170d |  |  | 180476.4706 |  |  | 180476.4706 |  | 174d | [5 empty] | 175030.6505 |  | 1 |  | 180476.4706 | 180476.4706 | C2013-07 Family Residence.xlsx
5 | 62 | Voorafgaande activiteiten | 2006-04-06 08:00 | 2006-04-06 17:00 | 1d |  | 0 | 1359.3101 | 0 | 0 | 1359.3101 | 2006-04-20 08:00 | 1d | 1359.3101 | 0 | 0 | -489.86 | 0 | 869.4501 | 0 | 1 | Finished | 1359.3101 | 1359.3101 | C2013-07 Family Residence.xlsx
6 | 61 | Werfinrichting | 2006-04-07 08:00 | 2006-04-07 17:00 | 1d |  | 0 | 214.62 | 0 | 0 | 214.62 | 2006-04-21 08:00 | 1d | 214.62 | 0 | 0 | 166.5 | 0 | 381.12 | 0 | 1 | Finished | 214.62 | 214.62 | C2013-07 Family Residence.xlsx
7 | 1 | Ruwbouw | 2006-04-10 08:00 | 2006-06-19 17:00 | 46d |  |  | 70726.4302 |  |  | 70726.4302 |  | 50d | [5 empty] | 66331.7201 |  | 1 |  | 70726.4302 | 70726.4302 | C2013-07 Family Residence.xlsx
8 | 2 | Fundering | 2006-04-10 08:00 | 2006-04-19 17:00 | 7d |  | 0 | 12649.1201 | 0 | 0 | 12649.1201 | 2006-04-24 08:00 | 7d | 12649.1201 | 0 | 0 | -768.98 | 0 | 11880.1401 | 0 | 1 | Finished | 12649.1201 | 12649.1201 | C2013-07 Family Residence.xlsx
9 | 3 | Metselwerken | 2006-04-21 08:00 | 2006-06-09 17:00 | 32d |  | 0 | 50655.3203 | 0 | 0 | 50655.3203 | 2006-05-12 08:00 | 36d | 50655.3203 | 0 | 0 | -3515.3501 | 0 | 47139.9702 | 0 | 1 | Finished | 50655.3203 | 50655.3203 | C2013-07 Family Residence.xlsx
10 | 4 | Dorpels | 2006-06-19 08:00 | 2006-06-19 17:00 | 1d |  | 0 | 1582.98 | 0 | 0 | 1582.98 | 2006-07-06 08:00 | 1d | 1582.98 | 0 | 0 | -109.85 | 0 | 1473.13 | 0 | 1 | Finished | 1582.98 | 1582.98 | C2013-07 Family Residence.xlsx
11 | 5 | Parement levering | 2006-04-21 08:00 | 2006-04-21 17:00 | 1d |  | 0 | 5839.0098 | 0 | 0 | 5839.0098 | 2006-05-12 08:00 | 1d | 5839.0098 | 0 | 0 | -0.53 | 0 | 5838.4798 | 0 | 1 | Finished | 5839.0098 | 5839.0098 | C2013-07 Family Residence.xlsx
12 | 6 | Voegwerken | 2006-06-14 08:00 | 2006-08-17 17:00 | 30d |  |  | 1676.5699 |  |  | 1676.5699 |  | 10d | [5 empty] | 2236 |  | 1 |  | 1676.5699 | 1676.5699 | C2013-07 Family Residence.xlsx
13 | 7 | Voegen schoorsteen-niet aanwezig + eggen schrijnwerk | 2006-06-14 08:00 | 2006-06-14 17:00 | 1d |  | 0 | 558.86 | 0 | 0 | 558.86 | 2006-07-10 08:00 | 1d | 558.86 | 0 | 0 | 186.48 | 0 | 745.34 | 0 | 1 | Finished | 558.86 | 558.86 | C2013-07 Family Residence.xlsx
14 | 8 | Volledige ruwbouw | 2006-08-16 08:00 | 2006-08-17 17:00 | 2d |  | 0 | 1117.71 | 0 | 0 | 1117.71 | 2006-07-20 08:00 | 2d | 1117.71 | 0 | 0 | 372.95 | 0 | 1490.66 | 0 | 1 | Finished | 1117.71 | 1117.71 | C2013-07 Family Residence.xlsx
15 | 9 | Kapconstructie | 2006-05-24 08:00 | 2006-06-23 17:00 | 20d |  |  | 6791.6599 |  |  | 6791.6599 |  | 11d | [5 empty] | 5493.7799 |  | 1 |  | 6791.6599 | 6791.6599 | C2013-07 Family Residence.xlsx
16 | 10 | Koppels | 2006-05-24 08:00 | 2006-05-24 17:00 | 1d |  | 0 | 970.24 | 0 | 0 | 970.24 | 2006-06-27 08:00 | 1d | 970.24 | 0 | 0 | -185.41 | 0 | 784.83 | 0 | 1 | Finished | 970.24 | 970.24 | C2013-07 Family Residence.xlsx
17 | 11 | Volledige kapconstructie | 2006-06-16 08:00 | 2006-06-23 17:00 | 6d |  | 0 | 5821.4199 | 0 | 0 | 5821.4199 | 2006-07-06 08:00 | 4d | 5821.4199 | 0 | 0 | -1112.47 | 0 | 4708.95 | 0 | 1 | Finished | 5821.4199 | 5821.4199 | C2013-07 Family Residence.xlsx
18 | 12 | Dakwerken | 2006-06-28 08:00 | 2006-07-19 17:00 | 16d |  |  | 6939.91 |  |  | 6939.91 |  | 4d | [5 empty] | 6475.53 |  | 1 |  | 6939.91 | 6939.91 | C2013-07 Family Residence.xlsx
19 | 13 | Zinkwerken | 2006-06-28 08:00 | 2006-06-29 17:00 | 2d |  | 0 | 2313.3 | 0 | 0 | 2313.3 | 2006-07-12 08:00 | 1d | 2313.3 | 0 | 0 | -154.79 | 0 | 2158.5101 | 0 | 1 | Finished | 2313.3 | 2313.3 | C2013-07 Family Residence.xlsx
20 | 14 | Onderdak | 2006-07-03 08:00 | 2006-07-03 17:00 | 1d |  | 0 | 1156.65 | 0 | 0 | 1156.65 | 2006-07-13 08:00 | 1d | 1156.65 | 0 | 0 | -77.4 | 0 | 1079.25 | 0 | 1 | Finished | 1156.65 | 1156.65 | C2013-07 Family Residence.xlsx
21 | 15 | Plaatsing pannen | 2006-07-17 08:00 | 2006-07-19 17:00 | 3d |  | 0 | 3469.96 | 0 | 0 | 3469.96 | 2006-07-14 08:00 | 2d | 3469.96 | 0 | 0 | -232.19 | 0 | 3237.77 | 0 | 1 | Finished | 3469.96 | 3469.96 | C2013-07 Family Residence.xlsx
22 | 16 | Buitenschrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 19170.7498 |  |  | 19170.7498 |  | 36d | [5 empty] | 19753.5097 |  | 1 |  | 19170.7498 | 19170.7498 | C2013-07 Family Residence.xlsx
23 | 17 | Schrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 16572.8896 |  |  | 16572.8896 |  | 30d | [5 empty] | 17429.8296 |  | 1 |  | 16572.8896 | 16572.8896 | C2013-07 Family Residence.xlsx
24 | 18 | Opmeting schrijnwerk | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 5524.2998 | 0 | 0 | 5524.2998 | 2006-07-12 08:00 | 1d | 5524.2998 | 0 | 0 | 285.65 | 0 | 5809.9498 | 0 | 1 | Finished | 5524.2998 | 5524.2998 | C2013-07 Family Residence.xlsx
25 | 19 | Plaatsing schrijnwerk | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 11048.5898 | 0 | 0 | 11048.5898 | 2006-09-13 08:00 | 2d | 11048.5898 | 0 | 0 | 571.29 | 0 | 11619.8798 | 0 | 1 | Finished | 11048.5898 | 11048.5898 | C2013-07 Family Residence.xlsx
26 | 20 | Poort | 2006-06-28 08:00 | 2006-09-04 17:00 | 32d |  |  | 2597.8601 |  |  | 2597.8601 |  | 34d | [5 empty] | 2323.6801 |  | 1 |  | 2597.8601 | 2597.8601 | C2013-07 Family Residence.xlsx
27 | 21 | Opmeting poort | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-07-14 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 1 | Finished | 1298.9301 | 1298.9301 | C2013-07 Family Residence.xlsx
28 | 22 | Plaatsing poort | 2006-09-04 08:00 | 2006-09-04 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-09-22 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 1 | Finished | 1298.9301 | 1298.9301 | C2013-07 Family Residence.xlsx
29 | 23 | Ruwbouw sanitair en cv | 2006-08-16 08:00 | 2006-08-21 17:00 | 4d |  | 0 | 11733.46 | 0 | 0 | 11733.46 | 2006-08-25 08:00 | 4d | 11733.46 | 0 | 0 | -507.34 | 0 | 11226.12 | 0 | 1 | Finished | 11733.46 | 11733.46 | C2013-07 Family Residence.xlsx
30 | 25 | Ruwbouw elektriciteit | 2006-08-25 08:00 | 2006-08-30 17:00 | 4d |  | 0 | 3594.54 | 0 | 0 | 3594.54 | 2006-09-05 08:00 | 4d | 3594.54 | 0 | 0 | 322.35 | 0 | 3916.89 | 0 | 1 | Finished | 3594.54 | 3594.54 | C2013-07 Family Residence.xlsx
31 | 26 | Ruwbouw ventilatie | 2006-08-24 08:00 | 2006-08-24 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 | 2006-09-01 08:00 | 1d | 1684.3101 | 0 | 0 | -188.45 | 0 | 1495.8601 | 0 | 1 | Finished | 1684.3101 | 1684.3101 | C2013-07 Family Residence.xlsx
32 | 27 | Dakisolatie | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 1014.92 | 0 | 0 | 1014.92 | 2006-09-13 08:00 | 2d | 1014.92 | 0 | 0 | 173.08 | 0 | 1188 | 0 | 1 | Finished | 1014.92 | 1014.92 | C2013-07 Family Residence.xlsx
33 | 28 | Pleisterwerken | 2006-09-18 08:00 | 2006-10-13 17:00 | 20d |  | 0 | 8332.7402 | 0 | 0 | 8332.7402 | 2006-09-27 08:00 | 22d | 8332.7402 | 0 | 0 | -87.65 | 0 | 8245.0902 | 0 | 1 | Finished | 8332.7402 | 8332.7402 | C2013-07 Family Residence.xlsx
34 | 29 | Spuitplamuur | 2006-09-20 08:00 | 2006-10-25 17:00 | 26d |  |  | 536.76 |  |  | 536.76 |  | 28d | [5 empty] | 465.42 |  | 1 |  | 536.76 | 536.76 | C2013-07 Family Residence.xlsx
35 | 30 | Opstop voegen | 2006-09-20 08:00 | 2006-09-20 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-09-29 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 1 | Finished | 178.92 | 178.92 | C2013-07 Family Residence.xlsx
36 | 31 | 1-ste laag | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-11-06 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 1 | Finished | 178.92 | 178.92 | C2013-07 Family Residence.xlsx
37 | 32 | 2-de laag | 2006-10-25 08:00 | 2006-10-25 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-11-10 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 1 | Finished | 178.92 | 178.92 | C2013-07 Family Residence.xlsx
38 | 33 | Plaatsing baden / douche's (1 inloopdouche voorzien) | 2006-10-16 08:00 | 2006-10-16 17:00 | 1d |  | 0 | 29.93 | 0 | 0 | 29.93 | 2006-10-30 08:00 | 1d | 29.93 | 0 | 0 | -5.14 | 0 | 24.79 | 0 | 1 | Finished | 29.93 | 29.93 | C2013-07 Family Residence.xlsx
39 | 63 | Verdichting inloopdouche plaatsen | 2006-10-23 08:00 | 2006-10-23 17:00 | 1d |  | 0 | 14.43 | 0 | 0 | 14.43 | 2006-11-21 08:00 | 1d | 14.43 | 0 | 0 | 0 | 0 | 14.43 | 0 | 1 | Finished | 14.43 | 14.43 | C2013-07 Family Residence.xlsx
40 | 34 | Chape | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 1598.6899 | 0 | 0 | 1598.6899 | 2006-11-07 08:00 | 1d | 1598.6899 | 0 | 0 | -6.89 | 0 | 1591.7999 | 0 | 1 | Finished | 1598.6899 | 1598.6899 | C2013-07 Family Residence.xlsx
41 | 35 | Bevloering en faiences | 2006-10-26 08:00 | 2006-11-16 17:00 | 13d |  |  | 11097.8301 |  |  | 11097.8301 |  | 19d | [5 empty] | 11211.1001 |  | 1 |  | 11097.8301 | 11097.8301 | C2013-07 Family Residence.xlsx
42 | 36 | Bevloering beneden+badkamer boven-wc boven | 2006-10-26 08:00 | 2006-11-09 17:00 | 8d |  | 0 | 6829.4302 | 0 | 0 | 6829.4302 | 2006-11-22 08:00 | 8d | 6829.4302 | 0 | 0 | 69.7 | 0 | 6899.1302 | 0 | 1 | Finished | 6829.4302 | 6829.4302 | C2013-07 Family Residence.xlsx
43 | 37 | Faiences boven | 2006-11-10 08:00 | 2006-11-16 17:00 | 5d |  | 0 | 4268.3999 | 0 | 0 | 4268.3999 | 2006-12-06 08:00 | 9d | 4268.3999 | 0 | 0 | 43.57 | 0 | 4311.9699 | 0 | 1 | Finished | 4268.3999 | 4268.3999 | C2013-07 Family Residence.xlsx
44 | 38 | Elektriciteit afwerking | 2006-11-15 08:00 | 2006-12-15 17:00 | 23d |  |  | 5278.84 |  |  | 5278.84 |  | 27d | [5 empty] | 5412.74 |  | 1 |  | 5278.84 | 5278.84 | C2013-07 Family Residence.xlsx
45 | 39 | Afwerking elektriciteit | 2006-11-15 08:00 | 2006-11-17 17:00 | 3d |  | 0 | 2695.8999 | 0 | 0 | 2695.8999 | 2006-12-15 08:00 | 3d | 2695.8999 | 0 | 0 | 241.76 | 0 | 2937.6599 | 0 | 1 | Finished | 2695.8999 | 2695.8999 | C2013-07 Family Residence.xlsx
46 | 40 | Keuring | 2006-12-04 08:00 | 2006-12-04 17:00 | 1d |  | 0 | 898.63 | 0 | 0 | 898.63 | 2007-01-23 08:00 | 1d | 898.63 | 0 | 0 | 80.59 | 0 | 979.22 | 0 | 1 | Finished | 898.63 | 898.63 | C2013-07 Family Residence.xlsx
47 | 41 | Afwerking ventilatie | 2006-12-15 08:00 | 2006-12-15 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 | 2007-02-05 08:00 | 1d | 1684.3101 | 0 | 0 | -188.45 | 0 | 1495.8601 | 0 | 1 | Finished | 1684.3101 | 1684.3101 | C2013-07 Family Residence.xlsx
48 | 42 | Binnenschrijnwerk | 2006-11-14 08:00 | 2006-12-08 17:00 | 19d |  |  | 4778 |  |  | 4778 |  | 23d | [5 empty] | 5208.01 |  | 1 |  | 4778 | 4778 | C2013-07 Family Residence.xlsx
49 | 43 | Opmeting binnenschrijnwerk | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1194.5 | 0 | 0 | 1194.5 | 2006-12-14 08:00 | 1d | 1194.5 | 0 | 0 | 107.5 | 0 | 1302 | 0 | 1 | Finished | 1194.5 | 1194.5 | C2013-07 Family Residence.xlsx
50 | 44 | Plaatsing binnenschrijnwerk | 2006-12-06 08:00 | 2006-12-08 17:00 | 3d |  | 0 | 3583.5 | 0 | 0 | 3583.5 | 2007-01-25 08:00 | 3d | 3583.5 | 0 | 0 | 322.51 | 0 | 3906.01 | 0 | 1 | Finished | 3583.5 | 3583.5 | C2013-07 Family Residence.xlsx
51 | 45 | Trap gelijkvl. - 1°verdiep | 2006-11-14 08:00 | 2006-12-13 17:00 | 22d |  |  | 3028.9199 |  |  | 3028.9199 |  | 26d | [5 empty] | 2955.0999 |  | 1 |  | 3028.9199 | 3028.9199 | C2013-07 Family Residence.xlsx
52 | 46 | Opmeting trap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 | 2006-12-14 08:00 | 1d | 1514.46 | 0 | 0 | -36.91 | 0 | 1477.55 | 0 | 1 | Finished | 1514.46 | 1514.46 | C2013-07 Family Residence.xlsx
53 | 47 | Plaatsing trap | 2006-12-13 08:00 | 2006-12-13 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 | 2007-02-01 08:00 | 1d | 1514.46 | 0 | 0 | -36.91 | 0 | 1477.55 | 0 | 1 | Finished | 1514.46 | 1514.46 | C2013-07 Family Residence.xlsx
54 | 48 | MAP-trap | 2006-11-14 08:00 | 2006-12-06 17:00 | 17d |  |  | 329 |  |  | 329 |  | 21d | [5 empty] | 345.6 |  | 1 |  | 329 | 329 | C2013-07 Family Residence.xlsx
55 | 49 | Opmeting zoldertrap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 | 2006-12-14 08:00 | 1d | 164.5 | 0 | 0 | 8.3 | 0 | 172.8 | 0 | 1 | Finished | 164.5 | 164.5 | C2013-07 Family Residence.xlsx
56 | 50 | Plaatsing zoldertrap | 2006-12-06 08:00 | 2006-12-06 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 | 2007-01-25 08:00 | 1d | 164.5 | 0 | 0 | 8.3 | 0 | 172.8 | 0 | 1 | Finished | 164.5 | 164.5 | C2013-07 Family Residence.xlsx
57 | 51 | Keukenmeubilair | 2006-11-15 08:00 | 2007-01-12 17:00 | 33d |  |  | 11829.5303 |  |  | 11829.5303 |  | 46d | [5 empty] | 11915.3803 |  | 1 |  | 11829.5303 | 11829.5303 | C2013-07 Family Residence.xlsx
58 | 52 | Opmeting keukenmeubilair | 2006-11-15 08:00 | 2006-11-15 17:00 | 1d |  | 0 | 2957.3799 | 0 | 0 | 2957.3799 | 2006-11-06 08:00 | 1d | 2957.3799 | 0 | 0 | 21.46 | 0 | 2978.8399 | 0 | 1 | Finished | 2957.3799 | 2957.3799 | C2013-07 Family Residence.xlsx
59 | 53 | Plaatsing keukenmeubilair | 2007-01-10 08:00 | 2007-01-12 17:00 | 3d |  | 0 | 8872.1504 | 0 | 0 | 8872.1504 | 2007-01-16 08:00 | 5d | 8872.1504 | 0 | 0 | 64.39 | 0 | 8936.5404 | 0 | 1 | Finished | 8872.1504 | 8872.1504 | C2013-07 Family Residence.xlsx
60 | 54 | Badmeubel | 2006-11-21 08:00 | 2006-12-20 17:00 | 22d |  |  | 86.58 |  |  | 86.58 |  | 42d | [5 empty] | 86.58 |  | 1 |  | 86.58 | 86.58 | C2013-07 Family Residence.xlsx
61 | 55 | Opmeting badmeubel | 2006-11-21 08:00 | 2006-11-21 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 | 2006-11-06 08:00 | 1d | 43.29 | 0 | 0 | 0 | 0 | 43.29 | 0 | 1 | Finished | 43.29 | 43.29 | C2013-07 Family Residence.xlsx
62 | 56 | Plaatsing badmeubel | 2006-12-20 08:00 | 2006-12-20 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 | 2007-01-16 08:00 | 1d | 43.29 | 0 | 0 | 0 | 0 | 43.29 | 0 | 1 | Finished | 43.29 | 43.29 | C2013-07 Family Residence.xlsx
63 | 57 | Nutsleidingen | 2006-05-05 08:00 | 2006-12-12 17:00 | 135d |  |  | 54 |  |  | 54 |  | 151d | [5 empty] | 0 |  | 1 |  | 54 | 54 | C2013-07 Family Residence.xlsx
64 | 58 | Aanvraag offertes | 2006-05-05 08:00 | 2006-05-05 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 2006-05-19 08:00 | 1d | 27 | 0 | 0 | -27 | 0 | 0 | 0 | 1 | Finished | 27 | 27 | C2013-07 Family Residence.xlsx
65 | 59 | Uitvoering aansluitingen | 2006-12-12 08:00 | 2006-12-12 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 2007-01-31 08:00 | 1d | 27 | 0 | 0 | -27 | 0 | 0 | 0 | 1 | Finished | 27 | 27 | C2013-07 Family Residence.xlsx
66 | 60 | Afwerking sanitair en cv | 2007-01-15 08:00 | 2007-01-17 17:00 | 3d |  | 0 | 8574.7402 | 0 | 0 | 8574.7402 | 2007-02-01 08:00 | 3d | 8574.7402 | 0 | 0 | -388.11 | 0 | 8186.6302 | 0 | 1 | Finished | 8574.7402 | 8574.7402 | C2013-07 Family Residence.xlsx
4 | 0 | Timber House | 2011-06-30 08:00 | 2012-07-02 17:00 | 216d |  |  | 501029.5121 |  |  | 501029.5121 |  | 235d | [5 empty] | 576624.0518 |  | 1 |  | 501029.5121 | 501029.5121 | C2013-08 Timber House.xlsx
5 | 2 | Voorbereiding | 2011-06-30 08:00 | 2012-02-07 17:00 | 119d |  |  | 904.3 |  |  | 904.3 |  | 119d | [5 empty] | 904.3 |  | 1 |  | 904.3 | 904.3 | C2013-08 Timber House.xlsx
6 | 1 | Bouwvergunning | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-06-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 1 | Finished | 30.86 | 30.86 | C2013-08 Timber House.xlsx
7 | 3 | Technische bespreking | 2011-08-26 08:00 | 2011-08-26 17:00 | 1d |  | 0 | 780.86 | 0 | 0 | 780.86 | 2011-08-26 08:00 | 1d | 780.86 | 0 | 0 | 0 | 0 | 780.86 | 0 | 1 | Finished | 780.86 | 780.86 | C2013-08 Timber House.xlsx
8 | 4 | Ondertekening definitief contract | 2011-09-23 08:00 | 2011-09-23 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-09-23 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 1 | Finished | 30.86 | 30.86 | C2013-08 Timber House.xlsx
9 | 5 | Bestelling technisch bureau | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 1 | Finished | 30.86 | 30.86 | C2013-08 Timber House.xlsx
10 | 6 | Bestelling projectleiders | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 1 | Finished | 30.86 | 30.86 | C2013-08 Timber House.xlsx
11 | 7 | Funderingen | 2012-02-14 08:00 | 2012-02-21 17:00 | 6d |  | 0 | 23047.4609 | 0 | 0 | 23047.4609 | 2012-02-14 08:00 | 6d | 23047.4609 | 0 | 0 | 0 | 0 | 23047.4609 | 0 | 1 | Finished | 23047.4609 | 23047.4609 | C2013-08 Timber House.xlsx
12 | 9 | Montage | 2012-02-20 08:00 | 2012-03-15 17:00 | 19d |  |  | 186369.3501 |  |  | 186369.3501 |  | 19d | [5 empty] | 195338.4602 |  | 1 |  | 186369.3501 | 186369.3501 | C2013-08 Timber House.xlsx
13 | 8 | Schrijnwerk (levering) | 2012-02-20 08:00 | 2012-02-20 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-02-20 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 1 | Finished | 1724.47 | 1724.47 | C2013-08 Timber House.xlsx
14 | 10 | Montage houten kit | 2012-02-27 08:00 | 2012-03-09 17:00 | 10d |  | 0 | 169353.5 | 0 | 0 | 169353.5 | 2012-02-27 08:00 | 12d | 169353.5 | 0 | 0 | 7519.3301 | 0 | 176872.8301 | 0 | 1 | Finished | 169353.5 | 169353.5 | C2013-08 Timber House.xlsx
15 | 11 | Schrijnwerk (plaatsing) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-03-15 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 1 | Finished | 1724.47 | 1724.47 | C2013-08 Timber House.xlsx
16 | 13 | Glas | 2012-03-15 08:00 | 2012-03-15 17:00 | 1d |  | 0 | 13566.9102 | 0 | 0 | 13566.9102 | 2012-03-15 08:00 | 1d | 13566.9102 | 0 | 0 | 825 | 0 | 14391.9102 | 0 | 1 | Finished | 13566.9102 | 13566.9102 | C2013-08 Timber House.xlsx
17 | 15 | Stelling | 2012-03-12 08:00 | 2012-05-04 17:00 | 36d |  |  | 61.72 |  |  | 61.72 |  | 48d | [5 empty] | 61.72 |  | 1 |  | 61.72 | 61.72 | C2013-08 Timber House.xlsx
18 | 14 | Stelling (opbouw) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-03-15 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 1 | Finished | 30.86 | 30.86 | C2013-08 Timber House.xlsx
19 | 16 | Stelling (afbraak) | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-05-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 1 | Finished | 30.86 | 30.86 | C2013-08 Timber House.xlsx
20 | 18 | Isolatie | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d |  |  | 22041.1902 |  |  | 22041.1902 |  | 6d | [5 empty] | 22041.1902 |  | 1 |  | 22041.1902 | 22041.1902 | C2013-08 Timber House.xlsx
21 | 17 | Muurisolatie | 2012-03-27 08:00 | 2012-04-02 17:00 | 5d |  | 0 | 18367.6602 | 0 | 0 | 18367.6602 | 2012-03-26 08:00 | 4d | 18367.6602 | 0 | 0 | 0 | 0 | 18367.6602 | 0 | 1 | Finished | 18367.6602 | 18367.6602 | C2013-08 Timber House.xlsx
22 | 19 | Pur | 2012-03-20 08:00 | 2012-03-20 17:00 | 1d |  | 0 | 3673.53 | 0 | 0 | 3673.53 | 2012-04-02 08:00 | 1d | 3673.53 | 0 | 0 | 0 | 0 | 3673.53 | 0 | 1 | Finished | 3673.53 | 3673.53 | C2013-08 Timber House.xlsx
23 | 21 | Technieken (eerste fase) | 2012-03-13 08:00 | 2012-03-23 17:00 | 9d |  |  | 51406.2207 |  |  | 51406.2207 |  | 15d | [5 empty] | 61636.5109 |  | 1 |  | 51406.2207 | 51406.2207 | C2013-08 Timber House.xlsx
24 | 20 | Elektriciteit (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 8928.5703 | 0 | 0 | 8928.5703 | 2012-03-16 08:00 | 5d | 8928.5703 | 0 | 0 | 5703.79 | 0 | 14632.3604 | 0 | 1 | Finished | 8928.5703 | 8928.5703 | C2013-08 Timber House.xlsx
25 | 22 | Sanitair - ventilatie (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 20995.9902 | 0 | 0 | 20995.9902 | 2012-03-20 08:00 | 7d 4h | 20995.9902 | 0 | 0 | 3901.3601 | 0 | 24897.3503 | 0 | 1 | Finished | 20995.9902 | 20995.9902 | C2013-08 Timber House.xlsx
26 | 23 | Verwarming (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 10695.25 | 0 | 0 | 10695.25 | 2012-03-20 08:00 | 7d 4h | 10695.25 | 0 | 0 | 625.14 | 0 | 11320.39 | 0 | 1 | Finished | 10695.25 | 10695.25 | C2013-08 Timber House.xlsx
27 | 24 | Vloerverwarming | 2012-03-21 08:00 | 2012-03-23 17:00 | 3d |  | 0 | 10786.4102 | 0 | 0 | 10786.4102 | 2012-04-03 08:00 | 3d | 10786.4102 | 0 | 0 | 0 | 0 | 10786.4102 | 0 | 1 | Finished | 10786.4102 | 10786.4102 | C2013-08 Timber House.xlsx
28 | 25 | Chape | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d |  | 0 | 4263.7402 | 0 | 0 | 4263.7402 | 2012-04-16 08:00 | 2d | 4263.7402 | 0 | 0 | 0 | 0 | 4263.7402 | 0 | 1 | Finished | 4263.7402 | 4263.7402 | C2013-08 Timber House.xlsx
29 | 27 | Zinkwerken | 2012-03-22 08:00 | 2012-06-07 17:00 | 49d |  |  | 9552.6401 |  |  | 9552.6401 |  | 63d | [5 empty] | 9306.0201 |  | 1 |  | 9552.6401 | 9552.6401 | C2013-08 Timber House.xlsx
30 | 26 | Goten | 2012-03-22 08:00 | 2012-03-23 17:00 | 2d |  | 0 | 6536.2002 | 0 | 0 | 6536.2002 | 2012-03-20 08:00 | 2d | 6536.2002 | 0 | 0 | 0 | 0 | 6536.2002 | 0 | 1 | Finished | 6536.2002 | 6536.2002 | C2013-08 Timber House.xlsx
31 | 28 | Afleiders | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 3016.4399 | 0 | 0 | 3016.4399 | 2012-06-25 08:00 | 1d | 3016.4399 | 0 | 0 | -246.62 | 0 | 2769.8199 | 0 | 1 | Finished | 3016.4399 | 3016.4399 | C2013-08 Timber House.xlsx
32 | 29 | Metselwerken | 2012-04-03 08:00 | 2012-04-25 17:00 | 15d |  | 0 | 29433.6797 | 0 | 0 | 29433.6797 | 2012-04-03 08:00 | 30d | 29433.6797 | 0 | 0 | 0 | 0 | 29433.6797 | 0 | 1 | Finished | 29433.6797 | 29433.6797 | C2013-08 Timber House.xlsx
33 | 30 | Voegwerken | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 3213.1699 | 0 | 0 | 3213.1699 | 2012-06-07 08:00 | 3d | 3213.1699 | 0 | 0 | 0 | 0 | 3213.1699 | 0 | 1 | Finished | 3213.1699 | 3213.1699 | C2013-08 Timber House.xlsx
34 | 31 | Stabilisé | 2012-05-14 08:00 | 2012-05-14 17:00 | 1d |  | 0 | 1962.25 | 0 | 0 | 1962.25 | 2012-06-07 08:00 | 1d | 1962.25 | 0 | 0 | 0 | 0 | 1962.25 | 0 | 1 | Finished | 1962.25 | 1962.25 | C2013-08 Timber House.xlsx
35 | 33 | Dakwerken | 2012-03-12 08:00 | 2012-03-29 17:00 | 14d |  |  | 21980.6396 |  |  | 21980.6396 |  | 67d | [5 empty] | 35125.1997 |  | 1 |  | 21980.6396 | 21980.6396 | C2013-08 Timber House.xlsx
36 | 32 | Pannenlatten | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 2012-03-12 08:00 | 2d | 4396.1299 | 0 | 0 | 2628.9099 | 0 | 7025.0398 | 0 | 1 | Finished | 4396.1299 | 4396.1299 | C2013-08 Timber House.xlsx
37 | 34 | Pannen | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 13188.3799 | 0 | 0 | 13188.3799 | 2012-03-23 08:00 | 5d | 13188.3799 | 0 | 0 | 7886.7402 | 0 | 21075.1201 | 0 | 1 | Finished | 13188.3799 | 13188.3799 | C2013-08 Timber House.xlsx
38 | 55 | Pannen (fase 2) | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 2012-06-21 08:00 | 1d | 4396.1299 | 0 | 0 | 2628.9099 | 0 | 7025.0398 | 0 | 1 | Finished | 4396.1299 | 4396.1299 | C2013-08 Timber House.xlsx
39 | 35 | Vloeren (eerste fase) | 2012-04-03 08:00 | 2012-04-05 17:00 | 3d |  | 0 | 19974.6504 | 0 | 0 | 19974.6504 | 2012-05-16 08:00 | 1d | 19974.6504 | 0 | 0 | -1364.45 | 0 | 18610.2004 | 0 | 1 | Finished | 19974.6504 | 19974.6504 | C2013-08 Timber House.xlsx
40 | 37 | Afwerking | 2012-04-10 08:00 | 2012-06-07 17:00 | 38d |  |  | 89234.9203 |  |  | 89234.9203 |  | 41d | [5 empty] | 135169.0797 |  | 1 |  | 89234.9203 | 89234.9203 | C2013-08 Timber House.xlsx
41 | 38 | Afwerking (intern) | 2012-05-07 08:00 | 2012-06-06 17:00 | 20d |  | 0 | 38565.1914 | 0 | 0 | 38565.1914 | 2012-06-04 08:00 | 25d | 38565.1914 | 0 | 0 | 12637.9697 | 0 | 51203.1611 | 0 | 1 | Finished | 38565.1914 | 38565.1914 | C2013-08 Timber House.xlsx
42 | 54 | Trappen | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 83.73 | 0 | 0 | 83.73 | 2012-07-12 08:00 | 1d | 83.73 | 0 | 0 | 4439.25 | 0 | 4522.98 | 0 | 1 | Finished | 83.73 | 83.73 | C2013-08 Timber House.xlsx
43 | 39 | Afwerking (extern) | 2012-04-26 08:00 | 2012-05-03 17:00 | 4d |  | 0 | 43852.3789 | 0 | 0 | 43852.3789 | 2012-05-23 08:00 | 4d | 43852.3789 | 0 | 0 | 1474.22 | 0 | 45326.5989 | 0 | 1 | Finished | 43852.3789 | 43852.3789 | C2013-08 Timber House.xlsx
44 | 40 | Houten terras | 2012-05-15 08:00 | 2012-05-16 17:00 | 2d |  | 0 | 2064.1399 | 0 | 0 | 2064.1399 | 2012-06-08 08:00 | 2d | 2064.1399 | 0 | 0 | 13095.7197 | 0 | 15159.8596 | 0 | 1 | Finished | 2064.1399 | 2064.1399 | C2013-08 Timber House.xlsx
45 | 41 | Maatwerk | 2012-05-23 08:00 | 2012-05-24 17:00 | 2d |  | 0 | 2003.3 | 0 | 0 | 2003.3 | 2012-07-06 08:00 | 2d | 2003.3 | 0 | 0 | 14287 | 0 | 16290.3 | 0 | 1 | Finished | 2003.3 | 2003.3 | C2013-08 Timber House.xlsx
46 | 42 | Gips | 2012-04-10 08:00 | 2012-04-12 17:00 | 3d |  | 0 | 1599.41 | 0 | 0 | 1599.41 | 2012-05-14 08:00 | 12d | 1599.41 | 0 | 0 | 0 | 0 | 1599.41 | 0 | 1 | Finished | 1599.41 | 1599.41 | C2013-08 Timber House.xlsx
47 | 43 | Opstop gips | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d |  | 0 | 1066.77 | 0 | 0 | 1066.77 | 2012-06-27 08:00 | 2d | 1066.77 | 0 | 0 | 0 | 0 | 1066.77 | 0 | 1 | Finished | 1066.77 | 1066.77 | C2013-08 Timber House.xlsx
48 | 44 | Vloeren (tweede fase) | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 13898.8301 | 0 | 0 | 13898.8301 | 2012-06-15 08:00 | 2d | 13898.8301 | 0 | 0 | -3734.3201 | 0 | 10164.51 | 0 | 1 | Finished | 13898.8301 | 13898.8301 | C2013-08 Timber House.xlsx
49 | 46 | Technieken tweede fase | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  |  | 22484.7498 |  |  | 22484.7498 |  | 10d | [5 empty] | 25146.5598 |  | 1 |  | 22484.7498 | 22484.7498 | C2013-08 Timber House.xlsx
50 | 45 | Elektriciteit (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 3571.4299 | 0 | 0 | 3571.4299 | 2012-06-27 08:00 | 2d | 3571.4299 | 0 | 0 | 2281.52 | 0 | 5852.95 | 0 | 1 | Finished | 3571.4299 | 3571.4299 | C2013-08 Timber House.xlsx
51 | 47 | Sanitair - ventilatie (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 14635.2197 | 0 | 0 | 14635.2197 | 2012-07-09 08:00 | 2d | 14635.2197 | 0 | 0 | 130.23 | 0 | 14765.4497 | 0 | 1 | Finished | 14635.2197 | 14635.2197 | C2013-08 Timber House.xlsx
52 | 48 | Verwarming (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 4278.1001 | 0 | 0 | 4278.1001 | 2012-07-03 08:00 | 2d | 4278.1001 | 0 | 0 | 250.06 | 0 | 4528.1601 | 0 | 1 | Finished | 4278.1001 | 4278.1001 | C2013-08 Timber House.xlsx
53 | 50 | Voorlopige oplevering | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  |  | 1200 |  |  | 1200 |  | 5d | [5 empty] | 1200 |  | 1 |  | 1200 | 1200 | C2013-08 Timber House.xlsx
54 | 49 | Oplevering | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 240 | 0 | 0 | 240 | 2012-08-24 08:00 | 1d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 1 | Finished | 240 | 240 | C2013-08 Timber House.xlsx
55 | 52 | Parket | 2012-06-19 08:00 | 2012-06-22 17:00 | 4d |  | 0 | 960 | 0 | 0 | 960 | 2012-08-20 08:00 | 2d | 960 | 0 | 0 | 0 | 0 | 960 | 0 | 1 | Finished | 960 | 960 | C2013-08 Timber House.xlsx
56 | 53 | Oplevering | 2012-07-02 17:00 | 2012-07-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-08 Timber House.xlsx
4 | 0 | Urban Development Project | 2007-12-07 08:00 | 2009-02-27 17:00 | 291d |  |  | 1537398.5147 |  |  | 1537398.5147 |  | 360d | [5 empty] | 1696971.7869 |  | 1 |  | 1537398.5147 | 1537398.5147 | C2013-09 Urban Development Project.xlsx
5 | 62 | Werfinrichting | 2007-12-07 08:00 | 2007-12-07 17:00 | 1d |  | 0 | 136108 | 0 | 0 | 136108 | 2007-12-07 08:00 | 1d | 136108 | 0 | 0 | 13458.6104 | 0 | 149566.6104 | 0 | 1 | Finished | 136108 | 136108 | C2013-09 Urban Development Project.xlsx
6 | 63 | Grondwerken | 2007-12-17 08:00 | 2007-12-21 17:00 | 5d |  | 0 | 2692.3 | 0 | 0 | 2692.3 | 2007-12-10 08:00 | 5d | 2692.3 | 0 | 0 | 245.79 | 0 | 2938.09 | 0 | 1 | Finished | 2692.3 | 2692.3 | C2013-09 Urban Development Project.xlsx
7 | 64 | Funderingen | 2008-01-07 08:00 | 2008-01-25 17:00 | 15d |  | 0 | 72594.4297 | 0 | 0 | 72594.4297 | 2007-12-31 08:00 | 15d | 72594.4297 | 0 | 0 | 5805.96 | 0 | 78400.3896 | 0 | 1 | Finished | 72594.4297 | 72594.4297 | C2013-09 Urban Development Project.xlsx
8 | 65 | Wanden op V0 | 2008-01-21 08:00 | 2008-02-15 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-01-14 08:00 | 20d | 55480.9805 | 0 | 0 | 5728.1802 | 0 | 61209.1606 | 0 | 1 | Finished | 55480.9805 | 55480.9805 | C2013-09 Urban Development Project.xlsx
9 | 66 | Afdekking V0 | 2008-02-11 08:00 | 2008-02-29 17:00 | 15d |  | 0 | 46319.7109 | 0 | 0 | 46319.7109 | 2008-02-04 08:00 | 15d | 46319.7109 | 0 | 0 | 4927.6499 | 0 | 51247.3608 | 0 | 1 | Finished | 46319.7109 | 46319.7109 | C2013-09 Urban Development Project.xlsx
10 | 67 | Wanden op V1 | 2008-02-25 08:00 | 2008-03-21 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-02-18 08:00 | 20d | 55480.9805 | 0 | 0 | 5728.1802 | 0 | 61209.1606 | 0 | 1 | Finished | 55480.9805 | 55480.9805 | C2013-09 Urban Development Project.xlsx
11 | 68 | Afdekking V1 | 2008-03-17 08:00 | 2008-03-28 17:00 | 10d |  | 0 | 30879.8105 | 0 | 0 | 30879.8105 | 2008-03-10 08:00 | 10d | 30879.8105 | 0 | 0 | 3285.1001 | 0 | 34164.9106 | 0 | 1 | Finished | 30879.8105 | 30879.8105 | C2013-09 Urban Development Project.xlsx
12 | 69 | Wanden op V2 | 2008-03-31 08:00 | 2008-04-11 17:00 | 10d |  | 0 | 27740.4902 | 0 | 0 | 27740.4902 | 2008-03-31 08:00 | 10d | 27740.4902 | 0 | 0 | 2864.0901 | 0 | 30604.5803 | 0 | 1 | Finished | 27740.4902 | 27740.4902 | C2013-09 Urban Development Project.xlsx
13 | 1 | Afdekking V2 | 2008-04-21 08:00 | 2008-04-25 17:00 | 5d |  | 0 | 23742.4199 | 0 | 0 | 23742.4199 | 2008-04-14 08:00 | 10d | 23742.4199 | 0 | 0 | 2380.4199 | 0 | 26122.8398 | 0 | 1 | Finished | 23742.4199 | 23742.4199 | C2013-09 Urban Development Project.xlsx
14 | 2 | Gevelmetselwerk | 2008-04-21 08:00 | 2008-06-06 17:00 | 35d |  | 0 | 128627.4375 | 0 | 0 | 128627.4375 | 2008-04-14 08:00 | 35d | 128627.4375 | 0 | 0 | 15508.4297 | 0 | 144135.8672 | 0 | 1 | Finished | 128627.4375 | 128627.4375 | C2013-09 Urban Development Project.xlsx
15 | 3 | Voegwerk | 2008-05-26 08:00 | 2008-06-20 17:00 | 20d |  | 0 | 3583.3701 | 0 | 0 | 3583.3701 | 2008-05-12 08:00 | 20d | 3583.3701 | 0 | 0 | -2061.99 | 0 | 1521.3801 | 0 | 1 | Finished | 3583.3701 | 3583.3701 | C2013-09 Urban Development Project.xlsx
16 | 4 | Opmeten dorpels | 2008-06-02 08:00 | 2008-06-02 17:00 | 1d |  | 0 | 382.03 | 0 | 0 | 382.03 | 2008-05-19 08:00 | 1d | 382.03 | 0 | 0 | -67.96 | 0 | 314.07 | 0 | 1 | Finished | 382.03 | 382.03 | C2013-09 Urban Development Project.xlsx
17 | 5 | Plaatsen dorpels | 2008-06-09 08:00 | 2008-06-13 17:00 | 5d |  | 0 | 1910.15 | 0 | 0 | 1910.15 | 2008-06-17 08:00 | 5d | 1910.15 | 0 | 0 | -339.78 | 0 | 1570.37 | 0 | 1 | Finished | 1910.15 | 1910.15 | C2013-09 Urban Development Project.xlsx
18 | 6 | Plaatsen bordessen + prefabtrappen | 2008-06-02 08:00 | 2008-06-06 17:00 | 5d |  | 0 | 26966.6191 | 0 | 0 | 26966.6191 | 2008-05-19 08:00 | 5d | 26966.6191 | 0 | 0 | 3127.5601 | 0 | 30094.1792 | 0 | 1 | Finished | 26966.6191 | 26966.6191 | C2013-09 Urban Development Project.xlsx
19 | 7 | Plaatsen RW afvoerbuizen + voorlopige aansluiting | 2008-05-26 08:00 | 2008-05-30 17:00 | 5d |  | 0 | 17353.25 | 0 | 0 | 17353.25 | 2008-05-12 08:00 | 5d | 17353.25 | 0 | 0 | 1447.55 | 0 | 18800.8 | 0 | 1 | Finished | 17353.25 | 17353.25 | C2013-09 Urban Development Project.xlsx
20 | 8 | Dakopstanden | 2008-04-28 08:00 | 2008-05-23 17:00 | 20d |  | 0 | 33210.0781 | 0 | 0 | 33210.0781 | 2008-04-28 08:00 | 5d | 33210.0781 | 0 | 0 | 3105.8401 | 0 | 36315.9182 | 0 | 1 | Finished | 33210.0781 | 33210.0781 | C2013-09 Urban Development Project.xlsx
21 | 9 | Technieken / leidingen in dak | 2008-05-26 08:00 | 2008-07-08 17:00 | 32d |  | 0 | 10512.2002 | 0 | 0 | 10512.2002 | 2008-05-12 08:00 | 5d | 10512.2002 | 0 | 0 | 1372.48 | 0 | 11884.6802 | 0 | 1 | Finished | 10512.2002 | 10512.2002 | C2013-09 Urban Development Project.xlsx
22 | 10 | Schuimbeton | 2008-07-09 08:00 | 2008-08-05 17:00 | 5d |  | 0 | 1379.79 | 0 | 0 | 1379.79 | 2008-05-19 08:00 | 5d | 1379.79 | 0 | 0 | 147.2 | 0 | 1526.99 | 0 | 1 | Finished | 1379.79 | 1379.79 | C2013-09 Urban Development Project.xlsx
23 | 11 | Isolatie + roofing platte daken | 2008-08-06 08:00 | 2008-09-02 17:00 | 20d |  | 0 | 64503.3516 | 0 | 0 | 64503.3516 | 2008-06-09 08:00 | 20d | 64503.3516 | 0 | 0 | 6914.6602 | 0 | 71418.0117 | 0 | 1 | Finished | 64503.3516 | 64503.3516 | C2013-09 Urban Development Project.xlsx
24 | 12 | Opmeten ramen en deuren | 2008-06-09 08:00 | 2008-06-09 17:00 | 1d |  | 0 | 23772.3008 | 0 | 0 | 23772.3008 | 2008-06-02 08:00 | 1d | 23772.3008 | 0 | 0 | 3661.55 | 0 | 27433.8508 | 0 | 1 | Finished | 23772.3008 | 23772.3008 | C2013-09 Urban Development Project.xlsx
25 | 13 | Plaatsen ramen en deuren | 2008-06-16 08:00 | 2008-06-20 17:00 | 5d |  | 0 | 118861.5234 | 0 | 0 | 118861.5234 | 2008-08-19 08:00 | 10d | 118861.5234 | 0 | 0 | 18307.7402 | 0 | 137169.2637 | 0 | 1 | Finished | 118861.5234 | 118861.5234 | C2013-09 Urban Development Project.xlsx
26 | 14 | Plaatsen gipsblokken_blok 1 | 2008-09-03 08:00 | 2008-09-09 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-07-07 08:00 | 10d | 10562.0996 | 0 | 0 | 1316.5601 | 0 | 11878.6597 | 0 | 1 | Finished | 10562.0996 | 10562.0996 | C2013-09 Urban Development Project.xlsx
27 | 15 | Plaatsen gipsblokken_blok 2 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-08-11 08:00 | 10d | 10562.0996 | 0 | 0 | 1316.5601 | 0 | 11878.6597 | 0 | 1 | Finished | 10562.0996 | 10562.0996 | C2013-09 Urban Development Project.xlsx
28 | 16 | Plaatsen gipsblokken_blok 3 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-08-25 08:00 | 10d | 10562.0996 | 0 | 0 | 1316.5601 | 0 | 11878.6597 | 0 | 1 | Finished | 10562.0996 | 10562.0996 | C2013-09 Urban Development Project.xlsx
29 | 17 | Plaatsen gipsblokken_blok 4 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-09-08 08:00 | 10d | 10562.0996 | 0 | 0 | 1316.5601 | 0 | 11878.6597 | 0 | 1 | Finished | 10562.0996 | 10562.0996 | C2013-09 Urban Development Project.xlsx
30 | 18 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-08-11 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.98 | 0 | 24843.0796 | 0 | 1 | Finished | 22595.0996 | 22595.0996 | C2013-09 Urban Development Project.xlsx
31 | 19 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 2 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-08-25 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.98 | 0 | 24843.0796 | 0 | 1 | Finished | 22595.0996 | 22595.0996 | C2013-09 Urban Development Project.xlsx
32 | 20 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 3 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-09-08 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.98 | 0 | 24843.0796 | 0 | 1 | Finished | 22595.0996 | 22595.0996 | C2013-09 Urban Development Project.xlsx
33 | 21 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 4 | 2008-10-01 08:00 | 2008-10-07 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-09-22 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.98 | 0 | 24843.0796 | 0 | 1 | Finished | 22595.0996 | 22595.0996 | C2013-09 Urban Development Project.xlsx
34 | 22 | Plaatsen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-17 08:00 | 2008-09-30 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-10-13 08:00 | 10d | 45190.1992 | 0 | 0 | 4495.9502 | 0 | 49686.1494 | 0 | 1 | Finished | 45190.1992 | 45190.1992 | C2013-09 Urban Development Project.xlsx
35 | 23 | Plaatsen elektriciteit / sanitair / HVAC_blok 2 | 2008-10-01 08:00 | 2008-10-14 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-11-03 08:00 | 10d | 45190.1992 | 0 | 0 | 4495.9502 | 0 | 49686.1494 | 0 | 1 | Finished | 45190.1992 | 45190.1992 | C2013-09 Urban Development Project.xlsx
36 | 24 | Plaatsen elektriciteit / sanitair / HVAC_blok 3 | 2008-10-15 08:00 | 2008-11-04 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-11-17 08:00 | 10d | 45190.1992 | 0 | 0 | 4495.9502 | 0 | 49686.1494 | 0 | 1 | Finished | 45190.1992 | 45190.1992 | C2013-09 Urban Development Project.xlsx
37 | 25 | Plaatsen elektriciteit / sanitair / HVAC_blok 4 | 2008-11-05 08:00 | 2008-11-18 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-12-01 08:00 | 10d | 45190.1992 | 0 | 0 | 4495.9502 | 0 | 49686.1494 | 0 | 1 | Finished | 45190.1992 | 45190.1992 | C2013-09 Urban Development Project.xlsx
38 | 26 | Opmeten keukens_blok 1 | 2008-10-01 08:00 | 2008-10-01 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-12 08:00 | 1d | 1517.39 | 0 | 0 | 127.15 | 0 | 1644.54 | 0 | 1 | Finished | 1517.39 | 1517.39 | C2013-09 Urban Development Project.xlsx
39 | 27 | Opmeten keukens_blok 2 | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-12 08:00 | 1d | 1517.39 | 0 | 0 | 127.15 | 0 | 1644.54 | 0 | 1 | Finished | 1517.39 | 1517.39 | C2013-09 Urban Development Project.xlsx
40 | 28 | Opmeten keukens_blok 3 | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-26 08:00 | 1d | 1517.39 | 0 | 0 | 127.15 | 0 | 1644.54 | 0 | 1 | Finished | 1517.39 | 1517.39 | C2013-09 Urban Development Project.xlsx
41 | 29 | Opmeten keukens_blok 4 | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-26 08:00 | 1d | 1517.39 | 0 | 0 | 127.15 | 0 | 1644.54 | 0 | 1 | Finished | 1517.39 | 1517.39 | C2013-09 Urban Development Project.xlsx
42 | 30 | Pleisterwerken_blok 1 | 2008-10-01 08:00 | 2008-10-08 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2008-11-03 08:00 | 15d | 13287.2803 | 0 | 0 | 1092.15 | 0 | 14379.4303 | 0 | 1 | Finished | 13287.2803 | 13287.2803 | C2013-09 Urban Development Project.xlsx
43 | 31 | Pleisterwerken_blok 2 | 2008-10-15 08:00 | 2008-10-22 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2008-11-24 08:00 | 10d | 13287.2803 | 0 | 0 | 1092.15 | 0 | 14379.4303 | 0 | 1 | Finished | 13287.2803 | 13287.2803 | C2013-09 Urban Development Project.xlsx
44 | 32 | Pleisterwerken_blok 3 | 2008-11-05 08:00 | 2008-11-12 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2008-12-08 08:00 | 15d | 13287.2803 | 0 | 0 | 1092.15 | 0 | 14379.4303 | 0 | 1 | Finished | 13287.2803 | 13287.2803 | C2013-09 Urban Development Project.xlsx
45 | 33 | Pleisterwerken_blok 4 | 2008-11-19 08:00 | 2008-11-26 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2009-01-12 08:00 | 10d | 13287.2803 | 0 | 0 | 1092.15 | 0 | 14379.4303 | 0 | 1 | Finished | 13287.2803 | 13287.2803 | C2013-09 Urban Development Project.xlsx
46 | 34 | Schuimbeton_blok 1 | 2008-10-09 08:00 | 2008-10-13 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2008-11-24 08:00 | 1d | 689.89 | 0 | 0 | 73.6 | 0 | 763.49 | 0 | 1 | Finished | 689.89 | 689.89 | C2013-09 Urban Development Project.xlsx
47 | 35 | Schuimbeton_blok 2 | 2008-10-23 08:00 | 2008-11-03 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2008-12-08 08:00 | 1d | 689.89 | 0 | 0 | 73.6 | 0 | 763.49 | 0 | 1 | Finished | 689.89 | 689.89 | C2013-09 Urban Development Project.xlsx
48 | 36 | Schuimbeton_blok 3 | 2008-11-13 08:00 | 2008-11-17 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2009-01-12 08:00 | 1d | 689.89 | 0 | 0 | 73.6 | 0 | 763.49 | 0 | 1 | Finished | 689.89 | 689.89 | C2013-09 Urban Development Project.xlsx
49 | 37 | Schuimbeton_blok 4 | 2008-11-27 08:00 | 2008-12-01 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2009-01-26 08:00 | 1d | 689.89 | 0 | 0 | 73.6 | 0 | 763.49 | 0 | 1 | Finished | 689.89 | 689.89 | C2013-09 Urban Development Project.xlsx
50 | 38 | Chape_blok 1 | 2008-10-13 13:00 | 2008-10-15 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2008-12-01 08:00 | 10d | 3740.6699 | 0 | 0 | 313.73 | 0 | 4054.3999 | 0 | 1 | Finished | 3740.6699 | 3740.6699 | C2013-09 Urban Development Project.xlsx
51 | 39 | Chape_blok 2 | 2008-11-03 13:00 | 2008-11-05 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2008-12-16 08:00 | 10d | 3740.6699 | 0 | 0 | 313.73 | 0 | 4054.3999 | 0 | 1 | Finished | 3740.6699 | 3740.6699 | C2013-09 Urban Development Project.xlsx
52 | 40 | Chape_blok 3 | 2008-11-17 13:00 | 2008-11-19 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2009-01-20 08:00 | 10d | 3740.6699 | 0 | 0 | 313.73 | 0 | 4054.3999 | 0 | 1 | Finished | 3740.6699 | 3740.6699 | C2013-09 Urban Development Project.xlsx
53 | 41 | Chape_blok 4 | 2008-12-01 13:00 | 2008-12-03 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2009-02-03 08:00 | 10d | 3740.6699 | 0 | 0 | 313.73 | 0 | 4054.3999 | 0 | 1 | Finished | 3740.6699 | 3740.6699 | C2013-09 Urban Development Project.xlsx
54 | 42 | Opmeten binnendeuren_blok 1 | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2008-12-15 08:00 | 1d | 877.83 | 0 | 0 | 76.81 | 0 | 954.64 | 0 | 1 | Finished | 877.83 | 877.83 | C2013-09 Urban Development Project.xlsx
55 | 43 | Opmeten binnendeuren_blok 2 | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2009-01-13 08:00 | 1d | 877.83 | 0 | 0 | 76.81 | 0 | 954.64 | 0 | 1 | Finished | 877.83 | 877.83 | C2013-09 Urban Development Project.xlsx
56 | 44 | Opmeten binnendeuren_blok 3 | 2008-11-20 08:00 | 2008-11-20 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2009-02-03 08:00 | 1d | 877.83 | 0 | 0 | 76.81 | 0 | 954.64 | 0 | 1 | Finished | 877.83 | 877.83 | C2013-09 Urban Development Project.xlsx
57 | 45 | Opmeten binnendeuren_blok 4 | 2008-12-04 08:00 | 2008-12-04 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2009-02-17 08:00 | 1d | 877.83 | 0 | 0 | 76.81 | 0 | 954.64 | 0 | 1 | Finished | 877.83 | 877.83 | C2013-09 Urban Development Project.xlsx
58 | 46 | Vloerafwerking_blok 1 | 2008-10-16 08:00 | 2008-11-03 12:00 | 7d 4h |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2008-12-15 08:00 | 10d | 22771.2695 | 0 | 0 | 1846.4 | 0 | 24617.6696 | 0 | 1 | Finished | 22771.2695 | 22771.2695 | C2013-09 Urban Development Project.xlsx
59 | 47 | Vloerafwerking_blok 2 | 2008-11-06 08:00 | 2008-11-14 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2009-01-13 08:00 | 10d | 22771.2695 | 0 | 0 | 1846.4 | 0 | 24617.6696 | 0 | 1 | Finished | 22771.2695 | 22771.2695 | C2013-09 Urban Development Project.xlsx
60 | 48 | Vloerafwerking_blok 3 | 2008-11-20 08:00 | 2008-11-28 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2009-02-03 08:00 | 10d | 22771.2695 | 0 | 0 | 1846.4 | 0 | 24617.6696 | 0 | 1 | Finished | 22771.2695 | 22771.2695 | C2013-09 Urban Development Project.xlsx
61 | 49 | Vloerafwerking_blok 4 | 2008-12-04 08:00 | 2008-12-12 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2009-02-17 08:00 | 10d | 22771.2695 | 0 | 0 | 1846.4 | 0 | 24617.6696 | 0 | 1 | Finished | 22771.2695 | 22771.2695 | C2013-09 Urban Development Project.xlsx
62 | 50 | Plaatsen badkamers_blok 1 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-01-12 08:00 | 5d | 755.04 | 0 | 0 | 136.61 | 0 | 891.65 | 0 | 1 | Finished | 755.04 | 755.04 | C2013-09 Urban Development Project.xlsx
63 | 51 | Plaatsen badkamers_blok 2 | 2008-11-17 08:00 | 2008-11-28 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-01-27 08:00 | 5d | 755.04 | 0 | 0 | 136.61 | 0 | 891.65 | 0 | 1 | Finished | 755.04 | 755.04 | C2013-09 Urban Development Project.xlsx
64 | 52 | Plaatsen badkamers_blok 3 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-02-17 08:00 | 5d | 755.04 | 0 | 0 | 136.61 | 0 | 891.65 | 0 | 1 | Finished | 755.04 | 755.04 | C2013-09 Urban Development Project.xlsx
65 | 53 | Plaatsen badkamers_blok 4 | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-03-03 08:00 | 5d | 755.04 | 0 | 0 | 136.61 | 0 | 891.65 | 0 | 1 | Finished | 755.04 | 755.04 | C2013-09 Urban Development Project.xlsx
66 | 54 | Plaatsen keukens_blok 1 | 2008-10-16 08:00 | 2008-11-05 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-02-17 08:00 | 5d | 15173.8604 | 0 | 0 | 1271.54 | 0 | 16445.4004 | 0 | 1 | Finished | 15173.8604 | 15173.8604 | C2013-09 Urban Development Project.xlsx
67 | 55 | Plaatsen keukens_blok 2 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-02-24 08:00 | 5d | 15173.8604 | 0 | 0 | 1271.54 | 0 | 16445.4004 | 0 | 1 | Finished | 15173.8604 | 15173.8604 | C2013-09 Urban Development Project.xlsx
68 | 56 | Plaatsen keukens_blok 3 | 2008-11-20 08:00 | 2008-12-03 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-03-03 08:00 | 5d | 15173.8604 | 0 | 0 | 1271.54 | 0 | 16445.4004 | 0 | 1 | Finished | 15173.8604 | 15173.8604 | C2013-09 Urban Development Project.xlsx
69 | 57 | Plaatsen keukens_blok 4 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-03-10 08:00 | 5d | 15173.8604 | 0 | 0 | 1271.54 | 0 | 16445.4004 | 0 | 1 | Finished | 15173.8604 | 15173.8604 | C2013-09 Urban Development Project.xlsx
70 | 58 | Plaatsen binnendeuren_blok 1 | 2008-11-04 08:00 | 2008-11-10 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-02-03 08:00 | 10d | 4389.1299 | 0 | 0 | 384.07 | 0 | 4773.1999 | 0 | 1 | Finished | 4389.1299 | 4389.1299 | C2013-09 Urban Development Project.xlsx
71 | 59 | Plaatsen binnendeuren_blok 2 | 2008-11-17 08:00 | 2008-11-21 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-02-24 08:00 | 10d | 4389.1299 | 0 | 0 | 384.07 | 0 | 4773.1999 | 0 | 1 | Finished | 4389.1299 | 4389.1299 | C2013-09 Urban Development Project.xlsx
72 | 60 | Plaatsen binnendeuren_blok 3 | 2008-12-01 08:00 | 2008-12-05 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-03-11 08:00 | 10d | 4389.1299 | 0 | 0 | 384.07 | 0 | 4773.1999 | 0 | 1 | Finished | 4389.1299 | 4389.1299 | C2013-09 Urban Development Project.xlsx
73 | 61 | Plaatsen binnendeuren_blok 4 | 2008-12-15 08:00 | 2008-12-19 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-03-25 08:00 | 10d | 4389.1299 | 0 | 0 | 384.07 | 0 | 4773.1999 | 0 | 1 | Finished | 4389.1299 | 4389.1299 | C2013-09 Urban Development Project.xlsx
74 | 70 | Schilderwerken | 2009-01-05 08:00 | 2009-02-13 17:00 | 30d |  | 0 | 29804.9297 | 0 | 0 | 29804.9297 | 2009-04-08 08:00 | 30d | 29804.9297 | 0 | 0 | 2562.3 | 0 | 32367.2297 | 0 | 1 | Finished | 29804.9297 | 29804.9297 | C2013-09 Urban Development Project.xlsx
75 | 71 | Opkuis | 2009-02-16 08:00 | 2009-02-27 17:00 | 10d |  | 0 | 59293.3281 | 0 | 0 | 59293.3281 | 2009-05-22 08:00 | 10d | 59293.3281 | 0 | 0 | 7933.5098 | 0 | 67226.8379 | 0 | 1 | Finished | 59293.3281 | 59293.3281 | C2013-09 Urban Development Project.xlsx
4 | 0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 785d | [5 empty] | 15218926.3789 |  | 1 |  | 11421890.3643 | 11421890.3643 | C2013-10 Town Square.xlsx
5 | 1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 144348.7344 | 0 | 156481.8545 | 0 | 1 | Finished | 12133.1201 | 12133.1201 | C2013-10 Town Square.xlsx
6 | 2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 144348.7344 | 0 | 156481.8545 | 0 | 1 | Finished | 12133.1201 | 12133.1201 | C2013-10 Town Square.xlsx
7 | 3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 144348.7344 | 0 | 156481.8545 | 0 | 1 | Finished | 12133.1201 | 12133.1201 | C2013-10 Town Square.xlsx
8 | 4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 144348.7344 | 0 | 156481.8545 | 0 | 1 | Finished | 12133.1201 | 12133.1201 | C2013-10 Town Square.xlsx
9 | 5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 144348.7344 | 0 | 156481.8545 | 0 | 1 | Finished | 12133.1201 | 12133.1201 | C2013-10 Town Square.xlsx
10 | 6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 144348.7344 | 0 | 156481.8545 | 0 | 1 | Finished | 12133.1201 | 12133.1201 | C2013-10 Town Square.xlsx
11 | 7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-10 Town Square.xlsx
12 | 8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -397916.9375 | 0 | 88475.1562 | 0 | 1 | Finished | 486392.0938 | 486392.0938 | C2013-10 Town Square.xlsx
13 | 9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | 62388.1914 | 0 | 143413.6992 | 0 | 1 | Finished | 81025.5078 | 81025.5078 | C2013-10 Town Square.xlsx
14 | 12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 237d | [5 empty] | 7123332.7389 |  | 1 |  | 4964207.224 | 4964207.224 | C2013-10 Town Square.xlsx
15 | 11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 1659909.796 |  | 1 |  | 1124458.5367 | 1124458.5367 | C2013-10 Town Square.xlsx
16 | 10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-10 Town Square.xlsx
17 | 14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 126120.6875 |  | 1 |  | 157522.5781 | 157522.5781 | C2013-10 Town Square.xlsx
18 | 13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -31401.8906 | 0 | 126120.6875 | 0 | 1 | Finished | 157522.5781 | 157522.5781 | C2013-10 Town Square.xlsx
19 | 16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 245983.8418 |  | 1 |  | 471488.6621 | 471488.6621 | C2013-10 Town Square.xlsx
20 | 15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 64153.7891 | 0 | 76550.6387 | 0 | 1 | Finished | 12396.8496 | 12396.8496 | C2013-10 Town Square.xlsx
21 | 17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -339556 | 0 | 109893.8125 | 0 | 1 | Finished | 449449.8125 | 449449.8125 | C2013-10 Town Square.xlsx
22 | 18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 49897.3906 | 0 | 59539.3906 | 0 | 1 | Finished | 9642 | 9642 | C2013-10 Town Square.xlsx
23 | 20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 291684.1437 |  | 1 |  | 143428.7985 | 143428.7985 | C2013-10 Town Square.xlsx
24 | 19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 54230.1094 | 0 | 65936.2695 | 0 | 1 | Finished | 11706.1602 | 11706.1602 | C2013-10 Town Square.xlsx
25 | 21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | 6009.0498 | 0 | 43957.5186 | 0 | 1 | Finished | 37948.4688 | 37948.4688 | C2013-10 Town Square.xlsx
26 | 22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | 93850.4766 | 0 | 151403.5469 | 0 | 1 | Finished | 57553.0703 | 57553.0703 | C2013-10 Town Square.xlsx
27 | 23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -12996.4404 | 0 | 21978.7588 | 0 | 1 | Finished | 34975.1992 | 34975.1992 | C2013-10 Town Square.xlsx
28 | 24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 7162.1499 | 0 | 8408.0499 | 0 | 1 | Finished | 1245.9 | 1245.9 | C2013-10 Town Square.xlsx
29 | 26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 996121.123 |  | 1 |  | 352018.498 | 352018.498 | C2013-10 Town Square.xlsx
30 | 25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 40654.1094 | 0 | 50448.2793 | 0 | 1 | Finished | 9794.1699 | 9794.1699 | C2013-10 Town Square.xlsx
31 | 27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 252985.5156 | 0 | 286160.3672 | 0 | 1 | Finished | 33174.8516 | 33174.8516 | C2013-10 Town Square.xlsx
32 | 28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | 97764.2812 | 0 | 373638.9062 | 0 | 1 | Finished | 275874.625 | 275874.625 | C2013-10 Town Square.xlsx
33 | 29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 252698.7188 | 0 | 285873.5703 | 0 | 1 | Finished | 33174.8516 | 33174.8516 | C2013-10 Town Square.xlsx
34 | 31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 475570.1774 |  | 1 |  | 338610.4794 | 338610.4794 | C2013-10 Town Square.xlsx
35 | 30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-10 Town Square.xlsx
36 | 33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 25224.1396 |  | 1 |  | 31504.5195 | 31504.5195 | C2013-10 Town Square.xlsx
37 | 32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -6280.3799 | 0 | 25224.1396 | 0 | 1 | Finished | 31504.5195 | 31504.5195 | C2013-10 Town Square.xlsx
38 | 35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 49979.4011 |  | 1 |  | 137589.7976 | 137589.7976 | C2013-10 Town Square.xlsx
39 | 34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 1 | Finished | 1377.4301 | 1377.4301 | C2013-10 Town Square.xlsx
40 | 36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -101866.7969 | 0 | 32968.1406 | 0 | 1 | Finished | 134834.9375 | 134834.9375 | C2013-10 Town Square.xlsx
41 | 37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 1 | Finished | 1377.4301 | 1377.4301 | C2013-10 Town Square.xlsx
42 | 39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 105411.4781 |  | 1 |  | 65597.2294 | 65597.2294 | C2013-10 Town Square.xlsx
43 | 38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 18076.6992 | 0 | 21978.7493 | 0 | 1 | Finished | 3902.05 | 3902.05 | C2013-10 Town Square.xlsx
44 | 40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | 1502.26 | 0 | 10989.3801 | 0 | 1 | Finished | 9487.1201 | 9487.1201 | C2013-10 Town Square.xlsx
45 | 41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | 26069.5801 | 0 | 42056.54 | 0 | 1 | Finished | 15986.96 | 15986.96 | C2013-10 Town Square.xlsx
46 | 42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -12996.4404 | 0 | 21978.7588 | 0 | 1 | Finished | 34975.1992 | 34975.1992 | C2013-10 Town Square.xlsx
47 | 43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 7162.1499 | 0 | 8408.0499 | 0 | 1 | Finished | 1245.9 | 1245.9 | C2013-10 Town Square.xlsx
48 | 45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 294955.1584 |  | 1 |  | 103918.9329 | 103918.9329 | C2013-10 Town Square.xlsx
49 | 44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 13551.3701 | 0 | 16816.0901 | 0 | 1 | Finished | 3264.72 | 3264.72 | C2013-10 Town Square.xlsx
50 | 46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 74407.5078 | 0 | 84164.8174 | 0 | 1 | Finished | 9757.3096 | 9757.3096 | C2013-10 Town Square.xlsx
51 | 47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | 28754.1992 | 0 | 109893.793 | 0 | 1 | Finished | 81139.5938 | 81139.5938 | C2013-10 Town Square.xlsx
52 | 48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 74323.1484 | 0 | 84080.458 | 0 | 1 | Finished | 9757.3096 | 9757.3096 | C2013-10 Town Square.xlsx
53 | 50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 475570.4879 |  | 1 |  | 338610.4794 | 338610.4794 | C2013-10 Town Square.xlsx
54 | 49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-10 Town Square.xlsx
55 | 52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 25224.1396 |  | 1 |  | 31504.5195 | 31504.5195 | C2013-10 Town Square.xlsx
56 | 51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -6280.3799 | 0 | 25224.1396 | 0 | 1 | Finished | 31504.5195 | 31504.5195 | C2013-10 Town Square.xlsx
57 | 54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 49979.4011 |  | 1 |  | 137589.7976 | 137589.7976 | C2013-10 Town Square.xlsx
58 | 53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 1 | Finished | 1377.4301 | 1377.4301 | C2013-10 Town Square.xlsx
59 | 55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -101866.7969 | 0 | 32968.1406 | 0 | 1 | Finished | 134834.9375 | 134834.9375 | C2013-10 Town Square.xlsx
60 | 56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 1 | Finished | 1377.4301 | 1377.4301 | C2013-10 Town Square.xlsx
61 | 58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 105411.4781 |  | 1 |  | 65597.2294 | 65597.2294 | C2013-10 Town Square.xlsx
62 | 57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 18076.6992 | 0 | 21978.7493 | 0 | 1 | Finished | 3902.05 | 3902.05 | C2013-10 Town Square.xlsx
63 | 59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | 1502.26 | 0 | 10989.3801 | 0 | 1 | Finished | 9487.1201 | 9487.1201 | C2013-10 Town Square.xlsx
64 | 60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | 26069.5801 | 0 | 42056.54 | 0 | 1 | Finished | 15986.96 | 15986.96 | C2013-10 Town Square.xlsx
65 | 61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -12996.4404 | 0 | 21978.7588 | 0 | 1 | Finished | 34975.1992 | 34975.1992 | C2013-10 Town Square.xlsx
66 | 62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 7162.1499 | 0 | 8408.0499 | 0 | 1 | Finished | 1245.9 | 1245.9 | C2013-10 Town Square.xlsx
67 | 64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 294955.469 |  | 1 |  | 103918.9329 | 103918.9329 | C2013-10 Town Square.xlsx
68 | 63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 13551.3701 | 0 | 16816.0901 | 0 | 1 | Finished | 3264.72 | 3264.72 | C2013-10 Town Square.xlsx
69 | 65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 74407.5078 | 0 | 84164.8174 | 0 | 1 | Finished | 9757.3096 | 9757.3096 | C2013-10 Town Square.xlsx
70 | 66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | 28754.5098 | 0 | 109894.1035 | 0 | 1 | Finished | 81139.5938 | 81139.5938 | C2013-10 Town Square.xlsx
71 | 67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 74323.1484 | 0 | 84080.458 | 0 | 1 | Finished | 9757.3096 | 9757.3096 | C2013-10 Town Square.xlsx
72 | 69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 505973.3207 |  | 1 |  | 503232.8461 | 503232.8461 | C2013-10 Town Square.xlsx
73 | 68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-10 Town Square.xlsx
74 | 71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 50448.2812 |  | 1 |  | 63009.0312 | 63009.0312 | C2013-10 Town Square.xlsx
75 | 70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -12560.75 | 0 | 50448.2812 | 0 | 1 | Finished | 63009.0312 | 63009.0312 | C2013-10 Town Square.xlsx
76 | 73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 82947.5417 |  | 1 |  | 272424.7351 | 272424.7351 | C2013-10 Town Square.xlsx
77 | 72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 1 | Finished | 1377.4301 | 1377.4301 | C2013-10 Town Square.xlsx
78 | 74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -203733.5938 | 0 | 65936.2812 | 0 | 1 | Finished | 269669.875 | 269669.875 | C2013-10 Town Square.xlsx
79 | 75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 1 | Finished | 1377.4301 | 1377.4301 | C2013-10 Town Square.xlsx
80 | 77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 180436.1686 |  | 1 |  | 102509.4586 | 102509.4586 | C2013-10 Town Square.xlsx
81 | 76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 27115.0605 | 0 | 32968.1406 | 0 | 1 | Finished | 5853.0801 | 5853.0801 | C2013-10 Town Square.xlsx
82 | 78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | 4506.7798 | 0 | 32968.1294 | 0 | 1 | Finished | 28461.3496 | 28461.3496 | C2013-10 Town Square.xlsx
83 | 79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | 52139.1602 | 0 | 84113.0898 | 0 | 1 | Finished | 31973.9297 | 31973.9297 | C2013-10 Town Square.xlsx
84 | 80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -12996.4404 | 0 | 21978.7588 | 0 | 1 | Finished | 34975.1992 | 34975.1992 | C2013-10 Town Square.xlsx
85 | 81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 7162.1499 | 0 | 8408.0499 | 0 | 1 | Finished | 1245.9 | 1245.9 | C2013-10 Town Square.xlsx
86 | 83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 192141.3291 |  | 1 |  | 65289.6211 | 65289.6211 | C2013-10 Town Square.xlsx
87 | 82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 20327.0508 | 0 | 25224.1406 | 0 | 1 | Finished | 4897.0898 | 4897.0898 | C2013-10 Town Square.xlsx
88 | 84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 74407.5078 | 0 | 84164.8174 | 0 | 1 | Finished | 9757.3096 | 9757.3096 | C2013-10 Town Square.xlsx
89 | 85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | 17252.5195 | 0 | 65936.2812 | 0 | 1 | Finished | 48683.7617 | 48683.7617 | C2013-10 Town Square.xlsx
90 | 86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 14864.6299 | 0 | 16816.0898 | 0 | 1 | Finished | 1951.46 | 1951.46 | C2013-10 Town Square.xlsx
91 | 88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 669003.2437 |  | 1 |  | 538512.749 | 538512.749 | C2013-10 Town Square.xlsx
92 | 87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-10 Town Square.xlsx
93 | 90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 50448.2812 |  | 1 |  | 63009.0312 | 63009.0312 | C2013-10 Town Square.xlsx
94 | 89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -12560.75 | 0 | 50448.2812 | 0 | 1 | Finished | 63009.0312 | 63009.0312 | C2013-10 Town Square.xlsx
95 | 92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 133981.3035 |  | 1 |  | 280689.3054 | 280689.3054 | C2013-10 Town Square.xlsx
96 | 91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 14256.4004 | 0 | 17011.2605 | 0 | 1 | Finished | 2754.8601 | 2754.8601 | C2013-10 Town Square.xlsx
97 | 93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -203733.5938 | 0 | 65936.2812 | 0 | 1 | Finished | 269669.875 | 269669.875 | C2013-10 Town Square.xlsx
98 | 94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 42769.1914 | 0 | 51033.7617 | 0 | 1 | Finished | 8264.5703 | 8264.5703 | C2013-10 Town Square.xlsx
99 | 96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 157777.0623 |  | 1 |  | 113256.4709 | 113256.4709 | C2013-10 Town Square.xlsx
100 | 95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 27115.0605 | 0 | 32968.1406 | 0 | 1 | Finished | 5853.0801 | 5853.0801 | C2013-10 Town Square.xlsx
101 | 97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | 3004.52 | 0 | 21978.7603 | 0 | 1 | Finished | 18974.2402 | 18974.2402 | C2013-10 Town Square.xlsx
102 | 98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | 26069.5801 | 0 | 42056.54 | 0 | 1 | Finished | 15986.96 | 15986.96 | C2013-10 Town Square.xlsx
103 | 99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -25992.8691 | 0 | 43957.5215 | 0 | 1 | Finished | 69950.3906 | 69950.3906 | C2013-10 Town Square.xlsx
104 | 100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 14324.2998 | 0 | 16816.0999 | 0 | 1 | Finished | 2491.8 | 2491.8 | C2013-10 Town Square.xlsx
105 | 102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 326796.5967 |  | 1 |  | 81557.9414 | 81557.9414 | C2013-10 Town Square.xlsx
106 | 101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 27102.7402 | 0 | 33632.1904 | 0 | 1 | Finished | 6529.4502 | 6529.4502 | C2013-10 Town Square.xlsx
107 | 103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 186018.7656 | 0 | 210412.0352 | 0 | 1 | Finished | 24393.2695 | 24393.2695 | C2013-10 Town Square.xlsx
108 | 104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | 17252.5195 | 0 | 65936.2812 | 0 | 1 | Finished | 48683.7617 | 48683.7617 | C2013-10 Town Square.xlsx
109 | 105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 14864.6299 | 0 | 16816.0898 | 0 | 1 | Finished | 1951.46 | 1951.46 | C2013-10 Town Square.xlsx
110 | 126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 70d | [5 empty] | 445290.7521 |  | 1 |  | 405866.8156 | 405866.8156 | C2013-10 Town Square.xlsx
111 | 125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-10 Town Square.xlsx
112 | 128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 7d | [5 empty] | 16816.0898 |  | 1 |  | 21003.0098 | 21003.0098 | C2013-10 Town Square.xlsx
113 | 127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 7d | 21003.0098 | 0 | 0 | -4186.9199 | 0 | 16816.0898 | 0 | 1 | Finished | 21003.0098 | 21003.0098 | C2013-10 Town Square.xlsx
114 | 130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 5d | [5 empty] | 80463.797 |  | 1 |  | 228857.1964 | 228857.1964 | C2013-10 Town Square.xlsx
115 | 129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-14 08:00 | 1d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 1 | Finished | 1377.4301 | 1377.4301 | C2013-10 Town Square.xlsx
116 | 131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 | 2004-10-15 08:00 | 3d | 224724.9062 | 0 | 0 | -169778 | 0 | 54946.9062 | 0 | 1 | Finished | 224724.9062 | 224724.9062 | C2013-10 Town Square.xlsx
117 | 132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-10-13 08:00 | 1d | 2754.8601 | 0 | 0 | 14256.4004 | 0 | 17011.2605 | 0 | 1 | Finished | 2754.8601 | 2754.8601 | C2013-10 Town Square.xlsx
118 | 134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 9d | [5 empty] | 169440.2466 |  | 1 |  | 104655.9199 | 104655.9199 | C2013-10 Town Square.xlsx
119 | 133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-10-14 08:00 | 4d | 3902.05 | 0 | 0 | 18076.6992 | 0 | 21978.7493 | 0 | 1 | Finished | 3902.05 | 3902.05 | C2013-10 Town Square.xlsx
120 | 135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-14 08:00 | 2d | 18974.2402 | 0 | 0 | 3004.52 | 0 | 21978.7603 | 0 | 1 | Finished | 18974.2402 | 18974.2402 | C2013-10 Town Square.xlsx
121 | 136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 2004-10-14 08:00 | 3d | 25579.1406 | 0 | 0 | 41711.3281 | 0 | 67290.4688 | 0 | 1 | Finished | 25579.1406 | 25579.1406 | C2013-10 Town Square.xlsx
122 | 137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2004-10-14 08:00 | 3d | 52462.7891 | 0 | 0 | -19494.6602 | 0 | 32968.1289 | 0 | 1 | Finished | 52462.7891 | 52462.7891 | C2013-10 Town Square.xlsx
123 | 138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 | 2004-10-22 08:00 | 3d | 3737.7 | 0 | 0 | 21486.4395 | 0 | 25224.1394 | 0 | 1 | Finished | 3737.7 | 3737.7 | C2013-10 Town Square.xlsx
124 | 140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 13d | [5 empty] | 178570.6187 |  | 1 |  | 51350.6895 | 51350.6895 | C2013-10 Town Square.xlsx
125 | 139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 | 2004-10-19 08:00 | 5d | 8161.8101 | 0 | 0 | 33878.4219 | 0 | 42040.2319 | 0 | 1 | Finished | 8161.8101 | 8161.8101 | C2013-10 Town Square.xlsx
126 | 141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-10-20 08:00 | 5d | 9757.3096 | 0 | 0 | 74407.5078 | 0 | 84164.8174 | 0 | 1 | Finished | 9757.3096 | 9757.3096 | C2013-10 Town Square.xlsx
127 | 142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 | 2004-11-02 08:00 | 3d | 32455.8398 | 0 | 0 | 11501.6797 | 0 | 43957.5195 | 0 | 1 | Finished | 32455.8398 | 32455.8398 | C2013-10 Town Square.xlsx
128 | 143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-11-05 08:00 | 1d | 975.73 | 0 | 0 | 7432.3198 | 0 | 8408.0498 | 0 | 1 | Finished | 975.73 | 975.73 | C2013-10 Town Square.xlsx
129 | 145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 223800.8491 |  | 1 |  | 229054.8557 | 229054.8557 | C2013-10 Town Square.xlsx
130 | 144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-10 Town Square.xlsx
131 | 147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 8458.4697 |  | 1 |  | 10501.5098 | 10501.5098 | C2013-10 Town Square.xlsx
132 | 146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -2043.04 | 0 | 8458.4697 | 0 | 1 | Finished | 10501.5098 | 10501.5098 | C2013-10 Town Square.xlsx
133 | 149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 50133.9006 |  | 1 |  | 137589.7976 | 137589.7976 | C2013-10 Town Square.xlsx
134 | 148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 7178.6201 | 0 | 8556.0502 | 0 | 1 | Finished | 1377.4301 | 1377.4301 | C2013-10 Town Square.xlsx
135 | 150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -101715.5469 | 0 | 33119.3906 | 0 | 1 | Finished | 134834.9375 | 134834.9375 | C2013-10 Town Square.xlsx
136 | 151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 7081.0298 | 0 | 8458.4598 | 0 | 1 | Finished | 1377.4301 | 1377.4301 | C2013-10 Town Square.xlsx
137 | 153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 128776.4287 |  | 1 |  | 69922.3984 | 69922.3984 | C2013-10 Town Square.xlsx
138 | 152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | 52643.3203 | 0 | 84617.25 | 0 | 1 | Finished | 31973.9297 | 31973.9297 | C2013-10 Town Square.xlsx
139 | 154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | 6210.71 | 0 | 44159.1787 | 0 | 1 | Finished | 37948.4688 | 37948.4688 | C2013-10 Town Square.xlsx
140 | 156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 36432.05 |  | 1 |  | 11041.1499 | 11041.1499 | C2013-10 Town Square.xlsx
141 | 155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 14982.3301 | 0 | 16933.79 | 0 | 1 | Finished | 1951.46 | 1951.46 | C2013-10 Town Square.xlsx
142 | 157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | 2925.8401 | 0 | 11039.8 | 0 | 1 | Finished | 8113.96 | 8113.96 | C2013-10 Town Square.xlsx
143 | 158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 7482.73 | 0 | 8458.46 | 0 | 1 | Finished | 975.73 | 975.73 | C2013-10 Town Square.xlsx
144 | 160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 50d | [5 empty] | 366935.3523 |  | 1 |  | 294665.2991 | 294665.2991 | C2013-10 Town Square.xlsx
145 | 159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-10 Town Square.xlsx
146 | 162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 16816.0898 |  | 1 |  | 21003.0098 | 21003.0098 | C2013-10 Town Square.xlsx
147 | 161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -4186.9199 | 0 | 16816.0898 | 0 | 1 | Finished | 21003.0098 | 21003.0098 | C2013-10 Town Square.xlsx
148 | 164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 16d | [5 empty] | 117146.1902 |  | 1 |  | 152542.948 | 152542.948 | C2013-10 Town Square.xlsx
149 | 163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 1 | Finished | 1377.4301 | 1377.4301 | C2013-10 Town Square.xlsx
150 | 165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 52311.2188 | 0 | 67264.3691 | 0 | 1 | Finished | 14953.1504 | 14953.1504 | C2013-10 Town Square.xlsx
151 | 166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 0 | -101866.7969 | 0 | 32968.1406 | 0 | 1 | Finished | 134834.9375 | 134834.9375 | C2013-10 Town Square.xlsx
152 | 167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-11 08:00 | 1d | 1377.4301 | 0 | 0 | 7030.6201 | 0 | 8408.0502 | 0 | 1 | Finished | 1377.4301 | 1377.4301 | C2013-10 Town Square.xlsx
153 | 169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 15d | [5 empty] | 196742.6826 |  | 1 |  | 110078.1914 | 110078.1914 | C2013-10 Town Square.xlsx
154 | 168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-12 08:00 | 2d | 18974.2402 | 0 | 0 | 3004.52 | 0 | 21978.7603 | 0 | 1 | Finished | 18974.2402 | 18974.2402 | C2013-10 Town Square.xlsx
155 | 170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 2004-10-12 08:00 | 2d | 21883.9902 | 0 | 0 | 94.77 | 0 | 21978.7602 | 0 | 1 | Finished | 21883.9902 | 21883.9902 | C2013-10 Town Square.xlsx
156 | 171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 2004-10-13 08:00 | 6d | 19184.3594 | 0 | 0 | 31283.4902 | 0 | 50467.8496 | 0 | 1 | Finished | 19184.3594 | 19184.3594 | C2013-10 Town Square.xlsx
157 | 172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 2004-10-13 08:00 | 14d | 50035.6016 | 0 | 0 | 52281.7109 | 0 | 102317.3125 | 0 | 1 | Finished | 50035.6016 | 50035.6016 | C2013-10 Town Square.xlsx
158 | 174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 36230.3896 |  | 1 |  | 11041.1499 | 11041.1499 | C2013-10 Town Square.xlsx
159 | 173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-10-21 08:00 | 2d | 1951.46 | 0 | 0 | 14881.5 | 0 | 16832.96 | 0 | 1 | Finished | 1951.46 | 1951.46 | C2013-10 Town Square.xlsx
160 | 175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-10-25 08:00 | 1d | 8113.96 | 0 | 0 | 2875.4199 | 0 | 10989.3799 | 0 | 1 | Finished | 8113.96 | 8113.96 | C2013-10 Town Square.xlsx
161 | 176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-10-26 08:00 | 1d | 975.73 | 0 | 0 | 7432.3198 | 0 | 8408.0498 | 0 | 1 | Finished | 975.73 | 975.73 | C2013-10 Town Square.xlsx
162 | 282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 140d | [5 empty] | 2301278.7598 |  | 1 |  | 1191195.1631 | 1191195.1631 | C2013-10 Town Square.xlsx
163 | 281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 140d | [5 empty] | 1461643.2598 |  | 1 |  | 423739.9941 | 423739.9941 | C2013-10 Town Square.xlsx
164 | 280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 0 | 788978.125 | 0 | 1177126.5 | 0 | 1 | Finished | 388148.375 | 388148.375 | C2013-10 Town Square.xlsx
165 | 283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 | 2005-01-31 08:00 | 15d | 10863.2598 | 0 | 0 | 171336.2031 | 0 | 182199.4629 | 0 | 1 | Finished | 10863.2598 | 10863.2598 | C2013-10 Town Square.xlsx
166 | 284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 | 2005-02-28 08:00 | 10d | 24728.3594 | 0 | 0 | 77588.9375 | 0 | 102317.2969 | 0 | 1 | Finished | 24728.3594 | 24728.3594 | C2013-10 Town Square.xlsx
167 | 286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 43d | [5 empty] | 419233.1855 |  | 1 |  | 319190.0439 | 319190.0439 | C2013-10 Town Square.xlsx
168 | 285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 | 2005-01-19 08:00 | 13d | 175400.3438 | 0 | 0 | -132872.2188 | 0 | 42528.125 | 0 | 1 | Finished | 175400.3438 | 175400.3438 | C2013-10 Town Square.xlsx
169 | 287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 | 2005-02-28 08:00 | 4d | 19108.3203 | 0 | 0 | 14523.8604 | 0 | 33632.1807 | 0 | 1 | Finished | 19108.3203 | 19108.3203 | C2013-10 Town Square.xlsx
170 | 288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 | 2005-02-14 08:00 | 20d | 88628.0391 | 0 | 0 | 79532.8906 | 0 | 168160.9297 | 0 | 1 | Finished | 88628.0391 | 88628.0391 | C2013-10 Town Square.xlsx
171 | 289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 | 2005-02-07 08:00 | 10d | 3926.79 | 0 | 0 | 80366.6875 | 0 | 84293.4775 | 0 | 1 | Finished | 3926.79 | 3926.79 | C2013-10 Town Square.xlsx
172 | 290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 | 2005-03-07 08:00 | 10d | 32126.5508 | 0 | 0 | 58491.9219 | 0 | 90618.4727 | 0 | 1 | Finished | 32126.5508 | 32126.5508 | C2013-10 Town Square.xlsx
173 | 291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 | 2005-01-10 08:00 | 50d | 448265.125 | 0 | 0 | -27862.8105 | 0 | 420402.3145 | 0 | 1 | Finished | 448265.125 | 448265.125 | C2013-10 Town Square.xlsx
174 | 192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 249d | [5 empty] | 6924813.6576 |  | 1 |  | 5817466.818 | 5817466.818 | C2013-10 Town Square.xlsx
175 | 191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 163d | [5 empty] | 361545.9715 |  | 1 |  | 228530.0125 | 228530.0125 | C2013-10 Town Square.xlsx
176 | 190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 75672.4111 |  | 1 |  | 57005.7715 | 57005.7715 | C2013-10 Town Square.xlsx
177 | 189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | 12764.5898 | 0 | 42040.2305 | 0 | 1 | Finished | 29275.6406 | 29275.6406 | C2013-10 Town Square.xlsx
178 | 193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | 5902.0498 | 0 | 33632.1807 | 0 | 1 | Finished | 27730.1309 | 27730.1309 | C2013-10 Town Square.xlsx
179 | 195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 156d | [5 empty] | 33632.1794 |  | 1 |  | 17023.8298 | 17023.8298 | C2013-10 Town Square.xlsx
180 | 194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 15438.1396 | 0 | 16816.0896 | 0 | 1 | Finished | 1377.95 | 1377.95 | C2013-10 Town Square.xlsx
181 | 196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 | 2004-10-28 08:00 | 2d | 15645.8799 | 0 | 0 | 1170.21 | 0 | 16816.0898 | 0 | 1 | Finished | 15645.8799 | 15645.8799 | C2013-10 Town Square.xlsx
182 | 198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 33632.1807 |  | 1 |  | 12365.5303 | 12365.5303 | C2013-10 Town Square.xlsx
183 | 197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | 21266.6504 | 0 | 33632.1807 | 0 | 1 | Finished | 12365.5303 | 12365.5303 | C2013-10 Town Square.xlsx
184 | 200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 218609.2003 |  | 1 |  | 142134.881 | 142134.881 | C2013-10 Town Square.xlsx
185 | 199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | 21591.0996 | 0 | 84080.459 | 0 | 1 | Finished | 62489.3594 | 62489.3594 | C2013-10 Town Square.xlsx
186 | 201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -7488.71 | 0 | 16816.0908 | 0 | 1 | Finished | 24304.8008 | 24304.8008 | C2013-10 Town Square.xlsx
187 | 202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 49990.3594 | 0 | 50448.2794 | 0 | 1 | Finished | 457.92 | 457.92 | C2013-10 Town Square.xlsx
188 | 203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | 12381.5703 | 0 | 67264.3711 | 0 | 1 | Finished | 54882.8008 | 54882.8008 | C2013-10 Town Square.xlsx
189 | 206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 465962.4204 |  | 1 |  | 487050.7034 | 487050.7034 | C2013-10 Town Square.xlsx
190 | 205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 100896.5615 |  | 1 |  | 53827.6813 | 53827.6813 | C2013-10 Town Square.xlsx
191 | 204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -1132.55 | 0 | 16816.0906 | 0 | 1 | Finished | 17948.6406 | 17948.6406 | C2013-10 Town Square.xlsx
192 | 207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 25019.9902 | 0 | 25224.1402 | 0 | 1 | Finished | 204.15 | 204.15 | C2013-10 Town Square.xlsx
193 | 208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -4399.7402 | 0 | 25224.1406 | 0 | 1 | Finished | 29623.8809 | 29623.8809 | C2013-10 Town Square.xlsx
194 | 209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 25019.9902 | 0 | 25224.1402 | 0 | 1 | Finished | 204.15 | 204.15 | C2013-10 Town Square.xlsx
195 | 210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | 2561.1899 | 0 | 8408.0498 | 0 | 1 | Finished | 5846.8599 | 5846.8599 | C2013-10 Town Square.xlsx
196 | 212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 16816.0802 |  | 1 |  | 7169.4 | 7169.4 | C2013-10 Town Square.xlsx
197 | 211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | 3042 | 0 | 8408.04 | 0 | 1 | Finished | 5366.04 | 5366.04 | C2013-10 Town Square.xlsx
198 | 213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 6604.6802 | 0 | 8408.0402 | 0 | 1 | Finished | 1803.36 | 1803.36 | C2013-10 Town Square.xlsx
199 | 215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 348249.7787 |  | 1 |  | 426053.6221 | 426053.6221 | C2013-10 Town Square.xlsx
200 | 214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | 1305.96 | 0 | 25224.1396 | 0 | 1 | Finished | 23918.1797 | 23918.1797 | C2013-10 Town Square.xlsx
201 | 216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | 247.56 | 0 | 16816.0893 | 0 | 1 | Finished | 16568.5293 | 16568.5293 | C2013-10 Town Square.xlsx
202 | 217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | 807.93 | 0 | 8408.0501 | 0 | 1 | Finished | 7600.1201 | 7600.1201 | C2013-10 Town Square.xlsx
203 | 218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -4385.1299 | 0 | 42040.2295 | 0 | 1 | Finished | 46425.3594 | 46425.3594 | C2013-10 Town Square.xlsx
204 | 219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -97.89 | 0 | 42040.2311 | 0 | 1 | Finished | 42138.1211 | 42138.1211 | C2013-10 Town Square.xlsx
205 | 220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -75682.2734 | 0 | 213721.0391 | 0 | 1 | Finished | 289403.3125 | 289403.3125 | C2013-10 Town Square.xlsx
206 | 223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 33632.1793 |  | 1 |  | 35936.4492 | 35936.4492 | C2013-10 Town Square.xlsx
207 | 222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 33632.1793 |  | 1 |  | 35936.4492 | 35936.4492 | C2013-10 Town Square.xlsx
208 | 221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -2342.4099 | 0 | 16816.0901 | 0 | 1 | Finished | 19158.5 | 19158.5 | C2013-10 Town Square.xlsx
209 | 224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | 38.14 | 0 | 16816.0892 | 0 | 1 | Finished | 16777.9492 | 16777.9492 | C2013-10 Town Square.xlsx
210 | 227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 905292.7441 |  | 1 |  | 868616.3242 | 868616.3242 | C2013-10 Town Square.xlsx
211 | 226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 327913.8003 |  | 1 |  | 285414.4492 | 285414.4492 | C2013-10 Town Square.xlsx
212 | 225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | 12303.1104 | 0 | 33632.1807 | 0 | 1 | Finished | 21329.0703 | 21329.0703 | C2013-10 Town Square.xlsx
213 | 228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-10 Town Square.xlsx
214 | 229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -4818.3999 | 0 | 58856.3188 | 0 | 1 | Finished | 63674.7188 | 63674.7188 | C2013-10 Town Square.xlsx
215 | 230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -3086.8 | 0 | 58856.3289 | 0 | 1 | Finished | 61943.1289 | 61943.1289 | C2013-10 Town Square.xlsx
216 | 231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | 3519.54 | 0 | 42040.2314 | 0 | 1 | Finished | 38520.6914 | 38520.6914 | C2013-10 Town Square.xlsx
217 | 232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | 3422.51 | 0 | 50448.2795 | 0 | 1 | Finished | 47025.7695 | 47025.7695 | C2013-10 Town Square.xlsx
218 | 233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | 31159.3906 | 0 | 84080.4609 | 0 | 1 | Finished | 52921.0703 | 52921.0703 | C2013-10 Town Square.xlsx
219 | 235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 168160.918 |  | 1 |  | 39283.5117 | 39283.5117 | C2013-10 Town Square.xlsx
220 | 234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 128877.4062 | 0 | 168160.918 | 0 | 1 | Finished | 39283.5117 | 39283.5117 | C2013-10 Town Square.xlsx
221 | 237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 67264.3696 |  | 1 |  | 82365.2695 | 82365.2695 | C2013-10 Town Square.xlsx
222 | 236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -7269.0601 | 0 | 33632.1899 | 0 | 1 | Finished | 40901.25 | 40901.25 | C2013-10 Town Square.xlsx
223 | 238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -7831.8398 | 0 | 33632.1797 | 0 | 1 | Finished | 41464.0195 | 41464.0195 | C2013-10 Town Square.xlsx
224 | 240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 341953.6562 |  | 1 |  | 461553.0938 | 461553.0938 | C2013-10 Town Square.xlsx
225 | 239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -119599.4375 | 0 | 341953.6562 | 0 | 1 | Finished | 461553.0938 | 461553.0938 | C2013-10 Town Square.xlsx
226 | 241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-10 Town Square.xlsx
227 | 244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 64d | [5 empty] | 561576.0433 |  | 1 |  | 1025826.356 | 1025826.356 | C2013-10 Town Square.xlsx
228 | 243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 169174.1597 |  | 1 |  | 83395.19 | 83395.19 | C2013-10 Town Square.xlsx
229 | 242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 59417.6406 | 0 | 59869.5806 | 0 | 1 | Finished | 451.94 | 451.94 | C2013-10 Town Square.xlsx
230 | 245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 7957.79 | 0 | 8408.04 | 0 | 1 | Finished | 450.25 | 450.25 | C2013-10 Town Square.xlsx
231 | 246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | 9201.7695 | 0 | 50448.2695 | 0 | 1 | Finished | 41246.5 | 41246.5 | C2013-10 Town Square.xlsx
232 | 247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | 9201.7695 | 0 | 50448.2695 | 0 | 1 | Finished | 41246.5 | 41246.5 | C2013-10 Town Square.xlsx
233 | 249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 50448.2585 |  | 1 |  | 47465.2285 | 47465.2285 | C2013-10 Town Square.xlsx
234 | 248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | 626.26 | 0 | 25224.1292 | 0 | 1 | Finished | 24597.8691 | 24597.8691 | C2013-10 Town Square.xlsx
235 | 250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | 2356.77 | 0 | 25224.1294 | 0 | 1 | Finished | 22867.3594 | 22867.3594 | C2013-10 Town Square.xlsx
236 | 252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 40d | [5 empty] | 341953.625 |  | 1 |  | 894965.9375 | 894965.9375 | C2013-10 Town Square.xlsx
237 | 251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 0 | -553012.3125 | 0 | 341953.625 | 0 | 1 | Finished | 894965.9375 | 894965.9375 | C2013-10 Town Square.xlsx
238 | 255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 45d | [5 empty] | 374177.8577 |  | 1 |  | 778542.7812 | 778542.7812 | C2013-10 Town Square.xlsx
239 | 254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 5d | [5 empty] | 42040.2285 |  | 1 |  | 33920.1484 | 33920.1484 | C2013-10 Town Square.xlsx
240 | 253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 | 2004-12-06 08:00 | 5d | 33920.1484 | 0 | 0 | 8120.0801 | 0 | 42040.2285 | 0 | 1 | Finished | 33920.1484 | 33920.1484 | C2013-10 Town Square.xlsx
241 | 257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 9d | [5 empty] | 75672.4104 |  | 1 |  | 76109.8203 | 76109.8203 | C2013-10 Town Square.xlsx
242 | 256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 | 2004-12-13 08:00 | 5d | 46090.3906 | 0 | 0 | -4050.1599 | 0 | 42040.2307 | 0 | 1 | Finished | 46090.3906 | 46090.3906 | C2013-10 Town Square.xlsx
243 | 258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 | 2004-12-20 08:00 | 4d | 30019.4297 | 0 | 0 | 3612.75 | 0 | 33632.1797 | 0 | 1 | Finished | 30019.4297 | 30019.4297 | C2013-10 Town Square.xlsx
244 | 260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 31d | [5 empty] | 256465.2188 |  | 1 |  | 668512.8125 | 668512.8125 | C2013-10 Town Square.xlsx
245 | 259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 | 2005-01-10 08:00 | 31d | 668512.8125 | 0 | 0 | -412047.5938 | 0 | 256465.2188 | 0 | 1 | Finished | 668512.8125 | 668512.8125 | C2013-10 Town Square.xlsx
246 | 262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 121d | [5 empty] | 1091455.9824 |  | 1 |  | 206424.2637 | 206424.2637 | C2013-10 Town Square.xlsx
247 | 261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 0 | 421427.7812 | 0 | 453092.3418 | 0 | 1 | Finished | 31664.5605 | 31664.5605 | C2013-10 Town Square.xlsx
248 | 263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 | 2004-11-22 08:00 | 74d | 174759.7031 | 0 | 0 | 463603.9375 | 0 | 638363.6406 | 0 | 1 | Finished | 174759.7031 | 174759.7031 | C2013-10 Town Square.xlsx
249 | 264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 | 2005-02-28 08:00 | 15d | 235690.6719 | 0 | 0 | -46522.9688 | 0 | 189167.7031 | 0 | 1 | Finished | 235690.6719 | 235690.6719 | C2013-10 Town Square.xlsx
250 | 293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 40d | [5 empty] | 369954.0244 |  | 1 |  | 24833.4189 | 24833.4189 | C2013-10 Town Square.xlsx
251 | 292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 | 2005-01-17 08:00 | 4d | 4644.7798 | 0 | 0 | 62619.5898 | 0 | 67264.3696 | 0 | 1 | Finished | 4644.7798 | 4644.7798 | C2013-10 Town Square.xlsx
252 | 294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 | 2005-01-31 08:00 | 6d | 3364.77 | 0 | 0 | 47083.5 | 0 | 50448.27 | 0 | 1 | Finished | 3364.77 | 3364.77 | C2013-10 Town Square.xlsx
253 | 295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 | 2005-02-08 08:00 | 24d | 16823.8691 | 0 | 0 | 235417.5156 | 0 | 252241.3848 | 0 | 1 | Finished | 16823.8691 | 16823.8691 | C2013-10 Town Square.xlsx
254 | 297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 84d | [5 empty] | 1469597.9602 |  | 1 |  | 1048283.1511 | 1048283.1511 | C2013-10 Town Square.xlsx
255 | 296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 | 2004-11-02 08:00 | 17d | 12038.2695 | 0 | 0 | 130898.5078 | 0 | 142936.7773 | 0 | 1 | Finished | 12038.2695 | 12038.2695 | C2013-10 Town Square.xlsx
256 | 298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 | 2004-11-05 08:00 | 17d | 3083.78 | 0 | 0 | 114628.8672 | 0 | 117712.6472 | 0 | 1 | Finished | 3083.78 | 3083.78 | C2013-10 Town Square.xlsx
257 | 299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 | 2004-11-15 08:00 | 20d | 31102.0195 | 0 | 0 | -22693.9805 | 0 | 8408.0391 | 0 | 1 | Finished | 31102.0195 | 31102.0195 | C2013-10 Town Square.xlsx
258 | 300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 | 2004-11-15 08:00 | 25d | 132006.2031 | 0 | 0 | -5565.98 | 0 | 126440.2231 | 0 | 1 | Finished | 132006.2031 | 132006.2031 | C2013-10 Town Square.xlsx
259 | 301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 | 2004-11-08 08:00 | 80d | 413377.0625 | 0 | 0 | 175414.5625 | 0 | 588791.625 | 0 | 1 | Finished | 413377.0625 | 413377.0625 | C2013-10 Town Square.xlsx
260 | 302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 | 2005-01-10 08:00 | 45d | 440020.6562 | 0 | 0 | -19618.3398 | 0 | 420402.3164 | 0 | 1 | Finished | 440020.6562 | 440020.6562 | C2013-10 Town Square.xlsx
261 | 303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 | 2005-02-04 08:00 | 7d | 16655.1602 | 0 | 0 | 48251.1719 | 0 | 64906.332 | 0 | 1 | Finished | 16655.1602 | 16655.1602 | C2013-10 Town Square.xlsx
262 | 305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 49d | [5 empty] | 504482.791 |  | 1 |  | 595707.5625 | 595707.5625 | C2013-10 Town Square.xlsx
263 | 304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 | 2005-01-11 08:00 | 35d | 322152.7812 | 0 | 0 | -69911.3906 | 0 | 252241.3906 | 0 | 1 | Finished | 322152.7812 | 322152.7812 | C2013-10 Town Square.xlsx
264 | 306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 | 2005-02-10 08:00 | 27d | 273554.7812 | 0 | 0 | -21313.3809 | 0 | 252241.4004 | 0 | 1 | Finished | 273554.7812 | 273554.7812 | C2013-10 Town Square.xlsx
265 | 308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 45d | [5 empty] | 253238.0931 |  | 1 |  | 104851.2127 | 104851.2127 | C2013-10 Town Square.xlsx
266 | 307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 | 2005-01-10 08:00 | 5d | 3592.98 | 0 | 0 | 38447.25 | 0 | 42040.23 | 0 | 1 | Finished | 3592.98 | 3592.98 | C2013-10 Town Square.xlsx
267 | 309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 | 2005-01-24 08:00 | 15d | 78335.2422 | 0 | 0 | 47785.4492 | 0 | 126120.6914 | 0 | 1 | Finished | 78335.2422 | 78335.2422 | C2013-10 Town Square.xlsx
268 | 310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 | 2005-02-14 08:00 | 3d | 182.46 | 0 | 0 | 16633.6309 | 0 | 16816.0909 | 0 | 1 | Finished | 182.46 | 182.46 | C2013-10 Town Square.xlsx
269 | 311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 | 2005-02-17 08:00 | 2d | 19392.5605 | 0 | 0 | 6124.3198 | 0 | 25516.8804 | 0 | 1 | Finished | 19392.5605 | 19392.5605 | C2013-10 Town Square.xlsx
270 | 312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 | 2005-03-07 08:00 | 5d | 3347.97 | 0 | 0 | 39396.2305 | 0 | 42744.2004 | 0 | 1 | Finished | 3347.97 | 3347.97 | C2013-10 Town Square.xlsx
271 | 314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 27d | [5 empty] | 344729.8871 |  | 1 |  | 177173.9105 | 177173.9105 | C2013-10 Town Square.xlsx
272 | 313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 | 2005-02-07 08:00 | 3d | 1511.83 | 0 | 0 | 23712.3105 | 0 | 25224.1405 | 0 | 1 | Finished | 1511.83 | 1511.83 | C2013-10 Town Square.xlsx
273 | 315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 | 2005-02-08 08:00 | 4d | 655.73 | 0 | 0 | 24568.4102 | 0 | 25224.1401 | 0 | 1 | Finished | 655.73 | 655.73 | C2013-10 Town Square.xlsx
274 | 316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 | 2005-02-21 08:00 | 10d | 14023.8896 | 0 | 0 | 112096.7969 | 0 | 126120.6865 | 0 | 1 | Finished | 14023.8896 | 14023.8896 | C2013-10 Town Square.xlsx
275 | 317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 | 2005-02-24 08:00 | 12d | 99261.0312 | 0 | 0 | -15180.5703 | 0 | 84080.4609 | 0 | 1 | Finished | 99261.0312 | 99261.0312 | C2013-10 Town Square.xlsx
276 | 318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 | 2005-02-28 08:00 | 12d | 61721.4297 | 0 | 0 | 22359.0293 | 0 | 84080.459 | 0 | 1 | Finished | 61721.4297 | 61721.4297 | C2013-10 Town Square.xlsx
4 | 0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 277d | [5 empty] | 5451028.0032 |  | 1 |  | 5480518.9127 | 5392111.2444 | C2013-11 Recreation Complex.xlsx
5 | 1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-11 Recreation Complex.xlsx
6 | 2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 277d | [5 empty] | 5451028.0032 |  | 1 |  | 5480518.9127 | 5392111.2444 | C2013-11 Recreation Complex.xlsx
7 | 3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 149650.4971 |  | 1 |  | 140380.5469 | 140380.5469 | C2013-11 Recreation Complex.xlsx
8 | 4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 9269.9502 | 0 | 149650.4971 | 0 | 1 | Finished | 140380.5469 | 140380.5469 | C2013-11 Recreation Complex.xlsx
9 | 5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 99d | [5 empty] | 358462.3806 |  | 1 |  | 366683.4202 | 366683.4202 | C2013-11 Recreation Complex.xlsx
10 | 6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | 2.8 | 0 | 688.48 | 0 | 1 | Finished | 685.68 | 685.68 | C2013-11 Recreation Complex.xlsx
11 | 7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 107985.739 |  | 1 |  | 117133.5588 | 117133.5588 | C2013-11 Recreation Complex.xlsx
12 | 265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-11 Recreation Complex.xlsx
13 | 266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 118.81 | 0 | 823.61 | 0 | 1 | Finished | 704.8 | 704.8 | C2013-11 Recreation Complex.xlsx
14 | 267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | 4.67 | 0 | 1147.47 | 0 | 1 | Finished | 1142.8 | 1142.8 | C2013-11 Recreation Complex.xlsx
15 | 8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | 3.73 | 0 | 917.97 | 0 | 1 | Finished | 914.24 | 914.24 | C2013-11 Recreation Complex.xlsx
16 | 9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | -6499.1499 | 0 | 64068.2876 | 0 | 1 | Finished | 70567.4375 | 70567.4375 | C2013-11 Recreation Complex.xlsx
17 | 10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -2775.8799 | 0 | 41028.4014 | 0 | 1 | Finished | 43804.2812 | 43804.2812 | C2013-11 Recreation Complex.xlsx
18 | 11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 99d | [5 empty] | 39121.2097 |  | 1 |  | 34170.5095 | 34170.5095 | C2013-11 Recreation Complex.xlsx
19 | 12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 297.02 | 0 | 2059.01 | 0 | 1 | Finished | 1761.99 | 1761.99 | C2013-11 Recreation Complex.xlsx
20 | 13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 90d | 32408.5195 | 0 | 0 | 4653.6802 | 0 | 37062.1997 | 0 | 1 | Finished | 32408.5195 | 32408.5195 | C2013-11 Recreation Complex.xlsx
21 | 14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 210666.9519 |  | 1 |  | 214693.6719 | 214693.6719 | C2013-11 Recreation Complex.xlsx
22 | 15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -4026.72 | 0 | 210666.9519 | 0 | 1 | Finished | 214693.6719 | 214693.6719 | C2013-11 Recreation Complex.xlsx
23 | 16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 159d | [5 empty] | 1686917.0672 |  | 1 |  | 1741960.3886 | 1741960.3886 | C2013-11 Recreation Complex.xlsx
24 | 17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 95589.4126 |  | 1 |  | 97505.4526 | 97505.4526 | C2013-11 Recreation Complex.xlsx
25 | 18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -139.9 | 0 | 6603.4901 | 0 | 1 | Finished | 6743.3901 | 6743.3901 | C2013-11 Recreation Complex.xlsx
26 | 19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -769.46 | 0 | 36319.1806 | 0 | 1 | Finished | 37088.6406 | 37088.6406 | C2013-11 Recreation Complex.xlsx
27 | 20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -1006.68 | 0 | 52666.7419 | 0 | 1 | Finished | 53673.4219 | 53673.4219 | C2013-11 Recreation Complex.xlsx
28 | 21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1147.47 |  | 1 |  | 1142.8 | 1142.8 | C2013-11 Recreation Complex.xlsx
29 | 22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | 4.67 | 0 | 1147.47 | 0 | 1 | Finished | 1142.8 | 1142.8 | C2013-11 Recreation Complex.xlsx
30 | 23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 146d | [5 empty] | 1590180.1846 |  | 1 |  | 1643312.1359 | 1643312.1359 | C2013-11 Recreation Complex.xlsx
31 | 163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | -9.84 | 0 | 2413.5799 | 0 | 1 | Finished | 2423.4199 | 2423.4199 | C2013-11 Recreation Complex.xlsx
32 | 24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | 1.87 | 0 | 458.99 | 0 | 1 | Finished | 457.12 | 457.12 | C2013-11 Recreation Complex.xlsx
33 | 164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | 0.93 | 0 | 229.49 | 0 | 1 | Finished | 228.56 | 228.56 | C2013-11 Recreation Complex.xlsx
34 | 165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -209.85 | 0 | 9905.2301 | 0 | 1 | Finished | 10115.0801 | 10115.0801 | C2013-11 Recreation Complex.xlsx
35 | 166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | -14512.9805 | 0 | 32689.8281 | 0 | 1 | Finished | 47202.8086 | 47202.8086 | C2013-11 Recreation Complex.xlsx
36 | 167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 1304.53 | 0 | 1761.65 | 0 | 1 | Finished | 457.12 | 457.12 | C2013-11 Recreation Complex.xlsx
37 | 168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -6556.02 | 0 | 41656.0112 | 0 | 1 | Finished | 48212.0312 | 48212.0312 | C2013-11 Recreation Complex.xlsx
38 | 169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | -4837.6602 | 0 | 10896.6094 | 0 | 1 | Finished | 15734.2695 | 15734.2695 | C2013-11 Recreation Complex.xlsx
39 | 170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 20358.6797 | 0 | 59300.2188 | 0 | 1 | Finished | 38941.5391 | 38941.5391 | C2013-11 Recreation Complex.xlsx
40 | 171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | -2695.74 | 0 | 163196.1975 | 0 | 1 | Finished | 165891.9375 | 165891.9375 | C2013-11 Recreation Complex.xlsx
41 | 38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -3278.01 | 0 | 20828.0095 | 0 | 1 | Finished | 24106.0195 | 24106.0195 | C2013-11 Recreation Complex.xlsx
42 | 172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-11 Recreation Complex.xlsx
43 | 173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 1454.9 | 0 | 3531.38 | 0 | 1 | Finished | 2076.48 | 2076.48 | C2013-11 Recreation Complex.xlsx
44 | 174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -13288.8896 | 0 | 7940.3896 | 0 | 1 | Finished | 21229.2793 | 21229.2793 | C2013-11 Recreation Complex.xlsx
45 | 40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | -928.26 | 0 | 1642.53 | 0 | 1 | Finished | 2570.79 | 2570.79 | C2013-11 Recreation Complex.xlsx
46 | 175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 212.86 | 0 | 441.42 | 0 | 1 | Finished | 228.56 | 228.56 | C2013-11 Recreation Complex.xlsx
47 | 176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -13288.8896 | 0 | 7940.3896 | 0 | 1 | Finished | 21229.2793 | 21229.2793 | C2013-11 Recreation Complex.xlsx
48 | 177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | -2784.77 | 0 | 4927.6099 | 0 | 1 | Finished | 7712.3799 | 7712.3799 | C2013-11 Recreation Complex.xlsx
49 | 178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-11 Recreation Complex.xlsx
50 | 179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | 3927.4199 | 0 | 6722.21 | 0 | 1 | Finished | 2794.79 | 2794.79 | C2013-11 Recreation Complex.xlsx
51 | 180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 20d | 62937.0781 | 0 | 0 | -19350.6406 | 0 | 43586.4375 | 0 | 1 | Finished | 62937.0781 | 62937.0781 | C2013-11 Recreation Complex.xlsx
52 | 181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 20d | 94089.9219 | 0 | 0 | -8665.5303 | 0 | 85424.3916 | 0 | 1 | Finished | 94089.9219 | 94089.9219 | C2013-11 Recreation Complex.xlsx
53 | 182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-11 Recreation Complex.xlsx
54 | 183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-11 Recreation Complex.xlsx
55 | 184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | -60.13 | 0 | 458.99 | 0 | 1 | Finished | 519.12 | 519.12 | C2013-11 Recreation Complex.xlsx
56 | 185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | 6665.6899 | 0 | 74831.9478 | 0 | 1 | Finished | 68166.2578 | 68166.2578 | C2013-11 Recreation Complex.xlsx
57 | 188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 41d | [5 empty] | 409520.537 |  | 1 |  | 384191.6268 | 384191.6268 | C2013-11 Recreation Complex.xlsx
58 | 43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-12 08:00 | 5d | 89807.4766 | 0 | 0 | 10606.2197 | 0 | 100413.6963 | 0 | 1 | Finished | 89807.4766 | 89807.4766 | C2013-11 Recreation Complex.xlsx
59 | 187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 | 2012-01-17 08:00 | 5d | 56129.6797 | 0 | 0 | 36690.3906 | 0 | 92820.0703 | 0 | 1 | Finished | 56129.6797 | 56129.6797 | C2013-11 Recreation Complex.xlsx
60 | 189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 | 2012-01-24 08:00 | 5d | 2578.22 | 0 | 0 | -149.87 | 0 | 2428.35 | 0 | 1 | Finished | 2578.22 | 2578.22 | C2013-11 Recreation Complex.xlsx
61 | 190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-01-31 08:00 | 2d | 644.55 | 0 | 0 | -37.47 | 0 | 607.08 | 0 | 1 | Finished | 644.55 | 644.55 | C2013-11 Recreation Complex.xlsx
62 | 192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2012-01-31 08:00 | 3d | 685.68 | 0 | 0 | 2.8 | 0 | 688.48 | 0 | 1 | Finished | 685.68 | 685.68 | C2013-11 Recreation Complex.xlsx
63 | 205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 | 2012-01-24 08:00 | 3d | 33677.8086 | 0 | 0 | 3977.3301 | 0 | 37655.1387 | 0 | 1 | Finished | 33677.8086 | 33677.8086 | C2013-11 Recreation Complex.xlsx
64 | 206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-27 08:00 | 1d | 768.63 | 0 | 0 | -1.86 | 0 | 766.77 | 0 | 1 | Finished | 768.63 | 768.63 | C2013-11 Recreation Complex.xlsx
65 | 207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 | 2012-01-30 08:00 | 5d | 38697.4805 | 0 | 0 | -8120.3398 | 0 | 30577.1406 | 0 | 1 | Finished | 38697.4805 | 38697.4805 | C2013-11 Recreation Complex.xlsx
66 | 208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 | 2012-02-06 08:00 | 2d | 28146.0098 | 0 | 0 | -15231.4004 | 0 | 12914.6094 | 0 | 1 | Finished | 28146.0098 | 28146.0098 | C2013-11 Recreation Complex.xlsx
67 | 209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 | 2012-02-08 08:00 | 1d | 118942.6016 | 0 | 0 | -1107.0601 | 0 | 117835.5415 | 0 | 1 | Finished | 118942.6016 | 118942.6016 | C2013-11 Recreation Complex.xlsx
68 | 210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 | 2012-02-09 08:00 | 3d | 14113.4902 | 0 | 0 | -1299.83 | 0 | 12813.6603 | 0 | 1 | Finished | 14113.4902 | 14113.4902 | C2013-11 Recreation Complex.xlsx
69 | 201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 70d | [5 empty] | 599876.137 |  | 1 |  | 621796.6673 | 621796.6673 | C2013-11 Recreation Complex.xlsx
70 | 42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-19 08:00 | 5d | 89807.4766 | 0 | 0 | 10606.2197 | 0 | 100413.6963 | 0 | 1 | Finished | 89807.4766 | 89807.4766 | C2013-11 Recreation Complex.xlsx
71 | 211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 | 2012-01-02 08:00 | 2d | 2114.3301 | 0 | 0 | 91.22 | 0 | 2205.5501 | 0 | 1 | Finished | 2114.3301 | 2114.3301 | C2013-11 Recreation Complex.xlsx
72 | 45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2012-01-09 08:00 | 6d | 89807.4766 | 0 | 0 | 10606.2197 | 0 | 100413.6963 | 0 | 1 | Finished | 89807.4766 | 89807.4766 | C2013-11 Recreation Complex.xlsx
73 | 202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 | 2012-01-02 08:00 | 5d | 4611.79 | 0 | 0 | -11.15 | 0 | 4600.64 | 0 | 1 | Finished | 4611.79 | 4611.79 | C2013-11 Recreation Complex.xlsx
74 | 212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-09 08:00 | 1d | 768.63 | 0 | 0 | -1.86 | 0 | 766.77 | 0 | 1 | Finished | 768.63 | 768.63 | C2013-11 Recreation Complex.xlsx
75 | 213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-13 08:00 | 4d | 33118.2695 | 0 | 0 | -6507.4399 | 0 | 26610.8296 | 0 | 1 | Finished | 33118.2695 | 33118.2695 | C2013-11 Recreation Complex.xlsx
76 | 203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 | 2012-01-19 08:00 | 2d | 22309.4199 | 0 | 0 | -13294.4697 | 0 | 9014.9502 | 0 | 1 | Finished | 22309.4199 | 22309.4199 | C2013-11 Recreation Complex.xlsx
77 | 214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 | 2012-01-23 08:00 | 3d | 2305.8999 | 0 | 0 | -5.57 | 0 | 2300.3299 | 0 | 1 | Finished | 2305.8999 | 2305.8999 | C2013-11 Recreation Complex.xlsx
78 | 215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-24 08:00 | 4d | 33118.2695 | 0 | 0 | -6507.4399 | 0 | 26610.8296 | 0 | 1 | Finished | 33118.2695 | 33118.2695 | C2013-11 Recreation Complex.xlsx
79 | 216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 | 2012-01-30 08:00 | 1d | 11154.71 | 0 | 0 | -6647.2402 | 0 | 4507.4697 | 0 | 1 | Finished | 11154.71 | 11154.71 | C2013-11 Recreation Complex.xlsx
80 | 50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 | 2012-01-31 08:00 | 5d | 23522.4805 | 0 | 0 | -2166.3799 | 0 | 21356.1006 | 0 | 1 | Finished | 23522.4805 | 23522.4805 | C2013-11 Recreation Complex.xlsx
81 | 217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 | 2012-01-31 08:00 | 20d | 115165.7109 | 0 | 0 | -2778.8401 | 0 | 112386.8708 | 0 | 1 | Finished | 115165.7109 | 115165.7109 | C2013-11 Recreation Complex.xlsx
82 | 218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 | 2012-03-09 08:00 | 6d | 191942.8438 | 0 | 0 | -4631.3999 | 0 | 187311.4438 | 0 | 1 | Finished | 191942.8438 | 191942.8438 | C2013-11 Recreation Complex.xlsx
83 | 56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 | 2012-03-26 08:00 | 5d | 1820.8 | 0 | 0 | -673.33 | 0 | 1147.47 | 0 | 1 | Finished | 1820.8 | 1820.8 | C2013-11 Recreation Complex.xlsx
84 | 219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-01 08:00 | 1d | 228.56 | 0 | 0 | 0.93 | 0 | 229.49 | 0 | 1 | Finished | 228.56 | 228.56 | C2013-11 Recreation Complex.xlsx
85 | 57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 190d | [5 empty] | 2255841.499 |  | 1 |  | 2231819.1877 | 2143411.5195 | C2013-11 Recreation Complex.xlsx
86 | 58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 8d | [5 empty] | 3294.4099 |  | 1 |  | 2819.1799 | 2819.1799 | C2013-11 Recreation Complex.xlsx
87 | 59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 | 2012-05-10 08:00 | 8d | 2819.1799 | 0 | 0 | 475.23 | 0 | 3294.4099 | 0 | 1 | Finished | 2819.1799 | 2819.1799 | C2013-11 Recreation Complex.xlsx
88 | 60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 15d | [5 empty] | 3442.4099 |  | 1 |  | 3428.4099 | 3428.4099 | C2013-11 Recreation Complex.xlsx
89 | 61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 | 2012-03-19 08:00 | 15d | 3428.4099 | 0 | 0 | 14 | 0 | 3442.4099 | 0 | 1 | Finished | 3428.4099 | 3428.4099 | C2013-11 Recreation Complex.xlsx
90 | 65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 9d | [5 empty] | 16805.54 |  | 1 |  | 6986.9902 | 6986.9902 | C2013-11 Recreation Complex.xlsx
91 | 66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 | 2012-01-23 08:00 | 9d | 6986.9902 | 0 | 0 | 9818.5498 | 0 | 16805.54 | 0 | 1 | Finished | 6986.9902 | 6986.9902 | C2013-11 Recreation Complex.xlsx
92 | 221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 41d | [5 empty] | 271542.2072 |  | 1 |  | 245403.4564 | 245403.4564 | C2013-11 Recreation Complex.xlsx
93 | 220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-03-01 08:00 | 6d | 644.55 | 0 | 0 | -37.47 | 0 | 607.08 | 0 | 1 | Finished | 644.55 | 644.55 | C2013-11 Recreation Complex.xlsx
94 | 223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-12 08:00 | 9d | 228.56 | 0 | 0 | 212.86 | 0 | 441.42 | 0 | 1 | Finished | 228.56 | 228.56 | C2013-11 Recreation Complex.xlsx
95 | 224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 | 2012-03-12 08:00 | 9d | 1371.36 | 0 | 0 | 1277.17 | 0 | 2648.53 | 0 | 1 | Finished | 1371.36 | 1371.36 | C2013-11 Recreation Complex.xlsx
96 | 225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 | 2012-03-12 08:00 | 9d | 116301.5078 | 0 | 0 | -11243.8496 | 0 | 105057.6582 | 0 | 1 | Finished | 116301.5078 | 116301.5078 | C2013-11 Recreation Complex.xlsx
97 | 226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-23 08:00 | 9d | 228.56 | 0 | 0 | 0.93 | 0 | 229.49 | 0 | 1 | Finished | 228.56 | 228.56 | C2013-11 Recreation Complex.xlsx
98 | 227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 | 2012-03-19 08:00 | 20d | 93216.1875 | 0 | 0 | 11738.3301 | 0 | 104954.5176 | 0 | 1 | Finished | 93216.1875 | 93216.1875 | C2013-11 Recreation Complex.xlsx
99 | 228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-04-17 08:00 | 2d | 457.12 | 0 | 0 | 1.87 | 0 | 458.99 | 0 | 1 | Finished | 457.12 | 457.12 | C2013-11 Recreation Complex.xlsx
100 | 229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 | 2012-04-19 08:00 | 4d | 994.24 | 0 | 0 | -76.27 | 0 | 917.97 | 0 | 1 | Finished | 994.24 | 994.24 | C2013-11 Recreation Complex.xlsx
101 | 230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 | 2012-04-16 08:00 | 10d | 20492.0508 | 0 | 0 | -1910.4301 | 0 | 18581.6207 | 0 | 1 | Finished | 20492.0508 | 20492.0508 | C2013-11 Recreation Complex.xlsx
102 | 231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 | 2012-04-16 08:00 | 10d | 3240.6299 | 0 | 0 | 28144.6504 | 0 | 31385.2803 | 0 | 1 | Finished | 3240.6299 | 3240.6299 | C2013-11 Recreation Complex.xlsx
103 | 222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 | 2012-04-16 08:00 | 10d | 8228.6904 | 0 | 0 | -1969.04 | 0 | 6259.6504 | 0 | 1 | Finished | 8228.6904 | 8228.6904 | C2013-11 Recreation Complex.xlsx
104 | 233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 77d | [5 empty] | 780586.304 |  | 1 |  | 745162.4451 | 745162.4451 | C2013-11 Recreation Complex.xlsx
105 | 232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 | 2012-03-05 08:00 | 2d | 231412.7969 | 0 | 0 | -2215.8 | 0 | 229196.9968 | 0 | 1 | Finished | 231412.7969 | 231412.7969 | C2013-11 Recreation Complex.xlsx
106 | 234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 | 2012-03-09 08:00 | 1d | 3903.4399 | 0 | 0 | 12196.1104 | 0 | 16099.5503 | 0 | 1 | Finished | 3903.4399 | 3903.4399 | C2013-11 Recreation Complex.xlsx
107 | 235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-26 08:00 | 5d | 1142.8 | 0 | 0 | 1064.3101 | 0 | 2207.1101 | 0 | 1 | Finished | 1142.8 | 1142.8 | C2013-11 Recreation Complex.xlsx
108 | 236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 | 2012-04-02 08:00 | 12d | 139561.8125 | 0 | 0 | -13492.6201 | 0 | 126069.1924 | 0 | 1 | Finished | 139561.8125 | 139561.8125 | C2013-11 Recreation Complex.xlsx
109 | 237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-01-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-11 Recreation Complex.xlsx
110 | 238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 | 2012-04-04 08:00 | 3d | 41378.1406 | 0 | 0 | 10415.5098 | 0 | 51793.6504 | 0 | 1 | Finished | 41378.1406 | 41378.1406 | C2013-11 Recreation Complex.xlsx
111 | 239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 | 2012-03-12 08:00 | 10d | 138237.1406 | 0 | 0 | -405.28 | 0 | 137831.8606 | 0 | 1 | Finished | 138237.1406 | 138237.1406 | C2013-11 Recreation Complex.xlsx
112 | 240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 | 2012-03-26 08:00 | 10d | 133165.9844 | 0 | 0 | 16769.0391 | 0 | 149935.0234 | 0 | 1 | Finished | 133165.9844 | 133165.9844 | C2013-11 Recreation Complex.xlsx
113 | 241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 2012-03-12 08:00 | 10d | 26881.5098 | 0 | 0 | -1315.21 | 0 | 25566.2998 | 0 | 1 | Finished | 26881.5098 | 26881.5098 | C2013-11 Recreation Complex.xlsx
114 | 242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 | 2012-04-02 08:00 | 3d | 29478.8203 | 0 | 0 | 12407.7998 | 0 | 41886.6201 | 0 | 1 | Finished | 29478.8203 | 29478.8203 | C2013-11 Recreation Complex.xlsx
115 | 75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 25d | [5 empty] | 6677.9701 |  | 1 |  | 7090.1001 | 7090.1001 | C2013-11 Recreation Complex.xlsx
116 | 76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 | 2012-04-19 08:00 | 25d | 7090.1001 | 0 | 0 | -412.13 | 0 | 6677.9701 | 0 | 1 | Finished | 7090.1001 | 7090.1001 | C2013-11 Recreation Complex.xlsx
117 | 77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 36d | [5 empty] | 6374.4202 |  | 1 |  | 6767.8202 | 6767.8202 | C2013-11 Recreation Complex.xlsx
118 | 78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 | 2012-04-24 08:00 | 15d | 4834.1602 | 0 | 0 | -281 | 0 | 4553.1602 | 0 | 1 | Finished | 4834.1602 | 4834.1602 | C2013-11 Recreation Complex.xlsx
119 | 79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 | 2012-03-23 08:00 | 6d | 1933.66 | 0 | 0 | -112.4 | 0 | 1821.26 | 0 | 1 | Finished | 1933.66 | 1933.66 | C2013-11 Recreation Complex.xlsx
120 | 89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 30d | [5 empty] | 39603.4387 |  | 1 |  | 39567.9688 | 39567.9688 | C2013-11 Recreation Complex.xlsx
121 | 90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 | 2012-08-01 08:00 | 30d | 35453.8789 | 0 | 0 | 18.67 | 0 | 35472.5489 | 0 | 1 | Finished | 35453.8789 | 35453.8789 | C2013-11 Recreation Complex.xlsx
122 | 91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 | 2012-08-01 08:00 | 25d | 4114.0898 | 0 | 0 | 16.8 | 0 | 4130.8898 | 0 | 1 | Finished | 4114.0898 | 4114.0898 | C2013-11 Recreation Complex.xlsx
123 | 92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 10d | [5 empty] | 25566.2998 |  | 1 |  | 26881.5098 | 26881.5098 | C2013-11 Recreation Complex.xlsx
124 | 93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 2012-06-19 08:00 | 10d | 26881.5098 | 0 | 0 | -1315.21 | 0 | 25566.2998 | 0 | 1 | Finished | 26881.5098 | 26881.5098 | C2013-11 Recreation Complex.xlsx
125 | 94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 20d | [5 empty] | 4582.41 |  | 1 |  | 4571.21 | 4571.21 | C2013-11 Recreation Complex.xlsx
126 | 95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-09-05 08:00 | 8d | 1828.48 | 0 | 0 | 0 | 0 | 1828.48 | 0 | 1 | Finished | 1828.48 | 1828.48 | C2013-11 Recreation Complex.xlsx
127 | 96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 | 2012-08-20 08:00 | 12d | 2742.73 | 0 | 0 | 11.2 | 0 | 2753.93 | 0 | 1 | Finished | 2742.73 | 2742.73 | C2013-11 Recreation Complex.xlsx
128 | 97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 19d | [5 empty] | 11459.6499 |  | 1 |  | 11507.1699 | 11507.1699 | C2013-11 Recreation Complex.xlsx
129 | 98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 | 2012-09-12 08:00 | 2d | 5376.2998 | 0 | 0 | 0 | 0 | 5376.2998 | 0 | 1 | Finished | 5376.2998 | 5376.2998 | C2013-11 Recreation Complex.xlsx
130 | 99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 | 2012-08-20 08:00 | 12d | 6130.8701 | 0 | 0 | -47.52 | 0 | 6083.3501 | 0 | 1 | Finished | 6130.8701 | 6130.8701 | C2013-11 Recreation Complex.xlsx
131 | 100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 26d | [5 empty] | 43167.8701 |  | 1 |  | 55882.5703 | 55882.5703 | C2013-11 Recreation Complex.xlsx
132 | 101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 | 2012-04-02 08:00 | 26d | 55882.5703 | 0 | 0 | -12714.7002 | 0 | 43167.8701 | 0 | 1 | Finished | 55882.5703 | 55882.5703 | C2013-11 Recreation Complex.xlsx
133 | 102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 52d | [5 empty] | 24536.7697 |  | 1 |  | 24596.2197 | 24596.2197 | C2013-11 Recreation Complex.xlsx
134 | 103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 | 2012-06-18 08:00 | 14d | 10760.8496 | 0 | 0 | -26.01 | 0 | 10734.8396 | 0 | 1 | Finished | 10760.8496 | 10760.8496 | C2013-11 Recreation Complex.xlsx
135 | 104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 | 2012-08-24 08:00 | 18d | 13835.3701 | 0 | 0 | -33.44 | 0 | 13801.9301 | 0 | 1 | Finished | 13835.3701 | 13835.3701 | C2013-11 Recreation Complex.xlsx
136 | 105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 25d | [5 empty] | 27569.3699 |  | 1 |  | 26429.0898 | 26429.0898 | C2013-11 Recreation Complex.xlsx
137 | 106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 | 2012-05-10 08:00 | 25d | 26429.0898 | 0 | 0 | 1140.28 | 0 | 27569.3699 | 0 | 1 | Finished | 26429.0898 | 26429.0898 | C2013-11 Recreation Complex.xlsx
138 | 107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 10d | [5 empty] | 11027.7596 |  | 1 |  | 10571.6396 | 10571.6396 | C2013-11 Recreation Complex.xlsx
139 | 108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 | 2012-08-20 08:00 | 5d | 5285.8198 | 0 | 0 | 228.06 | 0 | 5513.8798 | 0 | 1 | Finished | 5285.8198 | 5285.8198 | C2013-11 Recreation Complex.xlsx
140 | 109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 | 2012-08-13 08:00 | 5d | 5285.8198 | 0 | 0 | 228.06 | 0 | 5513.8798 | 0 | 1 | Finished | 5285.8198 | 5285.8198 | C2013-11 Recreation Complex.xlsx
141 | 110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 62d | [5 empty] | 32030.2609 |  | 1 |  | 82765.0089 | 82765.0089 | C2013-11 Recreation Complex.xlsx
142 | 111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 | 2012-06-11 08:00 | 25d | 21143.2695 | 0 | 0 | 912.22 | 0 | 22055.4895 | 0 | 1 | Finished | 21143.2695 | 21143.2695 | C2013-11 Recreation Complex.xlsx
143 | 112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 | 2012-06-25 08:00 | 5d | 10003.6396 | 0 | 0 | -8856.1699 | 0 | 1147.4697 | 0 | 1 | Finished | 10003.6396 | 10003.6396 | C2013-11 Recreation Complex.xlsx
144 | 264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-07-02 08:00 | 7d | 1599.92 | 0 | 0 | 1490.03 | 0 | 3089.9501 | 0 | 1 | Finished | 1599.92 | 1599.92 | C2013-11 Recreation Complex.xlsx
145 | 113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 | 2012-08-22 08:00 | 25d | 50018.1797 | 0 | 0 | -44280.8281 | 0 | 5737.3516 | 0 | 1 | Finished | 50018.1797 | 50018.1797 | C2013-11 Recreation Complex.xlsx
146 | 114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 10d | [5 empty] | 3671.8901 |  | 1 |  | 3656.9601 | 3656.9601 | C2013-11 Recreation Complex.xlsx
147 | 115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 2012-08-22 08:00 | 10d | 2285.6001 | 0 | 0 | 9.33 | 0 | 2294.9301 | 0 | 1 | Finished | 2285.6001 | 2285.6001 | C2013-11 Recreation Complex.xlsx
148 | 116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 | 2012-08-27 08:00 | 6d | 1371.36 | 0 | 0 | 5.6 | 0 | 1376.96 | 0 | 1 | Finished | 1371.36 | 1371.36 | C2013-11 Recreation Complex.xlsx
149 | 117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 19d | [5 empty] | 13655.32 |  | 1 |  | 13634.25 | 13634.25 | C2013-11 Recreation Complex.xlsx
150 | 118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 | 2012-08-22 08:00 | 19d | 13634.25 | 0 | 0 | 21.07 | 0 | 13655.32 | 0 | 1 | Finished | 13634.25 | 13634.25 | C2013-11 Recreation Complex.xlsx
151 | 119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 3d | [5 empty] | 14488.25 |  | 1 |  | 14488.25 | 14488.25 | C2013-11 Recreation Complex.xlsx
152 | 120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 | 2012-09-18 08:00 | 3d | 14488.25 | 0 | 0 | 0 | 0 | 14488.25 | 0 | 1 | Finished | 14488.25 | 14488.25 | C2013-11 Recreation Complex.xlsx
153 | 121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 175d | [5 empty] | 915758.9489 |  | 1 |  | 899608.939 | 811201.2708 | C2013-11 Recreation Complex.xlsx
154 | 122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 2011-12-01 08:00 | 17d | 24822.4199 | 0 | 0 | -1573 | 0 | 23249.4199 | 0 | 1 | Finished | 24822.4199 | 24822.4199 | C2013-11 Recreation Complex.xlsx
155 | 123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 2011-12-01 08:00 | 17d | 3885.53 | 0 | 0 | 15.87 | 0 | 3901.4 | 0 | 1 | Finished | 3885.53 | 3885.53 | C2013-11 Recreation Complex.xlsx
156 | 124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 2012-01-09 08:00 | 10d | 2285.6001 | 0 | 0 | 9.33 | 0 | 2294.9301 | 0 | 1 | Finished | 2285.6001 | 2285.6001 | C2013-11 Recreation Complex.xlsx
157 | 125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 1 | Finished | 1828.48 | 1828.48 | C2013-11 Recreation Complex.xlsx
158 | 126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 2011-12-01 08:00 | 8d | 5185.0098 | 0 | 0 | -3066.97 | 0 | 2118.0398 | 0 | 1 | Finished | 5185.0098 | 5185.0098 | C2013-11 Recreation Complex.xlsx
159 | 127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 1 | Finished | 1828.48 | 1828.48 | C2013-11 Recreation Complex.xlsx
160 | 243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 1 | Finished | 1828.48 | 1828.48 | C2013-11 Recreation Complex.xlsx
161 | 244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 | 2012-02-13 08:00 | 20d | 38626.6719 | 0 | 0 | -3355.99 | 0 | 35270.6819 | 0 | 1 | Finished | 38626.6719 | 38626.6719 | C2013-11 Recreation Complex.xlsx
162 | 245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 | 2012-03-12 08:00 | 10d | 85207.8281 | 0 | 0 | 8332.1104 | 0 | 93539.9385 | 0 | 1 | Finished | 85207.8281 | 0 | C2013-11 Recreation Complex.xlsx
163 | 246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2011-12-01 08:00 | 10d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 1 | Finished | 1828.48 | 1828.48 | C2013-11 Recreation Complex.xlsx
164 | 247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-03-26 08:00 | 15d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 1 | Finished | 1828.48 | 1828.48 | C2013-11 Recreation Complex.xlsx
165 | 248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 | 2012-03-26 08:00 | 12d | 214498.8438 | 0 | 0 | -3890.1699 | 0 | 210608.6738 | 0 | 1 | Finished | 214498.8438 | 214498.8438 | C2013-11 Recreation Complex.xlsx
166 | 249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-12 08:00 | 9d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 1 | Finished | 1828.48 | 1828.48 | C2013-11 Recreation Complex.xlsx
167 | 250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-12 08:00 | 6d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 1 | Finished | 1828.48 | 1828.48 | C2013-11 Recreation Complex.xlsx
168 | 251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-20 08:00 | 10d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 1 | Finished | 1828.48 | 1828.48 | C2013-11 Recreation Complex.xlsx
169 | 252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 | 2012-04-20 08:00 | 8d | 2880.76 | 0 | 0 | 413.66 | 0 | 3294.42 | 0 | 1 | Finished | 2880.76 | 2880.76 | C2013-11 Recreation Complex.xlsx
170 | 253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 | 2012-05-03 08:00 | 9d | 214560.4219 | 0 | 0 | -3951.75 | 0 | 210608.6719 | 0 | 1 | Finished | 214560.4219 | 214560.4219 | C2013-11 Recreation Complex.xlsx
171 | 254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-05-03 08:00 | 9d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 1 | Finished | 1828.48 | 1828.48 | C2013-11 Recreation Complex.xlsx
172 | 255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-05-16 08:00 | 10d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 1 | Finished | 1828.48 | 1828.48 | C2013-11 Recreation Complex.xlsx
173 | 256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-06-01 08:00 | 10d | 1599.92 | 0 | 0 | 6.53 | 0 | 1606.45 | 0 | 1 | Finished | 1599.92 | 1599.92 | C2013-11 Recreation Complex.xlsx
174 | 257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-06-15 08:00 | 10d | 1599.92 | 0 | 0 | 6.53 | 0 | 1606.45 | 0 | 1 | Finished | 1599.92 | 1599.92 | C2013-11 Recreation Complex.xlsx
175 | 258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 | 2012-06-29 08:00 | 30d | 58330.2695 | 0 | 0 | 6671.98 | 0 | 65002.2495 | 0 | 1 | Finished | 58330.2695 | 58330.2695 | C2013-11 Recreation Complex.xlsx
176 | 259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 | 2012-05-07 08:00 | 15d | 6831.02 | 0 | 0 | 21343.1895 | 0 | 28174.2095 | 0 | 1 | Finished | 6831.02 | 6831.02 | C2013-11 Recreation Complex.xlsx
177 | 260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 | 2012-06-01 08:00 | 10d | 188607.2344 | 0 | 0 | -3048.48 | 0 | 185558.7544 | 0 | 1 | Finished | 188607.2344 | 188607.2344 | C2013-11 Recreation Complex.xlsx
178 | 261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 | 2012-06-29 08:00 | 20d | 29202.8496 | 0 | 0 | -1850.59 | 0 | 27352.2596 | 0 | 1 | Finished | 29202.8496 | 29202.8496 | C2013-11 Recreation Complex.xlsx
179 | 262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-08-17 08:00 | 3d | 1599.92 | 0 | 0 | 6.53 | 0 | 1606.45 | 0 | 1 | Finished | 1599.92 | 0 | C2013-11 Recreation Complex.xlsx
180 | 263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-08-22 08:00 | 10d | 1599.92 | 0 | 0 | 6.53 | 0 | 1606.45 | 0 | 1 | Finished | 1599.92 | 0 | C2013-11 Recreation Complex.xlsx
181 | 130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 35d | [5 empty] | 383185.069 |  | 1 |  | 386283.059 | 386283.059 | C2013-11 Recreation Complex.xlsx
182 | 131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2012-03-01 08:00 | 5d | 1761.99 | 0 | 0 | 297.02 | 0 | 2059.01 | 0 | 1 | Finished | 1761.99 | 1761.99 | C2013-11 Recreation Complex.xlsx
183 | 132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-12 08:00 | 5d | 1142.8 | 0 | 0 | 4.67 | 0 | 1147.47 | 0 | 1 | Finished | 1142.8 | 1142.8 | C2013-11 Recreation Complex.xlsx
184 | 133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 | 2012-03-19 08:00 | 10d | 34647.6914 | 0 | 0 | 17.69 | 0 | 34665.3814 | 0 | 1 | Finished | 34647.6914 | 34647.6914 | C2013-11 Recreation Complex.xlsx
185 | 134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 | 2012-04-02 08:00 | 5d | 1611.39 | 0 | 0 | -93.67 | 0 | 1517.72 | 0 | 1 | Finished | 1611.39 | 1611.39 | C2013-11 Recreation Complex.xlsx
186 | 135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 | 2012-04-17 08:00 | 3d | 347119.1875 | 0 | 0 | -3323.7 | 0 | 343795.4875 | 0 | 1 | Finished | 347119.1875 | 347119.1875 | C2013-11 Recreation Complex.xlsx
187 | 136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 109d | [5 empty] | 593362.8701 |  | 1 |  | 594749.1602 | 594749.1602 | C2013-11 Recreation Complex.xlsx
188 | 137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 109d | [5 empty] | 269455.4231 |  | 1 |  | 270794.9531 | 270794.9531 | C2013-11 Recreation Complex.xlsx
189 | 138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 | 2012-03-01 08:00 | 65d | 79701.2578 | 0 | 0 | -617.71 | 0 | 79083.5478 | 0 | 1 | Finished | 79701.2578 | 79701.2578 | C2013-11 Recreation Complex.xlsx
190 | 139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 | 2012-05-07 08:00 | 42d | 74182.2734 | 0 | 0 | -516.37 | 0 | 73665.9034 | 0 | 1 | Finished | 74182.2734 | 74182.2734 | C2013-11 Recreation Complex.xlsx
191 | 140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 | 2012-06-26 08:00 | 30d | 116911.4219 | 0 | 0 | -205.45 | 0 | 116705.9719 | 0 | 1 | Finished | 116911.4219 | 116911.4219 | C2013-11 Recreation Complex.xlsx
192 | 141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 109d | [5 empty] | 139148.1781 |  | 1 |  | 139110.0781 | 139110.0781 | C2013-11 Recreation Complex.xlsx
193 | 142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 65d | 14856.4297 | 0 | 0 | 60.67 | 0 | 14917.0997 | 0 | 1 | Finished | 14856.4297 | 14856.4297 | C2013-11 Recreation Complex.xlsx
194 | 143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 | 2012-05-07 08:00 | 42d | 32282.5391 | 0 | 0 | -78.03 | 0 | 32204.5091 | 0 | 1 | Finished | 32282.5391 | 32282.5391 | C2013-11 Recreation Complex.xlsx
195 | 144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 | 2012-06-26 08:00 | 30d | 91971.1094 | 0 | 0 | 55.46 | 0 | 92026.5694 | 0 | 1 | Finished | 91971.1094 | 91971.1094 | C2013-11 Recreation Complex.xlsx
196 | 145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 109d | [5 empty] | 139148.1781 |  | 1 |  | 139110.0781 | 139110.0781 | C2013-11 Recreation Complex.xlsx
197 | 146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 65d | 14856.4297 | 0 | 0 | 60.67 | 0 | 14917.0997 | 0 | 1 | Finished | 14856.4297 | 14856.4297 | C2013-11 Recreation Complex.xlsx
198 | 147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 | 2012-05-07 08:00 | 42d | 32282.5391 | 0 | 0 | -78.03 | 0 | 32204.5091 | 0 | 1 | Finished | 32282.5391 | 32282.5391 | C2013-11 Recreation Complex.xlsx
199 | 148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 | 2012-06-26 08:00 | 30d | 91971.1094 | 0 | 0 | 55.46 | 0 | 92026.5694 | 0 | 1 | Finished | 91971.1094 | 91971.1094 | C2013-11 Recreation Complex.xlsx
200 | 149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 25d | [5 empty] | 45611.0908 |  | 1 |  | 45734.0508 | 45734.0508 | C2013-11 Recreation Complex.xlsx
201 | 150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 | 2012-05-29 08:00 | 15d | 18175.6309 | 0 | 0 | -73.78 | 0 | 18101.8509 | 0 | 1 | Finished | 18175.6309 | 18175.6309 | C2013-11 Recreation Complex.xlsx
202 | 151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 | 2012-06-19 08:00 | 10d | 27558.4199 | 0 | 0 | -49.18 | 0 | 27509.2399 | 0 | 1 | Finished | 27558.4199 | 27558.4199 | C2013-11 Recreation Complex.xlsx
203 | 152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 88d | [5 empty] | 2657.07 |  | 1 |  | 1142.8 | 1142.8 | C2013-11 Recreation Complex.xlsx
204 | 153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-04-19 08:00 | 2d | 457.12 | 0 | 0 | 1514.27 | 0 | 1971.39 | 0 | 1 | Finished | 457.12 | 457.12 | C2013-11 Recreation Complex.xlsx
205 | 154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-09-12 08:00 | 2d | 457.12 | 0 | 0 | 0 | 0 | 457.12 | 0 | 1 | Finished | 457.12 | 457.12 | C2013-11 Recreation Complex.xlsx
206 | 155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-09-12 08:00 | 1d | 228.56 | 0 | 0 | 0 | 0 | 228.56 | 0 | 1 | Finished | 228.56 | 228.56 | C2013-11 Recreation Complex.xlsx
207 | 156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 21d | [5 empty] | 20951.5502 |  | 1 |  | 17500.3502 | 17500.3502 | C2013-11 Recreation Complex.xlsx
208 | 157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 | 2012-09-21 08:00 | 2d | 450.5 | 0 | 0 | 0 | 0 | 450.5 | 0 | 1 | Finished | 450.5 | 450.5 | C2013-11 Recreation Complex.xlsx
209 | 158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 | 2012-09-18 08:00 | 3d | 735.65 | 0 | 0 | 0 | 0 | 735.65 | 0 | 1 | Finished | 735.65 | 735.65 | C2013-11 Recreation Complex.xlsx
210 | 159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 | 2012-09-07 08:00 | 10d | 675.75 | 0 | 0 | 0 | 0 | 675.75 | 0 | 1 | Finished | 675.75 | 675.75 | C2013-11 Recreation Complex.xlsx
211 | 160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 | 2012-08-28 08:00 | 20d | 15413.2002 | 0 | 0 | 3451.2 | 0 | 18864.4001 | 0 | 1 | Finished | 15413.2002 | 15413.2002 | C2013-11 Recreation Complex.xlsx
212 | 161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 | 2012-09-25 08:00 | 1d | 225.25 | 0 | 0 | 0 | 0 | 225.25 | 0 | 1 | Finished | 225.25 | 225.25 | C2013-11 Recreation Complex.xlsx
4 | 0 | Young Cattle Barn | 2010-09-08 08:00 | 2011-03-07 17:00 | 115d |  |  | 818439.9918 |  |  | 818439.9918 |  | 188d | [5 empty] | 879853.1711 |  | 1 |  | 818439.9918 | 818439.9918 | C2013-12 Young Cattle Barn.xlsx
5 | 1 | Begin | 2010-09-08 08:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-12 Young Cattle Barn.xlsx
6 | 2 | Werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 12659.2598 | 0 | 0 | 12659.2598 | 2010-09-08 08:00 | 10d | 12659.2598 | 0 | 0 | 9272.8896 | 0 | 21932.1494 | 0 | 1 | Finished | 12659.2598 | 12659.2598 | C2013-12 Young Cattle Barn.xlsx
7 | 3 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 7491.3901 | 0 | 0 | 7491.3901 | 2010-09-13 08:00 | 15d | 7491.3901 | 0 | 0 | 486.36 | 0 | 7977.7501 | 0 | 1 | Finished | 7491.3901 | 7491.3901 | C2013-12 Young Cattle Barn.xlsx
8 | 31 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-28 17:00 | 15d |  | 0 | 22474.1797 | 0 | 0 | 22474.1797 | 2010-11-29 09:00 | 15d | 22474.1797 | 0 | 0 | 1459.09 | 0 | 23933.2697 | 0 | 1 | Finished | 22474.1797 | 22474.1797 | C2013-12 Young Cattle Barn.xlsx
9 | 5 | Omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 26412.5801 | 0 | 0 | 26412.5801 | 2010-09-13 08:00 | 3d | 26412.5801 | 0 | 0 | -383.98 | 0 | 26028.6001 | 0 | 1 | Finished | 26412.5801 | 26412.5801 | C2013-12 Young Cattle Barn.xlsx
10 | 6 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 14850.3096 | 0 | 0 | 14850.3096 | 2010-09-30 08:00 | 4d | 14850.3096 | 0 | 0 | 15026.79 | 0 | 29877.0996 | 0 | 1 | Finished | 14850.3096 | 14850.3096 | C2013-12 Young Cattle Barn.xlsx
11 | 7 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 7491.3901 | 0 | 0 | 7491.3901 | 2010-12-20 08:00 | 3d | 7491.3901 | 0 | 0 | 486.36 | 0 | 7977.7501 | 0 | 1 | Finished | 7491.3901 | 7491.3901 | C2013-12 Young Cattle Barn.xlsx
12 | 8 | Plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 31783.8691 | 0 | 0 | 31783.8691 | 2010-10-14 08:00 | 8d | 31783.8691 | 0 | 0 | 8289.5596 | 0 | 40073.4287 | 0 | 1 | Finished | 31783.8691 | 31783.8691 | C2013-12 Young Cattle Barn.xlsx
13 | 9 | Funderingswanden | 2010-10-06 08:00 | 2010-11-03 17:00 | 20d |  | 0 | 118171.1719 | 0 | 0 | 118171.1719 | 2010-11-02 08:00 | 17d | 118171.1719 | 0 | 0 | 19921.3809 | 0 | 138092.5527 | 0 | 1 | Finished | 118171.1719 | 118171.1719 | C2013-12 Young Cattle Barn.xlsx
14 | 10 | Draagvloeren | 2010-11-04 08:00 | 2010-11-19 17:00 | 10d |  | 0 | 63201.1914 | 0 | 0 | 63201.1914 | 2011-01-17 08:00 | 5d | 63201.1914 | 0 | 0 | 9287.6299 | 0 | 72488.8213 | 0 | 1 | Finished | 63201.1914 | 63201.1914 | C2013-12 Young Cattle Barn.xlsx
15 | 11 | Wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 437.87 | 0 | 0 | 437.87 | 2011-02-14 08:00 | 5d | 437.87 | 0 | 0 | 819.02 | 0 | 1256.89 | 0 | 1 | Finished | 437.87 | 437.87 | C2013-12 Young Cattle Barn.xlsx
16 | 12 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 9987.6201 | 0 | 0 | 9987.6201 | 2011-03-07 08:00 | 10d | 9987.6201 | 0 | 0 | -667.76 | 0 | 9319.8601 | 0 | 1 | Finished | 9987.6201 | 9987.6201 | C2013-12 Young Cattle Barn.xlsx
17 | 32 | Betonnen binnenwanden | 2010-12-01 08:00 | 2010-12-07 17:00 | 5d |  | 0 | 3145.8401 | 0 | 0 | 3145.8401 | 2011-03-21 08:00 | 10d | 3145.8401 | 0 | 0 | 1512.4 | 0 | 4658.2401 | 0 | 1 | Finished | 3145.8401 | 3145.8401 | C2013-12 Young Cattle Barn.xlsx
18 | 14 | Wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 6072.3398 | 0 | 0 | 6072.3398 | 2011-02-14 08:00 | 5d | 6072.3398 | 0 | 0 | 3096.29 | 0 | 9168.6299 | 0 | 1 | Finished | 6072.3398 | 6072.3398 | C2013-12 Young Cattle Barn.xlsx
19 | 15 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 80027.8281 | 0 | 0 | 80027.8281 | 2011-02-21 08:00 | 10d | 80027.8281 | 0 | 0 | 1958.91 | 0 | 81986.7382 | 0 | 1 | Finished | 80027.8281 | 80027.8281 | C2013-12 Young Cattle Barn.xlsx
20 | 16 | Structuurelementen-gewapend beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 86174.0078 | 0 | 0 | 86174.0078 | 2011-03-07 08:00 | 5d | 86174.0078 | 0 | 0 | 19825.5098 | 0 | 105999.5176 | 0 | 1 | Finished | 86174.0078 | 86174.0078 | C2013-12 Young Cattle Barn.xlsx
21 | 33 | Dakstructuur | 2010-12-01 08:00 | 2010-12-07 17:00 | 5d |  | 0 | 24820.1094 | 0 | 0 | 24820.1094 | 2011-03-21 08:00 | 5d | 24820.1094 | 0 | 0 | -4538.8599 | 0 | 20281.2495 | 0 | 1 | Finished | 24820.1094 | 24820.1094 | C2013-12 Young Cattle Barn.xlsx
22 | 18 | Dakwerken | 2010-12-20 08:00 | 2011-01-17 17:00 | 10d |  | 0 | 60579.8086 | 0 | 0 | 60579.8086 | 2011-04-22 08:00 | 6d | 60579.8086 | 0 | 0 | -11716.2402 | 0 | 48863.5684 | 0 | 1 | Finished | 60579.8086 | 60579.8086 | C2013-12 Young Cattle Barn.xlsx
23 | 19 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 15649.6699 | 0 | 0 | 15649.6699 | 2011-04-14 08:00 | 4d | 15649.6699 | 0 | 0 | -990.37 | 0 | 14659.2999 | 0 | 1 | Finished | 15649.6699 | 15649.6699 | C2013-12 Young Cattle Barn.xlsx
24 | 20 | Gevelbekledingen | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 24598.5195 | 0 | 0 | 24598.5195 | 2011-05-04 08:00 | 9d | 24598.5195 | 0 | 0 | -4432.9502 | 0 | 20165.5693 | 0 | 1 | Finished | 24598.5195 | 24598.5195 | C2013-12 Young Cattle Barn.xlsx
25 | 34 | Elektrische windzeilen | 2011-02-01 08:00 | 2011-02-14 17:00 | 10d |  | 0 | 7995.0898 | 0 | 0 | 7995.0898 | 2011-05-16 08:00 | 5d | 7995.0898 | 0 | 0 | -956.18 | 0 | 7038.9099 | 0 | 1 | Finished | 7995.0898 | 7995.0898 | C2013-12 Young Cattle Barn.xlsx
26 | 35 | Poort melkveestal | 2011-02-01 08:00 | 2011-02-21 17:00 | 15d |  | 0 | 20107.6797 | 0 | 0 | 20107.6797 | 2011-05-16 08:00 | 15d | 20107.6797 | 0 | 0 | -1485.5601 | 0 | 18622.1196 | 0 | 1 | Finished | 20107.6797 | 20107.6797 | C2013-12 Young Cattle Barn.xlsx
27 | 23 | Rioleringen | 2011-01-25 08:00 | 2011-02-07 17:00 | 10d |  | 0 | 35762.7383 | 0 | 0 | 35762.7383 | 2011-05-11 08:00 | 15d | 35762.7383 | 0 | 0 | -1731.51 | 0 | 34031.2283 | 0 | 1 | Finished | 35762.7383 | 35762.7383 | C2013-12 Young Cattle Barn.xlsx
28 | 24 | Omgevingswerken | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 30891.0898 | 0 | 0 | 30891.0898 | 2011-06-01 08:00 | 10d | 30891.0898 | 0 | 0 | 7693.5698 | 0 | 38584.6597 | 0 | 1 | Finished | 30891.0898 | 30891.0898 | C2013-12 Young Cattle Barn.xlsx
29 | 26 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 2350.3601 | 0 | 0 | 2350.3601 | 2011-06-01 08:00 | 5d | 2350.3601 | 0 | 0 | -359.45 | 0 | 1990.9101 | 0 | 1 | Finished | 2350.3601 | 2350.3601 | C2013-12 Young Cattle Barn.xlsx
30 | 27 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 58538.5391 | 0 | 0 | 58538.5391 | 2011-05-04 08:00 | 10d | 58538.5391 | 0 | 0 | 2709.6101 | 0 | 61248.1492 | 0 | 1 | Finished | 58538.5391 | 58538.5391 | C2013-12 Young Cattle Barn.xlsx
31 | 28 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 45095.5898 | 0 | 0 | 45095.5898 | 2011-05-11 08:00 | 15d | 45095.5898 | 0 | 0 | -13169.3301 | 0 | 31926.2598 | 0 | 1 | Finished | 45095.5898 | 45095.5898 | C2013-12 Young Cattle Barn.xlsx
32 | 29 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 1669.95 | 0 | 0 | 1669.95 | 2011-05-11 08:00 | 15d | 1669.95 | 0 | 0 | 0 | 0 | 1669.95 | 0 | 1 | Finished | 1669.95 | 1669.95 | C2013-12 Young Cattle Barn.xlsx
33 | 30 | Einde | 2011-03-07 17:00 | 2011-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2013-12 Young Cattle Barn.xlsx
4 | 0 | Office Finishing Works (1) | 2010-08-02 08:00 | 2011-06-27 17:00 | 236d |  |  | 0 |  |  | 1118496.5927 |  | 217d | [5 empty] | 955929.2243 |  | 1 |  | 1118496.5927 | 1117403.7126 | C2013-13 Office Finishing Works (1).xlsx
5 | 3 | Diversen | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 21.87 | 15221.5206 | 15221.5206 | 2010-08-02 08:00 | 87d | 15221.5206 | 0 | 0 | -3280.3701 | 0 | 11941.1505 | 0 | 1 | Finished | 15221.5206 | 15221.5206 | C2013-13 Office Finishing Works (1).xlsx
6 | 10 | Regiewerken | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 1.62 | 1127.52 | 1127.52 | 2011-04-01 08:00 | 21d | 272.16 | 0 | 0 | 661.96 | 0 | 934.12 | 0 | 1 | Finished | 1127.52 | 1127.52 | C2013-13 Office Finishing Works (1).xlsx
7 | 11 | Zuivere OA (1) | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 3.54 | 2463.84 | 2463.84 | 2011-01-17 08:00 | 87d | 2463.84 | 0 | 0 | -317.37 | 0 | 2146.47 | 0 | 1 | Finished | 2463.84 | 2463.84 | C2013-13 Office Finishing Works (1).xlsx
8 | 4 | Zuivere OA (2) | 2010-08-02 08:00 | 2010-12-31 17:00 | 110d |  | 0 | 0 | 42.43 | 37338.4003 | 37338.4003 | 2010-09-01 08:00 | 110d | 37338.4003 | 0 | 0 | -10607.8301 | 0 | 26730.5702 | 0 | 1 | Finished | 37338.4003 | 37338.4003 | C2013-13 Office Finishing Works (1).xlsx
9 | 1 | Verplaatsbare wanden (1) | 2010-09-01 08:00 | 2011-01-21 17:00 | 103d |  | 0 | 0 | 1144.79 | 943306.9922 | 943306.9922 | 2010-08-02 08:00 | 103d | 943306.9922 | 0 | 0 | -130851.0781 | 0 | 812455.9141 | 0 | 1 | Finished | 943306.9922 | 943306.9922 | C2013-13 Office Finishing Works (1).xlsx
10 | 5 | Coördinatie OA | 2010-09-02 08:00 | 2010-12-22 17:00 | 80d |  | 0 | 0 | 0.34 | 217.6 | 217.6 | 2011-05-02 08:00 | 22d | 59.84 | 0 | 0 | 103.18 | 0 | 163.02 | 0 | 1 | Finished | 217.6 | 217.6 | C2013-13 Office Finishing Works (1).xlsx
11 | 2 | Verplaatsbare wanden (2) | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 0 | 5571.5298 | 44572.2383 | 44572.2383 | 2010-08-31 08:00 | 1d | 44572.2383 | 0 | 0 | -5120.0801 | 0 | 39452.1582 | 0 | 1 | Finished | 44572.2383 | 44572.2383 | C2013-13 Office Finishing Works (1).xlsx
12 | 6 | Coördinatie opmerkingen | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 166.77 | 64039.6816 | 64039.6816 | 2010-12-01 08:00 | 20d | 26683.2007 | 0 | 0 | 26618.7207 | 0 | 53301.9214 | 0 | 1 | Finished | 64039.6816 | 64039.6816 | C2013-13 Office Finishing Works (1).xlsx
13 | 8 | Systeemwanden | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 20.88 | 8017.9197 | 8017.9197 | 2011-05-02 08:00 | 22d | 3674.8799 | 0 | 0 | 3318.8501 | 0 | 6993.7299 | 0 | 1 | Finished | 8017.9197 | 8017.9197 | C2013-13 Office Finishing Works (1).xlsx
14 | 9 | Opmerkingen | 2011-03-30 08:00 | 2011-04-01 17:00 | 3d |  | 0 | 0 | 31.37 | 752.88 | 752.88 | 2011-04-01 08:00 | 3d | 752.88 | 0 | 0 | -131.31 | 0 | 621.57 | 0 | 1 | Finished | 752.88 | 752.88 | C2013-13 Office Finishing Works (1).xlsx
15 | 7 | Verplaatsbare wanden (3) | 2011-05-24 08:00 | 2011-06-27 17:00 | 25d |  | 0 | 0 | 7.19 | 1438 | 1438 | 2011-05-02 08:00 | 22d | 1265.44 | 0 | 0 | -76.84 | 0 | 1188.6 | 0 | 1 | Finished | 1438 | 345.12 | C2013-13 Office Finishing Works (1).xlsx
4 | 0 | Office Finishing Works (2) | 2011-02-14 08:00 | 2011-06-03 17:00 | 80d |  |  | 85847.8889 |  |  | 85847.8889 |  | 88d | [5 empty] | 75468.2987 |  | 1 |  | 85847.8889 | 85847.8889 | C2013-14 Office Finishing Works (2).xlsx
5 | 1 | Verplaatsbare wanden (1) | 2011-02-14 08:00 | 2011-02-14 17:00 | 1d |  | 0 | 3325.21 | 0 | 0 | 3325.21 | 2011-03-01 08:00 | 1d | 3325.21 | 0 | 0 | -271.73 | 0 | 3053.4799 | 0 | 1 | Finished | 3325.21 | 3325.21 | C2013-14 Office Finishing Works (2).xlsx
6 | 2 | Verplaatsbare wanden (2) | 2011-02-14 08:00 | 2011-02-14 17:00 | 1d |  | 0 | 3736.01 | 0 | 0 | 3736.01 | 2011-03-01 08:00 | 1d | 3736.01 | 0 | 0 | -509.15 | 0 | 3226.86 | 0 | 1 | Finished | 3736.01 | 3736.01 | C2013-14 Office Finishing Works (2).xlsx
7 | 4 | Systeemwanden | 2011-02-14 08:00 | 2011-05-11 17:00 | 63d |  | 0 | 22944.5195 | 0 | 0 | 22944.5195 | 2011-06-01 08:00 | 22d | 22944.5195 | 0 | 0 | -1486.78 | 0 | 21457.7395 | 0 | 1 | Finished | 22944.5195 | 22944.5195 | C2013-14 Office Finishing Works (2).xlsx
8 | 3 | Zuivere OA (1) | 2011-02-15 08:00 | 2011-02-15 17:00 | 1d |  | 0 | 179.02 | 0 | 0 | 179.02 | 2011-03-01 08:00 | 1d | 179.02 | 0 | 0 | -40.39 | 0 | 138.63 | 0 | 1 | Finished | 179.02 | 179.02 | C2013-14 Office Finishing Works (2).xlsx
9 | 5 | Akoestische dammen | 2011-03-22 08:00 | 2011-03-23 17:00 | 2d |  | 0 | 1092.75 | 0 | 0 | 1092.75 | 2011-06-01 08:00 | 2d | 1092.75 | 0 | 0 | -72.09 | 0 | 1020.66 | 0 | 1 | Finished | 1092.75 | 1092.75 | C2013-14 Office Finishing Works (2).xlsx
10 | 9 | Plafonds + AKD | 2011-03-22 08:00 | 2011-03-23 17:00 | 2d |  | 0 | 607.77 | 0 | 0 | 607.77 | 2011-06-01 08:00 | 2d | 607.77 | 0 | 0 | -40.09 | 0 | 567.68 | 0 | 1 | Finished | 607.77 | 607.77 | C2013-14 Office Finishing Works (2).xlsx
11 | 6 | Verplaatsbare wanden (3) | 2011-03-23 08:00 | 2011-03-28 17:00 | 4d |  | 0 | 23 | 0 | 0 | 23 | 2011-06-01 08:00 | 4d | 23 | 0 | 0 | -2.85 | 0 | 20.15 | 0 | 1 | Finished | 23 | 23 | C2013-14 Office Finishing Works (2).xlsx
12 | 7 | Verplaatsbare wanden (4) | 2011-04-18 08:00 | 2011-05-11 17:00 | 18d |  | 0 | 49527.6094 | 0 | 0 | 49527.6094 | 2011-06-01 08:00 | 18d | 49527.6094 | 0 | 0 | -6960.4702 | 0 | 42567.1392 | 0 | 1 | Finished | 49527.6094 | 49527.6094 | C2013-14 Office Finishing Works (2).xlsx
13 | 8 | Zuivere OA (2) | 2011-05-12 08:00 | 2011-06-03 17:00 | 17d |  | 0 | 4412 | 0 | 0 | 4412 | 2011-06-01 08:00 | 17d | 4412 | 0 | 0 | -996.04 | 0 | 3415.96 | 0 | 1 | Finished | 4412 | 4412 | C2013-14 Office Finishing Works (2).xlsx
4 | 0 | Office Finishing Works (3) | 2011-04-18 08:00 | 2011-12-12 17:00 | 171d |  |  | 1 |  |  | 341468.1141 |  | 115d | [5 empty] | 308343.7755 |  | 1 |  | 341468.1141 | 295360.0333 | C2013-15 Office Finishing Works (3).xlsx
5 | 16 | Diversen | 2011-04-18 08:00 | 2011-08-31 17:00 | 98d |  | 0 | 0 | 2.3 | 1803.2 | 1803.2 | 2011-07-01 08:00 | 21d | 386.4 | 0 | 0 | 709.94 | 0 | 1096.34 | 0 | 1 | Finished | 1803.2 | 1803.2 | C2013-15 Office Finishing Works (3).xlsx
6 | 10 | Opmerkingen oplevering | 2011-09-13 08:00 | 2011-12-12 17:00 | 65d |  | 0 | 0 | 113.01 | 58765.2011 | 58765.2011 | 2011-06-01 08:00 | 42d | 37971.3607 | 0 | 0 | 16769.2402 | 0 | 54740.601 | 0 | 1 | Finished | 58765.2011 | 12657.1202 | C2013-15 Office Finishing Works (3).xlsx
7 | 6 | Gipswanden | 2011-05-16 08:00 | 2011-06-28 17:00 | 32d |  | 0 | 0 | 60.82 | 15569.9199 | 15569.9199 | 2011-04-18 08:00 | 70d | 34059.1998 | 0 | 0 | -18276.6602 | 0 | 15782.5397 | 0 | 1 | Finished | 15569.9199 | 15569.9199 | C2013-15 Office Finishing Works (3).xlsx
8 | 1 | Vaste plafonds (1) | 2011-05-18 08:00 | 2011-07-01 17:00 | 33d |  | 0 | 0 | 106.8 | 28195.2008 | 28195.2008 | 2011-04-18 08:00 | 70d | 59808.0017 | 0 | 0 | -31547.1992 | 0 | 28260.8025 | 0 | 1 | Finished | 28195.2008 | 28195.2008 | C2013-15 Office Finishing Works (3).xlsx
9 | 9 | Plafonds + AKD | 2011-05-18 08:00 | 2011-08-12 17:00 | 63d |  | 0 | 0 | 4.33 | 2182.32 | 2182.32 | 2011-05-02 08:00 | 22d | 762.08 | 0 | 0 | 1174.5699 | 0 | 1936.6499 | 0 | 1 | Finished | 2182.32 | 2182.32 | C2013-15 Office Finishing Works (3).xlsx
10 | 3 | Akoestische dammen (1) | 2011-06-07 08:00 | 2011-06-10 17:00 | 4d |  | 0 | 0 | 106.14 | 3396.48 | 3396.48 | 2011-05-27 08:00 | 4d | 3396.48 | 0 | 0 | -383.77 | 0 | 3012.71 | 0 | 1 | Finished | 3396.48 | 3396.48 | C2013-15 Office Finishing Works (3).xlsx
11 | 8 | Schrijnwerk diversen | 2011-06-14 08:00 | 2011-06-24 17:00 | 9d |  | 0 | 0 | 190.2 | 13694.3998 | 13694.3998 | 2011-04-25 08:00 | 9d | 13694.3998 | 0 | 0 | -1547.05 | 0 | 12147.3497 | 0 | 1 | Finished | 13694.3998 | 13694.3998 | C2013-15 Office Finishing Works (3).xlsx
12 | 11 | Vaste plafonds (2) | 2011-07-04 08:00 | 2011-08-12 17:00 | 30d |  | 0 | 0 | 12.32 | 2956.7999 | 2956.7999 | 2011-07-01 08:00 | 21d | 2069.7599 | 0 | 0 | 292.54 | 0 | 2362.3 | 0 | 1 | Finished | 2956.7999 | 2956.7999 | C2013-15 Office Finishing Works (3).xlsx
13 | 2 | Metalen plafonds verdieping 3 | 2011-07-04 08:00 | 2011-08-19 17:00 | 35d |  | 0 | 0 | 209.26 | 58592.7985 | 58592.7985 | 2011-05-02 08:00 | 35d | 58592.7985 | 0 | 0 | -16992.0508 | 0 | 41600.7477 | 0 | 1 | Finished | 58592.7985 | 58592.7985 | C2013-15 Office Finishing Works (3).xlsx
14 | 13 | Extra ploeg metalen plafonds verdieping 2 | 2011-07-05 08:00 | 2011-07-15 17:00 | 9d |  | 0 | 0 | 121.42 | 8742.2399 | 8742.2399 | 2011-07-01 08:00 | 9d | 8742.2399 | 0 | 0 | -2103.24 | 0 | 6638.9999 | 0 | 1 | Finished | 8742.2399 | 8742.2399 | C2013-15 Office Finishing Works (3).xlsx
15 | 12 | Akoestische dammen (2) | 2011-07-11 08:00 | 2011-07-15 17:00 | 5d |  | 0 | 0 | 9.78 | 391.2 | 391.2 | 2011-07-01 08:00 | 5d | 391.2 | 0 | 0 | -44.05 | 0 | 347.15 | 0 | 1 | Finished | 391.2 | 391.2 | C2013-15 Office Finishing Works (3).xlsx
16 | 4 | Verplaatsbare wanden (1) | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 609.41 | 58503.3574 | 58503.3574 | 2011-06-23 08:00 | 12d | 58503.3574 | 0 | 0 | -19022.0391 | 0 | 39481.3184 | 0 | 1 | Finished | 58503.3574 | 58503.3574 | C2013-15 Office Finishing Works (3).xlsx
17 | 14 | Systeemwanden | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 79.75 | 7656 | 7656 | 2011-07-01 08:00 | 12d | 7656 | 0 | 0 | -1607.09 | 0 | 6048.91 | 0 | 1 | Finished | 7656 | 7656 | C2013-15 Office Finishing Works (3).xlsx
18 | 5 | Verplaatsbare wanden (2) | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 519.66 | 49887.3574 | 49887.3574 | 2011-06-23 08:00 | 12d | 49887.3574 | 0 | 0 | -6953.98 | 0 | 42933.3774 | 0 | 1 | Finished | 49887.3574 | 49887.3574 | C2013-15 Office Finishing Works (3).xlsx
19 | 7 | Deuren | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 405.43 | 29190.9595 | 29190.9595 | 2011-07-01 08:00 | 9d | 29190.9595 | 0 | 0 | -2634 | 0 | 26556.9595 | 0 | 1 | Finished | 29190.9595 | 29190.9595 | C2013-15 Office Finishing Works (3).xlsx
20 | 15 | Schrijnwerk | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 26.94 | 1939.68 | 1939.68 | 2011-07-01 08:00 | 9d | 1939.68 | 0 | 0 | -175.58 | 0 | 1764.1 | 0 | 1 | Finished | 1939.68 | 1939.68 | C2013-15 Office Finishing Works (3).xlsx
21 | 17 | MEERWERK | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-04-18 08:00 | 115d | 1 | 0 | 0 | 23631.9199 | 0 | 23632.9199 | 0 | 1 | Finished | 1 | 1 | C2013-15 Office Finishing Works (3).xlsx
4 | 0 | Office Finishing Works (4) | 2011-05-02 08:00 | 2012-01-30 17:00 | 196d |  |  | 2 |  |  | 248203.9245 |  | 108d | [5 empty] | 198567.0037 |  | 1 |  | 248203.9245 | 247647.5245 | C2013-16 Office Finishing Works (4).xlsx
5 | 9 | Verplaatsbare wanden (1) | 2011-05-02 08:00 | 2011-08-31 17:00 | 88d |  | 0 | 0 | 7.71 | 5427.84 | 5427.84 | 2011-06-01 08:00 | 87d | 5366.16 | 0 | 0 | -824.16 | 0 | 4542.0001 | 0 | 1 | Finished | 5427.84 | 5427.84 | C2013-16 Office Finishing Works (4).xlsx
6 | 1 | Akoestische dammen | 2011-06-17 08:00 | 2011-07-08 17:00 | 16d |  | 0 | 0 | 128.34 | 16427.5195 | 16427.5195 | 2011-06-17 08:00 | 75d | 77003.9978 | 0 | 0 | -64529 | 0 | 12474.9978 | 0 | 1 | Finished | 16427.5195 | 16427.5195 | C2013-16 Office Finishing Works (4).xlsx
7 | 2 | Verplaatsbare wanden (2) | 2011-06-17 08:00 | 2011-09-08 17:00 | 60d |  | 0 | 0 | 424.54 | 203779.2041 | 203779.2041 | 2011-06-17 08:00 | 60d | 203779.2041 | 0 | 0 | -49013.1992 | 0 | 154766.0049 | 0 | 1 | Finished | 203779.2041 | 203779.2041 | C2013-16 Office Finishing Works (4).xlsx
8 | 4 | Zuivere OA | 2011-06-28 08:00 | 2011-09-28 17:00 | 67d |  | 0 | 0 | 40.65 | 21788.4008 | 21788.4008 | 2011-06-28 08:00 | 67d | 21788.4008 | 0 | 0 | -7064.3999 | 0 | 14724.0009 | 0 | 1 | Finished | 21788.4008 | 21788.4008 | C2013-16 Office Finishing Works (4).xlsx
9 | 3 | Verplaatsbare wanden (3) | 2011-09-26 08:00 | 2012-01-30 17:00 | 91d |  | 0 | 0 | 1.07 | 778.96 | 778.96 | 2011-06-01 08:00 | 87d | 744.72 | 0 | 0 | -150.72 | 0 | 594 | 0 | 1 | Finished | 778.96 | 222.56 | C2013-16 Office Finishing Works (4).xlsx
10 | 10 | Meerwerken 1 | 2011-05-02 08:00 | 2011-05-02 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-09-01 08:00 | 20d | 1 | 0 | 0 | 10207 | 0 | 10208 | 0 | 1 | Finished | 1 | 1 | C2013-16 Office Finishing Works (4).xlsx
11 | 11 | meerwerken 2 | 2011-05-02 08:00 | 2011-05-02 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-10-03 08:00 | 20d | 1 | 0 | 0 | 1257 | 0 | 1258 | 0 | 1 | Finished | 1 | 1 | C2013-16 Office Finishing Works (4).xlsx
4 | 0 | Office Finishing Works (5) | 2012-05-01 08:00 | 2012-12-11 17:00 | 161d |  |  | 1 |  |  | 244205.3974 |  | 107d | [5 empty] | 203605.9696 |  | 1 |  | 244205.3974 | 226158.9171 | C2013-17 Office Finishing Works (5).xlsx
5 | 1 | Vaste plafonds | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 0 | 2.99 | 2128.88 | 2128.88 | 2012-07-02 08:00 | 22d | 526.24 | 0 | 0 | 1402.63 | 0 | 1928.87 | 0 | 1 | Finished | 2128.88 | 2128.88 | C2013-17 Office Finishing Works (5).xlsx
6 | 2 | Metalen plafonds | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 0 | 27.4 | 19508.7997 | 19508.7997 | 2012-07-02 08:00 | 62d | 13590.3998 | 0 | 0 | 6600.04 | 0 | 20190.4398 | 0 | 1 | Finished | 19508.7997 | 19508.7997 | C2013-17 Office Finishing Works (5).xlsx
7 | 4 | Verplaatsbare wanden (1) | 2012-05-15 08:00 | 2012-12-11 17:00 | 151d |  | 0 | 0 | 31.16 | 37641.2798 | 37641.2798 | 2012-07-02 08:00 | 22d | 5484.16 | 0 | 0 | 28120.4902 | 0 | 33604.6502 | 0 | 1 | Finished | 37641.2798 | 30412.1599 | C2013-17 Office Finishing Works (5).xlsx
8 | 6 | Gipswanden | 2012-05-15 08:00 | 2012-06-13 17:00 | 22d |  | 0 | 0 | 205.59 | 36183.8394 | 36183.8394 | 2012-06-01 08:00 | 81d | 133222.3176 | 0 | 0 | -99119.0078 | 0 | 34103.3098 | 0 | 1 | Finished | 36183.8394 | 36183.8394 | C2013-17 Office Finishing Works (5).xlsx
9 | 9 | Zuivere OA (1) | 2012-06-13 08:00 | 2012-06-13 17:00 | 1d |  | 0 | 0 | 134.92 | 1079.36 | 1079.36 | 2012-07-31 08:00 | 1d | 1079.36 | 0 | 0 | -232.71 | 0 | 846.65 | 0 | 1 | Finished | 1079.36 | 1079.36 | C2013-17 Office Finishing Works (5).xlsx
10 | 10 | Démontage plafonds | 2012-06-14 08:00 | 2012-06-22 17:00 | 7d |  | 0 | 0 | 44.8 | 2508.8 | 2508.8 | 2012-06-14 08:00 | 7d | 2508.8 | 0 | 0 | -231.93 | 0 | 2276.87 | 0 | 1 | Finished | 2508.8 | 2508.8 | C2013-17 Office Finishing Works (5).xlsx
11 | 12 | Uitregelen verhoogde vloer | 2012-07-23 08:00 | 2012-07-25 17:00 | 3d |  | 0 | 0 | 75 | 1800 | 1800 | 2012-07-23 08:00 | 3d | 1800 | 0 | 0 | -341.48 | 0 | 1458.52 | 0 | 1 | Finished | 1800 | 1800 | C2013-17 Office Finishing Works (5).xlsx
12 | 11 | Plaatsen tapijt | 2012-07-31 08:00 | 2012-08-06 17:00 | 5d |  | 0 | 0 | 679.06 | 27162.3999 | 27162.3999 | 2012-07-25 08:00 | 5d | 27162.3999 | 0 | 0 | -5705.3301 | 0 | 21457.0698 | 0 | 1 | Finished | 27162.3999 | 27162.3999 | C2013-17 Office Finishing Works (5).xlsx
13 | 21 | Zuivere OA (2) | 2012-07-31 08:00 | 2012-10-31 17:00 | 67d |  | 0 | 0 | 37.44 | 20067.8393 | 20067.8393 | 2012-07-02 08:00 | 22d | 6589.4398 | 0 | 0 | 9105.04 | 0 | 15694.4798 | 0 | 1 | Finished | 20067.8393 | 20067.8393 | C2013-17 Office Finishing Works (5).xlsx
14 | 13 | Plaatsen meubilair | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 1500.96 | 36023.0391 | 36023.0391 | 2012-08-16 08:00 | 3d | 36023.0391 | 0 | 0 | -6831.98 | 0 | 29191.0591 | 0 | 1 | Finished | 36023.0391 | 36023.0391 | C2013-17 Office Finishing Works (5).xlsx
15 | 14 | Leveren en plaatsen glas | 2012-08-30 08:00 | 2012-08-30 17:00 | 1d |  | 0 | 0 | 22.5 | 180 | 180 | 2012-10-01 08:00 | 1d | 180 | 0 | 0 | -2.04 | 0 | 177.96 | 0 | 1 | Finished | 180 | 180 | C2013-17 Office Finishing Works (5).xlsx
16 | 3 | Akoestische dammen | 2012-08-06 08:00 | 2012-08-07 17:00 | 2d |  | 0 | 0 | 104.63 | 1674.08 | 1674.08 | 2012-06-28 08:00 | 2d | 1674.08 | 0 | 0 | -154.58 | 0 | 1519.5 | 0 | 1 | Finished | 1674.08 | 1674.08 | C2013-17 Office Finishing Works (5).xlsx
17 | 20 | Verplaatsbare wanden (2) | 2012-08-13 08:00 | 2012-08-23 17:00 | 9d |  | 0 | 0 | 68.42 | 4926.2399 | 4926.2399 | 2012-07-19 08:00 | 9d | 4926.2399 | 0 | 0 | -1681.49 | 0 | 3244.7499 | 0 | 1 | Finished | 4926.2399 | 4926.2399 | C2013-17 Office Finishing Works (5).xlsx
18 | 5 | Verplaatsbare wanden (3) | 2012-08-13 08:00 | 2012-08-23 17:00 | 9d |  | 0 | 0 | 8.6 | 619.2 | 619.2 | 2012-09-03 08:00 | 9d | 619.2 | 0 | 0 | -4.11 | 0 | 615.09 | 0 | 1 | Finished | 619.2 | 619.2 | C2013-17 Office Finishing Works (5).xlsx
19 | 7 | Deuren | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 260.8 | 6259.1997 | 6259.1997 | 2012-06-29 08:00 | 3d | 6259.1997 | 0 | 0 | -730.47 | 0 | 5528.7297 | 0 | 1 | Finished | 6259.1997 | 6259.1997 | C2013-17 Office Finishing Works (5).xlsx
20 | 8 | Schrijnwerk diversen | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 81.83 | 1963.92 | 1963.92 | 2012-07-31 08:00 | 3d | 1963.92 | 0 | 0 | -181.27 | 0 | 1782.65 | 0 | 1 | Finished | 1963.92 | 1963.92 | C2013-17 Office Finishing Works (5).xlsx
21 | 17 | Schilderwerken | 2012-10-16 08:00 | 2012-12-11 17:00 | 41d |  | 0 | 0 | 26.03 | 8537.8402 | 8537.8402 | 2012-07-02 08:00 | 22d | 4581.2801 | 0 | 0 | 1604.1801 | 0 | 6185.4602 | 0 | 1 | Finished | 8537.8402 | 2498.8801 | C2013-17 Office Finishing Works (5).xlsx
22 | 19 | Bijkomende werken | 2012-10-29 08:00 | 2012-10-31 17:00 | 3d |  | 0 | 0 | 692.44 | 16618.5601 | 16618.5601 | 2012-08-29 08:00 | 3d | 16618.5601 | 0 | 0 | -15245.0195 | 0 | 1373.5405 | 0 | 1 | Finished | 16618.5601 | 16618.5601 | C2013-17 Office Finishing Works (5).xlsx
23 | 15 | Afwerkingen | 2012-08-27 08:00 | 2012-12-03 17:00 | 71d |  | 0 | 0 | 23.12 | 13132.1605 | 13132.1605 | 2012-06-01 08:00 | 65d | 12022.4004 | 0 | 0 | -102.5 | 0 | 11919.9004 | 0 | 1 | Finished | 13132.1605 | 8878.0803 | C2013-17 Office Finishing Works (5).xlsx
24 | 22 | Diversen | 2012-08-27 08:00 | 2012-12-11 17:00 | 77d |  | 0 | 0 | 1.62 | 997.92 | 997.92 | 2012-07-02 08:00 | 22d | 285.12 | 0 | 0 | 620.73 | 0 | 905.85 | 0 | 1 | Finished | 997.92 | 622.08 | C2013-17 Office Finishing Works (5).xlsx
25 | 16 | Aanpassingswerken meubilair | 2012-09-18 08:00 | 2012-12-11 17:00 | 61d |  | 0 | 0 | 0.64 | 312.32 | 312.32 | 2012-10-01 08:00 | 1h | 0.64 | 0 | 0 | -0.64 | 0 | 0 | 0 | 1 | Finished | 312.32 | 163.84 | C2013-17 Office Finishing Works (5).xlsx
26 | 18 | Verplaatsen versteviging schermen | 2012-10-25 08:00 | 2012-10-29 17:00 | 3d |  | 0 | 0 | 203.28 | 4878.72 | 4878.72 | 2012-10-25 08:00 | 3d | 4878.72 | 0 | 0 | -3973.25 | 0 | 905.47 | 0 | 1 | Finished | 4878.72 | 4878.72 | C2013-17 Office Finishing Works (5).xlsx
27 | 23 | MEERWERKEN | 2012-05-01 08:00 | 2012-05-01 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2012-06-01 08:00 | 85d | 1 | 0 | 0 | 8694.1504 | 0 | 8695.1504 | 0 | 1 | Finished | 1 | 1 | C2013-17 Office Finishing Works (5).xlsx
4 | 0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 448d | [5 empty] | 39777643.3008 |  | 1 |  | 38697822.7305 | 38697822.7305 | C2014-01 Mixed-use Building.xlsx
5 | 1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2014-01 Mixed-use Building.xlsx
6 | 6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 240d | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2014-01 Mixed-use Building.xlsx
7 | 2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-11-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2014-01 Mixed-use Building.xlsx
8 | 3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2014-01 Mixed-use Building.xlsx
9 | 4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-22 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2014-01 Mixed-use Building.xlsx
10 | 5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2014-01 Mixed-use Building.xlsx
11 | 11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 253d | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2014-01 Mixed-use Building.xlsx
12 | 7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2014-01 Mixed-use Building.xlsx
13 | 8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-05-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2014-01 Mixed-use Building.xlsx
14 | 9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-06-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2014-01 Mixed-use Building.xlsx
15 | 10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2014-01 Mixed-use Building.xlsx
16 | 12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2014-01 Mixed-use Building.xlsx
17 | 13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 1 | Finished | 139677 | 139677 | C2014-01 Mixed-use Building.xlsx
18 | 66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 448d | [5 empty] | 39632130.771 |  | 1 |  | 38558145.7305 | 38558145.7305 | C2014-01 Mixed-use Building.xlsx
19 | 14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2014-01 Mixed-use Building.xlsx
20 | 15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 1 | Finished | 2974378.75 | 2974378.75 | C2014-01 Mixed-use Building.xlsx
21 | 16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 1 | Finished | 1487539.125 | 1487539.125 | C2014-01 Mixed-use Building.xlsx
22 | 19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 260d | [5 empty] | 93908.8687 |  | 1 |  | 90142.8086 | 90142.8086 | C2014-01 Mixed-use Building.xlsx
23 | 17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 1 | Finished | 67607.1094 | 67607.1094 | C2014-01 Mixed-use Building.xlsx
24 | 18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 | 2012-06-01 08:00 | 5d | 22535.6992 | 0 | 0 | 941.52 | 0 | 23477.2192 | 0 | 1 | Finished | 22535.6992 | 22535.6992 | C2014-01 Mixed-use Building.xlsx
25 | 65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 344d | [5 empty] | 34889890.668 |  | 1 |  | 34006085.0469 | 34006085.0469 | C2014-01 Mixed-use Building.xlsx
26 | 39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 208d | [5 empty] | 10221001.1758 |  | 1 |  | 9830475.4062 | 9830475.4062 | C2014-01 Mixed-use Building.xlsx
27 | 25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 1 |  | 3096883.9688 | 3096883.9688 | C2014-01 Mixed-use Building.xlsx
28 | 20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 1 | Finished | 539823.8125 | 539823.8125 | C2014-01 Mixed-use Building.xlsx
29 | 21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 1 | Finished | 284117.7812 | 284117.7812 | C2014-01 Mixed-use Building.xlsx
30 | 22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 1 | Finished | 710294.5 | 710294.5 | C2014-01 Mixed-use Building.xlsx
31 | 23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 1 | Finished | 710294.5 | 710294.5 | C2014-01 Mixed-use Building.xlsx
32 | 24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 1 | Finished | 852353.375 | 852353.375 | C2014-01 Mixed-use Building.xlsx
33 | 38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 143d | [5 empty] | 6994733.3066 |  | 1 |  | 6733591.4375 | 6733591.4375 | C2014-01 Mixed-use Building.xlsx
34 | 26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 1 | Finished | 568235.5625 | 568235.5625 | C2014-01 Mixed-use Building.xlsx
35 | 27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 1 | Finished | 568235.5625 | 568235.5625 | C2014-01 Mixed-use Building.xlsx
36 | 28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-10 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 1 | Finished | 568235.5625 | 568235.5625 | C2014-01 Mixed-use Building.xlsx
37 | 29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-21 08:00 | 18d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 1 | Finished | 568235.5625 | 568235.5625 | C2014-01 Mixed-use Building.xlsx
38 | 30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-07 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 1 | Finished | 568235.5625 | 568235.5625 | C2014-01 Mixed-use Building.xlsx
39 | 31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-21 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 1 | Finished | 568235.5625 | 568235.5625 | C2014-01 Mixed-use Building.xlsx
40 | 32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-02 08:00 | 24d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 1 | Finished | 568235.5625 | 568235.5625 | C2014-01 Mixed-use Building.xlsx
41 | 33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-21 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 1 | Finished | 568235.5625 | 568235.5625 | C2014-01 Mixed-use Building.xlsx
42 | 34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-01-23 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 1 | Finished | 568235.5625 | 568235.5625 | C2014-01 Mixed-use Building.xlsx
43 | 35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-09 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 1 | Finished | 568235.5625 | 568235.5625 | C2014-01 Mixed-use Building.xlsx
44 | 36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-28 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 1 | Finished | 568235.5625 | 568235.5625 | C2014-01 Mixed-use Building.xlsx
45 | 37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 | 2012-03-16 08:00 | 19d | 483000.25 | 0 | 0 | 0 | 0 | 483000.25 | 0 | 1 | Finished | 483000.25 | 483000.25 | C2014-01 Mixed-use Building.xlsx
46 | 42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 147d | [5 empty] | 570987.3296 |  | 1 |  | 548088.8594 | 548088.8594 | C2014-01 Mixed-use Building.xlsx
47 | 40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 35d | 157496.7969 | 0 | 0 | 6580.02 | 0 | 164076.8169 | 0 | 1 | Finished | 157496.7969 | 157496.7969 | C2014-01 Mixed-use Building.xlsx
48 | 41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 2011-10-21 08:00 | 124d | 390592.0625 | 0 | 0 | 16318.4502 | 0 | 406910.5127 | 0 | 1 | Finished | 390592.0625 | 390592.0625 | C2014-01 Mixed-use Building.xlsx
49 | 46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 227d 1h | [5 empty] | 12357655.75 |  | 1 |  | 12357655.75 | 12357655.75 | C2014-01 Mixed-use Building.xlsx
50 | 43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 169d | 3319967.25 | 0 | 0 | 0 | 0 | 3319967.25 | 0 | 1 | Finished | 3319967.25 | 3319967.25 | C2014-01 Mixed-use Building.xlsx
51 | 44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 2011-10-18 08:00 | 211d | 6086606.5 | 0 | 0 | 2951082 | 0 | 9037688.5 | 0 | 1 | Finished | 6086606.5 | 6086606.5 | C2014-01 Mixed-use Building.xlsx
52 | 45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 | 2012-09-20 08:00 | 1h | 2951082 | 0 | 0 | -2951082 | 0 | 0 | 0 | 1 | Finished | 2951082 | 2951082 | C2014-01 Mixed-use Building.xlsx
53 | 50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 80d | [5 empty] | 810119.5068 |  | 1 |  | 777631.0469 | 777631.0469 | C2014-01 Mixed-use Building.xlsx
54 | 47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 | 2012-03-21 08:00 | 33d | 227095.7969 | 0 | 0 | 9487.7803 | 0 | 236583.5771 | 0 | 1 | Finished | 227095.7969 | 227095.7969 | C2014-01 Mixed-use Building.xlsx
55 | 48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 | 2012-04-03 08:00 | 61d | 412901.4375 | 0 | 0 | 17250.5098 | 0 | 430151.9473 | 0 | 1 | Finished | 412901.4375 | 412901.4375 | C2014-01 Mixed-use Building.xlsx
56 | 49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 | 2012-06-13 08:00 | 20d | 137633.8125 | 0 | 0 | 5750.1699 | 0 | 143383.9824 | 0 | 1 | Finished | 137633.8125 | 137633.8125 | C2014-01 Mixed-use Building.xlsx
57 | 54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 172d | [5 empty] | 5454432.3203 |  | 1 |  | 5235691.6562 | 5235691.6562 | C2014-01 Mixed-use Building.xlsx
58 | 51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-02 08:00 | 118d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 1 | Finished | 2356061.25 | 2356061.25 | C2014-01 Mixed-use Building.xlsx
59 | 52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-09 08:00 | 137d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 1 | Finished | 2356061.25 | 2356061.25 | C2014-01 Mixed-use Building.xlsx
60 | 53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 | 2012-06-01 08:00 | 30d | 523569.1562 | 0 | 0 | 21874.0703 | 0 | 545443.2266 | 0 | 1 | Finished | 523569.1562 | 523569.1562 | C2014-01 Mixed-use Building.xlsx
61 | 60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 233d | [5 empty] | 5122991.1558 |  | 1 |  | 4917542.3281 | 4917542.3281 | C2014-01 Mixed-use Building.xlsx
62 | 55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-10-06 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 1 | Finished | 83348.1797 | 83348.1797 | C2014-01 Mixed-use Building.xlsx
63 | 56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-11-29 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 1 | Finished | 83348.1797 | 83348.1797 | C2014-01 Mixed-use Building.xlsx
64 | 57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 | 2012-01-20 08:00 | 96d | 1500267.125 | 0 | 0 | 62679.3008 | 0 | 1562946.4258 | 0 | 1 | Finished | 1500267.125 | 1500267.125 | C2014-01 Mixed-use Building.xlsx
65 | 58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 | 2011-12-09 08:00 | 177d | 3083882.5 | 0 | 0 | 128840.7969 | 0 | 3212723.2969 | 0 | 1 | Finished | 3083882.5 | 3083882.5 | C2014-01 Mixed-use Building.xlsx
66 | 59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 | 2012-09-25 08:00 | 10d | 166696.3438 | 0 | 0 | 6964.3701 | 0 | 173660.7139 | 0 | 1 | Finished | 166696.3438 | 166696.3438 | C2014-01 Mixed-use Building.xlsx
67 | 61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 | 2012-06-01 08:00 | 41d | 328000 | 0 | 0 | 13703.4297 | 0 | 341703.4297 | 0 | 1 | Finished | 328000 | 328000 | C2014-01 Mixed-use Building.xlsx
68 | 62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 | 2012-09-13 08:00 | 23d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2014-01 Mixed-use Building.xlsx
69 | 63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 | 2012-10-16 08:00 | 23d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 1 | Finished | 1000 | 1000 | C2014-01 Mixed-use Building.xlsx
70 | 64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2014-01 Mixed-use Building.xlsx
4 | 0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 146d | [5 empty] | 190266.499 |  | 1 |  | 191492.699 | 191492.699 | C2014-02 Playing Cards.xlsx
5 | 2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 1 | Finished | 3000 | 3000 | C2014-02 Playing Cards.xlsx
6 | 3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 1 | Finished | 520 | 520 | C2014-02 Playing Cards.xlsx
7 | 4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 1 | Finished | 6926.7998 | 6926.7998 | C2014-02 Playing Cards.xlsx
8 | 5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 1 | Finished | 520 | 520 | C2014-02 Playing Cards.xlsx
9 | 6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 1 | Finished | 8658.5 | 8658.5 | C2014-02 Playing Cards.xlsx
10 | 7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 1 | Finished | 1731.7 | 1731.7 | C2014-02 Playing Cards.xlsx
11 | 8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 1 | Finished | 51629 | 51629 | C2014-02 Playing Cards.xlsx
12 | 9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 1 | Finished | 1721 | 1721 | C2014-02 Playing Cards.xlsx
13 | 10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 1 | Finished | 12238 | 12238 | C2014-02 Playing Cards.xlsx
14 | 11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 1 | Finished | 6119 | 6119 | C2014-02 Playing Cards.xlsx
15 | 12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-08-20 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 1 | Finished | 13851.0996 | 13851.0996 | C2014-02 Playing Cards.xlsx
16 | 13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-09-03 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 1 | Finished | 18357 | 18357 | C2014-02 Playing Cards.xlsx
17 | 14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 2012-09-19 08:00 | 1d | 1529.75 | 0 | 0 | 0 | 0 | 1529.75 | 0 | 1 | Finished | 1529.75 | 1529.75 | C2014-02 Playing Cards.xlsx
18 | 15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 | 2012-09-20 08:00 | 5d | 7648.75 | 0 | 0 | 0 | 0 | 7648.75 | 0 | 1 | Finished | 7648.75 | 7648.75 | C2014-02 Playing Cards.xlsx
19 | 16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-09-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2014-02 Playing Cards.xlsx
20 | 17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-09-27 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 1 | Finished | 1721 | 1721 | C2014-02 Playing Cards.xlsx
21 | 18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 | 2012-09-28 08:00 | 10d | 1696.5 | 0 | 0 | 0 | 0 | 1696.5 | 0 | 1 | Finished | 1696.5 | 1696.5 | C2014-02 Playing Cards.xlsx
22 | 19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-10-12 08:00 | 10d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 1 | Finished | 12238 | 12238 | C2014-02 Playing Cards.xlsx
23 | 20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-10-26 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 1 | Finished | 13851.0996 | 13851.0996 | C2014-02 Playing Cards.xlsx
24 | 21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-11-09 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 1 | Finished | 18357 | 18357 | C2014-02 Playing Cards.xlsx
25 | 22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 2012-11-16 08:00 | 1d | 1529.75 | 0 | 0 | 0 | 0 | 1529.75 | 0 | 1 | Finished | 1529.75 | 1529.75 | C2014-02 Playing Cards.xlsx
26 | 23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 | 2012-11-19 08:00 | 5d | 7648.75 | 0 | 0 | 0 | 0 | 7648.75 | 0 | 1 | Finished | 7648.75 | 7648.75 | C2014-02 Playing Cards.xlsx
27 | 24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2014-02 Playing Cards.xlsx
4 | 0 | Organizational Development | 2012-07-16 08:00 | 2013-05-30 15:00 | 228d 6h |  |  | 0 |  |  | 43170.15 |  | 260d | [5 empty] | 83712.15 |  | 1 |  | 43170.15 | 43170.15 | C2014-03 Organizational Development.xlsx
5 | 85 | Department A | 2012-07-16 08:00 | 2012-11-08 17:00 | 84d |  |  | 0 |  |  | 3516.15 |  | 205d | [5 empty] | 12066 |  | 1 |  | 3516.15 | 3516.15 | C2014-03 Organizational Development.xlsx
6 | 1 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
7 | 107 | Directieteam extra | 2012-07-16 09:00 | 2012-07-16 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 111 | 111 | 123 | 2012-08-27 08:00 | 5d | 4920 | 0 | 0 | 0 | 0 | 4920 | 0 | 1 | Finished | 123 | 123 | C2014-03 Organizational Development.xlsx
8 | 2 | Organisatorische oefening | 2012-07-17 11:00 | 2012-09-04 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 1 | Finished | 1680 | 1680 | C2014-03 Organizational Development.xlsx
9 | 3 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 1 | Finished | 1080 | 1080 | C2014-03 Organizational Development.xlsx
10 | 108 | Opleiding extra | 2012-09-25 11:00 | 2012-09-25 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 1 | Finished | 9 | 9 | C2014-03 Organizational Development.xlsx
11 | 4 | Testfase | 2012-09-26 14:00 | 2012-10-31 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 1 | Finished | 600 | 600 | C2014-03 Organizational Development.xlsx
12 | 5 | Live | 2012-10-31 14:00 | 2012-11-07 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 45d | 54 | 0 | 0 | 0 | 0 | 54 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
13 | 109 | Live extra | 2012-11-07 14:00 | 2012-11-07 15:00 | 1h | Personeel[0.01 #10] | 0.15 | 0 | 0 | 0 | 0.15 | 2013-02-04 08:00 | 10d | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | Finished | 0.15 | 0.15 | C2014-03 Organizational Development.xlsx
14 | 6 | Optimalisatie/standaardisatie | 2012-11-08 16:00 | 2012-11-08 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-18 08:00 | 50d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
15 | 86 | Department B | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 165d | [5 empty] | 6195 |  | 1 |  | 3411 | 3411 | C2014-03 Organizational Development.xlsx
16 | 7 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
17 | 110 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
18 | 8 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 1 | Finished | 1680 | 1680 | C2014-03 Organizational Development.xlsx
19 | 111 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 45d | 2160 | 0 | 0 | 0 | 0 | 2160 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
20 | 9 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 1 | Finished | 1080 | 1080 | C2014-03 Organizational Development.xlsx
21 | 112 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-06-10 08:00 | 10d | 720 | 0 | 0 | 0 | 0 | 720 | 0 | 1 | Finished | 9 | 9 | C2014-03 Organizational Development.xlsx
22 | 10 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-04-08 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | Finished | 600 | 600 | C2014-03 Organizational Development.xlsx
23 | 11 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-04-08 08:00 | 45d | 54 | 0 | 0 | 0 | 0 | 54 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
24 | 12 | Live extra | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-06-24 08:00 | 15d | 720 | 0 | 0 | -702 | 0 | 18 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
25 | 87 | Department C | 2012-07-16 08:00 | 2012-11-06 12:00 | 81d 4h |  |  | 0 |  |  | 3390 |  | 115d 1h | [5 empty] | 4116 |  | 1 |  | 3390 | 3390 | C2014-03 Organizational Development.xlsx
26 | 13 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
27 | 14 | Organisatorische oefening | 2012-07-16 09:00 | 2012-09-03 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 1 | Finished | 1680 | 1680 | C2014-03 Organizational Development.xlsx
28 | 113 | Organisatorische oefening extra | 2012-09-03 09:00 | 2012-09-03 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
29 | 15 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 1 | Finished | 1080 | 1080 | C2014-03 Organizational Development.xlsx
30 | 16 | Testfase | 2012-09-25 11:00 | 2012-10-30 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 1 | Finished | 600 | 600 | C2014-03 Organizational Development.xlsx
31 | 17 | Live | 2012-10-30 11:00 | 2012-11-06 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
32 | 18 | Optimalisatie/standaardisatie | 2012-11-06 11:00 | 2012-11-06 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-24 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
33 | 88 | Department D | 2013-02-05 08:00 | 2013-05-30 15:00 | 82d 6h |  |  | 0 |  |  | 3399 |  | 165d | [5 empty] | 6303 |  | 1 |  | 3399 | 3399 | C2014-03 Organizational Development.xlsx
34 | 19 | Directieteam | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
35 | 20 | Organisatorische oefening | 2013-02-05 09:00 | 2013-03-26 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 1 | Finished | 1680 | 1680 | C2014-03 Organizational Development.xlsx
36 | 114 | Organisatorische oefening extra | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 75d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
37 | 21 | Opleiding | 2013-03-27 11:00 | 2013-04-17 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 1 | Finished | 1080 | 1080 | C2014-03 Organizational Development.xlsx
38 | 115 | Opleiding extra | 2013-04-17 11:00 | 2013-04-17 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-05-06 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 1 | Finished | 9 | 9 | C2014-03 Organizational Development.xlsx
39 | 22 | Testfase | 2013-04-18 14:00 | 2013-05-23 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-05-13 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | Finished | 600 | 600 | C2014-03 Organizational Development.xlsx
40 | 23 | Live | 2013-05-23 14:00 | 2013-05-30 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-05-13 08:00 | 45d | 54 | 0 | 0 | 0 | 0 | 54 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
41 | 24 | Optimalisatie/standaardisatie | 2013-05-30 14:00 | 2013-05-30 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
42 | 89 | Department E | 2012-11-20 08:00 | 2013-04-10 11:00 | 101d 3h |  |  | 0 |  |  | 3402 |  | 125d | [5 empty] | 4971 |  | 1 |  | 3402 | 3402 | C2014-03 Organizational Development.xlsx
43 | 25 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
44 | 116 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
45 | 26 | Organisatorische oefening | 2012-12-18 08:00 | 2013-02-04 17:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 1 | Finished | 1680 | 1680 | C2014-03 Organizational Development.xlsx
46 | 117 | Organisatorische oefening extra | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
47 | 27 | Opleiding | 2013-02-06 10:00 | 2013-02-27 10:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 1 | Finished | 1080 | 1080 | C2014-03 Organizational Development.xlsx
48 | 28 | Testfase | 2013-02-27 10:00 | 2013-04-03 10:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-03-11 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | Finished | 600 | 600 | C2014-03 Organizational Development.xlsx
49 | 29 | Live | 2013-04-03 10:00 | 2013-04-10 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-03-11 08:00 | 40d | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
50 | 30 | Optimalisatie/standaardisatie | 2013-04-10 10:00 | 2013-04-10 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-05-06 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
51 | 90 | Department F | 2012-12-18 08:00 | 2013-04-09 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 170d | [5 empty] | 6189 |  | 1 |  | 3384 | 3384 | C2014-03 Organizational Development.xlsx
52 | 31 | Directieteam | 2012-12-18 08:00 | 2012-12-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
53 | 32 | Organisatorische oefening | 2012-12-18 09:00 | 2013-02-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 110d | 5280 | 0 | 0 | 0 | 0 | 5280 | 0 | 1 | Finished | 1680 | 1680 | C2014-03 Organizational Development.xlsx
54 | 33 | Opleiding | 2013-02-05 09:00 | 2013-02-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-04-29 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 1 | Finished | 1080 | 1080 | C2014-03 Organizational Development.xlsx
55 | 34 | Testfase | 2013-02-26 09:00 | 2013-04-02 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-05-06 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | Finished | 600 | 600 | C2014-03 Organizational Development.xlsx
56 | 35 | Live | 2013-04-02 09:00 | 2013-04-09 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-05-06 08:00 | 50d | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
57 | 36 | Optimalisatie/standaardisatie | 2013-04-09 09:00 | 2013-04-09 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
58 | 91 | Department G | 2012-11-20 08:00 | 2013-03-14 15:00 | 82d 6h |  |  | 0 |  |  | 3402 |  | 180d | [5 empty] | 9741 |  | 1 |  | 3402 | 3402 | C2014-03 Organizational Development.xlsx
59 | 37 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-05 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
60 | 118 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
61 | 38 | Organisatorische oefening | 2012-11-21 11:00 | 2013-01-09 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-19 08:00 | 80d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 1 | Finished | 1680 | 1680 | C2014-03 Organizational Development.xlsx
62 | 119 | Organisatorische oefening extra | 2013-01-09 11:00 | 2013-01-09 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-03-18 08:00 | 20d | 960 | 0 | 0 | 0 | 0 | 960 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
63 | 39 | Opleiding | 2013-01-10 14:00 | 2013-01-31 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-04-15 08:00 | 55d | 3960 | 0 | 0 | 0 | 0 | 3960 | 0 | 1 | Finished | 1080 | 1080 | C2014-03 Organizational Development.xlsx
64 | 40 | Testfase | 2013-01-31 14:00 | 2013-03-07 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-07-01 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | Finished | 600 | 600 | C2014-03 Organizational Development.xlsx
65 | 41 | Live | 2013-03-07 14:00 | 2013-03-14 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-01 08:00 | 10d | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
66 | 42 | Optimalisatie/standaardisatie | 2013-03-14 14:00 | 2013-03-14 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
67 | 92 | Department H | 2012-09-18 08:00 | 2013-01-08 09:00 | 80d 1h |  |  | 0 |  |  | 753 |  | 65d 1h | [5 empty] | 1137 |  | 1 |  | 753 | 753 | C2014-03 Organizational Development.xlsx
68 | 43 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
69 | 44 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 1 | Finished | 240 | 240 | C2014-03 Organizational Development.xlsx
70 | 45 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | Finished | 9 | 9 | C2014-03 Organizational Development.xlsx
71 | 46 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 1 | Finished | 480 | 480 | C2014-03 Organizational Development.xlsx
72 | 47 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
73 | 48 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
74 | 93 | Department I | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 225d | [5 empty] | 8127 |  | 1 |  | 3411 | 3411 | C2014-03 Organizational Development.xlsx
75 | 49 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-03 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
76 | 120 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
77 | 50 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-01 08:00 | 75d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 1 | Finished | 1680 | 1680 | C2014-03 Organizational Development.xlsx
78 | 121 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 35d | 1680 | 0 | 0 | 0 | 0 | 1680 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
79 | 51 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 1 | Finished | 1080 | 1080 | C2014-03 Organizational Development.xlsx
80 | 122 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-03-18 08:00 | 20d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 1 | Finished | 9 | 9 | C2014-03 Organizational Development.xlsx
81 | 52 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-04-15 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | Finished | 600 | 600 | C2014-03 Organizational Development.xlsx
82 | 53 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-04-15 08:00 | 65d | 78 | 0 | 0 | 0 | 0 | 78 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
83 | 54 | Optimalisatie/standaardisatie | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
84 | 106 | Department J | 2012-09-18 08:00 | 2012-10-30 11:00 | 30d 3h |  |  | 0 |  |  | 753 |  | 55d 1h | [5 empty] | 1125 |  | 1 |  | 753 | 753 | C2014-03 Organizational Development.xlsx
85 | 100 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
86 | 101 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 1 | Finished | 240 | 240 | C2014-03 Organizational Development.xlsx
87 | 102 | Opleiding | 2012-09-25 09:00 | 2012-09-25 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | Finished | 9 | 9 | C2014-03 Organizational Development.xlsx
88 | 103 | Testfase | 2012-09-25 10:00 | 2012-10-23 10:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 1 | Finished | 480 | 480 | C2014-03 Organizational Development.xlsx
89 | 104 | Live | 2012-10-23 10:00 | 2012-10-30 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 15d | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
90 | 105 | Optimalisatie/standaardisatie | 2012-10-30 10:00 | 2012-10-30 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-03 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
91 | 94 | Department K | 2012-10-23 08:00 | 2013-02-12 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 100d | [5 empty] | 5058.15 |  | 1 |  | 3384 | 3384 | C2014-03 Organizational Development.xlsx
92 | 55 | Directieteam | 2012-10-23 08:00 | 2012-10-23 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-02-25 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
93 | 56 | Organisatorische oefening | 2012-10-23 09:00 | 2012-12-11 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-03-04 08:00 | 95d | 4560 | 0 | 0 | 0 | 0 | 4560 | 0 | 1 | Finished | 1680 | 1680 | C2014-03 Organizational Development.xlsx
94 | 57 | Opleiding | 2012-12-11 09:00 | 2013-01-01 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-07-12 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | Finished | 1080 | 1080 | C2014-03 Organizational Development.xlsx
95 | 58 | Testfase | 2013-01-01 09:00 | 2013-02-05 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-07-12 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | Finished | 600 | 600 | C2014-03 Organizational Development.xlsx
96 | 59 | Live | 2013-02-05 09:00 | 2013-02-12 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 0.15 | 0 | 0 | 0 | 0 | 0.15 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
97 | 60 | Optimalisatie/standaardisatie | 2013-02-12 09:00 | 2013-02-12 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
98 | 95 | Department L | 2013-01-15 08:00 | 2013-05-07 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 100d | [5 empty] | 2787 |  | 1 |  | 3384 | 3384 | C2014-03 Organizational Development.xlsx
99 | 61 | Directieteam | 2013-01-15 08:00 | 2013-01-15 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-02-25 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
100 | 62 | Organisatorische oefening | 2013-01-15 09:00 | 2013-03-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-04-29 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 1 | Finished | 1680 | 1680 | C2014-03 Organizational Development.xlsx
101 | 63 | Opleiding | 2013-03-05 09:00 | 2013-03-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-06-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 1 | Finished | 1080 | 1080 | C2014-03 Organizational Development.xlsx
102 | 64 | Testfase | 2013-03-26 09:00 | 2013-04-30 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-06-24 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | Finished | 600 | 600 | C2014-03 Organizational Development.xlsx
103 | 65 | Live | 2013-04-30 09:00 | 2013-05-07 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-06-24 08:00 | 15d | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
104 | 66 | Optimalisatie/standaardisatie | 2013-05-07 09:00 | 2013-05-07 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
105 | 96 | Department M | 2012-12-04 08:00 | 2013-03-26 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 90d | [5 empty] | 4227 |  | 1 |  | 3384 | 3384 | C2014-03 Organizational Development.xlsx
106 | 67 | Directieteam | 2012-12-04 08:00 | 2012-12-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
107 | 68 | Organisatorische oefening | 2012-12-04 09:00 | 2013-01-22 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-03-18 08:00 | 55d | 2640 | 0 | 0 | 0 | 0 | 2640 | 0 | 1 | Finished | 1680 | 1680 | C2014-03 Organizational Development.xlsx
108 | 69 | Opleiding | 2013-01-22 09:00 | 2013-02-12 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-06-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 1 | Finished | 1080 | 1080 | C2014-03 Organizational Development.xlsx
109 | 70 | Testfase | 2013-02-12 09:00 | 2013-03-19 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-06-24 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | Finished | 600 | 600 | C2014-03 Organizational Development.xlsx
110 | 71 | Live | 2013-03-19 09:00 | 2013-03-26 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-06-24 08:00 | 15d | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
111 | 72 | Optimalisatie/standaardisatie | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
112 | 97 | Department N | 2012-09-04 08:00 | 2013-01-02 12:00 | 86d 4h |  |  | 0 |  |  | 3432 |  | 200d | [5 empty] | 8361 |  | 1 |  | 3432 | 3432 | C2014-03 Organizational Development.xlsx
113 | 73 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-10-08 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
114 | 123 | Directieteam extra 1 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-21 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
115 | 124 | Directieteam extra 2 | 2012-09-05 11:00 | 2012-09-05 12:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
116 | 74 | Organisatorische oefening | 2012-09-06 14:00 | 2012-10-25 14:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-15 08:00 | 65d | 3120 | 0 | 0 | 0 | 0 | 3120 | 0 | 1 | Finished | 1680 | 1680 | C2014-03 Organizational Development.xlsx
117 | 125 | Organisatorische oefening extra | 2012-10-25 14:00 | 2012-10-25 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
118 | 75 | Opleiding | 2012-10-26 16:00 | 2012-11-16 16:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 1 | Finished | 1080 | 1080 | C2014-03 Organizational Development.xlsx
119 | 126 | Opleiding extra 1 | 2012-11-16 16:00 | 2012-11-16 17:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-01-28 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 1 | Finished | 9 | 9 | C2014-03 Organizational Development.xlsx
120 | 127 | Opleiding extra 2 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-03-18 08:00 | 25d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 1 | Finished | 9 | 9 | C2014-03 Organizational Development.xlsx
121 | 76 | Testfase | 2012-11-21 11:00 | 2012-12-26 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-04-22 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | Finished | 600 | 600 | C2014-03 Organizational Development.xlsx
122 | 77 | Live | 2012-12-26 11:00 | 2013-01-02 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-04-22 08:00 | 60d | 72 | 0 | 0 | 0 | 0 | 72 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
123 | 78 | Optimalisatie/standaardisatie | 2013-01-02 11:00 | 2013-01-02 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
124 | 98 | Department O | 2012-09-18 08:00 | 2013-01-08 10:00 | 80d 2h |  |  | 0 |  |  | 765 |  | 105d 1h | [5 empty] | 3309 |  | 1 |  | 765 | 765 | C2014-03 Organizational Development.xlsx
125 | 79 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
126 | 80 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-10-22 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | Finished | 240 | 240 | C2014-03 Organizational Development.xlsx
127 | 81 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-10-22 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | Finished | 9 | 9 | C2014-03 Organizational Development.xlsx
128 | 82 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-10-22 08:00 | 15d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 1 | Finished | 480 | 480 | C2014-03 Organizational Development.xlsx
129 | 83 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 40d | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
130 | 84 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-11 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | Finished | 6 | 6 | C2014-03 Organizational Development.xlsx
131 | 128 | Hiatus | 2013-01-08 09:00 | 2013-01-08 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 25d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 1 | Finished | 12 | 12 | C2014-03 Organizational Development.xlsx
4 | 0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 844d | [5 empty] | 65526930.042 |  | 1 |  | 62385597.584 | 62385597.584 | C2014-04 Compressor Station Zelzate.xlsx
5 | 24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 1 | Finished | 6238559.9375 | 6238559.9375 | C2014-04 Compressor Station Zelzate.xlsx
6 | 1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 1 | Finished | 2052486.0234 | 2052486.0234 | C2014-04 Compressor Station Zelzate.xlsx
7 | 2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 1 | Finished | 879636.9766 | 879636.9766 | C2014-04 Compressor Station Zelzate.xlsx
8 | 3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 1 | Finished | 2564047.9922 | 2564047.9922 | C2014-04 Compressor Station Zelzate.xlsx
9 | 4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 1 | Finished | 2620195.0156 | 2620195.0156 | C2014-04 Compressor Station Zelzate.xlsx
10 | 5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 1 | Finished | 1116701.9531 | 1116701.9531 | C2014-04 Compressor Station Zelzate.xlsx
11 | 6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 1 | Finished | 1384960.0078 | 1384960.0078 | C2014-04 Compressor Station Zelzate.xlsx
12 | 7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 1 | Finished | 1391199.0234 | 1391199.0234 | C2014-04 Compressor Station Zelzate.xlsx
13 | 8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 1 | Finished | 4435615.9375 | 4435615.9375 | C2014-04 Compressor Station Zelzate.xlsx
14 | 9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 1 | Finished | 3668273.125 | 3668273.125 | C2014-04 Compressor Station Zelzate.xlsx
15 | 10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 1 | Finished | 2620194.9375 | 2620194.9375 | C2014-04 Compressor Station Zelzate.xlsx
16 | 11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 1 | Finished | 2626433.9688 | 2626433.9688 | C2014-04 Compressor Station Zelzate.xlsx
17 | 12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 1 | Finished | 7186820.8125 | 7186820.8125 | C2014-04 Compressor Station Zelzate.xlsx
18 | 13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 1 | Finished | 2663865.0156 | 2663865.0156 | C2014-04 Compressor Station Zelzate.xlsx
19 | 14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 1 | Finished | 2021293.0078 | 2021293.0078 | C2014-04 Compressor Station Zelzate.xlsx
20 | 15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 1 | Finished | 2738728.125 | 2738728.125 | C2014-04 Compressor Station Zelzate.xlsx
21 | 16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 1 | Finished | 2626433.9688 | 2626433.9688 | C2014-04 Compressor Station Zelzate.xlsx
22 | 17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 1 | Finished | 2595241 | 2595241 | C2014-04 Compressor Station Zelzate.xlsx
23 | 18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 1 | Finished | 1491015.9141 | 1491015.9141 | C2014-04 Compressor Station Zelzate.xlsx
24 | 19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 1 | Finished | 1297620.0195 | 1297620.0195 | C2014-04 Compressor Station Zelzate.xlsx
25 | 20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 12d | 475378.1719 | 0 | 0 | 0 | 0 | 475378.1719 | 0 | 1 | Finished | 792296.9531 | 792296.9531 | C2014-04 Compressor Station Zelzate.xlsx
26 | 21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 2008-04-15 08:00 | 122d | 23557990.3125 | 0 | 0 | -18239202 | 0 | 5318788.3125 | 0 | 1 | Finished | 4055063.9062 | 4055063.9062 | C2014-04 Compressor Station Zelzate.xlsx
27 | 22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 | 2008-10-08 08:00 | 73d | 662421.8896 | 0 | 0 | 876103.4375 | 0 | 1538525.3271 | 0 | 1 | Finished | 199633.9941 | 199633.9941 | C2014-04 Compressor Station Zelzate.xlsx
28 | 23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 | 2009-06-18 08:00 | 49d | 6947487.2031 | 0 | 0 | -3830555.5 | 0 | 3116931.7031 | 0 | 1 | Finished | 3119279.9688 | 3119279.9688 | C2014-04 Compressor Station Zelzate.xlsx
4 | 0 | Apartment Building (1) | 2011-10-03 08:00 | 2012-08-15 17:00 | 228d |  |  | 160067.4112 |  |  | 532410.2874 |  | 274d | [5 empty] | 591410.527 |  | 1 |  | 532410.2874 | 532410.2874 | C2014-05 Apartment Building (1).xlsx
5 | 1 | Sondering | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d |  | 0 | 620 | 0 | 0 | 620 | 2011-10-03 08:00 | 1d | 620 | 0 | 0 | 0 | 0 | 620 | 0 | 1 | Finished | 620 | 620 | C2014-05 Apartment Building (1).xlsx
6 | 2 | Inrichting | 2011-10-04 08:00 | 2011-10-04 17:00 | 1d |  | 0 | 679.65 | 198.23 | 1585.84 | 2265.49 | 2011-10-04 08:00 | 1d | 2265.49 | 0 | 0 | 0 | 0 | 2265.49 | 0 | 1 | Finished | 2265.49 | 2265.49 | C2014-05 Apartment Building (1).xlsx
7 | 3 | Bouwput + Kelders | 2011-10-19 08:00 | 2011-11-08 17:00 | 15d |  | 0 | 7924.96 | 154.1 | 18492.0007 | 26416.9607 | 2011-10-26 08:00 | 25d | 38744.9612 | 0 | 0 | 0 | 0 | 38744.9612 | 0 | 1 | Finished | 26416.9607 | 26416.9607 | C2014-05 Apartment Building (1).xlsx
8 | 4 | Bouw rioleringen | 2011-11-09 08:00 | 2011-11-29 17:00 | 15d |  | 0 | 9554.2002 | 185.78 | 22293.5999 | 31847.8 | 2011-11-30 08:00 | 20d | 39279 | 0 | 0 | 0 | 0 | 39279 | 0 | 1 | Finished | 31847.8 | 31847.8 | C2014-05 Apartment Building (1).xlsx
9 | 5 | Afbraakwerken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 2430 | 70.88 | 5670.3998 | 8100.3998 | 2011-10-05 08:00 | 15d | 10935.5997 | 0 | 0 | 0 | 0 | 10935.5997 | 0 | 1 | Finished | 8100.3998 | 8100.3998 | C2014-05 Apartment Building (1).xlsx
10 | 6 | Ruwbouw | 2011-11-30 08:00 | 2012-03-06 17:00 | 70d |  | 0 | 36455.0508 | 151.9 | 85063.9966 | 121519.0474 | 2011-12-28 08:00 | 90d | 145823.0464 | 0 | 0 | 0 | 0 | 145823.0464 | 0 | 1 | Finished | 121519.0474 | 121519.0474 | C2014-05 Apartment Building (1).xlsx
11 | 7 | Wachtgevel | 2012-03-07 08:00 | 2012-03-27 17:00 | 15d |  | 0 | 2937.1499 | 57.11 | 6853.2001 | 9790.35 | 2012-05-02 08:00 | 15d | 9790.35 | 0 | 0 | 0 | 0 | 9790.35 | 0 | 1 | Finished | 9790.35 | 9790.35 | C2014-05 Apartment Building (1).xlsx
12 | 8 | Dakisolatie | 2012-03-28 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 1663.59 | 48.52 | 3881.6 | 5545.19 | 2012-05-23 08:00 | 10d | 5545.19 | 0 | 0 | 0 | 0 | 5545.19 | 0 | 1 | Finished | 5545.19 | 5545.19 | C2014-05 Apartment Building (1).xlsx
13 | 9 | Dakbedekking & Zinkwerk | 2012-03-28 08:00 | 2012-05-08 17:00 | 30d |  | 0 | 13243.5801 | 128.76 | 30902.3987 | 44145.9788 | 2012-05-23 08:00 | 25d | 38995.579 | 0 | 0 | 0 | 0 | 38995.579 | 0 | 1 | Finished | 44145.9788 | 44145.9788 | C2014-05 Apartment Building (1).xlsx
14 | 10 | Buitenschrijnwerk | 2012-03-07 08:00 | 2012-04-03 17:00 | 20d |  | 0 | 21463.9805 | 313.02 | 50083.1982 | 71547.1787 | 2012-05-02 08:00 | 20d | 71547.1787 | 0 | 0 | 0 | 0 | 71547.1787 | 0 | 1 | Finished | 71547.1787 | 71547.1787 | C2014-05 Apartment Building (1).xlsx
15 | 11 | Sanitaire technieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 10020.4404 | 116.91 | 23382.0007 | 33402.4412 | 2012-06-27 08:00 | 30d | 38078.8413 | 0 | 0 | 0 | 0 | 38078.8413 | 0 | 1 | Finished | 33402.4412 | 33402.4412 | C2014-05 Apartment Building (1).xlsx
16 | 12 | Electriciteitstechnieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 8724.4297 | 101.79 | 20358.0002 | 29082.4299 | 2012-06-27 08:00 | 20d | 25010.8298 | 0 | 0 | 0 | 0 | 25010.8298 | 0 | 1 | Finished | 29082.4299 | 29082.4299 | C2014-05 Apartment Building (1).xlsx
17 | 13 | Ventilatietechnieken | 2012-05-09 08:00 | 2012-05-22 17:00 | 10d |  | 0 | 1917.6 | 55.93 | 4474.4 | 6392 | 2012-06-27 08:00 | 15d | 8629.2 | 0 | 0 | 0 | 0 | 8629.2 | 0 | 1 | Finished | 6392 | 6392 | C2014-05 Apartment Building (1).xlsx
18 | 14 | Trappen en Deuren | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 2906.04 | 169.52 | 6780.8002 | 9686.8402 | 2012-09-19 08:00 | 5d | 9686.8402 | 0 | 0 | 0 | 0 | 9686.8402 | 0 | 1 | Finished | 9686.8402 | 9686.8402 | C2014-05 Apartment Building (1).xlsx
19 | 15 | Keukens | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 1399.99 | 81.67 | 3266.7999 | 4666.7899 | 2012-09-19 08:00 | 10d | 7933.5898 | 0 | 0 | 0 | 0 | 7933.5898 | 0 | 1 | Finished | 4666.7899 | 4666.7899 | C2014-05 Apartment Building (1).xlsx
20 | 16 | Pleisterwerken | 2012-07-11 08:00 | 2012-07-24 17:00 | 10d |  | 0 | 4979.1401 | 145.22 | 11617.6001 | 16596.7402 | 2012-09-05 08:00 | 10d | 16596.7402 | 0 | 0 | 0 | 0 | 16596.7402 | 0 | 1 | Finished | 16596.7402 | 16596.7402 | C2014-05 Apartment Building (1).xlsx
21 | 17 | Buitenpleisterwerk | 2012-04-04 08:00 | 2012-04-24 17:00 | 15d |  | 0 | 10399.5498 | 202.21 | 24265.2008 | 34664.7506 | 2012-05-30 08:00 | 15d | 34664.7506 | 0 | 0 | 0 | 0 | 34664.7506 | 0 | 1 | Finished | 34664.7506 | 34664.7506 | C2014-05 Apartment Building (1).xlsx
22 | 18 | Afwerking Ventilatie | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 958.8 | 55.93 | 2237.2 | 3196 | 2012-09-19 08:00 | 10d | 5433.2 | 0 | 0 | 0 | 0 | 5433.2 | 0 | 1 | Finished | 3196 | 3196 | C2014-05 Apartment Building (1).xlsx
23 | 19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 3340.1499 | 97.42 | 7793.5999 | 11133.7498 | 2012-09-19 08:00 | 15d | 15030.5497 | 0 | 0 | 0 | 0 | 15030.5497 | 0 | 1 | Finished | 11133.7498 | 11133.7498 | C2014-05 Apartment Building (1).xlsx
24 | 20 | Afwerking | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 2908.1399 | 84.82 | 6785.6 | 9693.7399 | 2012-09-19 08:00 | 10d | 9693.7399 | 0 | 0 | 0 | 0 | 9693.7399 | 0 | 1 | Finished | 9693.7399 | 9693.7399 | C2014-05 Apartment Building (1).xlsx
25 | 21 | Chapewerken | 2012-06-13 08:00 | 2012-06-26 17:00 | 10d |  | 0 | 4264.8501 | 124.39 | 9951.2 | 14216.05 | 2012-08-08 08:00 | 10d | 14216.05 | 0 | 0 | 0 | 0 | 14216.05 | 0 | 1 | Finished | 14216.05 | 14216.05 | C2014-05 Apartment Building (1).xlsx
26 | 22 | Vloeren | 2012-06-27 08:00 | 2012-07-10 17:00 | 10d |  | 0 | 6533.21 | 190.55 | 15244.0002 | 21777.2102 | 2012-08-22 08:00 | 10d | 21777.2102 | 0 | 0 | 0 | 0 | 21777.2102 | 0 | 1 | Finished | 21777.2102 | 21777.2102 | C2014-05 Apartment Building (1).xlsx
27 | 23 | Buitenaanleg | 2011-11-30 08:00 | 2011-12-06 17:00 | 5d |  | 0 | 2021.1899 | 117.9 | 4716.0001 | 6737.19 | 2011-12-28 08:00 | 10d | 11453.1901 | 0 | 0 | 0 | 0 | 11453.1901 | 0 | 1 | Finished | 6737.19 | 6737.19 | C2014-05 Apartment Building (1).xlsx
28 | 24 | Schilderwerken | 2012-08-08 08:00 | 2012-08-14 17:00 | 5d |  | 0 | 2721.72 | 158.77 | 6350.8002 | 9072.5201 | 2012-10-10 08:00 | 5d | 9072.5201 | 0 | 0 | 0 | 0 | 9072.5201 | 0 | 1 | Finished | 9072.5201 | 9072.5201 | C2014-05 Apartment Building (1).xlsx
29 | 25 | Opkuis | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 36.68 | 293.44 | 293.44 | 2012-10-17 08:00 | 2d | 586.88 | 0 | 0 | 0 | 0 | 586.88 | 0 | 1 | Finished | 293.44 | 293.44 | C2014-05 Apartment Building (1).xlsx
4 | 0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 611d | [5 empty] | 3599114.1116 |  | 1 |  | 3486375.4699 | 3486375.4699 | C2014-06 Apartment Building (2).xlsx
5 | 1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 1 | Finished | 918.25 | 918.25 | C2014-06 Apartment Building (2).xlsx
6 | 2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 1 | Finished | 23316.2305 | 23316.2305 | C2014-06 Apartment Building (2).xlsx
7 | 3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 1 | Finished | 301581.3926 | 301581.3926 | C2014-06 Apartment Building (2).xlsx
8 | 4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 1 | Finished | 379002.7207 | 379002.7207 | C2014-06 Apartment Building (2).xlsx
9 | 5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 1 | Finished | 9632.5 | 9632.5 | C2014-06 Apartment Building (2).xlsx
10 | 6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 1 | Finished | 1708.42 | 1708.42 | C2014-06 Apartment Building (2).xlsx
11 | 7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 180d | 816497.8998 | 0 | 0 | 0 | 0 | 816497.8998 | 0 | 1 | Finished | 813478.6998 | 813478.6998 | C2014-06 Apartment Building (2).xlsx
12 | 8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 | 2010-02-03 08:00 | 15d | 23869.0804 | 0 | 0 | 0 | 0 | 23869.0804 | 0 | 1 | Finished | 27971.0806 | 27971.0806 | C2014-06 Apartment Building (2).xlsx
13 | 9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 | 2010-02-24 08:00 | 10d | 1922.65 | 0 | 0 | 0 | 0 | 1922.65 | 0 | 1 | Finished | 1922.65 | 1922.65 | C2014-06 Apartment Building (2).xlsx
14 | 10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 | 2010-02-24 08:00 | 15d | 121868.8207 | 0 | 0 | 0 | 0 | 121868.8207 | 0 | 1 | Finished | 128810.8208 | 128810.8208 | C2014-06 Apartment Building (2).xlsx
15 | 11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 | 2010-02-03 08:00 | 35d | 230024.7249 | 0 | 0 | 0 | 0 | 230024.7249 | 0 | 1 | Finished | 239770.3249 | 239770.3249 | C2014-06 Apartment Building (2).xlsx
16 | 12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 | 2010-03-17 08:00 | 74d | 230914.9022 | 0 | 0 | 0 | 0 | 230914.9022 | 0 | 1 | Finished | 227647.7023 | 227647.7023 | C2014-06 Apartment Building (2).xlsx
17 | 13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 | 2010-03-17 08:00 | 78d | 85933.937 | 0 | 0 | 0 | 0 | 85933.937 | 0 | 1 | Finished | 79576.1772 | 79576.1772 | C2014-06 Apartment Building (2).xlsx
18 | 14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 | 2010-03-17 08:00 | 60d | 30993.4906 | 0 | 0 | 0 | 0 | 30993.4906 | 0 | 1 | Finished | 24881.4905 | 24881.4905 | C2014-06 Apartment Building (2).xlsx
19 | 15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 | 2010-12-01 08:00 | 40d | 86234.2197 | 0 | 0 | 0 | 0 | 86234.2197 | 0 | 1 | Finished | 86234.2197 | 86234.2197 | C2014-06 Apartment Building (2).xlsx
20 | 16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 | 2010-12-01 08:00 | 55d | 179750.6016 | 0 | 0 | 0 | 0 | 179750.6016 | 0 | 1 | Finished | 169990.7615 | 169990.7615 | C2014-06 Apartment Building (2).xlsx
21 | 17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 | 2010-10-27 08:00 | 25d | 144107.8704 | 0 | 0 | 0 | 0 | 144107.8704 | 0 | 1 | Finished | 144107.8704 | 144107.8704 | C2014-06 Apartment Building (2).xlsx
22 | 18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 | 2010-03-24 08:00 | 20d | 38162.6392 | 0 | 0 | 0 | 0 | 38162.6392 | 0 | 1 | Finished | 38162.6392 | 38162.6392 | C2014-06 Apartment Building (2).xlsx
23 | 19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 | 2010-12-01 08:00 | 20d | 25833.0305 | 0 | 0 | 0 | 0 | 25833.0305 | 0 | 1 | Finished | 25833.0305 | 25833.0305 | C2014-06 Apartment Building (2).xlsx
24 | 20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 | 2010-12-01 08:00 | 50d | 232155.8169 | 0 | 0 | 0 | 0 | 232155.8169 | 0 | 1 | Finished | 232155.8169 | 232155.8169 | C2014-06 Apartment Building (2).xlsx
25 | 21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 | 2010-12-01 08:00 | 25d | 54629.999 | 0 | 0 | 0 | 0 | 54629.999 | 0 | 1 | Finished | 54629.999 | 54629.999 | C2014-06 Apartment Building (2).xlsx
26 | 22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 | 2010-03-17 08:00 | 10d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 1 | Finished | 56000 | 56000 | C2014-06 Apartment Building (2).xlsx
27 | 23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 | 2010-06-28 08:00 | 34d | 110642.2598 | 0 | 0 | 0 | 0 | 110642.2598 | 0 | 1 | Finished | 98800.3398 | 98800.3398 | C2014-06 Apartment Building (2).xlsx
28 | 24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 | 2010-08-18 08:00 | 50d | 206576.5923 | 0 | 0 | 0 | 0 | 206576.5923 | 0 | 1 | Finished | 206576.5923 | 206576.5923 | C2014-06 Apartment Building (2).xlsx
29 | 25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 | 2011-02-16 08:00 | 8d | 35543.3203 | 0 | 0 | 0 | 0 | 35543.3203 | 0 | 1 | Finished | 26480.9202 | 26480.9202 | C2014-06 Apartment Building (2).xlsx
30 | 26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 | 2011-02-16 08:00 | 5d | 43770.6406 | 0 | 0 | 0 | 0 | 43770.6406 | 0 | 1 | Finished | 43770.6406 | 43770.6406 | C2014-06 Apartment Building (2).xlsx
31 | 27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 | 2011-02-16 08:00 | 1d | 1826.09 | 0 | 0 | 0 | 0 | 1826.09 | 0 | 1 | Finished | 1826.09 | 1826.09 | C2014-06 Apartment Building (2).xlsx
32 | 28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 | 2011-02-28 08:00 | 3d | 13005.8901 | 0 | 0 | 0 | 0 | 13005.8901 | 0 | 1 | Finished | 21659.9702 | 21659.9702 | C2014-06 Apartment Building (2).xlsx
33 | 29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 | 2011-03-03 08:00 | 3d | 19928.1198 | 0 | 0 | 0 | 0 | 19928.1198 | 0 | 1 | Finished | 19928.1198 | 19928.1198 | C2014-06 Apartment Building (2).xlsx
4 | 0 | Apartment Building (3) | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 |  | 404d | [5 empty] | 1289696.7828 |  | 1 |  | 1102536.7838 | 1102536.7838 | C2014-07 Apartment Building (3).xlsx
5 | 1 | Sondering | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 2009-12-07 08:00 | 1d | 445.04 | 0 | 0 | 0 | 0 | 445.04 | 0 | 1 | Finished | 445.04 | 445.04 | C2014-07 Apartment Building (3).xlsx
6 | 2 | Inrichting | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 2009-12-08 08:00 | 1d | 3511.78 | 0 | 0 | 0 | 0 | 3511.78 | 0 | 1 | Finished | 3511.78 | 3511.78 | C2014-07 Apartment Building (3).xlsx
7 | 3 | Bouwput + Kelders | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 | 2010-01-27 08:00 | 30d | 69286.8679 | 0 | 0 | 0 | 0 | 69286.8679 | 0 | 1 | Finished | 51323.6685 | 51323.6685 | C2014-07 Apartment Building (3).xlsx
8 | 4 | Bouw rioleringen | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 | 2010-03-10 08:00 | 40d | 75661.7969 | 0 | 0 | 0 | 0 | 75661.7969 | 0 | 1 | Finished | 61347.3975 | 61347.3975 | C2014-07 Apartment Building (3).xlsx
9 | 5 | Afbraakwerken | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 2009-12-09 08:00 | 35d | 26658.9993 | 0 | 0 | 0 | 0 | 26658.9993 | 0 | 1 | Finished | 16661.7996 | 16661.7996 | C2014-07 Apartment Building (3).xlsx
10 | 6 | Ruwbouw | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 | 2010-05-05 08:00 | 100d | 305966.7812 | 0 | 0 | 0 | 0 | 305966.7812 | 0 | 1 | Finished | 283886.7812 | 283886.7812 | C2014-07 Apartment Building (3).xlsx
11 | 7 | Dakstructuur | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 | 2010-08-25 08:00 | 35d | 39476.7006 | 0 | 0 | 0 | 0 | 39476.7006 | 0 | 1 | Finished | 35352.3005 | 35352.3005 | C2014-07 Apartment Building (3).xlsx
12 | 8 | Dakisolatie | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 | 2010-10-13 08:00 | 20d | 7499.6002 | 0 | 0 | 0 | 0 | 7499.6002 | 0 | 1 | Finished | 7499.6002 | 7499.6002 | C2014-07 Apartment Building (3).xlsx
13 | 9 | Dakbedekking & Zinkwerk | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 | 2010-10-13 08:00 | 30d | 55714.2109 | 0 | 0 | 0 | 0 | 55714.2109 | 0 | 1 | Finished | 55714.2109 | 55714.2109 | C2014-07 Apartment Building (3).xlsx
14 | 10 | Plaatsen Ramen | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 | 2010-08-25 08:00 | 30d | 130653.4619 | 0 | 0 | 0 | 0 | 130653.4619 | 0 | 1 | Finished | 76855.061 | 76855.061 | C2014-07 Apartment Building (3).xlsx
15 | 11 | Sanitaire technieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 | 2010-11-24 08:00 | 55d | 69439.3799 | 0 | 0 | 0 | 0 | 69439.3799 | 0 | 1 | Finished | 64896.58 | 64896.58 | C2014-07 Apartment Building (3).xlsx
16 | 12 | Elektriciteitstechnieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 | 2010-11-24 08:00 | 50d | 40662.4614 | 0 | 0 | 0 | 0 | 40662.4614 | 0 | 1 | Finished | 40662.4614 | 40662.4614 | C2014-07 Apartment Building (3).xlsx
17 | 13 | Ventilatietechnieken | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 | 2010-11-24 08:00 | 35d | 19089.4003 | 0 | 0 | 0 | 0 | 19089.4003 | 0 | 1 | Finished | 17095.0002 | 17095.0002 | C2014-07 Apartment Building (3).xlsx
18 | 14 | Trappen en Deuren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 | 2011-04-27 08:00 | 25d | 49221.371 | 0 | 0 | 0 | 0 | 49221.371 | 0 | 1 | Finished | 41890.5708 | 41890.5708 | C2014-07 Apartment Building (3).xlsx
19 | 15 | Keukens | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 | 2011-04-27 08:00 | 30d | 57002.699 | 0 | 0 | 0 | 0 | 57002.699 | 0 | 1 | Finished | 42224.2993 | 42224.2993 | C2014-07 Apartment Building (3).xlsx
20 | 16 | Pleisterwerken | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 | 2011-03-30 08:00 | 20d | 52630.9595 | 0 | 0 | 0 | 0 | 52630.9595 | 0 | 1 | Finished | 52630.9595 | 52630.9595 | C2014-07 Apartment Building (3).xlsx
21 | 17 | Buitenpleisterwerk | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 | 2010-10-06 08:00 | 20d | 43275.0391 | 0 | 0 | 0 | 0 | 43275.0391 | 0 | 1 | Finished | 35087.8394 | 35087.8394 | C2014-07 Apartment Building (3).xlsx
22 | 18 | Afwerking Ventilatie | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 | 2011-04-27 08:00 | 10d | 8547.5001 | 0 | 0 | 0 | 0 | 8547.5001 | 0 | 1 | Finished | 8547.5001 | 8547.5001 | C2014-07 Apartment Building (3).xlsx
23 | 19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 | 2011-04-27 08:00 | 15d | 26769.4908 | 0 | 0 | 0 | 0 | 26769.4908 | 0 | 1 | Finished | 32447.8911 | 32447.8911 | C2014-07 Apartment Building (3).xlsx
24 | 20 | Afwerking | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 | 2011-04-27 08:00 | 15d | 27107.9106 | 0 | 0 | 0 | 0 | 27107.9106 | 0 | 1 | Finished | 27107.9106 | 27107.9106 | C2014-07 Apartment Building (3).xlsx
25 | 21 | Chapewerken | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 | 2011-02-02 08:00 | 20d | 31661.5098 | 0 | 0 | 0 | 0 | 31661.5098 | 0 | 1 | Finished | 25671.5098 | 25671.5098 | C2014-07 Apartment Building (3).xlsx
26 | 22 | Vloeren | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 | 2011-03-02 08:00 | 20d | 68045.752 | 0 | 0 | 0 | 0 | 68045.752 | 0 | 1 | Finished | 68045.752 | 68045.752 | C2014-07 Apartment Building (3).xlsx
27 | 23 | Tuinaanleg | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 | 2010-05-05 08:00 | 15d | 45151.8694 | 0 | 0 | 0 | 0 | 45151.8694 | 0 | 1 | Finished | 33445.8696 | 33445.8696 | C2014-07 Apartment Building (3).xlsx
28 | 24 | Schilderwerken | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 | 2011-06-08 08:00 | 10d | 30722.4009 | 0 | 0 | 0 | 0 | 30722.4009 | 0 | 1 | Finished | 18072.0005 | 18072.0005 | C2014-07 Apartment Building (3).xlsx
29 | 25 | Opkuis | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 | 2011-06-21 08:00 | 3d | 5493.8001 | 0 | 0 | 0 | 0 | 5493.8001 | 0 | 1 | Finished | 2113 | 2113 | C2014-07 Apartment Building (3).xlsx
4 | 0 | Apartment Building (4) | 2011-06-17 08:00 | 2012-05-08 17:00 | 233d |  |  | 0 |  |  | 1992222.0874 |  | 275d | [5 empty] | 2380299.8593 |  | 1 |  | 1992222.0874 | 1992222.0874 | C2014-08 Apartment Building (4).xlsx
5 | 40 | Algemeen | 2011-06-17 08:00 | 2011-12-22 17:00 | 135d |  |  | 0 |  |  | 298460.1586 |  | 150d | [5 empty] | 346819.5576 |  | 1 |  | 298460.1586 | 298460.1586 | C2014-08 Apartment Building (4).xlsx
6 | 1 | Werfinrichting | 2011-06-17 08:00 | 2011-06-20 17:00 | 2d |  | 0 | 0 | 418.81 | 6700.96 | 6700.96 | 2011-06-17 08:00 | 3d | 10051.4399 | 0 | 0 | -1005.14 | 0 | 9046.2999 | 0 | 1 | Finished | 6700.96 | 6700.96 | C2014-08 Apartment Building (4).xlsx
7 | 2 | Ontmanteling | 2011-06-21 08:00 | 2011-07-25 17:00 | 25d |  | 0 | 0 | 167.23 | 33445.9991 | 33445.9991 | 2011-06-22 08:00 | 35d | 46824.3988 | 0 | 0 | -4013.52 | 0 | 42810.8788 | 0 | 1 | Finished | 33445.9991 | 33445.9991 | C2014-08 Apartment Building (4).xlsx
8 | 3 | Ruwbouw Aanpassingen | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 890.55 | 142487.998 | 142487.998 | 2011-09-02 08:00 | 25d | 178109.9976 | 0 | 0 | -10686.5703 | 0 | 167423.4272 | 0 | 1 | Finished | 142487.998 | 142487.998 | C2014-08 Apartment Building (4).xlsx
9 | 4 | Valleidingen in schachten | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 843.69 | 67495.2002 | 67495.2002 | 2011-10-07 08:00 | 10d | 67495.2002 | 0 | 0 | 0 | 0 | 67495.2002 | 0 | 1 | Finished | 67495.2002 | 67495.2002 | C2014-08 Apartment Building (4).xlsx
10 | 5 | Dakisolatie 6de verdieping | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 418.35 | 16734.0002 | 16734.0002 | 2011-10-21 08:00 | 10d | 33468.0005 | 0 | 0 | -5020.25 | 0 | 28447.7505 | 0 | 1 | Finished | 16734.0002 | 16734.0002 | C2014-08 Apartment Building (4).xlsx
11 | 6 | Herstelling Liften | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 789.9 | 31596.001 | 31596.001 | 2012-01-06 08:00 | 5d | 31596.001 | 0 | 0 | 0 | 0 | 31596.001 | 0 | 1 | Finished | 31596.001 | 31596.001 | C2014-08 Apartment Building (4).xlsx
12 | 41 | Verdiepingen (6) | 2011-09-30 08:00 | 2012-05-08 17:00 | 158d |  |  | 0 |  |  | 1457768.0874 |  | 195d | [5 empty] | 1721107.1488 |  | 1 |  | 1457768.0874 | 1457768.0874 | C2014-08 Apartment Building (4).xlsx
13 | 7 | Uitzetten wanden | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 193.48 | 15478.3997 | 15478.3997 | 2011-10-07 08:00 | 15d | 23217.5995 | 0 | 0 | -2321.76 | 0 | 20895.8395 | 0 | 1 | Finished | 15478.3997 | 15478.3997 | C2014-08 Apartment Building (4).xlsx
14 | 8 | Leidingen Technieken | 2011-10-14 08:00 | 2011-10-27 17:00 | 10d |  | 0 | 0 | 1625.3101 | 130024.8047 | 130024.8047 | 2011-10-28 08:00 | 5d | 65012.4023 | 0 | 0 | 19503.6797 | 0 | 84516.082 | 0 | 1 | Finished | 130024.8047 | 130024.8047 | C2014-08 Apartment Building (4).xlsx
15 | 9 | Dekvloer (Chapewerken) | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1432.71 | 57308.3984 | 57308.3984 | 2011-11-04 08:00 | 5d | 57308.3984 | 0 | 0 | 0 | 0 | 57308.3984 | 0 | 1 | Finished | 57308.3984 | 57308.3984 | C2014-08 Apartment Building (4).xlsx
16 | 10 | Gyproc fase 1 | 2011-11-04 08:00 | 2011-12-01 17:00 | 20d |  | 0 | 0 | 657.99 | 105278.3984 | 105278.3984 | 2011-11-11 08:00 | 25d | 131597.998 | 0 | 0 | -7895.9199 | 0 | 123702.0781 | 0 | 1 | Finished | 105278.3984 | 105278.3984 | C2014-08 Apartment Building (4).xlsx
17 | 11 | Elektriciteit in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 962.54 | 77003.1982 | 77003.1982 | 2011-12-16 08:00 | 15d | 115504.7974 | 0 | 0 | -11550.5098 | 0 | 103954.2876 | 0 | 1 | Finished | 77003.1982 | 77003.1982 | C2014-08 Apartment Building (4).xlsx
18 | 12 | Sanitair in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 1083.53 | 86682.4023 | 86682.4023 | 2011-12-16 08:00 | 15d | 130023.6035 | 0 | 0 | -13002.2998 | 0 | 117021.3037 | 0 | 1 | Finished | 86682.4023 | 86682.4023 | C2014-08 Apartment Building (4).xlsx
19 | 13 | Gyproc fase 2 (dichten wanden) | 2011-12-16 08:00 | 2011-12-29 17:00 | 10d |  | 0 | 0 | 657.99 | 52639.1992 | 52639.1992 | 2012-01-06 08:00 | 10d | 52639.1992 | 0 | 0 | 0 | 0 | 52639.1992 | 0 | 1 | Finished | 52639.1992 | 52639.1992 | C2014-08 Apartment Building (4).xlsx
20 | 14 | Pleisterwerken | 2011-12-30 08:00 | 2012-01-05 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 | 2012-01-20 08:00 | 5d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 1 | Finished | 15000 | 15000 | C2014-08 Apartment Building (4).xlsx
21 | 15 | Plaatsen Sanitaire Installaties | 2012-01-06 08:00 | 2012-01-12 17:00 | 5d |  | 0 | 0 | 3051.1299 | 122045.1953 | 122045.1953 | 2012-01-27 08:00 | 10d | 244090.3906 | 0 | 0 | -36613.5781 | 0 | 207476.8125 | 0 | 1 | Finished | 122045.1953 | 122045.1953 | C2014-08 Apartment Building (4).xlsx
22 | 16 | Stenen vloeren en Faiences | 2012-01-13 08:00 | 2012-02-02 17:00 | 15d |  | 0 | 0 | 502.18 | 60261.5991 | 60261.5991 | 2012-02-10 08:00 | 15d | 60261.5991 | 0 | 0 | 0 | 0 | 60261.5991 | 0 | 1 | Finished | 60261.5991 | 60261.5991 | C2014-08 Apartment Building (4).xlsx
23 | 17 | Technieken Ventilatie | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 812.65 | 65012.002 | 65012.002 | 2012-03-02 08:00 | 10d | 65012.002 | 0 | 0 | 0 | 0 | 65012.002 | 0 | 1 | Finished | 65012.002 | 65012.002 | C2014-08 Apartment Building (4).xlsx
24 | 18 | Buitenschrijnwerk | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 1457.05 | 116564.0039 | 116564.0039 | 2012-03-02 08:00 | 15d | 174846.0059 | 0 | 0 | -17484.6094 | 0 | 157361.3965 | 0 | 1 | Finished | 116564.0039 | 116564.0039 | C2014-08 Apartment Building (4).xlsx
25 | 19 | Terrassen | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 344.33 | 41319.5984 | 41319.5984 | 2012-03-23 08:00 | 10d | 27546.3989 | 0 | 0 | 4131.9302 | 0 | 31678.3291 | 0 | 1 | Finished | 41319.5984 | 41319.5984 | C2014-08 Apartment Building (4).xlsx
26 | 20 | Gyproc: Vals plafond | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 657.99 | 78958.7988 | 78958.7988 | 2012-03-23 08:00 | 15d | 78958.7988 | 0 | 0 | 0 | 0 | 78958.7988 | 0 | 1 | Finished | 78958.7988 | 78958.7988 | C2014-08 Apartment Building (4).xlsx
27 | 21 | Parket | 2012-03-09 08:00 | 2012-03-22 17:00 | 10d |  | 0 | 0 | 630.88 | 50470.4004 | 50470.4004 | 2012-04-13 08:00 | 15d | 75705.6006 | 0 | 0 | -7570.5 | 0 | 68135.1006 | 0 | 1 | Finished | 50470.4004 | 50470.4004 | C2014-08 Apartment Building (4).xlsx
28 | 22 | Binnenschrijnwerk | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 0 | 1063.64 | 85091.2012 | 85091.2012 | 2012-05-04 08:00 | 15d | 127636.8018 | 0 | 0 | -12763.6396 | 0 | 114873.1621 | 0 | 1 | Finished | 85091.2012 | 85091.2012 | C2014-08 Apartment Building (4).xlsx
29 | 23 | Keukens | 2012-03-23 08:00 | 2012-04-19 17:00 | 20d |  | 0 | 0 | 1525.4301 | 244068.8086 | 244068.8086 | 2012-05-04 08:00 | 25d | 305086.0107 | 0 | 0 | -18305.1895 | 0 | 286780.8213 | 0 | 1 | Finished | 244068.8086 | 244068.8086 | C2014-08 Apartment Building (4).xlsx
30 | 24 | Afwerken Elektriciteit en Sanitair | 2012-04-20 08:00 | 2012-05-03 17:00 | 10d |  | 0 | 0 | 481.27 | 38501.5991 | 38501.5991 | 2012-06-08 08:00 | 15d | 57752.3987 | 0 | 0 | -5775.2598 | 0 | 51977.1389 | 0 | 1 | Finished | 38501.5991 | 38501.5991 | C2014-08 Apartment Building (4).xlsx
31 | 25 | Opkuis | 2012-05-04 08:00 | 2012-05-08 17:00 | 3d |  | 0 | 0 | 669.17 | 16060.0796 | 16060.0796 | 2012-06-29 08:00 | 5d | 26766.7993 | 0 | 0 | -3212 | 0 | 23554.7993 | 0 | 1 | Finished | 16060.0796 | 16060.0796 | C2014-08 Apartment Building (4).xlsx
32 | 42 | Gelijkvloers | 2011-10-14 08:00 | 2012-01-30 17:00 | 77d |  |  | 0 |  |  | 235993.8414 |  | 97d | [5 empty] | 312373.1528 |  | 1 |  | 235993.8414 | 235993.8414 | C2014-08 Apartment Building (4).xlsx
33 | 26 | Uitzetten wanden | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 161.33 | 6453.2001 | 6453.2001 | 2011-10-28 08:00 | 10d | 12906.4001 | 0 | 0 | -1935.96 | 0 | 10970.4402 | 0 | 1 | Finished | 6453.2001 | 6453.2001 | C2014-08 Apartment Building (4).xlsx
34 | 27 | Leidingen Technieken | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1083.54 | 43341.6016 | 43341.6016 | 2011-11-11 08:00 | 10d | 86683.2031 | 0 | 0 | -13002.4502 | 0 | 73680.7529 | 0 | 1 | Finished | 43341.6016 | 43341.6016 | C2014-08 Apartment Building (4).xlsx
35 | 28 | Dekvloer (Chapewerken) | 2011-11-04 08:00 | 2011-11-10 17:00 | 5d |  | 0 | 0 | 736.8 | 29471.9995 | 29471.9995 | 2011-11-25 08:00 | 5d | 29471.9995 | 0 | 0 | 0 | 0 | 29471.9995 | 0 | 1 | Finished | 29471.9995 | 29471.9995 | C2014-08 Apartment Building (4).xlsx
36 | 29 | Gyproc fase 1 | 2011-11-11 08:00 | 2011-11-24 17:00 | 10d |  | 0 | 0 | 438.66 | 35092.8003 | 35092.8003 | 2011-12-02 08:00 | 15d | 52639.2004 | 0 | 0 | -5263.9399 | 0 | 47375.2605 | 0 | 1 | Finished | 35092.8003 | 35092.8003 | C2014-08 Apartment Building (4).xlsx
37 | 30 | Elektriciteit in wanden | 2011-11-25 08:00 | 2011-12-01 17:00 | 5d |  | 0 | 0 | 320.85 | 12834.0002 | 12834.0002 | 2011-12-23 08:00 | 5d | 12834.0002 | 0 | 0 | 0 | 0 | 12834.0002 | 0 | 1 | Finished | 12834.0002 | 12834.0002 | C2014-08 Apartment Building (4).xlsx
38 | 31 | Gyproc fase 2 (dichten wanden) | 2011-12-02 08:00 | 2011-12-08 17:00 | 5d |  | 0 | 0 | 438.66 | 17546.4001 | 17546.4001 | 2011-12-30 08:00 | 10d | 35092.8003 | 0 | 0 | -5263.9399 | 0 | 29828.8604 | 0 | 1 | Finished | 17546.4001 | 17546.4001 | C2014-08 Apartment Building (4).xlsx
39 | 32 | Pleisterwerken | 2011-12-09 08:00 | 2011-12-15 17:00 | 5d |  | 0 | 0 | 230.8 | 9232.0001 | 9232.0001 | 2012-01-13 08:00 | 5d | 9232.0001 | 0 | 0 | 0 | 0 | 9232.0001 | 0 | 1 | Finished | 9232.0001 | 9232.0001 | C2014-08 Apartment Building (4).xlsx
40 | 33 | Stenen vloeren en Faiences | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 251.09 | 10043.5999 | 10043.5999 | 2012-01-20 08:00 | 10d | 20087.1997 | 0 | 0 | -3013.05 | 0 | 17074.1497 | 0 | 1 | Finished | 10043.5999 | 10043.5999 | C2014-08 Apartment Building (4).xlsx
41 | 34 | Buitenschrijnwerk | 2011-12-23 08:00 | 2011-12-29 17:00 | 5d |  | 0 | 0 | 485.66 | 19426.4001 | 19426.4001 | 2012-02-03 08:00 | 5d | 19426.4001 | 0 | 0 | 0 | 0 | 19426.4001 | 0 | 1 | Finished | 19426.4001 | 19426.4001 | C2014-08 Apartment Building (4).xlsx
42 | 35 | Gyproc: Vals plafond | 2011-12-30 08:00 | 2012-01-12 17:00 | 10d |  | 0 | 0 | 329 | 26320 | 26320 | 2012-02-10 08:00 | 10d | 26320 | 0 | 0 | 0 | 0 | 26320 | 0 | 1 | Finished | 26320 | 26320 | C2014-08 Apartment Building (4).xlsx
43 | 36 | Binnenschrijnwerk | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 354.55 | 14181.9995 | 14181.9995 | 2012-02-24 08:00 | 10d | 28363.999 | 0 | 0 | -4254.5498 | 0 | 24109.4492 | 0 | 1 | Finished | 14181.9995 | 14181.9995 | C2014-08 Apartment Building (4).xlsx
44 | 37 | Brievenbussen | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 73.91 | 2956.4001 | 2956.4001 | 2012-02-24 08:00 | 5d | 2956.4001 | 0 | 0 | 0 | 0 | 2956.4001 | 0 | 1 | Finished | 2956.4001 | 2956.4001 | C2014-08 Apartment Building (4).xlsx
45 | 38 | Afwerken Elektriciteit | 2012-01-20 08:00 | 2012-01-26 17:00 | 5d |  | 0 | 0 | 160.42 | 6416.7999 | 6416.7999 | 2012-03-02 08:00 | 5d | 6416.7999 | 0 | 0 | 0 | 0 | 6416.7999 | 0 | 1 | Finished | 6416.7999 | 6416.7999 | C2014-08 Apartment Building (4).xlsx
46 | 39 | Opkuis | 2012-01-27 08:00 | 2012-01-30 17:00 | 2d |  | 0 | 0 | 167.29 | 2676.6399 | 2676.6399 | 2012-03-09 08:00 | 2d | 2676.6399 | 0 | 0 | 0 | 0 | 2676.6399 | 0 | 1 | Finished | 2676.6399 | 2676.6399 | C2014-08 Apartment Building (4).xlsx
4 | 0 | Young Cattle Barn (2) | 2010-09-08 08:00 | 2011-03-09 17:00 | 131d |  |  | 0 |  |  | 612769.4399 |  | 209d 7h | [5 empty] | 646473.646 |  | 1 |  | 612769.4399 | 612769.4399 | C2015-01 Young Cattle Barn (2).xlsx
5 | 1 | werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 0 | 104.63 | 8370.3998 | 8370.3998 | 2010-09-08 08:00 | 10d | 8370.3998 | 0 | 0 | 0 | 0 | 8370.3998 | 0 | 1 | Finished | 8370.3998 | 8370.3998 | C2015-01 Young Cattle Barn (2).xlsx
6 | 2 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-09-13 08:00 | 15d | 43805.9985 | 0 | 0 | -26666.0293 | 0 | 17139.9692 | 0 | 1 | Finished | 14601.9995 | 14601.9995 | C2015-01 Young Cattle Barn (2).xlsx
7 | 3 | omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 0 | 2424.1299 | 19393.0391 | 19393.0391 | 2010-09-13 08:00 | 3d | 58179.1172 | 0 | 0 | -38786.1211 | 0 | 19392.9961 | 0 | 1 | Finished | 19393.0391 | 19393.0391 | C2015-01 Young Cattle Barn (2).xlsx
8 | 4 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2010-11-29 08:00 | 15d | 120 | 0 | 0 | 10930 | 0 | 11050 | 0 | 1 | Finished | 1 | 1 | C2015-01 Young Cattle Barn (2).xlsx
9 | 5 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 289.45 | 11578.0005 | 11578.0005 | 2010-10-04 08:00 | 2d | 4631.2002 | 0 | 0 | 14695.4102 | 0 | 19326.6104 | 0 | 1 | Finished | 11578.0005 | 11578.0005 | C2015-01 Young Cattle Barn (2).xlsx
10 | 6 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-12-20 08:00 | 2d 7h | 8396.1497 | 0 | 0 | 6942.8501 | 0 | 15338.9998 | 0 | 1 | Finished | 14601.9995 | 14601.9995 | C2015-01 Young Cattle Barn (2).xlsx
11 | 7 | plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 0 | 272.68 | 21814.3994 | 21814.3994 | 2010-10-14 08:00 | 10d | 21814.3994 | 0 | 0 | 6746.5 | 0 | 28560.8994 | 0 | 1 | Finished | 21814.3994 | 21814.3994 | C2015-01 Young Cattle Barn (2).xlsx
12 | 8 | funderingswanden | 2010-10-06 08:00 | 2010-11-02 17:00 | 20d |  | 0 | 0 | 448.54 | 71766.4014 | 71766.4014 | 2010-11-02 08:00 | 15d | 53824.801 | 0 | 0 | 33081.1484 | 0 | 86905.9495 | 0 | 1 | Finished | 71766.4014 | 71766.4014 | C2015-01 Young Cattle Barn (2).xlsx
13 | 9 | Draagvloeren | 2010-11-04 08:00 | 2010-11-17 17:00 | 10d |  | 0 | 0 | 615.95 | 49276.001 | 49276.001 | 2011-01-17 08:00 | 5d | 24638.0005 | 0 | 0 | 18294.0801 | 0 | 42932.0806 | 0 | 1 | Finished | 49276.001 | 49276.001 | C2015-01 Young Cattle Barn (2).xlsx
14 | 10 | wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 0 | 126.9 | 2030.4 | 2030.4 | 2011-02-14 08:00 | 3d | 3045.6 | 0 | 0 | -669.93 | 0 | 2375.67 | 0 | 1 | Finished | 2030.4 | 2030.4 | C2015-01 Young Cattle Barn (2).xlsx
15 | 11 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 157.6 | 6304.0002 | 6304.0002 | 2011-03-07 08:00 | 9d | 11347.2004 | 0 | 0 | -5422.3901 | 0 | 5924.8103 | 0 | 1 | Finished | 6304.0002 | 6304.0002 | C2015-01 Young Cattle Barn (2).xlsx
16 | 12 | wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 0 | 126.9 | 3045.6 | 3045.6 | 2011-02-14 08:00 | 3d | 3045.6 | 0 | 0 | 518.03 | 0 | 3563.6301 | 0 | 1 | Finished | 3045.6 | 3045.6 | C2015-01 Young Cattle Barn (2).xlsx
17 | 13 | betonnen binnenwanden | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2011-03-21 08:00 | 10d | 80 | 0 | 0 | 10301.5 | 0 | 10381.5 | 0 | 1 | Finished | 1 | 1 | C2015-01 Young Cattle Barn (2).xlsx
18 | 14 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 0 | 1559.88 | 62395.2002 | 62395.2002 | 2011-02-21 08:00 | 8d | 99832.3203 | 0 | 0 | -41126.3203 | 0 | 58706 | 0 | 1 | Finished | 62395.2002 | 62395.2002 | C2015-01 Young Cattle Barn (2).xlsx
19 | 15 | structuurelementen-gew.beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 1679.67 | 67186.8018 | 67186.8018 | 2011-03-07 08:00 | 5d | 67186.8018 | 0 | 0 | 15457.2695 | 0 | 82644.0713 | 0 | 1 | Finished | 67186.8018 | 67186.8018 | C2015-01 Young Cattle Barn (2).xlsx
20 | 16 | Dakstructuur | 2010-12-20 08:00 | 2010-12-20 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2011-03-21 08:00 | 5d | 40 | 0 | 0 | 15743.4404 | 0 | 15783.4404 | 0 | 1 | Finished | 1 | 1 | C2015-01 Young Cattle Barn (2).xlsx
21 | 17 | Dakwerken | 2010-12-21 08:00 | 2011-01-03 17:00 | 10d |  | 0 | 0 | 832.29 | 66583.1982 | 66583.1982 | 2011-04-20 08:00 | 7d | 46608.2388 | 0 | 0 | -8569.29 | 0 | 38038.9487 | 0 | 1 | Finished | 66583.1982 | 66583.1982 | C2015-01 Young Cattle Barn (2).xlsx
22 | 18 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 0 | 426.4 | 34111.9995 | 34111.9995 | 2011-04-15 08:00 | 6d | 20467.1997 | 0 | 0 | 12194.2002 | 0 | 32661.3999 | 0 | 1 | Finished | 34111.9995 | 34111.9995 | C2015-01 Young Cattle Barn (2).xlsx
23 | 19 | Gevelbekledingen | 2011-01-19 08:00 | 2011-02-01 17:00 | 10d |  | 0 | 0 | 239.73 | 19178.3997 | 19178.3997 | 2011-05-04 08:00 | 9d | 17260.5597 | 0 | 0 | -13006.5098 | 0 | 4254.0499 | 0 | 1 | Finished | 19178.3997 | 19178.3997 | C2015-01 Young Cattle Barn (2).xlsx
24 | 20 | Rioleringen | 2011-01-27 08:00 | 2011-02-09 17:00 | 10d |  | 0 | 0 | 348.54 | 27883.2007 | 27883.2007 | 2011-05-25 08:00 | 23d | 64131.3616 | 0 | 0 | -37598.3594 | 0 | 26533.0022 | 0 | 1 | Finished | 27883.2007 | 27883.2007 | C2015-01 Young Cattle Barn (2).xlsx
25 | 21 | Omgevingeswerken | 2011-02-10 08:00 | 2011-03-09 17:00 | 20d |  | 0 | 0 | 150.53 | 24084.7998 | 24084.7998 | 2011-06-17 08:00 | 7d 7h | 9483.3899 | 0 | 0 | 17458.6094 | 0 | 26941.9993 | 0 | 1 | Finished | 24084.7998 | 24084.7998 | C2015-01 Young Cattle Barn (2).xlsx
26 | 22 | Elektrische windzeilen | 2011-01-04 08:00 | 2011-01-04 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2011-06-23 08:00 | 2d | 16 | 0 | 0 | 5587.5 | 0 | 5603.5 | 0 | 1 | Finished | 1 | 1 | C2015-01 Young Cattle Barn (2).xlsx
27 | 23 | Binnenplaatafwerking | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 0 | 57.8 | 4623.9999 | 4623.9999 | 2011-05-11 08:00 | 1h | 57.8 | 0 | 0 | -57.8 | 0 | 0 | 0 | 1 | Finished | 4623.9999 | 4623.9999 | C2015-01 Young Cattle Barn (2).xlsx
28 | 24 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 0 | 45.81 | 1832.4001 | 1832.4001 | 2011-06-15 08:00 | 7h | 320.67 | 0 | 0 | 1231.58 | 0 | 1552.25 | 0 | 1 | Finished | 1832.4001 | 1832.4001 | C2015-01 Young Cattle Barn (2).xlsx
29 | 25 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 0 | 380.34 | 45640.7996 | 45640.7996 | 2011-05-04 08:00 | 11d | 33469.9197 | 0 | 0 | 12959.6396 | 0 | 46429.5593 | 0 | 1 | Finished | 45640.7996 | 45640.7996 | C2015-01 Young Cattle Barn (2).xlsx
30 | 26 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 219.75 | 35160 | 35160 | 2011-05-11 08:00 | 12d | 21096 | 0 | 0 | 13663.5098 | 0 | 34759.5098 | 0 | 1 | Finished | 35160 | 35160 | C2015-01 Young Cattle Barn (2).xlsx
31 | 27 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 8.14 | 1302.4001 | 1302.4001 | 2011-05-11 08:00 | 20d | 1302.4001 | 0 | 0 | 0 | 0 | 1302.4001 | 0 | 1 | Finished | 1302.4001 | 1302.4001 | C2015-01 Young Cattle Barn (2).xlsx
4 | 0 | Railway Station (1) | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 1121316.9422 |  | 501d | [5 empty] | 967988.7905 |  | 1 |  | 1121316.9422 | 1121316.9422 | C2015-02 Railway Station (1).xlsx
5 | 49 | Grondwerken en infrastructuur-zone B | 2011-01-10 08:00 | 2011-07-08 17:00 | 130d |  |  | 0 |  |  | 213962.3182 |  | 335d | [5 empty] | 302546.9178 |  | 1 |  | 213962.3182 | 213962.3182 | C2015-02 Railway Station (1).xlsx
6 | 1 | Werfinstalatie | 2011-01-11 08:00 | 2011-04-15 17:00 | 69d |  | 0 | 0 | 301.34 | 166339.678 | 166339.678 | 2011-01-10 08:00 | 90d | 216964.7974 | 0 | 0 | 0 | 0 | 216964.7974 | 0 | 1 | Finished | 166339.678 | 166339.678 | C2015-02 Railway Station (1).xlsx
7 | 2 | afbraakwerken en ontmanteling perrons | 2011-01-10 08:00 | 2011-02-18 17:00 | 30d |  | 0 | 0 | 3.67 | 880.8 | 880.8 | 2011-01-10 08:00 | 30d | 880.8 | 0 | 0 | 0 | 0 | 880.8 | 0 | 1 | Finished | 880.8 | 880.8 | C2015-02 Railway Station (1).xlsx
8 | 3 | test uitvoering talud | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-02-11 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
9 | 4 | grondwerken (1ste) | 2011-01-25 08:00 | 2011-02-25 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-02-21 08:00 | 12d | 1528.32 | 0 | 0 | 0 | 0 | 1528.32 | 0 | 1 | Finished | 3056.64 | 3056.64 | C2015-02 Railway Station (1).xlsx
10 | 5 | vermaling talud 1ste niveau | 2011-02-07 08:00 | 2011-02-24 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 2011-02-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 1 | Finished | 1783.04 | 1783.04 | C2015-02 Railway Station (1).xlsx
11 | 6 | bescherming talud 1ste niveau | 2011-02-08 08:00 | 2011-03-04 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-02-28 08:00 | 11d | 1400.96 | 0 | 0 | 0 | 0 | 1400.96 | 0 | 1 | Finished | 2419.84 | 2419.84 | C2015-02 Railway Station (1).xlsx
12 | 7 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 11d | 0.88 | 0 | 0 | 1400.96 | 0 | 1401.84 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
13 | 8 | grondwerken (2de) | 2011-02-15 08:00 | 2011-03-14 17:00 | 20d |  | 0 | 0 | 15.92 | 2547.2 | 2547.2 | 2011-03-21 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 1 | Finished | 2547.2 | 2547.2 | C2015-02 Railway Station (1).xlsx
14 | 9 | vermaling beschoeiing & talud (2de niveau) | 2011-02-21 08:00 | 2011-03-15 17:00 | 17d |  | 0 | 0 | 15.92 | 2165.12 | 2165.12 | 2011-03-23 08:00 | 27d | 3438.72 | 0 | 0 | 0 | 0 | 3438.72 | 0 | 1 | Finished | 2165.12 | 2165.12 | C2015-02 Railway Station (1).xlsx
15 | 10 | bescherming talud - 2de niveau | 2011-02-25 08:00 | 2011-03-15 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-03-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 1 | Finished | 1655.68 | 1655.68 | C2015-02 Railway Station (1).xlsx
16 | 11 | beschoeiing | 2011-01-28 08:00 | 2011-03-01 17:00 | 23d |  | 0 | 0 | 15.92 | 2929.28 | 2929.28 | 2011-04-07 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 1 | Finished | 2929.28 | 2929.28 | C2015-02 Railway Station (1).xlsx
17 | 12 | grondwerken fase 3 | 2011-03-11 08:00 | 2011-03-25 17:00 | 11d |  | 0 | 0 | 15.92 | 1400.96 | 1400.96 | 2011-08-15 08:00 | 72d | 9169.92 | 0 | 0 | 0 | 0 | 9169.92 | 0 | 1 | Finished | 1400.96 | 1400.96 | C2015-02 Railway Station (1).xlsx
18 | 13 | diepe fundering | 2011-03-17 08:00 | 2011-03-30 17:00 | 10d |  | 0 | 0 | 15.92 | 1273.6 | 1273.6 | 2011-08-18 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 1 | Finished | 1273.6 | 1273.6 | C2015-02 Railway Station (1).xlsx
19 | 14 | riolering en aarding | 2011-03-21 08:00 | 2011-05-18 17:00 | 43d |  | 0 | 0 | 15.92 | 5476.48 | 5476.48 | 2011-08-16 08:00 | 79d | 10061.44 | 0 | 0 | 0 | 0 | 10061.44 | 0 | 1 | Finished | 5476.48 | 5476.48 | C2015-02 Railway Station (1).xlsx
20 | 15 | vloerplaat -1 | 2011-03-28 08:00 | 2011-06-27 17:00 | 66d |  | 0 | 0 | 15.92 | 8405.76 | 8405.76 | 2011-08-08 08:00 | 88d | 11207.6801 | 0 | 0 | 0 | 0 | 11207.6801 | 0 | 1 | Finished | 8405.76 | 8405.76 | C2015-02 Railway Station (1).xlsx
21 | 16 | vloerkolommen en wanden | 2011-04-11 08:00 | 2011-07-04 17:00 | 61d |  | 0 | 0 | 15.92 | 7768.96 | 7768.96 | 2011-08-30 08:00 | 79d | 10061.44 | 0 | 0 | 0 | 0 | 10061.44 | 0 | 1 | Finished | 7768.96 | 7768.96 | C2015-02 Railway Station (1).xlsx
22 | 17 | vloerplaat gelijkvloers | 2011-05-06 08:00 | 2011-07-08 17:00 | 46d |  | 0 | 0 | 15.92 | 5858.56 | 5858.56 | 2011-11-17 08:00 | 74d | 9424.64 | 0 | 0 | 0 | 0 | 9424.64 | 0 | 1 | Finished | 5858.56 | 5858.56 | C2015-02 Railway Station (1).xlsx
23 | 18 | verankering talud 3de niveau | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-19 08:00 | 15d | 1.2 | 0 | 0 | 1910.4 | 0 | 1911.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
24 | 19 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-26 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
25 | 20 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-18 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
26 | 21 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-17 08:00 | 73d | 5.84 | 0 | 0 | 9292.2803 | 0 | 9298.1203 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
27 | 22 | ontdubbelde vloerplaat -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-11 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
28 | 23 | kolommen staal overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-18 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
29 | 24 | kolommen staal overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-25 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
30 | 50 | Grondwerken en infrastructuur-zone C | 2011-01-10 08:00 | 2011-10-21 17:00 | 205d |  |  | 0 |  |  | 67095.0404 |  | 337d | [5 empty] | 67400.5602 |  | 1 |  | 67095.0404 | 67095.0404 | C2015-02 Railway Station (1).xlsx
31 | 25 | plaatsing bescherming reizigers | 2011-01-21 08:00 | 2011-03-10 17:00 | 35d |  | 0 | 0 | 3.67 | 1027.6 | 1027.6 | 2011-03-07 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 1 | Finished | 1027.6 | 1027.6 | C2015-02 Railway Station (1).xlsx
32 | 26 | afbraakwerken en ontmanteling perron | 2011-01-10 08:00 | 2011-02-28 17:00 | 36d |  | 0 | 0 | 3.67 | 1056.96 | 1056.96 | 2011-01-10 08:00 | 36d | 1056.96 | 0 | 0 | 0 | 0 | 1056.96 | 0 | 1 | Finished | 1056.96 | 1056.96 | C2015-02 Railway Station (1).xlsx
33 | 27 | afbraakwerken reizigerstunnel | 2011-03-11 08:00 | 2011-05-16 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 1 | Finished | 1379.92 | 1379.92 | C2015-02 Railway Station (1).xlsx
34 | 28 | afbraakwerken diensttunnel | 2011-02-16 08:00 | 2011-04-01 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 1 | Finished | 968.88 | 968.88 | C2015-02 Railway Station (1).xlsx
35 | 29 | grondwerken(1ste) | 2011-02-16 08:00 | 2011-04-04 17:00 | 34d |  | 0 | 0 | 15.92 | 4330.24 | 4330.24 | 2011-05-06 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 1 | Finished | 4330.24 | 4330.24 | C2015-02 Railway Station (1).xlsx
36 | 30 | vermaling talud - 1ste niv | 2011-03-03 08:00 | 2011-03-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-05-16 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 1 | Finished | 1655.68 | 1655.68 | C2015-02 Railway Station (1).xlsx
37 | 31 | bescherming talud - 1ste niv | 2011-03-04 08:00 | 2011-03-24 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-05-17 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 1 | Finished | 1910.4 | 1910.4 | C2015-02 Railway Station (1).xlsx
38 | 32 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-20 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
39 | 33 | grondwerken (2de niv) | 2011-04-11 08:00 | 2011-05-13 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 | 2011-05-24 08:00 | 21d | 2674.56 | 0 | 0 | 0 | 0 | 2674.56 | 0 | 1 | Finished | 3184 | 3184 | C2015-02 Railway Station (1).xlsx
40 | 34 | vermaling beschoeiing & talud - 2de niv | 2011-04-21 08:00 | 2011-05-19 17:00 | 21d |  | 0 | 0 | 15.92 | 2674.56 | 2674.56 | 2011-06-01 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 1 | Finished | 2674.56 | 2674.56 | C2015-02 Railway Station (1).xlsx
41 | 35 | bescherming talud - 2de niv | 2011-05-03 08:00 | 2011-05-19 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-06-07 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 1 | Finished | 1655.68 | 1655.68 | C2015-02 Railway Station (1).xlsx
42 | 36 | beschoeiiing | 2011-02-22 08:00 | 2011-03-30 17:00 | 27d |  | 0 | 0 | 15.92 | 3438.72 | 3438.72 | 2011-08-11 08:00 | 21d | 2674.56 | 0 | 0 | 0 | 0 | 2674.56 | 0 | 1 | Finished | 3438.72 | 3438.72 | C2015-02 Railway Station (1).xlsx
43 | 37 | grondwerken - fase 3 | 2011-05-11 08:00 | 2011-06-01 17:00 | 16d |  | 0 | 0 | 15.92 | 2037.76 | 2037.76 | 2011-08-18 08:00 | 18d | 2292.48 | 0 | 0 | 0 | 0 | 2292.48 | 0 | 1 | Finished | 2037.76 | 2037.76 | C2015-02 Railway Station (1).xlsx
44 | 38 | verankering talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 14d | 1.12 | 0 | 0 | 1783.04 | 0 | 1784.16 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
45 | 39 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-23 08:00 | 30d | 2.4 | 0 | 0 | 1783.04 | 0 | 1785.44 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
46 | 40 | diepe fundering | 2011-05-16 08:00 | 2011-06-16 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-08-24 08:00 | 18d | 2292.48 | 0 | 0 | 0 | 0 | 2292.48 | 0 | 1 | Finished | 3056.64 | 3056.64 | C2015-02 Railway Station (1).xlsx
47 | 41 | riolering en aarding | 2011-05-18 08:00 | 2011-08-29 17:00 | 74d |  | 0 | 0 | 15.92 | 9424.64 | 9424.64 | 2011-11-25 08:00 | 10d | 1273.6 | 0 | 0 | 0 | 0 | 1273.6 | 0 | 1 | Finished | 9424.64 | 9424.64 | C2015-02 Railway Station (1).xlsx
48 | 42 | vloerplaat -1 | 2011-05-25 08:00 | 2011-09-26 17:00 | 89d |  | 0 | 0 | 15.92 | 11335.0401 | 11335.0401 | 2011-09-07 08:00 | 115d | 14646.4001 | 0 | 0 | 0 | 0 | 14646.4001 | 0 | 1 | Finished | 11335.0401 | 11335.0401 | C2015-02 Railway Station (1).xlsx
49 | 43 | kolommen en wanden | 2011-06-15 08:00 | 2011-10-12 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 | 2012-01-09 08:00 | 63d | 8023.68 | 0 | 0 | 0 | 0 | 8023.68 | 0 | 1 | Finished | 10952.9601 | 10952.9601 | C2015-02 Railway Station (1).xlsx
50 | 44 | vloerplaat gelijkvloers | 2011-08-08 08:00 | 2011-10-21 17:00 | 55d |  | 0 | 0 | 15.92 | 7004.8 | 7004.8 | 2012-03-20 08:00 | 26d | 3311.36 | 0 | 0 | 0 | 0 | 3311.36 | 0 | 1 | Finished | 7004.8 | 7004.8 | C2015-02 Railway Station (1).xlsx
51 | 45 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-23 08:00 | 10d | 0.8 | 0 | 0 | 1273.6 | 0 | 1274.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
52 | 46 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-29 08:00 | 61d | 4.88 | 0 | 0 | 7768.96 | 0 | 7773.84 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
53 | 47 | ontdubbelde vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-30 08:00 | 9d | 0.72 | 0 | 0 | 1146.24 | 0 | 1146.96 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
54 | 48 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-07 08:00 | 10d | 0.8 | 0 | 0 | 1273.6 | 0 | 1274.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
55 | 69 | Grondwerken en infrastructuur-zone D | 2011-01-10 08:00 | 2011-10-18 17:00 | 202d |  |  | 0 |  |  | 33295.8402 |  | 498d | [5 empty] | 39271.0401 |  | 1 |  | 33295.8402 | 33295.8402 | C2015-02 Railway Station (1).xlsx
56 | 51 | plaatsing bescherming reizigers | 2011-02-08 08:00 | 2011-03-25 17:00 | 34d |  | 0 | 0 | 3.67 | 998.24 | 998.24 | 2011-04-14 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 1 | Finished | 998.24 | 998.24 | C2015-02 Railway Station (1).xlsx
57 | 52 | afbraakwerken wegtunnel | 2011-01-13 08:00 | 2011-03-18 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-01-13 08:00 | 47d | 1379.92 | 0 | 0 | 0 | 0 | 1379.92 | 0 | 1 | Finished | 1379.92 | 1379.92 | C2015-02 Railway Station (1).xlsx
58 | 53 | afbraakwerken tramtunnel (deel 1) | 2011-03-04 08:00 | 2011-04-15 17:00 | 31d |  | 0 | 0 | 3.67 | 910.16 | 910.16 | 2011-04-26 08:00 | 29d | 851.44 | 0 | 0 | 0 | 0 | 851.44 | 0 | 1 | Finished | 910.16 | 910.16 | C2015-02 Railway Station (1).xlsx
59 | 54 | afbraakwerken tramtunnel (deel 2) | 2011-03-28 08:00 | 2011-05-11 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-05-18 08:00 | 33d | 968.88 | 0 | 0 | 0 | 0 | 968.88 | 0 | 1 | Finished | 968.88 | 968.88 | C2015-02 Railway Station (1).xlsx
60 | 55 | grondwerken (1ste niv) | 2011-05-03 08:00 | 2011-06-06 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 | 2012-12-10 08:00 | 1d | 127.36 | 0 | 0 | 0 | 0 | 127.36 | 0 | 1 | Finished | 3184 | 3184 | C2015-02 Railway Station (1).xlsx
61 | 56 | vermalling talud - 1ste niv | 2011-05-24 08:00 | 2011-06-10 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 2012-03-12 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 1 | Finished | 1783.04 | 1783.04 | C2015-02 Railway Station (1).xlsx
62 | 57 | grondwerken | 2011-06-01 08:00 | 2011-06-21 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-06-07 08:00 | 25d | 3184 | 0 | 0 | 0 | 0 | 3184 | 0 | 1 | Finished | 1910.4 | 1910.4 | C2015-02 Railway Station (1).xlsx
63 | 58 | Beschoeiing liftput | 2011-06-03 08:00 | 2011-06-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2012-12-10 08:00 | 1d | 127.36 | 0 | 0 | 0 | 0 | 127.36 | 0 | 1 | Finished | 1655.68 | 1655.68 | C2015-02 Railway Station (1).xlsx
64 | 59 | diepe fundering 1 | 2011-06-07 08:00 | 2011-07-01 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-10-12 08:00 | 5d | 636.8 | 0 | 0 | 0 | 0 | 636.8 | 0 | 1 | Finished | 2419.84 | 2419.84 | C2015-02 Railway Station (1).xlsx
65 | 60 | diepe fundering 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-29 08:00 | 6d | 0.48 | 0 | 0 | 0 | 0 | 0.48 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
66 | 61 | riolering en aarding | 2011-06-20 08:00 | 2011-09-05 17:00 | 56d |  | 0 | 0 | 15.92 | 7132.16 | 7132.16 | 2011-12-08 08:00 | 41d | 5221.76 | 0 | 0 | 0 | 0 | 5221.76 | 0 | 1 | Finished | 7132.16 | 7132.16 | C2015-02 Railway Station (1).xlsx
67 | 62 | funderingszolen | 2011-06-21 08:00 | 2011-10-18 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 | 2011-11-03 08:00 | 78d | 9934.08 | 0 | 0 | 0 | 0 | 9934.08 | 0 | 1 | Finished | 10952.9601 | 10952.9601 | C2015-02 Railway Station (1).xlsx
68 | 63 | Bufferbekken onder | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-02 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
69 | 64 | Bufferbekken midden | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-04 08:00 | 25d | 2 | 0 | 0 | 3184 | 0 | 3186 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
70 | 65 | verplatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-30 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
71 | 66 | funderingszolen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-19 08:00 | 24d | 1.92 | 0 | 0 | 3056.6399 | 0 | 3058.5599 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
72 | 67 | bufferbekken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-08-21 08:00 | 30d | 2.4 | 0 | 0 | 3820.8 | 0 | 3823.2 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
73 | 68 | beschoeiing achter lift | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-18 08:00 | 18d | 1.44 | 0 | 0 | 2292.48 | 0 | 2293.92 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
74 | 87 | Superstructuur-zone B | 2011-01-10 08:00 | 2011-09-29 17:00 | 189d |  |  | 0 |  |  | 73415.839 |  | 301d | [5 empty] | 59682.1594 |  | 1 |  | 73415.839 | 73415.839 | C2015-02 Railway Station (1).xlsx
75 | 70 | uitvoering kolommen | 2011-05-12 08:00 | 2011-07-08 17:00 | 42d |  | 0 | 0 | 28.15 | 9458.3999 | 9458.3999 | 2012-12-10 08:00 | 1d | 225.2 | 0 | 0 | 0 | 0 | 225.2 | 0 | 1 | Finished | 9458.3999 | 9458.3999 | C2015-02 Railway Station (1).xlsx
76 | 71 | uitvoering structuur overspanning 1 | 2011-05-19 08:00 | 2011-07-04 17:00 | 33d |  | 0 | 0 | 28.15 | 7431.5999 | 7431.5999 | 2011-11-28 08:00 | 64d | 14412.7998 | 0 | 0 | 0 | 0 | 14412.7998 | 0 | 1 | Finished | 7431.5999 | 7431.5999 | C2015-02 Railway Station (1).xlsx
77 | 72 | structurele afwerking overspanning 1 | 2011-06-14 08:00 | 2011-08-16 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 | 2012-02-24 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 1 | Finished | 10359.1999 | 10359.1999 | C2015-02 Railway Station (1).xlsx
78 | 73 | uitvoering structuur overspanning 2 | 2011-06-14 08:00 | 2011-08-05 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 | 2012-03-27 08:00 | 22d | 4954.3999 | 0 | 0 | 0 | 0 | 4954.3999 | 0 | 1 | Finished | 8782.7999 | 8782.7999 | C2015-02 Railway Station (1).xlsx
79 | 74 | structurele afwerking overspanning 2 | 2011-06-30 08:00 | 2011-09-01 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 | 2012-04-04 08:00 | 24d | 5404.7999 | 0 | 0 | 0 | 0 | 5404.7999 | 0 | 1 | Finished | 10359.1999 | 10359.1999 | C2015-02 Railway Station (1).xlsx
80 | 75 | uitvoering structuur overspanning 3 | 2011-06-30 08:00 | 2011-08-22 17:00 | 38d |  | 0 | 0 | 28.15 | 8557.5999 | 8557.5999 | 2012-03-27 08:00 | 22d | 4954.3999 | 0 | 0 | 0 | 0 | 4954.3999 | 0 | 1 | Finished | 8557.5999 | 8557.5999 | C2015-02 Railway Station (1).xlsx
81 | 76 | structurele afwerking overspanning 3 | 2011-08-04 08:00 | 2011-09-15 17:00 | 31d |  | 0 | 0 | 28.15 | 6981.1999 | 6981.1999 | 2012-04-24 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 1 | Finished | 6981.1999 | 6981.1999 | C2015-02 Railway Station (1).xlsx
82 | 77 | uitvoering structuur overspanning 4 | 2011-08-04 08:00 | 2011-09-01 17:00 | 21d |  | 0 | 0 | 28.15 | 4729.1999 | 4729.1999 | 2012-05-02 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 1 | Finished | 4729.1999 | 4729.1999 | C2015-02 Railway Station (1).xlsx
83 | 78 | structurele afwerking overspanning 4 | 2011-08-19 08:00 | 2011-09-29 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 | 2012-05-31 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 1 | Finished | 6755.9999 | 6755.9999 | C2015-02 Railway Station (1).xlsx
84 | 79 | plaatsing kolommen staal-overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-17 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
85 | 80 | plaatsing kolommen staal-overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-17 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
86 | 81 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-21 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
87 | 82 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-21 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
88 | 83 | ontkisten 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-20 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
89 | 84 | ontkisten 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-24 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
90 | 85 | ontkisten 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-20 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
91 | 86 | ontkisten 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-31 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
92 | 115 | Superstructuur-zone C | 2011-01-10 08:00 | 2012-01-17 17:00 | 267d |  |  | 0 |  |  | 91207.1188 |  | 206d | [5 empty] | 71621.4393 |  | 1 |  | 91207.1188 | 91207.1188 | C2015-02 Railway Station (1).xlsx
93 | 88 | uitvoering kolommen | 2011-09-01 08:00 | 2011-11-29 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 2012-12-10 08:00 | 1d | 225.2 | 0 | 0 | 0 | 0 | 225.2 | 0 | 1 | Finished | 14412.7998 | 14412.7998 | C2015-02 Railway Station (1).xlsx
94 | 89 | uitvoering structuur groot overspanning 1 | 2011-09-15 08:00 | 2011-12-16 17:00 | 67d |  | 0 | 0 | 28.15 | 15088.3998 | 15088.3998 | 2012-03-29 08:00 | 34d | 7656.7999 | 0 | 0 | 0 | 0 | 7656.7999 | 0 | 1 | Finished | 15088.3998 | 15088.3998 | C2015-02 Railway Station (1).xlsx
95 | 90 | uitvoering structuur groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 28.15 | 225.2 | 225.2 | 2012-04-25 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 1 | Finished | 225.2 | 225.2 | C2015-02 Railway Station (1).xlsx
96 | 91 | structurele afwerking groot overspanning 1 | 2011-10-20 08:00 | 2012-01-17 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 2012-06-14 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 1 | Finished | 14412.7998 | 14412.7998 | C2015-02 Railway Station (1).xlsx
97 | 92 | structurele afwerking groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-16 08:00 | 15d | 1.2 | 0 | 0 | 3378 | 0 | 3379.2 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
98 | 93 | uitvoering structuur overspanning 5 | 2011-08-19 08:00 | 2011-09-15 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-05-23 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 1 | Finished | 4503.9999 | 4503.9999 | C2015-02 Railway Station (1).xlsx
99 | 94 | structurele afwerking overspanning 5 | 2011-09-02 08:00 | 2011-10-13 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 | 2012-06-15 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 1 | Finished | 6755.9999 | 6755.9999 | C2015-02 Railway Station (1).xlsx
100 | 95 | uitvoering structuur overspanning 6 | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-06-20 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 1 | Finished | 4503.9999 | 4503.9999 | C2015-02 Railway Station (1).xlsx
101 | 96 | structurele afwerking overspanning 6 | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 | 2012-07-09 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 1 | Finished | 6755.9999 | 6755.9999 | C2015-02 Railway Station (1).xlsx
102 | 97 | uitvoering structuur overspanning 7 | 2011-09-16 08:00 | 2011-10-13 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-06-06 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 1 | Finished | 4503.9999 | 4503.9999 | C2015-02 Railway Station (1).xlsx
103 | 98 | structurele afwerking overspanning 7 | 2011-09-30 08:00 | 2011-11-16 17:00 | 34d |  | 0 | 0 | 28.15 | 7656.7999 | 7656.7999 | 2012-06-28 08:00 | 25d | 5629.9999 | 0 | 0 | 0 | 0 | 5629.9999 | 0 | 1 | Finished | 7656.7999 | 7656.7999 | C2015-02 Railway Station (1).xlsx
104 | 99 | uitvoering structuur overspanning 8 | 2011-09-30 08:00 | 2011-10-27 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-05-09 08:00 | 25d | 5629.9999 | 0 | 0 | 0 | 0 | 5629.9999 | 0 | 1 | Finished | 4503.9999 | 4503.9999 | C2015-02 Railway Station (1).xlsx
105 | 100 | structurele afwerking overspanning 8 | 2011-10-17 08:00 | 2011-12-02 17:00 | 35d |  | 0 | 0 | 28.15 | 7881.9999 | 7881.9999 | 2012-06-08 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 1 | Finished | 7881.9999 | 7881.9999 | C2015-02 Railway Station (1).xlsx
106 | 101 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-08 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
107 | 102 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-26 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
108 | 103 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-02-27 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
109 | 104 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-12 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
110 | 105 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-14 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
111 | 106 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-28 08:00 | 11d | 0.88 | 0 | 0 | 2477.2 | 0 | 2478.08 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
112 | 107 | opstorten vloerplaat na plaatsing kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-08 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
113 | 108 | dichtstellen openingen vloerplaat boven -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-18 08:00 | 9d | 0.72 | 0 | 0 | 2026.8 | 0 | 2027.52 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
114 | 109 | verplaatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-24 08:00 | 10d | 0.8 | 0 | 0 | 2252 | 0 | 2252.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
115 | 111 | ontkisten 5 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-15 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
116 | 112 | ontkisten 7 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-07-06 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
117 | 113 | ontkisten 6 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-06-14 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
118 | 114 | ontkisten 8 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-06-27 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
119 | 135 | Superstructuur-zone D | 2011-01-10 08:00 | 2012-02-14 17:00 | 287d |  |  | 0 |  |  | 65083.7591 |  | 196d | [5 empty] | 49099.7595 |  | 1 |  | 65083.7591 | 65083.7591 | C2015-02 Railway Station (1).xlsx
120 | 116 | uitvoering kolommen | 2011-08-31 08:00 | 2011-11-28 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 2012-12-10 08:00 | 1d | 225.2 | 0 | 0 | 0 | 0 | 225.2 | 0 | 1 | Finished | 14412.7998 | 14412.7998 | C2015-02 Railway Station (1).xlsx
121 | 117 | uitvoering structuur overspanning 9 | 2011-10-17 08:00 | 2011-11-23 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 | 2012-05-25 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 1 | Finished | 6305.5999 | 6305.5999 | C2015-02 Railway Station (1).xlsx
122 | 118 | structurele afwerking overspanning 9 | 2011-11-04 08:00 | 2011-12-23 17:00 | 36d |  | 0 | 0 | 28.15 | 8107.1999 | 8107.1999 | 2012-06-27 08:00 | 30d | 6755.9999 | 0 | 0 | 0 | 0 | 6755.9999 | 0 | 1 | Finished | 8107.1999 | 8107.1999 | C2015-02 Railway Station (1).xlsx
123 | 119 | uitvoering structuur overspanning 10 | 2011-11-03 08:00 | 2011-12-12 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 | 2012-06-04 08:00 | 19d | 4278.7999 | 0 | 0 | 0 | 0 | 4278.7999 | 0 | 1 | Finished | 6305.5999 | 6305.5999 | C2015-02 Railway Station (1).xlsx
124 | 120 | structurele afwerking overspanning 10 | 2011-12-05 08:00 | 2012-02-07 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 | 2012-08-01 08:00 | 21d | 4729.1999 | 0 | 0 | 0 | 0 | 4729.1999 | 0 | 1 | Finished | 10584.3999 | 10584.3999 | C2015-02 Railway Station (1).xlsx
125 | 121 | uitvoering structuur overspanning 11 | 2011-11-22 08:00 | 2012-01-13 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 | 2012-06-11 08:00 | 19d | 4278.7999 | 0 | 0 | 0 | 0 | 4278.7999 | 0 | 1 | Finished | 8782.7999 | 8782.7999 | C2015-02 Railway Station (1).xlsx
126 | 122 | structurele afwerking overspanning 11 | 2011-12-12 08:00 | 2012-02-14 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 | 2012-07-11 08:00 | 31d | 6981.1999 | 0 | 0 | 0 | 0 | 6981.1999 | 0 | 1 | Finished | 10584.3999 | 10584.3999 | C2015-02 Railway Station (1).xlsx
127 | 123 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-30 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
128 | 124 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-12 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
129 | 125 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-11 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
130 | 126 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-14 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
131 | 127 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-13 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
132 | 128 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-23 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
133 | 129 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-17 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
134 | 130 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-04 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
135 | 131 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-19 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
136 | 132 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-17 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
137 | 133 | Plaatsing HS kabel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-23 08:00 | 15d | 1.2 | 0 | 0 | 3378 | 0 | 3379.2 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
138 | 134 | montage bekisting | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-02 08:00 | 15d | 1.2 | 0 | 0 | 3378 | 0 | 3379.2 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
139 | 150 | KOK A | 2011-01-10 08:00 | 2012-08-09 17:00 | 414d |  |  | 0 |  |  | 50117.5188 |  | 149d | [5 empty] | 12470.96 |  | 1 |  | 50117.5188 | 50117.5188 | C2015-02 Railway Station (1).xlsx
140 | 136 | Plaatsing staalstructuur | 2011-11-10 08:00 | 2012-01-20 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 | 2012-10-01 08:00 | 10d | 1272 | 0 | 0 | 0 | 0 | 1272 | 0 | 1 | Finished | 6614.3998 | 6614.3998 | C2015-02 Railway Station (1).xlsx
141 | 137 | dackdichting-beplanting | 2012-01-13 08:00 | 2012-03-26 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 | 2012-10-17 08:00 | 5d | 636 | 0 | 0 | 0 | 0 | 636 | 0 | 1 | Finished | 6614.3998 | 6614.3998 | C2015-02 Railway Station (1).xlsx
142 | 138 | dakdichting-waterdichting | 2012-01-30 08:00 | 2012-05-16 17:00 | 78d |  | 0 | 0 | 15.9 | 9921.5998 | 9921.5998 | 2012-10-25 08:00 | 4d | 508.8 | 0 | 0 | 0 | 0 | 508.8 | 0 | 1 | Finished | 9921.5998 | 9921.5998 | C2015-02 Railway Station (1).xlsx
143 | 139 | afwerking perron | 2012-02-20 08:00 | 2012-08-09 17:00 | 124d |  | 0 | 0 | 15.9 | 15772.7996 | 15772.7996 | 2012-12-10 08:00 | 1d | 127.2 | 0 | 0 | 0 | 0 | 127.2 | 0 | 1 | Finished | 15772.7996 | 15772.7996 | C2015-02 Railway Station (1).xlsx
144 | 140 | plaatsing lift | 2012-02-23 08:00 | 2012-06-25 17:00 | 88d |  | 0 | 0 | 15.9 | 11193.5997 | 11193.5997 | 2012-08-13 08:00 | 11d | 1399.2 | 0 | 0 | 0 | 0 | 1399.2 | 0 | 1 | Finished | 11193.5997 | 11193.5997 | C2015-02 Railway Station (1).xlsx
145 | 141 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-22 08:00 | 5d | 0.4 | 0 | 0 | 636 | 0 | 636.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
146 | 142 | voorbereiding perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-16 08:00 | 38d | 3.04 | 0 | 0 | 4833.6001 | 0 | 4836.6401 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
147 | 143 | integratie speciale technieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-17 08:00 | 5d | 0.4 | 0 | 0 | 636 | 0 | 636.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
148 | 144 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-26 08:00 | 3d | 0.24 | 0 | 0 | 381.6 | 0 | 381.84 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
149 | 145 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-31 08:00 | 5d | 0.4 | 0 | 0 | 636 | 0 | 636.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
150 | 146 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-01 08:00 | 1d | 0.08 | 0 | 0 | 127.2 | 0 | 127.28 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
151 | 147 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-26 08:00 | 3d | 0.24 | 0 | 0 | 381.6 | 0 | 381.84 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
152 | 148 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-04 08:00 | 3d | 0.24 | 0 | 0 | 381.6 | 0 | 381.84 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
153 | 149 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-25 08:00 | 4d | 0.32 | 0 | 0 | 508.8 | 0 | 509.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
154 | 165 | KOK B | 2011-01-10 08:00 | 2012-08-03 17:00 | 410d |  |  | 0 |  |  | 52740.3985 |  | 56d | [5 empty] | 6443.0398 |  | 1 |  | 52740.3985 | 52740.3985 | C2015-02 Railway Station (1).xlsx
155 | 151 | voorbereiding perron | 2011-09-14 08:00 | 2011-12-15 17:00 | 67d |  | 0 | 0 | 15.19 | 8141.8398 | 8141.8398 | 2012-12-10 08:00 | 1d | 121.52 | 0 | 0 | 0 | 0 | 121.52 | 0 | 1 | Finished | 8141.8398 | 8141.8398 | C2015-02 Railway Station (1).xlsx
156 | 152 | plaatsing staalstructuur | 2011-10-05 08:00 | 2012-01-17 17:00 | 75d |  | 0 | 0 | 15.19 | 9113.9997 | 9113.9997 | 2012-10-01 08:00 | 10d | 1215.2 | 0 | 0 | 0 | 0 | 1215.2 | 0 | 1 | Finished | 9113.9997 | 9113.9997 | C2015-02 Railway Station (1).xlsx
157 | 153 | dakdichting - beplanting | 2011-11-18 08:00 | 2012-01-31 17:00 | 53d |  | 0 | 0 | 15.19 | 6440.5598 | 6440.5598 | 2012-10-15 08:00 | 5d | 607.6 | 0 | 0 | 0 | 0 | 607.6 | 0 | 1 | Finished | 6440.5598 | 6440.5598 | C2015-02 Railway Station (1).xlsx
158 | 154 | dakdichting - waterdichting | 2011-12-05 08:00 | 2012-03-15 17:00 | 74d |  | 0 | 0 | 15.19 | 8992.4798 | 8992.4798 | 2012-10-23 08:00 | 5d | 607.6 | 0 | 0 | 0 | 0 | 607.6 | 0 | 1 | Finished | 8992.4798 | 8992.4798 | C2015-02 Railway Station (1).xlsx
159 | 155 | afwerking perron | 2011-12-19 08:00 | 2012-08-03 17:00 | 165d |  | 0 | 0 | 15.19 | 20050.7994 | 20050.7994 | 2012-12-10 08:00 | 1d | 121.52 | 0 | 0 | 0 | 0 | 121.52 | 0 | 1 | Finished | 20050.7994 | 20050.7994 | C2015-02 Railway Station (1).xlsx
160 | 156 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-19 08:00 | 4d | 0.32 | 0 | 0 | 486.08 | 0 | 486.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
161 | 157 | integrateie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-17 08:00 | 4d | 0.32 | 0 | 0 | 486.08 | 0 | 486.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
162 | 158 | beglazing gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-15 08:00 | 3d | 0.24 | 0 | 0 | 364.56 | 0 | 364.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
163 | 159 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-24 08:00 | 3d | 0.24 | 0 | 0 | 364.56 | 0 | 364.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
164 | 160 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-30 08:00 | 5d | 0.4 | 0 | 0 | 607.6 | 0 | 608 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
165 | 161 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-01 08:00 | 1d | 0.08 | 0 | 0 | 121.52 | 0 | 121.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
166 | 162 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-24 08:00 | 3d | 0.24 | 0 | 0 | 364.56 | 0 | 364.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
167 | 163 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-04 08:00 | 3d | 0.24 | 0 | 0 | 364.56 | 0 | 364.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
168 | 164 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-22 08:00 | 5d | 0.4 | 0 | 0 | 607.6 | 0 | 608 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
169 | 199 | GOK | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 167143.036 |  | 171d | [5 empty] | 67685.7998 |  | 1 |  | 167143.036 | 167143.036 | C2015-02 Railway Station (1).xlsx
170 | 166 | plaatsing staalstructuur | 2011-08-05 08:00 | 2012-01-16 17:00 | 117d |  | 0 | 0 | 31.8 | 29764.7993 | 29764.7993 | 2012-08-16 08:00 | 28d | 7123.1998 | 0 | 0 | 0 | 0 | 7123.1998 | 0 | 1 | Finished | 29764.7993 | 29764.7993 | C2015-02 Railway Station (1).xlsx
171 | 167 | dakdichting - beplanting | 2011-09-13 08:00 | 2012-02-24 17:00 | 119d |  | 0 | 0 | 31.8 | 30273.5993 | 30273.5993 | 2012-09-25 08:00 | 20d | 5087.9999 | 0 | 0 | 0 | 0 | 5087.9999 | 0 | 1 | Finished | 30273.5993 | 30273.5993 | C2015-02 Railway Station (1).xlsx
172 | 168 | plaatsing beglazing | 2011-10-17 08:00 | 2012-03-23 17:00 | 115d |  | 0 | 0 | 31.8 | 29255.9993 | 29255.9993 | 2012-11-16 08:00 | 7d | 1780.8 | 0 | 0 | 0 | 0 | 1780.8 | 0 | 1 | Finished | 29255.9993 | 29255.9993 | C2015-02 Railway Station (1).xlsx
173 | 169 | dakdichting - waterdichting | 2011-11-02 08:00 | 2012-04-06 17:00 | 113d |  | 0 | 0 | 31.8 | 28747.1993 | 28747.1993 | 2012-10-16 08:00 | 10d | 2543.9999 | 0 | 0 | 0 | 0 | 2543.9999 | 0 | 1 | Finished | 28747.1993 | 28747.1993 | C2015-02 Railway Station (1).xlsx
174 | 170 | afwerking perron | 2011-11-18 08:00 | 2012-08-14 17:00 | 193d |  | 0 | 0 | 31.8 | 49099.1988 | 49099.1988 | 2012-12-10 08:00 | 1d | 254.4 | 0 | 0 | 0 | 0 | 254.4 | 0 | 1 | Finished | 49099.1988 | 49099.1988 | C2015-02 Railway Station (1).xlsx
175 | 171 | diepe fundering kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-16 08:00 | 12d | 0.96 | 0 | 0 | 3052.8 | 0 | 3053.76 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
176 | 172 | funderingszolen kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-23 08:00 | 16d | 1.28 | 0 | 0 | 4070.3999 | 0 | 4071.6799 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
177 | 173 | kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-08-13 08:00 | 2d | 0.16 | 0 | 0 | 508.8 | 0 | 508.96 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
178 | 174 | ontrokingskoker langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-24 08:00 | 10d | 0.8 | 0 | 0 | 2544 | 0 | 2544.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
179 | 175 | slibvanger langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-23 08:00 | 5d | 0.4 | 0 | 0 | 1272 | 0 | 1272.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
180 | 176 | voorlopige aansluiting riolering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-14 08:00 | 10d | 0.8 | 0 | 0 | 2544 | 0 | 2544.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
181 | 177 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-02 08:00 | 15d | 1.2 | 0 | 0 | 3816 | 0 | 3817.2 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
182 | 178 | integratie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-02 08:00 | 15d | 1.2 | 0 | 0 | 3816 | 0 | 3817.2 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
183 | 179 | Gevelbekleding metaal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-12-10 08:00 | 1d | 0.08 | 0 | 0 | 254.2 | 0 | 254.28 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
184 | 180 | integratie elec in gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-11-21 08:00 | 14d | 1.12 | 0 | 0 | 3561.6001 | 0 | 3562.7201 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
185 | 181 | beplanting onderkant dakstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-12-10 08:00 | 1d | 0.08 | 0 | 0 | 254.2 | 0 | 254.28 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
186 | 182 | bekledingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-11-05 08:00 | 10d | 0.8 | 0 | 0 | 2544 | 0 | 2544.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
187 | 183 | onderhoud en veiligheidsuitrusting - structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-09 08:00 | 10d | 0.8 | 0 | 0 | 2544 | 0 | 2544.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
188 | 184 | elektrische voorzieningen op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-30 08:00 | 7d | 0.56 | 0 | 0 | 1780.8 | 0 | 1781.36 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
189 | 185 | extractoren en wateraanvoer op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-30 08:00 | 7d | 0.56 | 0 | 0 | 1780.8 | 0 | 1781.36 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
190 | 186 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-30 08:00 | 7d | 0.56 | 0 | 0 | 1780.8 | 0 | 1781.36 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
191 | 187 | Onderhoud en veiligheidsuitrusting - toebehoren | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-11-06 08:00 | 5d | 0.4 | 0 | 0 | 1272 | 0 | 1272.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
192 | 188 | voorlopige trap toegang perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-29 08:00 | 10d | 0.8 | 0 | 0 | 2544 | 0 | 2544.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
193 | 189 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-01 08:00 | 1d | 0.08 | 0 | 0 | 254.2 | 0 | 254.28 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
194 | 190 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-24 08:00 | 3d | 0.24 | 0 | 0 | 763.2 | 0 | 763.44 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
195 | 191 | Herstellingen staalstructuur 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-05 08:00 | 5d | 0.4 | 0 | 0 | 1272 | 0 | 1272.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
196 | 192 | herstellingen staalstructuur 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-12 08:00 | 5d | 0.4 | 0 | 0 | 1272 | 0 | 1272.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
197 | 193 | Herstellingen staalstructuur 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-19 08:00 | 5d | 0.4 | 0 | 0 | 1272 | 0 | 1272.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
198 | 194 | herstellingen staalstructuur 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-26 08:00 | 5d | 0.4 | 0 | 0 | 1272 | 0 | 1272.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
199 | 195 | herstellingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-03 08:00 | 5d | 0.4 | 0 | 0 | 1272 | 0 | 1272.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
200 | 196 | Bekabeling in portieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-01 08:00 | 8d | 0.64 | 0 | 0 | 2035.2 | 0 | 2035.84 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
201 | 197 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-03 08:00 | 3d | 0.24 | 0 | 0 | 763.2 | 0 | 763.44 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
202 | 198 | Paaltjes bovendaks | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-25 08:00 | 3d | 0.24 | 0 | 0 | 763.2 | 0 | 763.44 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
203 | 200 | Technieken | 2011-09-08 08:00 | 2012-01-17 17:00 | 94d |  | 0 | 0 | 235.79 | 177314.075 | 177314.075 | 2012-08-17 08:00 | 73d | 137701.3561 | 0 | 0 | 0 | 0 | 137701.3561 | 0 | 1 | Finished | 177314.075 | 177314.075 | C2015-02 Railway Station (1).xlsx
204 | 227 | Superstructuur-zone A | 2011-01-10 08:00 | 2012-03-20 17:00 | 312d |  |  | 0 |  |  | 129941.9982 |  | 463d | [5 empty] | 154065.7585 |  | 1 |  | 129941.9982 | 129941.9982 | C2015-02 Railway Station (1).xlsx
205 | 201 | vloerplaat en keermuur reservelokaal 1 | 2011-01-31 08:00 | 2011-05-04 17:00 | 68d |  | 0 | 0 | 28.15 | 15313.5998 | 15313.5998 | 2012-12-10 08:00 | 1d | 225.2 | 0 | 0 | 0 | 0 | 225.2 | 0 | 1 | Finished | 15313.5998 | 15313.5998 | C2015-02 Railway Station (1).xlsx
206 | 202 | vloerplaat en keermuur reservelokaal 2 | 2011-03-21 08:00 | 2011-06-20 17:00 | 66d |  | 0 | 0 | 28.15 | 14863.1998 | 14863.1998 | 2011-08-29 08:00 | 77d | 17340.3998 | 0 | 0 | 0 | 0 | 17340.3998 | 0 | 1 | Finished | 14863.1998 | 14863.1998 | C2015-02 Railway Station (1).xlsx
207 | 203 | vloerplaat en keermuur reservelokaal 3 | 2011-05-05 08:00 | 2011-08-23 17:00 | 79d |  | 0 | 0 | 28.15 | 17790.7998 | 17790.7998 | 2011-11-28 08:00 | 51d | 11485.1998 | 0 | 0 | 0 | 0 | 11485.1998 | 0 | 1 | Finished | 17790.7998 | 17790.7998 | C2015-02 Railway Station (1).xlsx
208 | 204 | vloerplaat en keermuur reservelokaal 4 | 2011-06-21 08:00 | 2011-10-04 17:00 | 76d |  | 0 | 0 | 28.15 | 17115.1998 | 17115.1998 | 2011-12-12 08:00 | 64d | 14412.7998 | 0 | 0 | 0 | 0 | 14412.7998 | 0 | 1 | Finished | 17115.1998 | 17115.1998 | C2015-02 Railway Station (1).xlsx
209 | 205 | vloerplaat en keermuur reservelokaal 5 | 2011-08-24 08:00 | 2011-11-21 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 2012-02-06 08:00 | 50d | 11259.9998 | 0 | 0 | 0 | 0 | 11259.9998 | 0 | 1 | Finished | 14412.7998 | 14412.7998 | C2015-02 Railway Station (1).xlsx
210 | 206 | Dakplaat reservelokaal (incl. technische koker) | 2011-05-12 08:00 | 2012-03-20 17:00 | 224d |  | 0 | 0 | 28.15 | 50444.7993 | 50444.7993 | 2011-10-27 08:00 | 101d | 22745.1997 | 0 | 0 | 0 | 0 | 22745.1997 | 0 | 1 | Finished | 50444.7993 | 50444.7993 | C2015-02 Railway Station (1).xlsx
211 | 207 | Beschoeiing onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-06 08:00 | 9d | 0.72 | 0 | 0 | 2027.52 | 0 | 2028.24 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
212 | 208 | Verankering keermuur onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-08 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
213 | 209 | Keerwand onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-07-05 08:00 | 11d | 0.88 | 0 | 0 | 2477.2 | 0 | 2478.08 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
214 | 210 | Vloerplaat onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-02 08:00 | 25d | 2 | 0 | 0 | 5630 | 0 | 5632 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
215 | 211 | Wanden onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-12 08:00 | 22d | 1.76 | 0 | 0 | 4954.3999 | 0 | 4956.1599 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
216 | 212 | Vloerplaat +x onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-26 08:00 | 20d | 1.6 | 0 | 0 | 4504 | 0 | 4505.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
217 | 213 | Structuur spoor boven onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-16 08:00 | 38d | 3.04 | 0 | 0 | 8557.5996 | 0 | 8560.6396 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
218 | 214 | profielen voor beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 1d | 0.08 | 0 | 0 | 225.2 | 0 | 225.28 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
219 | 215 | Afbraak en grondwerk (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-10 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
220 | 216 | Verankering beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-11 08:00 | 13d | 1.04 | 0 | 0 | 2702.3999 | 0 | 2703.4399 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
221 | 217 | Vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-12 08:00 | 12d | 0.96 | 0 | 0 | 0 | 0 | 0.96 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
222 | 218 | Keerwand (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-21 08:00 | 9d | 0.72 | 0 | 0 | 2026.8 | 0 | 2027.52 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
223 | 219 | Verwijderen verdeelprofielen + keerwand (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 18d | 1.44 | 0 | 0 | 4053.6001 | 0 | 4055.0401 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
224 | 220 | Vloerplaat & keermuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 49d | 3.92 | 0 | 0 | 11034.7998 | 0 | 11038.7198 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
225 | 221 | Voorbereidende afbraakwerken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
226 | 222 | Beschoeiing fase 1 tem niv verankering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
227 | 223 | Beschoeiing fase (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-14 08:00 | 12d | 0.96 | 0 | 0 | 2702.3999 | 0 | 2703.3599 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
228 | 224 | Afbraakwerken (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-08 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
229 | 225 | Dakplaat reservelokaal dienstperron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-09 08:00 | 72d | 5.76 | 0 | 0 | 16214.4004 | 0 | 16220.1604 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
230 | 226 | Beton kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-13 08:00 | 10d | 0.8 | 0 | 0 | 2252 | 0 | 2252.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-02 Railway Station (1).xlsx
4 | 0 | Industrial Complex (1) | 2012-10-29 08:00 | 2013-10-22 17:00 | 257d |  |  | 0 |  |  | 2244090.7396 |  | 278d | [5 empty] | 1868796.2835 |  | 0.99722 |  | 2237845.5394 | 2244090.7396 | C2015-03 Industrial Complex (1).xlsx
5 | 67 | Ruwbouw | 2012-10-29 08:00 | 2013-05-31 17:00 | 155d |  |  | 0 |  |  | 1401806.7273 |  | 206d | [5 empty] | 1107493.9518 |  | 1 |  | 1401806.7273 | 1401806.7273 | C2015-03 Industrial Complex (1).xlsx
6 | 6 | Funderingswerken | 2012-10-29 08:00 | 2013-01-29 09:00 | 66d 1h |  |  | 0 |  |  | 102786.4896 |  | 75d | [5 empty] | 92734.6399 |  | 1 |  | 102786.4896 | 102786.4896 | C2015-03 Industrial Complex (1).xlsx
7 | 1 | Paalfundering | 2012-10-29 08:00 | 2012-11-09 17:00 | 10d |  | 0 | 0 | 413.98 | 33118.4009 | 33118.4009 | 2012-10-29 08:00 | 8d | 26494.7207 | 0 | 0 | 0 | 0 | 26494.7207 | 0 | 1 | Finished | 33118.4009 | 33118.4009 | C2015-03 Industrial Complex (1).xlsx
8 | 2 | Knippen van de palen | 2012-11-15 08:00 | 2012-11-15 17:00 | 1d |  | 0 | 0 | 198.26 | 1586.08 | 1586.08 | 2012-11-15 08:00 | 1d | 1586.08 | 0 | 0 | 0 | 0 | 1586.08 | 0 | 1 | Finished | 1586.08 | 1586.08 | C2015-03 Industrial Complex (1).xlsx
9 | 3 | Grondwerken | 2012-11-13 08:00 | 2012-12-11 17:00 | 21d |  | 0 | 0 | 119.57 | 20087.7599 | 20087.7599 | 2012-11-13 08:00 | 21d | 20087.7599 | 0 | 0 | 0 | 0 | 20087.7599 | 0 | 1 | Finished | 20087.7599 | 20087.7599 | C2015-03 Industrial Complex (1).xlsx
10 | 4 | Funderingsbalken | 2012-12-03 08:00 | 2013-01-09 17:00 | 28d |  | 0 | 0 | 214.26 | 47994.2388 | 47994.2388 | 2012-12-03 08:00 | 17d | 29139.3593 | 0 | 0 | 0 | 0 | 29139.3593 | 0 | 1 | Finished | 47994.2388 | 47994.2388 | C2015-03 Industrial Complex (1).xlsx
11 | 5 | Funderingsbalken en aanpassingen | 2013-01-29 08:00 | 2013-01-29 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-01-29 08:00 | 9d | 0.72 | 0 | 0 | 15426 | 0 | 15426.72 | 0 | 1 | Finished | 0.01 | 0.01 | C2015-03 Industrial Complex (1).xlsx
12 | 17 | Bovenbouw A | 2013-01-08 08:00 | 2013-02-08 17:00 | 24d |  |  | 0 |  |  | 399881.043 |  | 18d | [5 empty] | 183963.8413 |  | 1 |  | 399881.043 | 399881.043 | C2015-03 Industrial Complex (1).xlsx
13 | 12 | Montage prefab | 2013-01-08 08:00 | 2013-02-04 17:00 | 20d |  |  | 0 |  |  | 361653.7622 |  | 18d | [5 empty] | 166320.481 |  | 1 |  | 361653.7622 | 361653.7622 | C2015-03 Industrial Complex (1).xlsx
14 | 7 | Kolommen | 2013-01-08 08:00 | 2013-01-11 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-01-29 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 1 | Finished | 13493.1201 | 13493.1201 | C2015-03 Industrial Complex (1).xlsx
15 | 8 | balken | 2013-01-17 08:00 | 2013-01-18 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-05 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 1 | Finished | 3980.48 | 3980.48 | C2015-03 Industrial Complex (1).xlsx
16 | 9 | Structurele wand | 2013-01-14 08:00 | 2013-01-16 17:00 | 3d |  | 0 | 0 | 12208.3301 | 292999.9219 | 292999.9219 | 2013-02-04 08:00 | 1d | 97666.6406 | 0 | 0 | 0 | 0 | 97666.6406 | 0 | 1 | Finished | 292999.9219 | 292999.9219 | C2015-03 Industrial Complex (1).xlsx
17 | 10 | Welfsles | 2013-01-21 08:00 | 2013-01-22 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-07 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 1 | Finished | 37872 | 37872 | C2015-03 Industrial Complex (1).xlsx
18 | 11 | SW-panelen | 2013-01-31 08:00 | 2013-02-04 17:00 | 3d |  | 0 | 0 | 554.51 | 13308.2402 | 13308.2402 | 2013-02-19 08:00 | 3d | 13308.2402 | 0 | 0 | 0 | 0 | 13308.2402 | 0 | 1 | Finished | 13308.2402 | 13308.2402 | C2015-03 Industrial Complex (1).xlsx
19 | 16 | Ruwbouwwerken | 2013-01-23 08:00 | 2013-02-08 17:00 | 13d |  |  | 0 |  |  | 38227.2808 |  | 6d | [5 empty] | 17643.3604 |  | 1 |  | 38227.2808 | 38227.2808 | C2015-03 Industrial Complex (1).xlsx
20 | 13 | Voorbereiding opstortbeton | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-11 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 1 | Finished | 5881.1201 | 5881.1201 | C2015-03 Industrial Complex (1).xlsx
21 | 14 | opstort niv 1 en 2 | 2013-01-25 08:00 | 2013-01-25 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-12 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 1 | Finished | 2940.5601 | 2940.5601 | C2015-03 Industrial Complex (1).xlsx
22 | 15 | Metselwerken | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 367.57 | 29405.6006 | 29405.6006 | 2013-02-13 08:00 | 4d | 11762.2402 | 0 | 0 | 0 | 0 | 11762.2402 | 0 | 1 | Finished | 29405.6006 | 29405.6006 | C2015-03 Industrial Complex (1).xlsx
23 | 27 | Bovenbouw B | 2013-01-23 08:00 | 2013-02-11 17:00 | 14d |  |  | 0 |  |  | 80995.6807 |  | 11d | [5 empty] | 69233.4404 |  | 1 |  | 80995.6807 | 80995.6807 | C2015-03 Industrial Complex (1).xlsx
24 | 22 | Montage prefab | 2013-01-23 08:00 | 2013-02-06 17:00 | 11d |  |  | 0 |  |  | 57471.2002 |  | 11d | [5 empty] | 57471.2002 |  | 1 |  | 57471.2002 | 57471.2002 | C2015-03 Industrial Complex (1).xlsx
25 | 18 | Kolommen | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 421.66 | 6746.5601 | 6746.5601 | 2013-02-11 08:00 | 2d | 6746.5601 | 0 | 0 | 0 | 0 | 6746.5601 | 0 | 1 | Finished | 6746.5601 | 6746.5601 | C2015-03 Industrial Complex (1).xlsx
26 | 19 | Balken | 2013-01-25 08:00 | 2013-01-28 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-13 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 1 | Finished | 3980.48 | 3980.48 | C2015-03 Industrial Complex (1).xlsx
27 | 20 | Welfsels | 2013-01-29 08:00 | 2013-01-30 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-15 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 1 | Finished | 37872 | 37872 | C2015-03 Industrial Complex (1).xlsx
28 | 21 | SW-panelen | 2013-02-05 08:00 | 2013-02-06 17:00 | 2d |  | 0 | 0 | 554.51 | 8872.1602 | 8872.1602 | 2013-02-22 08:00 | 2d | 8872.1602 | 0 | 0 | 0 | 0 | 8872.1602 | 0 | 1 | Finished | 8872.1602 | 8872.1602 | C2015-03 Industrial Complex (1).xlsx
29 | 26 | Ruwbouwwerken | 2013-01-31 08:00 | 2013-02-11 17:00 | 8d |  |  | 0 |  |  | 23524.4805 |  | 4d | [5 empty] | 11762.2402 |  | 1 |  | 23524.4805 | 23524.4805 | C2015-03 Industrial Complex (1).xlsx
30 | 23 | voorbereiding opstortbeton | 2013-01-31 08:00 | 2013-02-01 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-19 08:00 | 2d | 5881.1201 | 0 | 0 | 0 | 0 | 5881.1201 | 0 | 1 | Finished | 5881.1201 | 5881.1201 | C2015-03 Industrial Complex (1).xlsx
31 | 24 | Opstort niv 1 en 2 | 2013-02-04 08:00 | 2013-02-04 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-21 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 1 | Finished | 2940.5601 | 2940.5601 | C2015-03 Industrial Complex (1).xlsx
32 | 25 | metselwerken | 2013-02-05 08:00 | 2013-02-11 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 2013-02-22 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 1 | Finished | 14702.8003 | 14702.8003 | C2015-03 Industrial Complex (1).xlsx
33 | 38 | Bovenbouw C | 2013-02-07 08:00 | 2013-04-15 17:00 | 48d |  |  | 0 |  |  | 271266.8025 |  | 38d | [5 empty] | 191365.6018 |  | 1 |  | 271266.8025 | 271266.8025 | C2015-03 Industrial Complex (1).xlsx
34 | 33 | Montage prefab | 2013-02-07 08:00 | 2013-04-08 17:00 | 43d |  |  | 0 |  |  | 194812.241 |  | 37d | [5 empty] | 138435.5208 |  | 1 |  | 194812.241 | 194812.241 | C2015-03 Industrial Complex (1).xlsx
35 | 28 | kolommen | 2013-02-07 08:00 | 2013-02-12 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-02-26 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 1 | Finished | 13493.1201 | 13493.1201 | C2015-03 Industrial Complex (1).xlsx
36 | 29 | centrale kern | 2013-02-13 08:00 | 2013-02-18 17:00 | 4d |  | 0 | 0 | 345.56 | 11057.9199 | 11057.9199 | 2013-03-04 08:00 | 5d | 13822.3999 | 0 | 0 | 0 | 0 | 13822.3999 | 0 | 1 | Finished | 11057.9199 | 11057.9199 | C2015-03 Industrial Complex (1).xlsx
37 | 30 | balken | 2013-02-19 08:00 | 2013-03-01 17:00 | 9d |  | 0 | 0 | 248.78 | 17912.1599 | 17912.1599 | 2013-03-11 08:00 | 5d | 9951.2 | 0 | 0 | 0 | 0 | 9951.2 | 0 | 1 | Finished | 17912.1599 | 17912.1599 | C2015-03 Industrial Complex (1).xlsx
38 | 31 | welfsels | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 2367 | 94680 | 94680 | 2013-03-18 08:00 | 3d | 56808 | 0 | 0 | 0 | 0 | 56808 | 0 | 1 | Finished | 94680 | 94680 | C2015-03 Industrial Complex (1).xlsx
39 | 32 | SW panelen | 2013-03-21 08:00 | 2013-04-08 17:00 | 13d |  | 0 | 0 | 554.51 | 57669.041 | 57669.041 | 2013-04-04 08:00 | 10d | 44360.8008 | 0 | 0 | 0 | 0 | 44360.8008 | 0 | 1 | Finished | 57669.041 | 57669.041 | C2015-03 Industrial Complex (1).xlsx
40 | 37 | Ruwbouwwerken | 2013-03-11 08:00 | 2013-04-15 17:00 | 26d |  |  | 0 |  |  | 76454.5615 |  | 21d | [5 empty] | 52930.0811 |  | 1 |  | 76454.5615 | 76454.5615 | C2015-03 Industrial Complex (1).xlsx
41 | 34 | voorbereiding opstortbeton | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 2013-03-21 08:00 | 4d | 11762.2402 | 0 | 0 | 0 | 0 | 11762.2402 | 0 | 1 | Finished | 14702.8003 | 14702.8003 | C2015-03 Industrial Complex (1).xlsx
42 | 35 | opstort niv 1, 2 en 3 | 2013-03-18 08:00 | 2013-03-20 17:00 | 3d |  | 0 | 0 | 367.57 | 8821.6802 | 8821.6802 | 2013-03-27 08:00 | 3d | 8821.6802 | 0 | 0 | 0 | 0 | 8821.6802 | 0 | 1 | Finished | 8821.6802 | 8821.6802 | C2015-03 Industrial Complex (1).xlsx
43 | 36 | Metselwerk | 2013-03-21 08:00 | 2013-04-15 17:00 | 18d |  | 0 | 0 | 367.57 | 52930.0811 | 52930.0811 | 2013-04-04 08:00 | 11d | 32346.1606 | 0 | 0 | 0 | 0 | 32346.1606 | 0 | 1 | Finished | 52930.0811 | 52930.0811 | C2015-03 Industrial Complex (1).xlsx
44 | 47 | Draagvloer gv | 2013-03-21 08:00 | 2013-05-23 17:00 | 46d |  |  | 0 |  |  | 183634.01 |  | 55d | [5 empty] | 175536.24 |  | 1 |  | 183634.01 | 183634.01 | C2015-03 Industrial Complex (1).xlsx
45 | 39 | rioleringswerken | 2013-03-21 08:00 | 2013-04-04 17:00 | 11d |  | 0 | 0 | 487.75 | 42922 | 42922 | 2013-04-04 08:00 | 8d | 31216 | 0 | 0 | 0 | 0 | 31216 | 0 | 1 | Finished | 42922 | 42922 | C2015-03 Industrial Complex (1).xlsx
46 | 40 | aanvulling gestabiliseerd zand | 2013-04-05 08:00 | 2013-04-18 17:00 | 10d |  | 0 | 0 | 451 | 36080 | 36080 | 2013-04-16 08:00 | 5d | 18040 | 0 | 0 | 0 | 0 | 18040 | 0 | 1 | Finished | 36080 | 36080 | C2015-03 Industrial Complex (1).xlsx
47 | 41 | plaatsen vloerisolatie | 2013-04-17 08:00 | 2013-04-22 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 2013-04-19 08:00 | 4d | 14432 | 0 | 0 | 0 | 0 | 14432 | 0 | 1 | Finished | 14432 | 14432 | C2015-03 Industrial Complex (1).xlsx
48 | 42 | plaatsen wapening | 2013-04-19 08:00 | 2013-04-24 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 2013-04-23 08:00 | 4d | 14432 | 0 | 0 | 0 | 0 | 14432 | 0 | 1 | Finished | 14432 | 14432 | C2015-03 Industrial Complex (1).xlsx
49 | 43 | bekistingswerken | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 | 2013-04-29 08:00 | 2d | 7216 | 0 | 0 | 0 | 0 | 7216 | 0 | 1 | Finished | 7216 | 7216 | C2015-03 Industrial Complex (1).xlsx
50 | 44 | stort vloerplaat gv | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 | 2013-05-02 08:00 | 2d | 7216 | 0 | 0 | 0 | 0 | 7216 | 0 | 1 | Finished | 7216 | 7216 | C2015-03 Industrial Complex (1).xlsx
51 | 45 | vloerplaat centrum | 2013-05-02 08:00 | 2013-05-02 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-17 08:00 | 3d | 0.24 | 0 | 0 | 10824 | 0 | 10824.24 | 0 | 1 | Finished | 0.01 | 0.01 | C2015-03 Industrial Complex (1).xlsx
52 | 46 | metselwerken | 2013-05-01 08:00 | 2013-05-23 17:00 | 17d |  | 0 | 0 | 451 | 61336 | 61336 | 2013-05-06 08:00 | 20d | 72160 | 0 | 0 | 0 | 0 | 72160 | 0 | 1 | Finished | 61336 | 61336 | C2015-03 Industrial Complex (1).xlsx
53 | 50 | Regenwater afvoeren | 2013-02-27 08:00 | 2013-03-20 09:00 | 15d 1h |  |  | 0 |  |  | 0.02 |  | 9d | [5 empty] | 11288.5901 |  | 1 |  | 0.02 | 0.02 | C2015-03 Industrial Complex (1).xlsx
54 | 48 | RW deel 1 | 2013-02-27 08:00 | 2013-02-27 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-21 08:00 | 4d | 0.32 | 0 | 0 | 5016.8301 | 0 | 5017.1501 | 0 | 1 | Finished | 0.01 | 0.01 | C2015-03 Industrial Complex (1).xlsx
55 | 49 | RW deel 2 | 2013-03-20 08:00 | 2013-03-20 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-27 08:00 | 5d | 0.4 | 0 | 0 | 6271.04 | 0 | 6271.44 | 0 | 1 | Finished | 0.01 | 0.01 | C2015-03 Industrial Complex (1).xlsx
56 | 54 | Dakwerken deel 1 | 2013-04-11 08:00 | 2013-05-13 17:00 | 23d |  |  | 0 |  |  | 73670.4004 |  | 8d | [5 empty] | 40518.7202 |  | 1 |  | 73670.4004 | 73670.4004 | C2015-03 Industrial Complex (1).xlsx
57 | 51 | hellingsbeton | 2013-04-11 08:00 | 2013-04-15 17:00 | 3d |  | 0 | 0 | 460.44 | 11050.5601 | 11050.5601 | 2013-06-07 08:00 | 3d | 11050.5601 | 0 | 0 | 0 | 0 | 11050.5601 | 0 | 1 | Finished | 11050.5601 | 11050.5601 | C2015-03 Industrial Complex (1).xlsx
58 | 52 | dampscherm + isolatie + afwerking | 2013-04-19 08:00 | 2013-05-03 17:00 | 11d |  | 0 | 0 | 460.44 | 40518.7202 | 40518.7202 | 2013-06-03 08:00 | 4d | 14734.0801 | 0 | 0 | 0 | 0 | 14734.0801 | 0 | 1 | Finished | 40518.7202 | 40518.7202 | C2015-03 Industrial Complex (1).xlsx
59 | 53 | Aanwerken aan bestaande toestand | 2013-05-06 08:00 | 2013-05-13 17:00 | 6d |  | 0 | 0 | 460.44 | 22101.1201 | 22101.1201 | 2013-06-07 08:00 | 4d | 14734.0801 | 0 | 0 | 0 | 0 | 14734.0801 | 0 | 1 | Finished | 22101.1201 | 22101.1201 | C2015-03 Industrial Complex (1).xlsx
60 | 58 | Dakwerken deel 2 | 2013-04-19 14:00 | 2013-04-24 17:00 | 3d 3h |  |  | 0 |  |  | 0.03 |  | 14d | [5 empty] | 62621.1989 |  | 1 |  | 0.03 | 0.03 | C2015-03 Industrial Complex (1).xlsx
61 | 55 | hellingsbeton | 2013-04-19 14:00 | 2013-04-19 15:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-07 08:00 | 3d | 0.24 | 0 | 0 | 11050.5596 | 0 | 11050.7996 | 0 | 1 | Finished | 0.01 | 0.01 | C2015-03 Industrial Complex (1).xlsx
62 | 56 | dampscherm + isolatie + afwerking | 2013-04-24 15:00 | 2013-04-24 16:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-07 08:00 | 10d | 0.8 | 0 | 0 | 36835.1992 | 0 | 36835.9992 | 0 | 1 | Finished | 0.01 | 0.01 | C2015-03 Industrial Complex (1).xlsx
63 | 57 | Aanwerken aan bestaande toestand | 2013-04-24 16:00 | 2013-04-24 17:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-21 08:00 | 4d | 0.32 | 0 | 0 | 14734.0801 | 0 | 14734.4001 | 0 | 1 | Finished | 0.01 | 0.01 | C2015-03 Industrial Complex (1).xlsx
64 | 61 | Buitenschrijnwerk deel 1 | 2013-05-14 08:00 | 2013-05-31 17:00 | 14d |  |  | 0 |  |  | 56046.2502 |  | 39d | [5 empty] | 93410.8784 |  | 1 |  | 56046.2502 | 56046.2502 | C2015-03 Industrial Complex (1).xlsx
65 | 59 | Alu ramen | 2013-05-14 08:00 | 2013-05-14 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-06 08:00 | 6d | 0.48 | 0 | 0 | 56046.2383 | 0 | 56046.7183 | 0 | 1 | Finished | 0.01 | 0.01 | C2015-03 Industrial Complex (1).xlsx
66 | 60 | sectionaalpoorten | 2013-05-24 08:00 | 2013-05-31 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 2013-06-24 08:00 | 4d | 37364.1602 | 0 | 0 | 0 | 0 | 37364.1602 | 0 | 1 | Finished | 56046.2402 | 56046.2402 | C2015-03 Industrial Complex (1).xlsx
67 | 66 | Buitenschrijnwerk deel 2 | 2013-04-25 08:00 | 2013-05-21 17:00 | 19d |  |  | 0 |  |  | 233526.001 |  | 46d | [5 empty] | 186820.8008 |  | 1 |  | 233526.001 | 233526.001 | C2015-03 Industrial Complex (1).xlsx
68 | 62 | Alu ramen | 2013-04-25 08:00 | 2013-05-06 17:00 | 8d |  | 0 | 0 | 1167.63 | 74728.3203 | 74728.3203 | 2013-06-10 08:00 | 10d | 93410.4004 | 0 | 0 | 0 | 0 | 93410.4004 | 0 | 1 | Finished | 74728.3203 | 74728.3203 | C2015-03 Industrial Complex (1).xlsx
69 | 63 | gordijngevel elementen | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 2013-06-10 08:00 | 4d | 37364.1602 | 0 | 0 | 0 | 0 | 37364.1602 | 0 | 1 | Finished | 56046.2402 | 56046.2402 | C2015-03 Industrial Complex (1).xlsx
70 | 64 | automatische deuren | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 2013-08-05 08:00 | 2d | 18682.0801 | 0 | 0 | 0 | 0 | 18682.0801 | 0 | 1 | Finished | 56046.2402 | 56046.2402 | C2015-03 Industrial Complex (1).xlsx
71 | 65 | vouwgeheel | 2013-05-15 08:00 | 2013-05-21 17:00 | 5d |  | 0 | 0 | 1167.63 | 46705.2002 | 46705.2002 | 2013-08-07 08:00 | 4d | 37364.1602 | 0 | 0 | 0 | 0 | 37364.1602 | 0 | 1 | Finished | 46705.2002 | 46705.2002 | C2015-03 Industrial Complex (1).xlsx
72 | 163 | Planning afwerking | 2013-06-03 08:00 | 2013-10-22 17:00 | 102d |  |  | 0 |  |  | 842284.0123 |  | 143d | [5 empty] | 761302.3317 |  | 0.99259 |  | 836038.8121 | 842284.0123 | C2015-03 Industrial Complex (1).xlsx
73 | 80 | 1e verdieping landscape links | 2013-06-03 08:00 | 2013-09-16 17:00 | 76d |  |  | 0 |  |  | 167563.2785 |  | 143d | [5 empty] | 133535.6786 |  | 0.96273 |  | 161318.0783 | 167563.2785 | C2015-03 Industrial Complex (1).xlsx
74 | 68 | HVAC plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-05-06 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 1 | Finished | 5462.4001 | 5462.4001 | C2015-03 Industrial Complex (1).xlsx
75 | 69 | Elektriciteit plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-05-06 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 1 | Finished | 5462.4001 | 5462.4001 | C2015-03 Industrial Complex (1).xlsx
76 | 70 | Schilderwerk wanden | 2013-06-24 08:00 | 2013-06-26 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-06-07 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 1 | Finished | 2227.2001 | 2227.2001 | C2015-03 Industrial Complex (1).xlsx
77 | 71 | Structuur valse plafond | 2013-06-27 08:00 | 2013-07-01 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 | 2013-06-12 08:00 | 3d | 1092.48 | 0 | 0 | 0 | 0 | 1092.48 | 0 | 1 | Finished | 1092.48 | 1092.48 | C2015-03 Industrial Complex (1).xlsx
78 | 72 | elecktriciteit vloer | 2013-07-02 08:00 | 2013-08-02 17:00 | 24d |  | 0 | 0 | 298.47 | 57306.2402 | 57306.2402 | 2013-08-09 08:00 | 8d | 19102.0801 | 0 | 0 | 0 | 0 | 19102.0801 | 0 | 1 | Finished | 57306.2402 | 57306.2402 | C2015-03 Industrial Complex (1).xlsx
79 | 73 | Verhoogde vloer | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 | 2013-08-23 08:00 | 5d | 11938.8 | 0 | 0 | 0 | 0 | 11938.8 | 0 | 1 | Finished | 11938.8 | 11938.8 | C2015-03 Industrial Complex (1).xlsx
80 | 74 | HVAC toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 | 2013-06-21 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 1 | Finished | 2184.96 | 2184.96 | C2015-03 Industrial Complex (1).xlsx
81 | 75 | Elektriciteit toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 | 2013-06-21 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 1 | Finished | 2184.96 | 2184.96 | C2015-03 Industrial Complex (1).xlsx
82 | 76 | Binnenschrijnwerk | 2013-08-20 08:00 | 2013-08-26 17:00 | 5d |  | 0 | 0 | 1688.6899 | 67547.5977 | 67547.5977 | 2013-06-27 08:00 | 5d | 67547.5977 | 0 | 0 | 0 | 0 | 67547.5977 | 0 | 1 | Finished | 67547.5977 | 67547.5977 | C2015-03 Industrial Complex (1).xlsx
83 | 77 | Schilderwerk | 2013-08-27 08:00 | 2013-09-03 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 2013-07-04 08:00 | 22d | 16332.8005 | 0 | 0 | 0 | 0 | 16332.8005 | 0 | 1 | Finished | 4454.4001 | 4454.4001 | C2015-03 Industrial Complex (1).xlsx
84 | 78 | plafondtegels | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-08-05 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 1 | Finished | 1456.64 | 1456.64 | C2015-03 Industrial Complex (1).xlsx
85 | 79 | tapijt | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0 | Not Started | 0 | 6245.2002 | C2015-03 Industrial Complex (1).xlsx
86 | 84 | Schacht | 2013-06-03 08:00 | 2013-06-25 17:00 | 17d |  |  | 0 |  |  | 24293.2003 |  | 14d | [5 empty] | 22312.0002 |  | 1 |  | 24293.2003 | 24293.2003 | C2015-03 Industrial Complex (1).xlsx
87 | 81 | Sanitair plaatsen aan een afvoerleiding in schacht | 2013-06-03 08:00 | 2013-06-11 17:00 | 7d |  | 0 | 0 | 82.55 | 4622.8002 | 4622.8002 | 2013-06-10 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 1 | Finished | 4622.8002 | 4622.8002 | C2015-03 Industrial Complex (1).xlsx
88 | 82 | HVAC | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 200.36 | 16028.8 | 16028.8 | 2013-06-14 08:00 | 10d | 16028.8 | 0 | 0 | 0 | 0 | 16028.8 | 0 | 1 | Finished | 16028.8 | 16028.8 | C2015-03 Industrial Complex (1).xlsx
89 | 83 | Elektriciteit | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 45.52 | 3641.6 | 3641.6 | 2013-06-14 08:00 | 10d | 3641.6 | 0 | 0 | 0 | 0 | 3641.6 | 0 | 1 | Finished | 3641.6 | 3641.6 | C2015-03 Industrial Complex (1).xlsx
90 | 92 | 2e verdieping sanitair | 2013-06-12 08:00 | 2013-08-13 17:00 | 45d |  |  | 0 |  |  | 28397.201 |  | 54d | [5 empty] | 17830.8007 |  | 1 |  | 28397.201 | 28397.201 | C2015-03 Industrial Complex (1).xlsx
91 | 85 | aan en afvoerleidingen | 2013-06-12 08:00 | 2013-06-17 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-06-14 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 1 | Finished | 2641.6001 | 2641.6001 | C2015-03 Industrial Complex (1).xlsx
92 | 86 | montage toiletten | 2013-06-18 08:00 | 2013-06-19 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-06-20 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 1 | Finished | 1320.8 | 1320.8 | C2015-03 Industrial Complex (1).xlsx
93 | 87 | bezettingswerken (cementering) | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 2013-06-26 08:00 | 5d | 3302.0001 | 0 | 0 | 0 | 0 | 3302.0001 | 0 | 1 | Finished | 3302.0001 | 3302.0001 | C2015-03 Industrial Complex (1).xlsx
94 | 88 | pur en chape | 2013-07-01 08:00 | 2013-07-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-05 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 1 | Finished | 1320.8 | 1320.8 | C2015-03 Industrial Complex (1).xlsx
95 | 89 | gyproc | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-07 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 1 | Finished | 1320.8 | 1320.8 | C2015-03 Industrial Complex (1).xlsx
96 | 90 | tegelwerken | 2013-07-05 08:00 | 2013-08-09 17:00 | 26d |  | 0 | 0 | 82.55 | 17170.4006 | 17170.4006 | 2013-08-09 08:00 | 10d | 6604.0002 | 0 | 0 | 0 | 0 | 6604.0002 | 0 | 1 | Finished | 17170.4006 | 17170.4006 | C2015-03 Industrial Complex (1).xlsx
97 | 91 | plafond | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-27 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 1 | Finished | 1320.8 | 1320.8 | C2015-03 Industrial Complex (1).xlsx
98 | 100 | 1e verdieping sanitair | 2013-06-20 08:00 | 2013-08-22 17:00 | 46d |  |  | 0 |  |  | 19151.6007 |  | 46d | [5 empty] | 28397.201 |  | 1 |  | 19151.6007 | 19151.6007 | C2015-03 Industrial Complex (1).xlsx
99 | 93 | aan en afvoerleidingen | 2013-06-20 08:00 | 2013-06-25 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-06-24 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 1 | Finished | 2641.6001 | 2641.6001 | C2015-03 Industrial Complex (1).xlsx
100 | 94 | montage hangtoiletten | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-06-28 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 1 | Finished | 1320.8 | 1320.8 | C2015-03 Industrial Complex (1).xlsx
101 | 95 | bezettingswerken (cementering) | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 2013-07-03 08:00 | 21d | 13868.4005 | 0 | 0 | 0 | 0 | 13868.4005 | 0 | 1 | Finished | 3302.0001 | 3302.0001 | C2015-03 Industrial Complex (1).xlsx
102 | 96 | pur en chape | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-01 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 1 | Finished | 1320.8 | 1320.8 | C2015-03 Industrial Complex (1).xlsx
103 | 97 | gyproc | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-05 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 1 | Finished | 1320.8 | 1320.8 | C2015-03 Industrial Complex (1).xlsx
104 | 98 | tegelwerken | 2013-08-05 08:00 | 2013-08-20 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 | 2013-08-07 08:00 | 10d | 6604.0002 | 0 | 0 | 0 | 0 | 6604.0002 | 0 | 1 | Finished | 7924.8003 | 7924.8003 | C2015-03 Industrial Complex (1).xlsx
105 | 99 | plafond | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-23 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 1 | Finished | 1320.8 | 1320.8 | C2015-03 Industrial Complex (1).xlsx
106 | 107 | gv sanitair links | 2013-06-28 08:00 | 2013-09-18 17:00 | 59d |  |  | 0 |  |  | 38963.6014 |  | 59d | [5 empty] | 37642.8014 |  | 1 |  | 38963.6014 | 38963.6014 | C2015-03 Industrial Complex (1).xlsx
107 | 101 | aan en afvoerleidingen | 2013-06-28 08:00 | 2013-07-30 17:00 | 23d |  | 0 | 0 | 82.55 | 15189.2006 | 15189.2006 | 2013-07-02 08:00 | 23d | 15189.2006 | 0 | 0 | 0 | 0 | 15189.2006 | 0 | 1 | Finished | 15189.2006 | 15189.2006 | C2015-03 Industrial Complex (1).xlsx
108 | 102 | montage hangtoiletten | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-08-02 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 1 | Finished | 2641.6001 | 2641.6001 | C2015-03 Industrial Complex (1).xlsx
109 | 103 | bezettingswerken (cementering) | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 | 2013-08-08 08:00 | 10d | 6604.0002 | 0 | 0 | 0 | 0 | 6604.0002 | 0 | 1 | Finished | 7924.8003 | 7924.8003 | C2015-03 Industrial Complex (1).xlsx
110 | 104 | gyproc | 2013-08-22 08:00 | 2013-08-23 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-26 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 1 | Finished | 1320.8 | 1320.8 | C2015-03 Industrial Complex (1).xlsx
111 | 105 | tegelwerken | 2013-08-26 08:00 | 2013-09-13 17:00 | 15d |  | 0 | 0 | 82.55 | 9906.0004 | 9906.0004 | 2013-08-28 08:00 | 15d | 9906.0004 | 0 | 0 | 0 | 0 | 9906.0004 | 0 | 1 | Finished | 9906.0004 | 9906.0004 | C2015-03 Industrial Complex (1).xlsx
112 | 106 | plafond | 2013-09-16 08:00 | 2013-09-18 17:00 | 3d |  | 0 | 0 | 82.55 | 1981.2001 | 1981.2001 | 2013-09-18 08:00 | 3d | 1981.2001 | 0 | 0 | 0 | 0 | 1981.2001 | 0 | 1 | Finished | 1981.2001 | 1981.2001 | C2015-03 Industrial Complex (1).xlsx
113 | 115 | Gelijkvloers sanitair rechts | 2013-07-31 08:00 | 2013-09-09 17:00 | 29d |  |  | 0 |  |  | 17830.8007 |  | 29d | [5 empty] | 17830.8007 |  | 1 |  | 17830.8007 | 17830.8007 | C2015-03 Industrial Complex (1).xlsx
114 | 108 | aan en afvoerleidingen | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-08-02 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 1 | Finished | 2641.6001 | 2641.6001 | C2015-03 Industrial Complex (1).xlsx
115 | 109 | montage hangtoiletten | 2013-08-06 08:00 | 2013-08-07 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-08 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 1 | Finished | 1320.8 | 1320.8 | C2015-03 Industrial Complex (1).xlsx
116 | 110 | bezettingswerken (cementering) | 2013-08-08 08:00 | 2013-08-14 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 2013-08-12 08:00 | 5d | 3302.0001 | 0 | 0 | 0 | 0 | 3302.0001 | 0 | 1 | Finished | 3302.0001 | 3302.0001 | C2015-03 Industrial Complex (1).xlsx
117 | 111 | pur en chape | 2013-08-19 08:00 | 2013-08-20 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-21 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 1 | Finished | 1320.8 | 1320.8 | C2015-03 Industrial Complex (1).xlsx
118 | 112 | gyproc | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-23 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 1 | Finished | 1320.8 | 1320.8 | C2015-03 Industrial Complex (1).xlsx
119 | 113 | tegelwerken | 2013-08-23 08:00 | 2013-09-05 17:00 | 10d |  | 0 | 0 | 82.55 | 6604.0002 | 6604.0002 | 2013-08-27 08:00 | 10d | 6604.0002 | 0 | 0 | 0 | 0 | 6604.0002 | 0 | 1 | Finished | 6604.0002 | 6604.0002 | C2015-03 Industrial Complex (1).xlsx
120 | 114 | plafond | 2013-09-06 08:00 | 2013-09-09 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-09-10 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 1 | Finished | 1320.8 | 1320.8 | C2015-03 Industrial Complex (1).xlsx
121 | 129 | 2e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-17 17:00 | 84d |  |  | 0 |  |  | 157445.123 |  | 76d | [5 empty] | 148486.9634 |  | 1 |  | 157445.123 | 157445.123 | C2015-03 Industrial Complex (1).xlsx
122 | 116 | HVAC plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 1 | Finished | 12017.2801 | 12017.2801 | C2015-03 Industrial Complex (1).xlsx
123 | 117 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 1 | Finished | 12017.2801 | 12017.2801 | C2015-03 Industrial Complex (1).xlsx
124 | 118 | Schilderwerken wanden | 2013-08-08 08:00 | 2013-08-12 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-08-09 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 1 | Finished | 2227.2001 | 2227.2001 | C2015-03 Industrial Complex (1).xlsx
125 | 119 | structuur vals plafond | 2013-08-13 08:00 | 2013-08-21 17:00 | 7d |  | 0 | 0 | 45.52 | 2549.12 | 2549.12 | 2013-08-14 08:00 | 5d | 1820.8 | 0 | 0 | 0 | 0 | 1820.8 | 0 | 1 | Finished | 2549.12 | 2549.12 | C2015-03 Industrial Complex (1).xlsx
126 | 120 | Elektriciteit vloer | 2013-08-22 08:00 | 2013-09-04 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 | 2013-08-19 08:00 | 4d | 9551.04 | 0 | 0 | 0 | 0 | 9551.04 | 0 | 1 | Finished | 23877.6001 | 23877.6001 | C2015-03 Industrial Complex (1).xlsx
127 | 121 | verhoogde vloer | 2013-09-05 08:00 | 2013-09-13 17:00 | 7d |  | 0 | 0 | 298.47 | 16714.3201 | 16714.3201 | 2013-08-19 08:00 | 4d | 9551.04 | 0 | 0 | 0 | 0 | 9551.04 | 0 | 1 | Finished | 16714.3201 | 16714.3201 | C2015-03 Industrial Complex (1).xlsx
128 | 122 | HVAC toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-08-23 08:00 | 5d | 1820.8 | 0 | 0 | 0 | 0 | 1820.8 | 0 | 1 | Finished | 1456.64 | 1456.64 | C2015-03 Industrial Complex (1).xlsx
129 | 123 | Elektriciteit toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-08-23 08:00 | 5d | 1820.8 | 0 | 0 | 0 | 0 | 1820.8 | 0 | 1 | Finished | 1456.64 | 1456.64 | C2015-03 Industrial Complex (1).xlsx
130 | 124 | Binnenschrijnwerk | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 | 2013-08-30 08:00 | 6d | 81056.6426 | 0 | 0 | 0 | 0 | 81056.6426 | 0 | 1 | Finished | 67547.2021 | 67547.2021 | C2015-03 Industrial Complex (1).xlsx
131 | 125 | keuken | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 135.64 | 5425.6 | 5425.6 | 2013-09-09 08:00 | 4d | 4340.48 | 0 | 0 | 0 | 0 | 4340.48 | 0 | 1 | Finished | 5425.6 | 5425.6 | C2015-03 Industrial Complex (1).xlsx
132 | 126 | Schilderwerken | 2013-09-27 08:00 | 2013-10-04 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 2013-09-13 08:00 | 10d | 7424.0002 | 0 | 0 | 0 | 0 | 7424.0002 | 0 | 1 | Finished | 4454.4001 | 4454.4001 | C2015-03 Industrial Complex (1).xlsx
133 | 127 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-27 08:00 | 7d | 2549.12 | 0 | 0 | 0 | 0 | 2549.12 | 0 | 1 | Finished | 1456.64 | 1456.64 | C2015-03 Industrial Complex (1).xlsx
134 | 128 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 | 2013-10-08 08:00 | 3d | 3747.1201 | 0 | 0 | 0 | 0 | 3747.1201 | 0 | 1 | Finished | 6245.2002 | 6245.2002 | C2015-03 Industrial Complex (1).xlsx
135 | 142 | 1e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-07 17:00 | 76d |  |  | 0 |  |  | 144330.723 |  | 86d 1h | [5 empty] | 133310.0028 |  | 1 |  | 144330.723 | 144330.723 | C2015-03 Industrial Complex (1).xlsx
136 | 130 | HVAC plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 1 | Finished | 11288.9601 | 11288.9601 | C2015-03 Industrial Complex (1).xlsx
137 | 131 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 1 | Finished | 11288.9601 | 11288.9601 | C2015-03 Industrial Complex (1).xlsx
138 | 132 | Schilderwerken wanden | 2013-08-06 08:00 | 2013-08-08 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-08-09 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 1 | Finished | 2227.2001 | 2227.2001 | C2015-03 Industrial Complex (1).xlsx
139 | 133 | structuur valse plafond | 2013-08-09 08:00 | 2013-08-13 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 | 2013-08-14 08:00 | 3d | 1092.48 | 0 | 0 | 0 | 0 | 1092.48 | 0 | 1 | Finished | 1092.48 | 1092.48 | C2015-03 Industrial Complex (1).xlsx
140 | 134 | Elektriciteit vloer | 2013-08-14 08:00 | 2013-08-27 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 | 2013-08-21 08:00 | 8d | 19102.0801 | 0 | 0 | 0 | 0 | 19102.0801 | 0 | 1 | Finished | 23877.6001 | 23877.6001 | C2015-03 Industrial Complex (1).xlsx
141 | 135 | verhoogde vloer | 2013-08-28 08:00 | 2013-09-03 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 | 2013-09-02 08:00 | 5d | 11938.8 | 0 | 0 | 0 | 0 | 11938.8 | 0 | 1 | Finished | 11938.8 | 11938.8 | C2015-03 Industrial Complex (1).xlsx
142 | 136 | HVAC toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-09 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 1 | Finished | 1456.64 | 1456.64 | C2015-03 Industrial Complex (1).xlsx
143 | 137 | Elektriciteit toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-09 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 1 | Finished | 1456.64 | 1456.64 | C2015-03 Industrial Complex (1).xlsx
144 | 138 | Binnenschrijnwerk | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 | 2013-09-13 08:00 | 5d | 67547.2021 | 0 | 0 | 0 | 0 | 67547.2021 | 0 | 1 | Finished | 67547.2021 | 67547.2021 | C2015-03 Industrial Complex (1).xlsx
145 | 139 | schilderwerken | 2013-09-17 08:00 | 2013-09-24 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 2013-09-20 08:00 | 6d | 4454.4001 | 0 | 0 | 0 | 0 | 4454.4001 | 0 | 1 | Finished | 4454.4001 | 4454.4001 | C2015-03 Industrial Complex (1).xlsx
146 | 140 | plafondtegels | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-30 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 1 | Finished | 1456.64 | 1456.64 | C2015-03 Industrial Complex (1).xlsx
147 | 141 | tapijt | 2013-10-01 08:00 | 2013-10-07 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 | 2013-10-25 08:00 | 1h | 156.13 | 0 | 0 | -156.13 | 0 | 0 | 0 | 1 | Finished | 6245.2002 | 6245.2002 | C2015-03 Industrial Complex (1).xlsx
148 | 155 | gv landscape rechts | 2013-08-06 08:00 | 2013-10-17 17:00 | 53d |  |  | 0 |  |  | 101860.7995 |  | 55d 1h | [5 empty] | 94158.9593 |  | 1 |  | 101860.7995 | 101860.7995 | C2015-03 Industrial Complex (1).xlsx
149 | 143 | HVAC plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 | 2013-08-09 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 1 | Finished | 6190.7201 | 6190.7201 | C2015-03 Industrial Complex (1).xlsx
150 | 144 | Elektriciteit plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 | 2013-08-09 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 1 | Finished | 6190.7201 | 6190.7201 | C2015-03 Industrial Complex (1).xlsx
151 | 145 | Schilderwerk wanden | 2013-08-29 08:00 | 2013-09-02 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-09-03 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 1 | Finished | 2227.2001 | 2227.2001 | C2015-03 Industrial Complex (1).xlsx
152 | 146 | structuur valse plafond | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 | 2013-09-06 08:00 | 3d | 1092.48 | 0 | 0 | 0 | 0 | 1092.48 | 0 | 1 | Finished | 1092.48 | 1092.48 | C2015-03 Industrial Complex (1).xlsx
153 | 147 | elektriciteit vloer | 2013-09-06 08:00 | 2013-09-17 17:00 | 8d |  | 0 | 0 | 298.47 | 19102.0801 | 19102.0801 | 2013-09-27 08:00 | 8d | 19102.0801 | 0 | 0 | 0 | 0 | 19102.0801 | 0 | 1 | Finished | 19102.0801 | 19102.0801 | C2015-03 Industrial Complex (1).xlsx
154 | 148 | verhoogde vloer | 2013-09-18 08:00 | 2013-09-24 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 | 2013-10-09 08:00 | 5d | 11938.8 | 0 | 0 | 0 | 0 | 11938.8 | 0 | 1 | Finished | 11938.8 | 11938.8 | C2015-03 Industrial Complex (1).xlsx
155 | 149 | HVAC toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-11 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 1 | Finished | 1456.64 | 1456.64 | C2015-03 Industrial Complex (1).xlsx
156 | 150 | Elektriciteit toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-11 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 1 | Finished | 1456.64 | 1456.64 | C2015-03 Industrial Complex (1).xlsx
157 | 151 | Binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-02 17:00 | 2d |  | 0 | 0 | 2688.6799 | 43018.8789 | 43018.8789 | 2013-09-17 08:00 | 2d | 43018.8789 | 0 | 0 | 0 | 0 | 43018.8789 | 0 | 1 | Finished | 43018.8789 | 43018.8789 | C2015-03 Industrial Complex (1).xlsx
158 | 152 | Schilderwerk | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 92.8 | 1484.8 | 1484.8 | 2013-09-19 08:00 | 2d | 1484.8 | 0 | 0 | 0 | 0 | 1484.8 | 0 | 1 | Finished | 1484.8 | 1484.8 | C2015-03 Industrial Complex (1).xlsx
159 | 153 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-23 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 1 | Finished | 1456.64 | 1456.64 | C2015-03 Industrial Complex (1).xlsx
160 | 154 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 | 2013-10-25 08:00 | 1h | 156.13 | 0 | 0 | -156.13 | 0 | 0 | 0 | 1 | Finished | 6245.2002 | 6245.2002 | C2015-03 Industrial Complex (1).xlsx
161 | 162 | overige delen gv | 2013-06-27 08:00 | 2013-10-22 17:00 | 84d |  |  | 0 |  |  | 142447.6841 |  | 62d | [5 empty] | 127797.1237 |  | 1 |  | 142447.6841 | 142447.6841 | C2015-03 Industrial Complex (1).xlsx
162 | 156 | schilderwerk | 2013-06-27 08:00 | 2013-08-19 17:00 | 38d |  | 0 | 0 | 92.8 | 28211.2009 | 28211.2009 | 2013-08-01 08:00 | 20d | 14848.0005 | 0 | 0 | 0 | 0 | 14848.0005 | 0 | 1 | Finished | 28211.2009 | 28211.2009 | C2015-03 Industrial Complex (1).xlsx
163 | 157 | HVAC plafond | 2013-08-20 08:00 | 2013-09-09 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-09-02 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 1 | Finished | 5462.4001 | 5462.4001 | C2015-03 Industrial Complex (1).xlsx
164 | 158 | Elektriciteit plafond | 2013-09-10 08:00 | 2013-09-30 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-09-23 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 1 | Finished | 5462.4001 | 5462.4001 | C2015-03 Industrial Complex (1).xlsx
165 | 159 | binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-09 17:00 | 7d |  | 0 | 0 | 1688.6801 | 94566.083 | 94566.083 | 2013-10-14 08:00 | 7d | 94566.083 | 0 | 0 | 0 | 0 | 94566.083 | 0 | 1 | Finished | 94566.083 | 94566.083 | C2015-03 Industrial Complex (1).xlsx
166 | 160 | gyproc werken | 2013-09-17 08:00 | 2013-10-14 17:00 | 20d |  | 0 | 0 | 26.82 | 4291.2 | 4291.2 | 2013-09-30 08:00 | 14d | 3003.84 | 0 | 0 | 0 | 0 | 3003.84 | 0 | 1 | Finished | 4291.2 | 4291.2 | C2015-03 Industrial Complex (1).xlsx
167 | 161 | Schilderwerken | 2013-10-15 08:00 | 2013-10-22 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 2013-10-18 08:00 | 6d | 4454.4001 | 0 | 0 | 0 | 0 | 4454.4001 | 0 | 1 | Finished | 4454.4001 | 4454.4001 | C2015-03 Industrial Complex (1).xlsx
4 | 0 | Apartment Building (5) | 2013-02-25 08:00 | 2013-10-04 17:00 | 160d |  |  | 0 |  |  | 2750937.9996 |  | 205d | [5 empty] | 2590796.7261 |  | 1 |  | 2750937.9996 | 2750937.9996 | C2015-04 Apartment Building (5).xlsx
5 | 1 | Dakwerken | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 5000 | 200000 | 200000 | 2013-02-25 08:00 | 5d | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | 1 | Finished | 200000 | 200000 | C2015-04 Apartment Building (5).xlsx
6 | 2 | Schrijnwerk | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 10253.9102 | 410156.4062 | 410156.4062 | 2013-03-04 08:00 | 5d | 410156.4062 | 0 | 0 | 0 | 0 | 410156.4062 | 0 | 1 | Finished | 410156.4062 | 410156.4062 | C2015-04 Apartment Building (5).xlsx
7 | 3 | Ventilatie | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 4375 | 175000 | 175000 | 2013-03-11 08:00 | 5d | 175000 | 0 | 0 | 0 | 0 | 175000 | 0 | 1 | Finished | 175000 | 175000 | C2015-04 Apartment Building (5).xlsx
8 | 4 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 4268.29 | 170731.6016 | 170731.6016 | 2013-03-18 08:00 | 5d | 170731.6016 | 0 | 0 | 0 | 0 | 170731.6016 | 0 | 1 | Finished | 170731.6016 | 170731.6016 | C2015-04 Apartment Building (5).xlsx
9 | 5 | Elektriciteit | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1801.67 | 72066.8018 | 72066.8018 | 2013-03-25 08:00 | 5d | 72066.8018 | 0 | 0 | 0 | 0 | 72066.8018 | 0 | 1 | Finished | 72066.8018 | 72066.8018 | C2015-04 Apartment Building (5).xlsx
10 | 6 | Sanitair | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 3585.3701 | 143414.8047 | 143414.8047 | 2013-04-01 08:00 | 5d | 143414.8047 | 0 | 0 | 0 | 0 | 143414.8047 | 0 | 1 | Finished | 143414.8047 | 143414.8047 | C2015-04 Apartment Building (5).xlsx
11 | 7 | Isolatie zolder | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-01 08:00 | 5d | 3571.6 | 0 | 0 | -1785.8 | 0 | 1785.8 | 0 | 1 | Finished | 3571.6 | 3571.6 | C2015-04 Apartment Building (5).xlsx
12 | 8 | Elektriciteit | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 1 | Finished | 12533.1995 | 12533.1995 | C2015-04 Apartment Building (5).xlsx
13 | 9 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-04-08 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 1 | Finished | 27316.7993 | 27316.7993 | C2015-04 Apartment Building (5).xlsx
14 | 10 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 1 | Finished | 12533.1995 | 12533.1995 | C2015-04 Apartment Building (5).xlsx
15 | 11 | Sanitair | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1195.12 | 47804.7998 | 47804.7998 | 2013-04-08 08:00 | 5d | 47804.7998 | 0 | 0 | 0 | 0 | 47804.7998 | 0 | 1 | Finished | 47804.7998 | 47804.7998 | C2015-04 Apartment Building (5).xlsx
16 | 12 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-22 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 1 | Finished | 12533.1995 | 12533.1995 | C2015-04 Apartment Building (5).xlsx
17 | 13 | Sanitair | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1365.85 | 54633.999 | 54633.999 | 2013-04-22 08:00 | 5d | 54633.999 | 0 | 0 | 0 | 0 | 54633.999 | 0 | 1 | Finished | 54633.999 | 54633.999 | C2015-04 Apartment Building (5).xlsx
18 | 14 | Isolatie zolder | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-22 08:00 | 5d | 3571.6 | 0 | 0 | 0 | 0 | 3571.6 | 0 | 1 | Finished | 3571.6 | 3571.6 | C2015-04 Apartment Building (5).xlsx
19 | 15 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 2013-04-29 08:00 | 5d | 14285.6006 | 0 | 0 | 0 | 0 | 14285.6006 | 0 | 1 | Finished | 14285.6006 | 14285.6006 | C2015-04 Apartment Building (5).xlsx
20 | 16 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-29 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 1 | Finished | 12533.1995 | 12533.1995 | C2015-04 Apartment Building (5).xlsx
21 | 17 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-04-29 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 1 | Finished | 27316.7993 | 27316.7993 | C2015-04 Apartment Building (5).xlsx
22 | 18 | Isolatie zolder | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-29 08:00 | 5d | 3571.6 | 0 | 0 | 0 | 0 | 3571.6 | 0 | 1 | Finished | 3571.6 | 3571.6 | C2015-04 Apartment Building (5).xlsx
23 | 19 | Chap | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 2013-05-06 08:00 | 5d | 14285.6006 | 0 | 0 | 0 | 0 | 14285.6006 | 0 | 1 | Finished | 14285.6006 | 14285.6006 | C2015-04 Apartment Building (5).xlsx
24 | 20 | Elektriciteit | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-05-06 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 1 | Finished | 12533.1995 | 12533.1995 | C2015-04 Apartment Building (5).xlsx
25 | 21 | Sanitair | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-05-06 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 1 | Finished | 27316.7993 | 27316.7993 | C2015-04 Apartment Building (5).xlsx
26 | 22 | Bevloering en faience | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 | 2013-05-13 08:00 | 5d | 18750 | 0 | 0 | 18750 | 0 | 37500 | 0 | 1 | Finished | 18750 | 18750 | C2015-04 Apartment Building (5).xlsx
27 | 23 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-05-13 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 1 | Finished | 12533.1995 | 12533.1995 | C2015-04 Apartment Building (5).xlsx
28 | 24 | Sanitair | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 | 2013-05-13 08:00 | 5d | 6829.1998 | 0 | 0 | 0 | 0 | 6829.1998 | 0 | 1 | Finished | 6829.1998 | 6829.1998 | C2015-04 Apartment Building (5).xlsx
29 | 25 | Elektriciteit | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1400 | 56000 | 56000 | 2013-05-20 08:00 | 5d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 1 | Finished | 56000 | 56000 | C2015-04 Apartment Building (5).xlsx
30 | 26 | Isolatie chap/pure | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-05-20 08:00 | 5d | 17857.1997 | 0 | 0 | 0 | 0 | 17857.1997 | 0 | 1 | Finished | 17857.1997 | 17857.1997 | C2015-04 Apartment Building (5).xlsx
31 | 27 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 | 2013-06-10 08:00 | 5d | 6829.1998 | 0 | 0 | 0 | 0 | 6829.1998 | 0 | 1 | Finished | 6829.1998 | 6829.1998 | C2015-04 Apartment Building (5).xlsx
32 | 28 | Chape | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-08-19 08:00 | 5d | 17857.1997 | 0 | 0 | 0 | 0 | 17857.1997 | 0 | 1 | Finished | 17857.1997 | 17857.1997 | C2015-04 Apartment Building (5).xlsx
33 | 29 | Parket | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 | 2013-10-07 08:00 | 5d | 18750 | 0 | 0 | 18750 | 0 | 37500 | 0 | 1 | Finished | 18750 | 18750 | C2015-04 Apartment Building (5).xlsx
34 | 30 | Vloer | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 2013-10-07 08:00 | 10d | 75000 | 0 | 0 | -37500 | 0 | 37500 | 0 | 1 | Finished | 37500 | 37500 | C2015-04 Apartment Building (5).xlsx
35 | 31 | Isolatie chape/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 | 2013-08-26 08:00 | 5d | 12500 | 0 | 0 | 0 | 0 | 12500 | 0 | 1 | Finished | 12500 | 12500 | C2015-04 Apartment Building (5).xlsx
36 | 32 | Ventilatie | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 | 2013-08-19 08:00 | 5d | 49000 | 0 | 0 | 0 | 0 | 49000 | 0 | 1 | Finished | 49000 | 49000 | C2015-04 Apartment Building (5).xlsx
37 | 33 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 391.67 | 15666.8005 | 15666.8005 | 2013-09-16 08:00 | 5d | 15666.8005 | 0 | 0 | 0 | 0 | 15666.8005 | 0 | 1 | Finished | 15666.8005 | 15666.8005 | C2015-04 Apartment Building (5).xlsx
38 | 34 | Vloer | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 | 2013-10-07 08:00 | 5d | 56250 | 0 | 0 | -18750 | 0 | 37500 | 0 | 1 | Finished | 56250 | 56250 | C2015-04 Apartment Building (5).xlsx
39 | 35 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 | 2013-09-02 08:00 | 5d | 12500 | 0 | 0 | 0 | 0 | 12500 | 0 | 1 | Finished | 12500 | 12500 | C2015-04 Apartment Building (5).xlsx
40 | 36 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 410.16 | 16406.4001 | 16406.4001 | 2013-08-19 08:00 | 5d | 16406.4001 | 0 | 0 | 0 | 0 | 16406.4001 | 0 | 1 | Finished | 16406.4001 | 16406.4001 | C2015-04 Apartment Building (5).xlsx
41 | 37 | Sanitair | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 | 2013-06-10 08:00 | 5d | 13658.3997 | 0 | 0 | 13658.4004 | 0 | 27316.8 | 0 | 1 | Finished | 13658.3997 | 13658.3997 | C2015-04 Apartment Building (5).xlsx
42 | 38 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 | 2013-09-09 08:00 | 30d | 112800 | 0 | 0 | -94000 | 0 | 18800 | 0 | 1 | Finished | 18800 | 18800 | C2015-04 Apartment Building (5).xlsx
43 | 39 | Vloer | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 2013-11-25 08:00 | 5d | 37500 | 0 | 0 | 18750 | 0 | 56250 | 0 | 1 | Finished | 37500 | 37500 | C2015-04 Apartment Building (5).xlsx
44 | 40 | Keuken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 546.87 | 21874.7998 | 21874.7998 | 2013-11-18 08:00 | 5d | 21874.7998 | 0 | 0 | 0 | 0 | 21874.7998 | 0 | 1 | Finished | 21874.7998 | 21874.7998 | C2015-04 Apartment Building (5).xlsx
45 | 41 | Parket | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 2013-09-09 08:00 | 5d | 37500 | 0 | 0 | 56250 | 0 | 93750 | 0 | 1 | Finished | 37500 | 37500 | C2015-04 Apartment Building (5).xlsx
46 | 42 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 512.2 | 20488.0005 | 20488.0005 | 2013-10-21 08:00 | 5d | 20488.0005 | 0 | 0 | -6829.3301 | 0 | 13658.6704 | 0 | 1 | Finished | 20488.0005 | 20488.0005 | C2015-04 Apartment Building (5).xlsx
47 | 43 | Elektriciteit | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 | 2013-06-10 08:00 | 20d | 75200 | 0 | 0 | -56400 | 0 | 18800 | 0 | 1 | Finished | 18800 | 18800 | C2015-04 Apartment Building (5).xlsx
48 | 44 | Ventilatie | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 1750 | 70000 | 70000 | 2013-09-16 08:00 | 20d | 280000 | 0 | 0 | -210000 | 0 | 70000 | 0 | 1 | Finished | 70000 | 70000 | C2015-04 Apartment Building (5).xlsx
49 | 45 | Sanitair | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 | 2013-07-01 08:00 | 10d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 1 | Finished | 13658.3997 | 13658.3997 | C2015-04 Apartment Building (5).xlsx
50 | 46 | Schrijnwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 | 2013-09-30 08:00 | 20d | 131249.5996 | 0 | 0 | -98437 | 0 | 32812.5996 | 0 | 1 | Finished | 32812.3999 | 32812.3999 | C2015-04 Apartment Building (5).xlsx
51 | 47 | Parket | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 | 2013-09-23 08:00 | 5d | 56250 | 0 | 0 | -18750 | 0 | 37500 | 0 | 1 | Finished | 56250 | 56250 | C2015-04 Apartment Building (5).xlsx
52 | 48 | Ventilatie | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 | 2013-10-07 08:00 | 10d | 98000 | 0 | 0 | -49000 | 0 | 49000 | 0 | 1 | Finished | 49000 | 49000 | C2015-04 Apartment Building (5).xlsx
53 | 49 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 2013-10-07 08:00 | 10d | 87500 | 0 | 0 | -43750 | 0 | 43750 | 0 | 1 | Finished | 43750 | 43750 | C2015-04 Apartment Building (5).xlsx
54 | 50 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1230.47 | 49218.7988 | 49218.7988 | 2013-09-30 08:00 | 5d | 49218.7988 | 0 | 0 | -16406 | 0 | 32812.7988 | 0 | 1 | Finished | 49218.7988 | 49218.7988 | C2015-04 Apartment Building (5).xlsx
55 | 51 | Parket | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 2013-10-28 08:00 | 10d | 75000 | 0 | 0 | -18750 | 0 | 56250 | 0 | 1 | Finished | 37500 | 37500 | C2015-04 Apartment Building (5).xlsx
56 | 52 | Keuken | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 1640.63 | 65625.2002 | 65625.2002 | 2013-10-14 08:00 | 5d | 65625.2002 | 0 | 0 | -21875 | 0 | 43750.2002 | 0 | 1 | Finished | 65625.2002 | 65625.2002 | C2015-04 Apartment Building (5).xlsx
57 | 53 | Schrijnwerk | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 | 2013-11-18 08:00 | 5d | 32812.3999 | 0 | 0 | 16406.1992 | 0 | 49218.5991 | 0 | 1 | Finished | 32812.3999 | 32812.3999 | C2015-04 Apartment Building (5).xlsx
58 | 54 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 2013-12-02 08:00 | 5d | 43750 | 0 | 0 | 21875 | 0 | 65625 | 0 | 1 | Finished | 43750 | 43750 | C2015-04 Apartment Building (5).xlsx
59 | 55 | Plakwerken | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 916.67 | 36666.7993 | 36666.7993 | 2013-12-02 08:00 | 1h | 916.67 | 0 | 0 | 0 | 0 | 916.67 | 0 | 1 | Finished | 36666.7993 | 36666.7993 | C2015-04 Apartment Building (5).xlsx
60 | 56 | Plakwerken deel 2 | 2013-09-09 08:00 | 2013-10-04 17:00 | 20d |  | 0 | 0 | 1489.58 | 238332.793 | 238332.793 | 2013-12-02 08:00 | 1h | 1489.58 | 0 | 0 | 0 | 0 | 1489.58 | 0 | 1 | Finished | 238332.793 | 238332.793 | C2015-04 Apartment Building (5).xlsx
4 | 0 | Apartment Building (6) | 2013-01-14 08:00 | 2013-06-28 17:00 | 120d |  |  | 0 |  |  | 2524765.1855 |  | 130d | [5 empty] | 2563675.8643 |  | 1 |  | 2524765.1855 | 2524765.1855 | C2015-05 Apartment Building (6).xlsx
5 | 1 | Dakwerken | 2013-01-14 08:00 | 2013-01-18 17:00 | 5d |  | 0 | 0 | 2578.95 | 103157.998 | 103157.998 | 2013-01-14 08:00 | 5d | 103157.998 | 0 | 0 | 0 | 0 | 103157.998 | 0 | 1 | Finished | 103157.998 | 103157.998 | C2015-05 Apartment Building (6).xlsx
6 | 2 | Sanitair | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 1666.67 | 66666.8018 | 66666.8018 | 2013-01-21 08:00 | 5d | 66666.8018 | 0 | 0 | 0 | 0 | 66666.8018 | 0 | 1 | Finished | 66666.8018 | 66666.8018 | C2015-05 Apartment Building (6).xlsx
7 | 3 | Dakwerken | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 3546.05 | 141842.002 | 141842.002 | 2013-01-21 08:00 | 5d | 141842.002 | 0 | 0 | 0 | 0 | 141842.002 | 0 | 1 | Finished | 141842.002 | 141842.002 | C2015-05 Apartment Building (6).xlsx
8 | 4 | Elektriciteit | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1447.37 | 57894.7998 | 57894.7998 | 2013-01-28 08:00 | 5d | 57894.7998 | 0 | 0 | 0 | 0 | 57894.7998 | 0 | 1 | Finished | 57894.7998 | 57894.7998 | C2015-05 Apartment Building (6).xlsx
9 | 5 | Ventilatie | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 10000 | 400000 | 400000 | 2013-01-28 08:00 | 5d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 1 | Finished | 400000 | 400000 | C2015-05 Apartment Building (6).xlsx
10 | 6 | Plakwerken | 2013-02-04 08:00 | 2013-02-22 17:00 | 15d |  | 0 | 0 | 421.05 | 50525.9985 | 50525.9985 | 2013-02-04 08:00 | 15d | 50525.9985 | 0 | 0 | 0 | 0 | 50525.9985 | 0 | 1 | Finished | 50525.9985 | 50525.9985 | C2015-05 Apartment Building (6).xlsx
11 | 7 | Sanitair | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 2291.6699 | 91666.7969 | 91666.7969 | 2013-02-04 08:00 | 5d | 91666.7969 | 0 | 0 | 0 | 0 | 91666.7969 | 0 | 1 | Finished | 91666.7969 | 91666.7969 | C2015-05 Apartment Building (6).xlsx
12 | 8 | Plakwerken | 2013-02-18 08:00 | 2013-04-05 17:00 | 35d |  | 0 | 0 | 421.05 | 117893.9966 | 117893.9966 | 2013-02-18 08:00 | 35d | 117893.9966 | 0 | 0 | 0 | 0 | 117893.9966 | 0 | 1 | Finished | 117893.9966 | 117893.9966 | C2015-05 Apartment Building (6).xlsx
13 | 9 | Isolatie zolder | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-03-11 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 1 | Finished | 5952.3999 | 5952.3999 | C2015-05 Apartment Building (6).xlsx
14 | 10 | Sanitair | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 2291.6699 | 91666.7969 | 91666.7969 | 2013-02-18 08:00 | 5d | 91666.7969 | 0 | 0 | 0 | 0 | 91666.7969 | 0 | 1 | Finished | 91666.7969 | 91666.7969 | C2015-05 Apartment Building (6).xlsx
15 | 11 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1666.67 | 66666.8018 | 66666.8018 | 2013-03-04 08:00 | 5d | 66666.8018 | 0 | 0 | 0 | 0 | 66666.8018 | 0 | 1 | Finished | 66666.8018 | 66666.8018 | C2015-05 Apartment Building (6).xlsx
16 | 12 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 | 2013-03-25 08:00 | 5d | 21710.4004 | 0 | 0 | 0 | 0 | 21710.4004 | 0 | 1 | Finished | 21710.4004 | 21710.4004 | C2015-05 Apartment Building (6).xlsx
17 | 13 | Sanitair | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 833.33 | 33333.2007 | 33333.2007 | 2013-03-04 08:00 | 5d | 33333.2007 | 0 | 0 | 16666.6602 | 0 | 49999.8608 | 0 | 1 | Finished | 33333.2007 | 33333.2007 | C2015-05 Apartment Building (6).xlsx
18 | 14 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 1447.37 | 57894.7998 | 57894.7998 | 2013-03-04 08:00 | 5d | 57894.7998 | 0 | 0 | -28947.4004 | 0 | 28947.3994 | 0 | 1 | Finished | 57894.7998 | 57894.7998 | C2015-05 Apartment Building (6).xlsx
19 | 15 | Plakwerken | 2013-03-04 08:00 | 2013-03-22 17:00 | 15d |  | 0 | 0 | 421.05 | 50525.9985 | 50525.9985 | 2013-03-04 08:00 | 15d | 50525.9985 | 0 | 0 | 0 | 0 | 50525.9985 | 0 | 1 | Finished | 50525.9985 | 50525.9985 | C2015-05 Apartment Building (6).xlsx
20 | 16 | Isolatie chape/pure | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 297.62 | 11904.7998 | 11904.7998 | 2013-03-11 08:00 | 5d | 11904.7998 | 0 | 0 | 0 | 0 | 11904.7998 | 0 | 1 | Finished | 11904.7998 | 11904.7998 | C2015-05 Apartment Building (6).xlsx
21 | 17 | Elektriciteit | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1085.53 | 43421.2012 | 43421.2012 | 2013-03-11 08:00 | 10d | 86842.4023 | 0 | 0 | -43421.1992 | 0 | 43421.2031 | 0 | 1 | Finished | 43421.2012 | 43421.2012 | C2015-05 Apartment Building (6).xlsx
22 | 18 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-04-01 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 1 | Finished | 5952.3999 | 5952.3999 | C2015-05 Apartment Building (6).xlsx
23 | 19 | Chape | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 297.62 | 11904.7998 | 11904.7998 | 2013-03-18 08:00 | 5d | 11904.7998 | 0 | 0 | 0 | 0 | 11904.7998 | 0 | 1 | Finished | 11904.7998 | 11904.7998 | C2015-05 Apartment Building (6).xlsx
24 | 20 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-03-04 08:00 | 5d | 16666.8005 | 0 | 0 | 0 | 0 | 16666.8005 | 0 | 1 | Finished | 16666.8005 | 16666.8005 | C2015-05 Apartment Building (6).xlsx
25 | 21 | Vloer | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 | 2013-03-25 08:00 | 5d | 14583.1995 | 0 | 0 | 0 | 0 | 14583.1995 | 0 | 1 | Finished | 14583.1995 | 14583.1995 | C2015-05 Apartment Building (6).xlsx
26 | 22 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-03-11 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 1 | Finished | 5952.3999 | 5952.3999 | C2015-05 Apartment Building (6).xlsx
27 | 23 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1041.67 | 41666.8018 | 41666.8018 | 2013-04-01 08:00 | 5d | 41666.8018 | 0 | 0 | 0 | 0 | 41666.8018 | 0 | 1 | Finished | 41666.8018 | 41666.8018 | C2015-05 Apartment Building (6).xlsx
28 | 24 | Plakwerk | 2013-03-25 08:00 | 2013-04-19 17:00 | 20d |  | 0 | 0 | 421.05 | 67367.998 | 67367.998 | 2013-03-25 08:00 | 20d | 67367.998 | 0 | 0 | 0 | 0 | 67367.998 | 0 | 1 | Finished | 67367.998 | 67367.998 | C2015-05 Apartment Building (6).xlsx
29 | 25 | Vloer | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 2013-04-01 08:00 | 5d | 43750 | 0 | 0 | 0 | 0 | 43750 | 0 | 1 | Finished | 43750 | 43750 | C2015-05 Apartment Building (6).xlsx
30 | 26 | Chape | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-03-25 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 1 | Finished | 5952.3999 | 5952.3999 | C2015-05 Apartment Building (6).xlsx
31 | 27 | Isolatie chap/pure | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 372.02 | 14880.7996 | 14880.7996 | 2013-04-08 08:00 | 5d | 14880.7996 | 0 | 0 | 0 | 0 | 14880.7996 | 0 | 1 | Finished | 14880.7996 | 14880.7996 | C2015-05 Apartment Building (6).xlsx
32 | 28 | Elektriciteit | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 | 2013-04-08 08:00 | 5d | 7236.7999 | 0 | 0 | 0 | 0 | 7236.7999 | 0 | 1 | Finished | 7236.7999 | 7236.7999 | C2015-05 Apartment Building (6).xlsx
33 | 29 | Vloer | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-03-25 08:00 | 5d | 58333.1982 | 0 | 0 | 0 | 0 | 58333.1982 | 0 | 1 | Finished | 58333.1982 | 58333.1982 | C2015-05 Apartment Building (6).xlsx
34 | 30 | Chape | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 372.02 | 14880.7996 | 14880.7996 | 2013-04-15 08:00 | 5d | 14880.7996 | 0 | 0 | 0 | 0 | 14880.7996 | 0 | 1 | Finished | 14880.7996 | 14880.7996 | C2015-05 Apartment Building (6).xlsx
35 | 31 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 361.84 | 14473.5999 | 14473.5999 | 2013-04-29 08:00 | 5d | 14473.5999 | 0 | 0 | 0 | 0 | 14473.5999 | 0 | 1 | Finished | 14473.5999 | 14473.5999 | C2015-05 Apartment Building (6).xlsx
36 | 32 | Vloer | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1822.92 | 72916.8018 | 72916.8018 | 2013-04-15 08:00 | 30d | 437500.8105 | 0 | 0 | -364583.1875 | 0 | 72917.623 | 0 | 1 | Finished | 72916.8018 | 72916.8018 | C2015-05 Apartment Building (6).xlsx
37 | 33 | Sanitair | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-04-22 08:00 | 5d | 16666.8005 | 0 | 0 | 0 | 0 | 16666.8005 | 0 | 1 | Finished | 16666.8005 | 16666.8005 | C2015-05 Apartment Building (6).xlsx
38 | 34 | Sanitair | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-04-15 08:00 | 25d | 291665.9912 | 0 | 0 | -233333 | 0 | 58332.9912 | 0 | 1 | Finished | 58333.1982 | 58333.1982 | C2015-05 Apartment Building (6).xlsx
39 | 35 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 361.84 | 14473.5999 | 14473.5999 | 2013-04-29 08:00 | 5d | 14473.5999 | 0 | 0 | 0 | 0 | 14473.5999 | 0 | 1 | Finished | 14473.5999 | 14473.5999 | C2015-05 Apartment Building (6).xlsx
40 | 36 | Vloer | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 2013-04-29 08:00 | 5d | 43750 | 0 | 0 | 0 | 0 | 43750 | 0 | 1 | Finished | 43750 | 43750 | C2015-05 Apartment Building (6).xlsx
41 | 37 | Isolatie chap/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-04-29 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 1 | Finished | 5952.3999 | 5952.3999 | C2015-05 Apartment Building (6).xlsx
42 | 38 | Keuken | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 2013-05-13 08:00 | 5d | 17307.6001 | 0 | 0 | 0 | 0 | 17307.6001 | 0 | 1 | Finished | 17307.6001 | 17307.6001 | C2015-05 Apartment Building (6).xlsx
43 | 39 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-05-13 08:00 | 5d | 16666.8005 | 0 | 0 | 0 | 0 | 16666.8005 | 0 | 1 | Finished | 16666.8005 | 16666.8005 | C2015-05 Apartment Building (6).xlsx
44 | 40 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 | 2013-05-13 08:00 | 5d | 21710.4004 | 0 | 0 | 0 | 0 | 21710.4004 | 0 | 1 | Finished | 21710.4004 | 21710.4004 | C2015-05 Apartment Building (6).xlsx
45 | 41 | Chape | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-05-06 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 1 | Finished | 5952.3999 | 5952.3999 | C2015-05 Apartment Building (6).xlsx
46 | 42 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-04-22 08:00 | 25d | 89285.9985 | 0 | 0 | -71428.7969 | 0 | 17857.2017 | 0 | 1 | Finished | 17857.1997 | 17857.1997 | C2015-05 Apartment Building (6).xlsx
47 | 43 | Keuken | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 | 2013-05-20 08:00 | 5d | 34615.2002 | 0 | 0 | 0 | 0 | 34615.2002 | 0 | 1 | Finished | 34615.2002 | 34615.2002 | C2015-05 Apartment Building (6).xlsx
48 | 44 | Sanitair | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-05-13 08:00 | 20d | 66667.2021 | 0 | 0 | -16666.8008 | 0 | 50000.4014 | 0 | 1 | Finished | 16666.8005 | 16666.8005 | C2015-05 Apartment Building (6).xlsx
49 | 45 | Vloer | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 | 2013-05-13 08:00 | 5d | 14583.1995 | 0 | 0 | 0 | 0 | 14583.1995 | 0 | 1 | Finished | 14583.1995 | 14583.1995 | C2015-05 Apartment Building (6).xlsx
50 | 46 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-04-29 08:00 | 25d | 89285.9985 | 0 | 0 | -53571.6016 | 0 | 35714.397 | 0 | 1 | Finished | 17857.1997 | 17857.1997 | C2015-05 Apartment Building (6).xlsx
51 | 47 | Keuken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 | 2013-06-24 08:00 | 10d | 69230.4004 | 0 | 0 | -34615.1992 | 0 | 34615.2012 | 0 | 1 | Finished | 34615.2002 | 34615.2002 | C2015-05 Apartment Building (6).xlsx
52 | 48 | Sanitair | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-06-17 08:00 | 10d | 33333.6011 | 0 | 0 | -16666.8008 | 0 | 16666.8003 | 0 | 1 | Finished | 16666.8005 | 16666.8005 | C2015-05 Apartment Building (6).xlsx
53 | 49 | Vloer | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-05-20 08:00 | 5d | 58333.1982 | 0 | 0 | 0 | 0 | 58333.1982 | 0 | 1 | Finished | 58333.1982 | 58333.1982 | C2015-05 Apartment Building (6).xlsx
54 | 50 | Chape | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-04-29 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 1 | Finished | 5952.3999 | 5952.3999 | C2015-05 Apartment Building (6).xlsx
55 | 51 | Keuken | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 | 2013-06-24 08:00 | 10d | 69230.4004 | 0 | 0 | -34615.1992 | 0 | 34615.2012 | 0 | 1 | Finished | 34615.2002 | 34615.2002 | C2015-05 Apartment Building (6).xlsx
56 | 52 | Elektriciteit | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 | 2013-06-03 08:00 | 5d | 7236.7999 | 0 | 0 | 0 | 0 | 7236.7999 | 0 | 1 | Finished | 7236.7999 | 7236.7999 | C2015-05 Apartment Building (6).xlsx
57 | 53 | Vloer | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-06-03 08:00 | 10d | 116666.3965 | 0 | 0 | -58333.1992 | 0 | 58333.1973 | 0 | 1 | Finished | 58333.1982 | 58333.1982 | C2015-05 Apartment Building (6).xlsx
58 | 54 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 | 2013-05-13 08:00 | 5d | 8333.2001 | 0 | 0 | 0 | 0 | 8333.2001 | 0 | 1 | Finished | 8333.2001 | 8333.2001 | C2015-05 Apartment Building (6).xlsx
59 | 55 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 | 2013-05-27 08:00 | 20d | 86841.6016 | 0 | 0 | -65131.1992 | 0 | 21710.4023 | 0 | 1 | Finished | 21710.4004 | 21710.4004 | C2015-05 Apartment Building (6).xlsx
60 | 56 | Vloer | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 | 2013-05-27 08:00 | 5d | 14583.1995 | 0 | 0 | 0 | 0 | 14583.1995 | 0 | 1 | Finished | 14583.1995 | 14583.1995 | C2015-05 Apartment Building (6).xlsx
61 | 57 | Keuken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 2013-05-27 08:00 | 5d | 17307.6001 | 0 | 0 | 0 | 0 | 17307.6001 | 0 | 1 | Finished | 17307.6001 | 17307.6001 | C2015-05 Apartment Building (6).xlsx
62 | 58 | Sanitair | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 | 2013-06-17 08:00 | 5d | 8333.2001 | 0 | 0 | 0 | 0 | 8333.2001 | 0 | 1 | Finished | 8333.2001 | 8333.2001 | C2015-05 Apartment Building (6).xlsx
63 | 59 | Elektriciteit | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 | 2013-05-27 08:00 | 5d | 7236.7999 | 0 | 0 | 0 | 0 | 7236.7999 | 0 | 1 | Finished | 7236.7999 | 7236.7999 | C2015-05 Apartment Building (6).xlsx
64 | 60 | Keuken | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 2013-06-24 08:00 | 5d | 17307.6001 | 0 | 0 | 0 | 0 | 17307.6001 | 0 | 1 | Finished | 17307.6001 | 17307.6001 | C2015-05 Apartment Building (6).xlsx
65 | 61 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-07-01 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 1 | Finished | 25000 | 25000 | C2015-05 Apartment Building (6).xlsx
66 | 62 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1298.08 | 51923.1982 | 51923.1982 | 2013-07-08 08:00 | 5d | 51923.1982 | 0 | 0 | 0 | 0 | 51923.1982 | 0 | 1 | Finished | 51923.1982 | 51923.1982 | C2015-05 Apartment Building (6).xlsx
67 | 63 | Sanitair | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 | 2013-06-03 08:00 | 5d | 8333.2001 | 0 | 0 | 0 | 0 | 8333.2001 | 0 | 1 | Finished | 8333.2001 | 8333.2001 | C2015-05 Apartment Building (6).xlsx
68 | 64 | Keuken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 2013-06-10 08:00 | 5d | 17307.6001 | 0 | 0 | 0 | 0 | 17307.6001 | 0 | 1 | Finished | 17307.6001 | 17307.6001 | C2015-05 Apartment Building (6).xlsx
4 | 0 | Family Residence (2) | 2013-01-28 08:00 | 2014-01-24 17:00 | 260d |  |  | 0 |  |  | 143673.2003 |  | 290d | [5 empty] | 186107.0003 |  | 1 |  | 143673.2003 | 143673.2003 | C2015-06 Family Residence (2).xlsx
5 | 1 | Spanten | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-01-28 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 1 | Finished | 947.2 | 947.2 | C2015-06 Family Residence (2).xlsx
6 | 2 | Isolatie chap/pure | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-01-28 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
7 | 3 | Plakwerken | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-01-28 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 1 | Finished | 1111.2 | 1111.2 | C2015-06 Family Residence (2).xlsx
8 | 4 | Schrijnwerk | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-01-28 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 1 | Finished | 780 | 780 | C2015-06 Family Residence (2).xlsx
9 | 5 | Schrijnwerk deel 2 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 2013-01-28 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 1 | Finished | 390 | 390 | C2015-06 Family Residence (2).xlsx
10 | 6 | Chape | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
11 | 7 | Sanitair | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 7.31 | 584.8 | 584.8 | 2013-02-04 08:00 | 10d | 584.8 | 0 | 0 | 0 | 0 | 584.8 | 0 | 1 | Finished | 584.8 | 584.8 | C2015-06 Family Residence (2).xlsx
12 | 8 | Elektriciteit | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-04 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 1 | Finished | 346 | 346 | C2015-06 Family Residence (2).xlsx
13 | 9 | Spanten | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-03-25 08:00 | 10d | 1420.8 | 0 | 0 | 0 | 0 | 1420.8 | 0 | 1 | Finished | 1420.8 | 1420.8 | C2015-06 Family Residence (2).xlsx
14 | 10 | Dakconstructie | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-02-25 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 1 | Finished | 947.2 | 947.2 | C2015-06 Family Residence (2).xlsx
15 | 11 | Isolatie chap/pure | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 1 | Finished | 132 | 132 | C2015-06 Family Residence (2).xlsx
16 | 12 | Chape | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 1 | Finished | 132 | 132 | C2015-06 Family Residence (2).xlsx
17 | 13 | Elektriciteit | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-18 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 1 | Finished | 346 | 346 | C2015-06 Family Residence (2).xlsx
18 | 14 | Ruwbouw | 2013-02-18 08:00 | 2013-04-19 17:00 | 45d |  | 0 | 0 | 69.26 | 24933.6008 | 24933.6008 | 2013-02-25 08:00 | 75d | 41556.0013 | 0 | 0 | 0 | 0 | 41556.0013 | 0 | 1 | Finished | 24933.6008 | 24933.6008 | C2015-06 Family Residence (2).xlsx
19 | 15 | Sanitair | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-02-18 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 1 | Finished | 566.4 | 566.4 | C2015-06 Family Residence (2).xlsx
20 | 16 | Ruwbouw deel 2 | 2013-02-18 08:00 | 2013-04-26 17:00 | 50d |  | 0 | 0 | 27.71 | 11083.9996 | 11083.9996 | 2013-02-18 08:00 | 85d | 18842.7994 | 0 | 0 | 0 | 0 | 18842.7994 | 0 | 1 | Finished | 11083.9996 | 11083.9996 | C2015-06 Family Residence (2).xlsx
21 | 17 | Dakconstructie | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-04-08 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 1 | Finished | 473.6 | 473.6 | C2015-06 Family Residence (2).xlsx
22 | 18 | Schrijnwerk | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-02-25 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 1 | Finished | 780 | 780 | C2015-06 Family Residence (2).xlsx
23 | 19 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-03-04 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 1 | Finished | 173.2 | 173.2 | C2015-06 Family Residence (2).xlsx
24 | 20 | Vloer | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-02-18 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 1 | Finished | 394.4 | 394.4 | C2015-06 Family Residence (2).xlsx
25 | 21 | Isolatie zolder | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
26 | 22 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-02-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 1 | Finished | 283.2 | 283.2 | C2015-06 Family Residence (2).xlsx
27 | 23 | Elektriciteit deel 2 | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-02-18 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 1 | Finished | 346.4 | 346.4 | C2015-06 Family Residence (2).xlsx
28 | 24 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.31 | 532.4 | 532.4 | 2013-03-11 08:00 | 5d | 532.4 | 0 | 0 | 0 | 0 | 532.4 | 0 | 1 | Finished | 532.4 | 532.4 | C2015-06 Family Residence (2).xlsx
29 | 25 | Vloer | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-03-04 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 1 | Finished | 394.4 | 394.4 | C2015-06 Family Residence (2).xlsx
30 | 26 | Plakwerken | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-03-04 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 1 | Finished | 555.6 | 555.6 | C2015-06 Family Residence (2).xlsx
31 | 27 | Isolatie zolder | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-03-04 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 1 | Finished | 132 | 132 | C2015-06 Family Residence (2).xlsx
32 | 28 | Schrijnwerk | 2013-03-11 08:00 | 2013-04-19 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-03-18 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 1 | Finished | 1171.2 | 1171.2 | C2015-06 Family Residence (2).xlsx
33 | 29 | Sanitair | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-03-18 08:00 | 10d | 848.8 | 0 | 0 | 0 | 0 | 848.8 | 0 | 1 | Finished | 848.8 | 848.8 | C2015-06 Family Residence (2).xlsx
34 | 30 | Elektriciteit | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-11 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 1 | Finished | 346.4 | 346.4 | C2015-06 Family Residence (2).xlsx
35 | 31 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-11 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
36 | 32 | Schrijnwerk | 2013-03-11 08:00 | 2013-03-29 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 2013-05-27 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 1 | Finished | 1170 | 1170 | C2015-06 Family Residence (2).xlsx
37 | 33 | Elektriciteit | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-25 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 1 | Finished | 346.4 | 346.4 | C2015-06 Family Residence (2).xlsx
38 | 34 | Keuken | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-03-25 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 1 | Finished | 263.2 | 263.2 | C2015-06 Family Residence (2).xlsx
39 | 35 | Schrijnwerk | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-03-18 08:00 | 10d | 390.4 | 0 | 0 | 0 | 0 | 390.4 | 0 | 1 | Finished | 390.4 | 390.4 | C2015-06 Family Residence (2).xlsx
40 | 36 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-18 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 1 | Finished | 283.2 | 283.2 | C2015-06 Family Residence (2).xlsx
41 | 37 | Plakwerk | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-03-18 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 1 | Finished | 1111.2 | 1111.2 | C2015-06 Family Residence (2).xlsx
42 | 38 | Isolatie zolder | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-08 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
43 | 39 | Sanitair | 2013-03-25 08:00 | 2013-04-05 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-03-25 08:00 | 10d | 566.4 | 0 | 0 | 283.2 | 0 | 849.6 | 0 | 1 | Finished | 566.4 | 566.4 | C2015-06 Family Residence (2).xlsx
44 | 40 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
45 | 41 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 1 | Finished | 283.2 | 283.2 | C2015-06 Family Residence (2).xlsx
46 | 42 | Keuken | 2013-04-01 08:00 | 2013-04-12 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-04-01 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 1 | Finished | 526.4 | 526.4 | C2015-06 Family Residence (2).xlsx
47 | 43 | Schrijnwerk | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-04-08 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 1 | Finished | 195.2 | 195.2 | C2015-06 Family Residence (2).xlsx
48 | 44 | Plakwerken | 2013-04-08 08:00 | 2013-04-19 17:00 | 10d |  | 0 | 0 | 14.01 | 1120.8 | 1120.8 | 2013-04-15 08:00 | 10d | 1120.8 | 0 | 0 | 0 | 0 | 1120.8 | 0 | 1 | Finished | 1120.8 | 1120.8 | C2015-06 Family Residence (2).xlsx
49 | 45 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-04-08 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 1 | Finished | 566.4 | 566.4 | C2015-06 Family Residence (2).xlsx
50 | 46 | Isolatie chap/pure | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
51 | 47 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 1 | Finished | 173.2 | 173.2 | C2015-06 Family Residence (2).xlsx
52 | 48 | Vloer | 2013-04-15 08:00 | 2013-04-26 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-15 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 1 | Finished | 394.4 | 394.4 | C2015-06 Family Residence (2).xlsx
53 | 49 | Isolatie chap/pure | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
54 | 50 | Sanitair | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-04-22 08:00 | 20d | 1697.5999 | 0 | 0 | 0 | 0 | 1697.5999 | 0 | 1 | Finished | 848.8 | 848.8 | C2015-06 Family Residence (2).xlsx
55 | 51 | Spanten | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 29.61 | 2368.8 | 2368.8 | 2013-05-20 08:00 | 25d | 5922.0001 | 0 | 0 | 0 | 0 | 5922.0001 | 0 | 1 | Finished | 2368.8 | 2368.8 | C2015-06 Family Residence (2).xlsx
56 | 52 | Chape | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 2.48 | 198.4 | 198.4 | 2013-04-22 08:00 | 10d | 198.4 | 0 | 0 | 0 | 0 | 198.4 | 0 | 1 | Finished | 198.4 | 198.4 | C2015-06 Family Residence (2).xlsx
57 | 53 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-22 08:00 | 5d | 173.2 | 0 | 0 | 173.2 | 0 | 346.4 | 0 | 1 | Finished | 173.2 | 173.2 | C2015-06 Family Residence (2).xlsx
58 | 54 | Ruwbouw | 2013-04-22 08:00 | 2013-06-28 17:00 | 50d |  | 0 | 0 | 13.85 | 5540.0002 | 5540.0002 | 2013-05-13 08:00 | 75d | 8310.0002 | 0 | 0 | 0 | 0 | 8310.0002 | 0 | 1 | Finished | 5540.0002 | 5540.0002 | C2015-06 Family Residence (2).xlsx
59 | 55 | Isolatie chape/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-22 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
60 | 56 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-04-29 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 1 | Finished | 346.4 | 346.4 | C2015-06 Family Residence (2).xlsx
61 | 57 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
62 | 58 | Vloer | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-29 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 1 | Finished | 394.4 | 394.4 | C2015-06 Family Residence (2).xlsx
63 | 59 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-04-29 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 1 | Finished | 283.2 | 283.2 | C2015-06 Family Residence (2).xlsx
64 | 60 | Vloer deel 2 | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 4.93 | 591.6 | 591.6 | 2013-04-29 08:00 | 15d | 591.6 | 0 | 0 | 0 | 0 | 591.6 | 0 | 1 | Finished | 591.6 | 591.6 | C2015-06 Family Residence (2).xlsx
65 | 61 | Spanten | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-08-05 08:00 | 5d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 1 | Finished | 947.2 | 947.2 | C2015-06 Family Residence (2).xlsx
66 | 62 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
67 | 63 | Dakwerken | 2013-05-06 08:00 | 2013-05-17 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-05-27 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 1 | Finished | 473.6 | 473.6 | C2015-06 Family Residence (2).xlsx
68 | 64 | Plakwerken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-13 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 1 | Finished | 555.6 | 555.6 | C2015-06 Family Residence (2).xlsx
69 | 65 | Isolatie chap/pure | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
70 | 66 | Schrijnwerk | 2013-05-13 08:00 | 2013-06-21 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-05-13 08:00 | 30d | 1171.2 | 0 | 0 | 0 | 0 | 1171.2 | 0 | 1 | Finished | 1171.2 | 1171.2 | C2015-06 Family Residence (2).xlsx
71 | 67 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-05-06 08:00 | 10d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 1 | Finished | 346.4 | 346.4 | C2015-06 Family Residence (2).xlsx
72 | 68 | Vloer | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-05-13 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 1 | Finished | 394.4 | 394.4 | C2015-06 Family Residence (2).xlsx
73 | 69 | Dakwerken | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-06-03 08:00 | 60d | 8524.8001 | 0 | 0 | 0 | 0 | 8524.8001 | 0 | 1 | Finished | 1420.8 | 1420.8 | C2015-06 Family Residence (2).xlsx
74 | 70 | Chape | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
75 | 71 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-05-20 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 1 | Finished | 283.2 | 283.2 | C2015-06 Family Residence (2).xlsx
76 | 72 | Isolatie zolder | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-13 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
77 | 73 | Elektriciteit | 2013-05-20 08:00 | 2013-05-31 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 1 | Finished | 346.4 | 346.4 | C2015-06 Family Residence (2).xlsx
78 | 74 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-05-20 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 1 | Finished | 566.4 | 566.4 | C2015-06 Family Residence (2).xlsx
79 | 75 | Vloer | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-03 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 1 | Finished | 394.4 | 394.4 | C2015-06 Family Residence (2).xlsx
80 | 76 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 1 | Finished | 173.2 | 173.2 | C2015-06 Family Residence (2).xlsx
81 | 77 | keuken | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 1 | Finished | 526.4 | 526.4 | C2015-06 Family Residence (2).xlsx
82 | 78 | Plakwerken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-20 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 1 | Finished | 555.6 | 555.6 | C2015-06 Family Residence (2).xlsx
83 | 79 | Schrijnwerk | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-05-20 08:00 | 15d | 585.6 | 0 | 0 | 0 | 0 | 585.6 | 0 | 1 | Finished | 390.4 | 390.4 | C2015-06 Family Residence (2).xlsx
84 | 80 | Schrijnwerk deel 2 | 2013-05-27 08:00 | 2013-06-28 17:00 | 25d |  | 0 | 0 | 9.75 | 1950 | 1950 | 2013-06-10 08:00 | 15d | 1170 | 0 | 0 | 0 | 0 | 1170 | 0 | 1 | Finished | 1950 | 1950 | C2015-06 Family Residence (2).xlsx
85 | 81 | Schrijnwerk deel 3 | 2013-05-27 08:00 | 2013-06-14 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 2013-08-26 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 1 | Finished | 1170 | 1170 | C2015-06 Family Residence (2).xlsx
86 | 82 | Schrijnwerk deel 4 | 2013-05-27 08:00 | 2013-07-05 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 | 2013-08-05 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 1 | Finished | 2340 | 2340 | C2015-06 Family Residence (2).xlsx
87 | 83 | Isolatie chap/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-03 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
88 | 84 | Schrijnwerk | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-05-20 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 1 | Finished | 195.2 | 195.2 | C2015-06 Family Residence (2).xlsx
89 | 85 | Sanitair | 2013-06-03 08:00 | 2013-06-14 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-05-20 08:00 | 20d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 1 | Finished | 566.4 | 566.4 | C2015-06 Family Residence (2).xlsx
90 | 86 | Ruwbouw | 2013-06-03 08:00 | 2013-08-23 17:00 | 60d |  | 0 | 0 | 13.86 | 6652.7998 | 6652.7998 | 2013-08-05 08:00 | 80d | 8870.3998 | 0 | 0 | 0 | 0 | 8870.3998 | 0 | 1 | Finished | 6652.7998 | 6652.7998 | C2015-06 Family Residence (2).xlsx
91 | 87 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-10 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
92 | 88 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-17 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 1 | Finished | 173.2 | 173.2 | C2015-06 Family Residence (2).xlsx
93 | 89 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 21.24 | 849.6 | 849.6 | 2013-06-10 08:00 | 5d | 849.6 | 0 | 0 | 0 | 0 | 849.6 | 0 | 1 | Finished | 849.6 | 849.6 | C2015-06 Family Residence (2).xlsx
94 | 90 | Keuken | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 25d | 1316 | 0 | 0 | 0 | 0 | 1316 | 0 | 1 | Finished | 526.4 | 526.4 | C2015-06 Family Residence (2).xlsx
95 | 91 | Vloer | 2013-06-17 08:00 | 2013-06-28 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-17 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 1 | Finished | 394.4 | 394.4 | C2015-06 Family Residence (2).xlsx
96 | 92 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-06-24 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 1 | Finished | 195.2 | 195.2 | C2015-06 Family Residence (2).xlsx
97 | 93 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 1 | Finished | 263.2 | 263.2 | C2015-06 Family Residence (2).xlsx
98 | 94 | Isolatie chap/pure | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-17 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
99 | 95 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-08-26 08:00 | 5d | 173.2 | 0 | 0 | -86.6 | 0 | 86.6 | 0 | 1 | Finished | 173.2 | 173.2 | C2015-06 Family Residence (2).xlsx
100 | 96 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-07-01 08:00 | 5d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 1 | Finished | 566.4 | 566.4 | C2015-06 Family Residence (2).xlsx
101 | 97 | Chape | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-24 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
102 | 98 | Elektriciteit | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 17.32 | 692.8 | 692.8 | 2013-07-08 08:00 | 5d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 1 | Finished | 692.8 | 692.8 | C2015-06 Family Residence (2).xlsx
103 | 99 | Keuken | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-07-01 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 1 | Finished | 263.2 | 263.2 | C2015-06 Family Residence (2).xlsx
104 | 100 | Vloer | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-07-29 08:00 | 5d | 197.2 | 0 | 0 | 0 | 0 | 197.2 | 0 | 1 | Finished | 394.4 | 394.4 | C2015-06 Family Residence (2).xlsx
105 | 101 | Spanten | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-06-24 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 1 | Finished | 947.2 | 947.2 | C2015-06 Family Residence (2).xlsx
106 | 102 | Ruwbouw | 2013-07-01 08:00 | 2013-10-04 17:00 | 70d |  | 0 | 0 | 23.68 | 13260.8002 | 13260.8002 | 2013-08-05 08:00 | 40d | 7577.6001 | 0 | 0 | 0 | 0 | 7577.6001 | 0 | 1 | Finished | 13260.8002 | 13260.8002 | C2015-06 Family Residence (2).xlsx
107 | 103 | Schrijnwerk | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-08-05 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 1 | Finished | 195.2 | 195.2 | C2015-06 Family Residence (2).xlsx
108 | 104 | Sanitair | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-07-08 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 1 | Finished | 283.2 | 283.2 | C2015-06 Family Residence (2).xlsx
109 | 105 | Isolatie zolder | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-16 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
110 | 106 | Elektriciteit | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-08-12 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 1 | Finished | 346.4 | 346.4 | C2015-06 Family Residence (2).xlsx
111 | 107 | Elektriciteit | 2013-07-15 08:00 | 2013-07-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-24 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 1 | Finished | 173.2 | 173.2 | C2015-06 Family Residence (2).xlsx
112 | 108 | Sanitair | 2013-07-22 08:00 | 2013-07-26 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-07-08 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 1 | Finished | 283.2 | 283.2 | C2015-06 Family Residence (2).xlsx
113 | 109 | Elektriciteit | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-07-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 1 | Finished | 173.2 | 173.2 | C2015-06 Family Residence (2).xlsx
114 | 110 | Sanitair | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 14.15 | 1132 | 1132 | 2013-08-05 08:00 | 50d | 5659.9998 | 0 | 0 | 0 | 0 | 5659.9998 | 0 | 1 | Finished | 1132 | 1132 | C2015-06 Family Residence (2).xlsx
115 | 111 | Isolatie zolder | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-08-05 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
116 | 112 | Elektriciteit | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-08-05 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 1 | Finished | 346.4 | 346.4 | C2015-06 Family Residence (2).xlsx
117 | 113 | Dakconstructie | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 27.71 | 2216.7999 | 2216.7999 | 2013-08-05 08:00 | 10d | 2216.7999 | 0 | 0 | 0 | 0 | 2216.7999 | 0 | 1 | Finished | 2216.7999 | 2216.7999 | C2015-06 Family Residence (2).xlsx
118 | 114 | Plakwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-10-07 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 1 | Finished | 555.6 | 555.6 | C2015-06 Family Residence (2).xlsx
119 | 115 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-08-19 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 1 | Finished | 263.2 | 263.2 | C2015-06 Family Residence (2).xlsx
120 | 116 | Plakwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-08-12 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 1 | Finished | 555.6 | 555.6 | C2015-06 Family Residence (2).xlsx
121 | 117 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-08-12 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 1 | Finished | 195.2 | 195.2 | C2015-06 Family Residence (2).xlsx
122 | 118 | Isolatie zolder | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-08-12 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 1 | Finished | 132 | 132 | C2015-06 Family Residence (2).xlsx
123 | 119 | Elektriciteit | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-08-12 08:00 | 20d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 1 | Finished | 346.4 | 346.4 | C2015-06 Family Residence (2).xlsx
124 | 120 | Sanitair | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-08-19 08:00 | 5d | 566 | 0 | 0 | 0 | 0 | 566 | 0 | 1 | Finished | 566 | 566 | C2015-06 Family Residence (2).xlsx
125 | 121 | Schrijnwerk | 2013-08-19 08:00 | 2013-09-13 17:00 | 20d |  | 0 | 0 | 4.88 | 780.8 | 780.8 | 2013-08-19 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 1 | Finished | 780.8 | 780.8 | C2015-06 Family Residence (2).xlsx
126 | 122 | Plakwerk | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 | 2013-08-19 08:00 | 10d | 1110.4 | 0 | 0 | 0 | 0 | 1110.4 | 0 | 1 | Finished | 1110.4 | 1110.4 | C2015-06 Family Residence (2).xlsx
127 | 123 | Schrijnwerk deel 2 | 2013-08-19 08:00 | 2013-09-27 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-10-14 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 1 | Finished | 1171.2 | 1171.2 | C2015-06 Family Residence (2).xlsx
128 | 124 | Isolatie zolder | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-02 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 1 | Finished | 132 | 132 | C2015-06 Family Residence (2).xlsx
129 | 125 | Sanitair | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-08-26 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 1 | Finished | 283.2 | 283.2 | C2015-06 Family Residence (2).xlsx
130 | 126 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-08-26 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 1 | Finished | 263.2 | 263.2 | C2015-06 Family Residence (2).xlsx
131 | 127 | Isolatie chap/pure | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-16 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
132 | 128 | Spanten | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-11-25 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 1 | Finished | 473.6 | 473.6 | C2015-06 Family Residence (2).xlsx
133 | 129 | Isolatie chap/pure | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-02 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
134 | 130 | Sanitair | 2013-09-02 08:00 | 2013-09-13 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-09-02 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 1 | Finished | 566.4 | 566.4 | C2015-06 Family Residence (2).xlsx
135 | 131 | Chape | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-11-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
136 | 132 | Plakwerk | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 | 2013-09-09 08:00 | 10d | 1110.4 | 0 | 0 | 0 | 0 | 1110.4 | 0 | 1 | Finished | 1110.4 | 1110.4 | C2015-06 Family Residence (2).xlsx
137 | 133 | Chape | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-09 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
138 | 134 | Isolatie chap/pure | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-09 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 1 | Finished | 132 | 132 | C2015-06 Family Residence (2).xlsx
139 | 135 | Vloer | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-11-11 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 1 | Finished | 394.4 | 394.4 | C2015-06 Family Residence (2).xlsx
140 | 136 | Dakwerken | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-12-09 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 1 | Finished | 473.6 | 473.6 | C2015-06 Family Residence (2).xlsx
141 | 137 | Sanitair | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-09-23 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 1 | Finished | 566.4 | 566.4 | C2015-06 Family Residence (2).xlsx
142 | 138 | Vloer | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-09-16 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 1 | Finished | 394.4 | 394.4 | C2015-06 Family Residence (2).xlsx
143 | 139 | Elektriciteit | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-09-16 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 1 | Finished | 173.2 | 173.2 | C2015-06 Family Residence (2).xlsx
144 | 140 | Chape | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-16 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 1 | Finished | 132 | 132 | C2015-06 Family Residence (2).xlsx
145 | 141 | Isolatie chap/pure | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-10-14 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 132 | 132 | C2015-06 Family Residence (2).xlsx
146 | 142 | Sanitair | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-09-23 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 1 | Finished | 283.2 | 283.2 | C2015-06 Family Residence (2).xlsx
147 | 143 | Vloer | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-09-23 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 1 | Finished | 394.4 | 394.4 | C2015-06 Family Residence (2).xlsx
148 | 144 | Elektriciteit | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-11-25 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 1 | Finished | 173.2 | 173.2 | C2015-06 Family Residence (2).xlsx
149 | 145 | Schrijnwerk | 2013-09-23 08:00 | 2013-10-25 17:00 | 25d |  | 0 | 0 | 4.88 | 976 | 976 | 2014-01-06 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 1 | Finished | 976 | 976 | C2015-06 Family Residence (2).xlsx
150 | 146 | Chape | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-10-21 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 132 | 132 | C2015-06 Family Residence (2).xlsx
151 | 147 | Elektriciteit | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 12.98 | 519.2 | 519.2 | 2013-10-14 08:00 | 25d | 2595.9999 | 0 | 0 | 0 | 0 | 2595.9999 | 0 | 1 | Finished | 519.2 | 519.2 | C2015-06 Family Residence (2).xlsx
152 | 148 | Vloer | 2013-09-30 08:00 | 2013-10-11 17:00 | 10d |  | 0 | 0 | 9.86 | 788.8 | 788.8 | 2013-09-30 08:00 | 20d | 1577.5999 | 0 | 0 | 0 | 0 | 1577.5999 | 0 | 1 | Finished | 788.8 | 788.8 | C2015-06 Family Residence (2).xlsx
153 | 149 | Schrijnwerk | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-12-02 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 1 | Finished | 195.2 | 195.2 | C2015-06 Family Residence (2).xlsx
154 | 150 | Isolatie zolder | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-10-07 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
155 | 151 | Elektriciteit | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-10-07 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 1 | Finished | 346.4 | 346.4 | C2015-06 Family Residence (2).xlsx
156 | 152 | Sanitair | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-10-21 08:00 | 10d | 1132 | 0 | 0 | 0 | 0 | 1132 | 0 | 1 | Finished | 566 | 566 | C2015-06 Family Residence (2).xlsx
157 | 153 | Vloer | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-11-04 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 1 | Finished | 394.4 | 394.4 | C2015-06 Family Residence (2).xlsx
158 | 154 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-10-28 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 1 | Finished | 195.2 | 195.2 | C2015-06 Family Residence (2).xlsx
159 | 155 | Plakwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-10-21 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 1 | Finished | 555.6 | 555.6 | C2015-06 Family Residence (2).xlsx
160 | 156 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-10-21 08:00 | 10d | 390.4 | 0 | 0 | 0 | 0 | 390.4 | 0 | 1 | Finished | 390.4 | 390.4 | C2015-06 Family Residence (2).xlsx
161 | 157 | Elektriciteit | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 6.49 | 519.2 | 519.2 | 2013-10-21 08:00 | 20d | 1038.4 | 0 | 0 | 0 | 0 | 1038.4 | 0 | 1 | Finished | 519.2 | 519.2 | C2015-06 Family Residence (2).xlsx
162 | 158 | Keuken | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-12-16 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 1 | Finished | 263.2 | 263.2 | C2015-06 Family Residence (2).xlsx
163 | 159 | Sanitair | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-10-21 08:00 | 15d | 1698 | 0 | 0 | 0 | 0 | 1698 | 0 | 1 | Finished | 566 | 566 | C2015-06 Family Residence (2).xlsx
164 | 160 | Schrijnwerk | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 2013-11-11 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 1 | Finished | 390 | 390 | C2015-06 Family Residence (2).xlsx
165 | 161 | Isolatie zolder | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-12-02 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
166 | 162 | Keuken | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-11-11 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 1 | Finished | 263.2 | 263.2 | C2015-06 Family Residence (2).xlsx
167 | 163 | Sanitair | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-11-04 08:00 | 5d | 566 | 0 | 0 | 0 | 0 | 566 | 0 | 1 | Finished | 566 | 566 | C2015-06 Family Residence (2).xlsx
168 | 164 | Keuken | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-11-04 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 1 | Finished | 526.4 | 526.4 | C2015-06 Family Residence (2).xlsx
169 | 165 | Sanitair deel 2 | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-11-25 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 1 | Finished | 566.4 | 566.4 | C2015-06 Family Residence (2).xlsx
170 | 166 | Spanten | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-10-14 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 1 | Finished | 947.2 | 947.2 | C2015-06 Family Residence (2).xlsx
171 | 167 | Isolatie chap/pure | 2013-11-11 08:00 | 2013-11-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-11-11 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
172 | 168 | Keuken | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-12-02 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 1 | Finished | 526.4 | 526.4 | C2015-06 Family Residence (2).xlsx
173 | 169 | Chape | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-11-18 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
174 | 170 | Sanitair | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-11-18 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 1 | Finished | 283.2 | 283.2 | C2015-06 Family Residence (2).xlsx
175 | 171 | Dakwerken | 2013-11-18 08:00 | 2013-11-29 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-10-14 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 1 | Finished | 947.2 | 947.2 | C2015-06 Family Residence (2).xlsx
176 | 172 | Vloer | 2013-11-25 08:00 | 2013-12-06 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-11-25 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 1 | Finished | 394.4 | 394.4 | C2015-06 Family Residence (2).xlsx
177 | 173 | Isolatie chap/pure | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2014-01-13 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
178 | 174 | Chape | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2014-01-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 1 | Finished | 66 | 66 | C2015-06 Family Residence (2).xlsx
179 | 175 | Schrijnwerk | 2013-12-02 08:00 | 2014-01-10 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 | 2013-11-04 08:00 | 35d | 2730 | 0 | 0 | 0 | 0 | 2730 | 0 | 1 | Finished | 2340 | 2340 | C2015-06 Family Residence (2).xlsx
180 | 176 | Elektriciteit | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-12-09 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 1 | Finished | 173.2 | 173.2 | C2015-06 Family Residence (2).xlsx
181 | 177 | Vloer | 2013-12-09 08:00 | 2013-12-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2014-01-27 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 1 | Finished | 394.4 | 394.4 | C2015-06 Family Residence (2).xlsx
182 | 178 | Schrijnwerk | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-12-16 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 1 | Finished | 195.2 | 195.2 | C2015-06 Family Residence (2).xlsx
183 | 179 | Sanitair | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-12-23 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 1 | Finished | 283.2 | 283.2 | C2015-06 Family Residence (2).xlsx
184 | 180 | Elektriciteit | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2014-02-10 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 1 | Finished | 173.2 | 173.2 | C2015-06 Family Residence (2).xlsx
185 | 181 | Keuken | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2014-01-13 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 1 | Finished | 263.2 | 263.2 | C2015-06 Family Residence (2).xlsx
186 | 182 | Schrijnwerk | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2014-02-17 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 1 | Finished | 195.2 | 195.2 | C2015-06 Family Residence (2).xlsx
187 | 183 | Sanitair | 2014-01-13 08:00 | 2014-01-17 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2014-02-24 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 1 | Finished | 283.2 | 283.2 | C2015-06 Family Residence (2).xlsx
188 | 184 | Keuken | 2014-01-20 08:00 | 2014-01-24 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2014-03-03 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 1 | Finished | 263.2 | 263.2 | C2015-06 Family Residence (2).xlsx
4 | 0 | Industrial Complex (2) | 2013-02-18 08:00 | 2014-04-08 17:00 | 297d |  |  | 0 |  |  | 5999600 |  | 313d | [5 empty] | 5414544 |  | 1 |  | 5999600 | 5999600 | C2015-07 Industrial Complex (2).xlsx
5 | 6 | Voobereindende werken | 2013-02-18 08:00 | 2013-03-25 17:00 | 26d |  |  | 0 |  |  | 89984 |  | 5d | [5 empty] | 89984 |  | 1 |  | 89984 | 89984 | C2015-07 Industrial Complex (2).xlsx
6 | 1 | plaatsen werfhekkens | 2013-02-18 08:00 | 2013-02-18 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 1 | Finished | 11248 | 11248 | C2015-07 Industrial Complex (2).xlsx
7 | 2 | Afbraakwerken | 2013-02-18 08:00 | 2013-02-21 17:00 | 4d |  | 0 | 0 | 1406 | 44992 | 44992 | 2013-02-18 08:00 | 4d | 44992 | 0 | 0 | 0 | 0 | 44992 | 0 | 1 | Finished | 44992 | 44992 | C2015-07 Industrial Complex (2).xlsx
8 | 3 | Werfinrichting | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 1 | Finished | 11248 | 11248 | C2015-07 Industrial Complex (2).xlsx
9 | 4 | uitzetten assen | 2013-02-21 08:00 | 2013-02-21 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-22 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 1 | Finished | 11248 | 11248 | C2015-07 Industrial Complex (2).xlsx
10 | 5 | Fundering torenkraan | 2013-03-25 08:00 | 2013-03-25 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-21 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 1 | Finished | 11248 | 11248 | C2015-07 Industrial Complex (2).xlsx
11 | 13 | Riolering + Parkings | 2013-02-22 08:00 | 2013-03-19 17:00 | 18d |  |  | 0 |  |  | 130000 |  | 18d | [5 empty] | 130000 |  | 1 |  | 130000 | 130000 | C2015-07 Industrial Complex (2).xlsx
12 | 7 | droogzuiging | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 625 | 5000 | 5000 | 2013-02-22 08:00 | 1d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | Finished | 5000 | 5000 | C2015-07 Industrial Complex (2).xlsx
13 | 8 | Rechterdeel parking aanvullen + onderfundering | 2013-02-22 08:00 | 2013-02-28 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-02-22 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 1 | Finished | 25000 | 25000 | C2015-07 Industrial Complex (2).xlsx
14 | 9 | Plaatsing RW-putten + riolering | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 625 | 50000 | 50000 | 2013-03-04 08:00 | 10d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 1 | Finished | 50000 | 50000 | C2015-07 Industrial Complex (2).xlsx
15 | 10 | Linkerdeel parking aanvullen + onderfundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-03-11 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 1 | Finished | 25000 | 25000 | C2015-07 Industrial Complex (2).xlsx
16 | 11 | Overige parkeerplaatsen aanvullen + onderfundering | 2013-03-13 08:00 | 2013-03-15 17:00 | 3d |  | 0 | 0 | 625 | 15000 | 15000 | 2013-03-13 08:00 | 3d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 1 | Finished | 15000 | 15000 | C2015-07 Industrial Complex (2).xlsx
17 | 12 | Uitbraak bestaande parking | 2013-03-18 08:00 | 2013-03-19 17:00 | 2d |  | 0 | 0 | 625 | 10000 | 10000 | 2013-03-18 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2015-07 Industrial Complex (2).xlsx
18 | 39 | Productiehal | 2013-03-13 08:00 | 2013-09-23 17:00 | 139d |  |  | 0 |  |  | 1311416 |  | 136d | [5 empty] | 1311416 |  | 1 |  | 1311416 | 1311416 | C2015-07 Industrial Complex (2).xlsx
19 | 14 | Funderingswerken productiehal | 2013-03-18 08:00 | 2013-04-05 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-03-18 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 1 | Finished | 67560 | 67560 | C2015-07 Industrial Complex (2).xlsx
20 | 26 | Ruwbouwwerken + onder dak productiehal | 2013-04-09 08:00 | 2013-06-28 17:00 | 59d |  |  | 0 |  |  | 504000 |  | 60d | [5 empty] | 504000 |  | 1 |  | 504000 | 504000 | C2015-07 Industrial Complex (2).xlsx
21 | 15 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-04-15 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 600 | 120000 | 120000 | 2013-04-15 08:00 | 25d | 120000 | 0 | 0 | 0 | 0 | 120000 | 0 | 1 | Finished | 120000 | 120000 | C2015-07 Industrial Complex (2).xlsx
22 | 16 | Metselwerken technische lokalen + montage welfsels | 2013-05-13 08:00 | 2013-05-22 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-05-13 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 1 | Finished | 38400 | 38400 | C2015-07 Industrial Complex (2).xlsx
23 | 17 | uitbraak bestaande gevelelementen + schoring | 2013-04-09 08:00 | 2013-04-15 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-04-08 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 1 | Finished | 24000 | 24000 | C2015-07 Industrial Complex (2).xlsx
24 | 18 | staalconstructie rolbrug en spuitcabine | 2013-05-22 08:00 | 2013-05-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-22 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 1 | Finished | 24000 | 24000 | C2015-07 Industrial Complex (2).xlsx
25 | 19 | Onderfunderingen betonvloer + rioleringswerken + vloerisolatie rondom | 2013-05-27 08:00 | 2013-06-11 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-05-27 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 1 | Finished | 57600 | 57600 | C2015-07 Industrial Complex (2).xlsx
26 | 20 | Veiligheidsnetten + steeldeck | 2013-05-29 08:00 | 2013-06-14 17:00 | 13d |  | 0 | 0 | 600 | 62400 | 62400 | 2013-05-29 08:00 | 13d | 62400 | 0 | 0 | 0 | 0 | 62400 | 0 | 1 | Finished | 62400 | 62400 | C2015-07 Industrial Complex (2).xlsx
27 | 21 | Isolatie + dakbedekking + RWA | 2013-06-06 08:00 | 2013-06-26 17:00 | 15d |  | 0 | 0 | 600 | 72000 | 72000 | 2013-06-06 08:00 | 15d | 72000 | 0 | 0 | 0 | 0 | 72000 | 0 | 1 | Finished | 72000 | 72000 | C2015-07 Industrial Complex (2).xlsx
28 | 22 | Rookkoepels | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-26 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 1 | Finished | 9600 | 9600 | C2015-07 Industrial Complex (2).xlsx
29 | 23 | Netwapening + polybetonvloer | 2013-06-05 08:00 | 2013-06-18 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-06-05 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 1 | Finished | 48000 | 48000 | C2015-07 Industrial Complex (2).xlsx
30 | 24 | Metselwerken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 1 | Finished | 24000 | 24000 | C2015-07 Industrial Complex (2).xlsx
31 | 25 | Brandwerende schildering | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 1 | Finished | 24000 | 24000 | C2015-07 Industrial Complex (2).xlsx
32 | 29 | Binnenafwerking productiehal | 2013-09-18 08:00 | 2013-09-23 17:00 | 4d |  |  | 0 |  |  | 15616 |  | 8d | [5 empty] | 15616 |  | 1 |  | 15616 | 15616 | C2015-07 Industrial Complex (2).xlsx
33 | 27 | Stalen binnentrap | 2013-09-19 08:00 | 2013-09-23 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2013-09-09 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 1 | Finished | 11712 | 11712 | C2015-07 Industrial Complex (2).xlsx
34 | 28 | Binnendeuren | 2013-09-18 08:00 | 2013-09-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2013-09-18 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 1 | Finished | 3904 | 3904 | C2015-07 Industrial Complex (2).xlsx
35 | 33 | Gevelbekleding productiehal | 2013-06-19 08:00 | 2013-09-12 17:00 | 62d |  |  | 0 |  |  | 92928 |  | 62d | [5 empty] | 92928 |  | 1 |  | 92928 | 92928 | C2015-07 Industrial Complex (2).xlsx
36 | 30 | Alu buitenschrijnwerk + beglazing + polycarbonaatplaten | 2013-06-19 08:00 | 2013-07-02 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2013-06-19 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 1 | Finished | 38720 | 38720 | C2015-07 Industrial Complex (2).xlsx
37 | 31 | Montage poorten | 2013-08-26 08:00 | 2013-08-29 17:00 | 4d |  | 0 | 0 | 484 | 15488 | 15488 | 2013-08-26 08:00 | 4d | 15488 | 0 | 0 | 0 | 0 | 15488 | 0 | 1 | Finished | 15488 | 15488 | C2015-07 Industrial Complex (2).xlsx
38 | 32 | Gevelbekleding metaalcassettes | 2013-08-30 08:00 | 2013-09-12 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2013-08-30 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 1 | Finished | 38720 | 38720 | C2015-07 Industrial Complex (2).xlsx
39 | 38 | Technieken productiehal | 2013-03-13 08:00 | 2013-09-05 17:00 | 127d |  |  | 0 |  |  | 631312 |  | 127d | [5 empty] | 631312 |  | 1 |  | 631312 | 631312 | C2015-07 Industrial Complex (2).xlsx
40 | 34 | Afbraakwerken | 2013-03-13 08:00 | 2013-03-14 17:00 | 2d |  | 0 | 0 | 469 | 7504 | 7504 | 2013-03-13 08:00 | 2d | 7504 | 0 | 0 | 0 | 0 | 7504 | 0 | 1 | Finished | 7504 | 7504 | C2015-07 Industrial Complex (2).xlsx
41 | 35 | HVAC | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 720 | 311040 | 311040 | 2013-06-24 08:00 | 54d | 311040 | 0 | 0 | 0 | 0 | 311040 | 0 | 1 | Finished | 311040 | 311040 | C2015-07 Industrial Complex (2).xlsx
42 | 36 | Sanitair | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 129 | 55728 | 55728 | 2013-06-24 08:00 | 54d | 55728 | 0 | 0 | 0 | 0 | 55728 | 0 | 1 | Finished | 55728 | 55728 | C2015-07 Industrial Complex (2).xlsx
43 | 37 | Elecktriciteit | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 595 | 257040 | 257040 | 2013-06-24 08:00 | 54d | 257040 | 0 | 0 | 0 | 0 | 257040 | 0 | 1 | Finished | 257040 | 257040 | C2015-07 Industrial Complex (2).xlsx
44 | 60 | Stockruimte | 2013-05-02 08:00 | 2013-11-12 17:00 | 139d |  |  | 0 |  |  | 800216 |  | 142d | [5 empty] | 835152 |  | 1 |  | 800216 | 800216 | C2015-07 Industrial Complex (2).xlsx
45 | 40 | Afbraak | 2013-05-02 08:00 | 2013-05-08 17:00 | 5d |  | 0 | 0 | 1406 | 56240 | 56240 | 2013-03-18 08:00 | 19d | 213712 | 0 | 0 | 0 | 0 | 213712 | 0 | 1 | Finished | 56240 | 56240 | C2015-07 Industrial Complex (2).xlsx
46 | 41 | Funderingswerken stockruimte | 2013-05-13 08:00 | 2013-05-20 17:00 | 6d |  | 0 | 0 | 563 | 27024 | 27024 | 2013-04-29 08:00 | 8d | 36032 | 0 | 0 | 0 | 0 | 36032 | 0 | 1 | Finished | 27024 | 27024 | C2015-07 Industrial Complex (2).xlsx
47 | 51 | Ruwbouwwerken + onder dak stockruimte | 2013-05-22 08:00 | 2013-08-15 17:00 | 62d |  |  | 0 |  |  | 196800 |  | 62d | [5 empty] | 196800 |  | 1 |  | 196800 | 196800 | C2015-07 Industrial Complex (2).xlsx
48 | 42 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-05-24 08:00 | 2013-06-05 17:00 | 9d |  | 0 | 0 | 600 | 43200 | 43200 | 2013-05-24 08:00 | 9d | 43200 | 0 | 0 | 0 | 0 | 43200 | 0 | 1 | Finished | 43200 | 43200 | C2015-07 Industrial Complex (2).xlsx
49 | 43 | Uitbraak bestaande gevelelementen | 2013-05-22 08:00 | 2013-05-22 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-05-22 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 1 | Finished | 4800 | 4800 | C2015-07 Industrial Complex (2).xlsx
50 | 44 | Nivelleren + rioleringswerken | 2013-06-06 08:00 | 2013-06-06 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-06 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 1 | Finished | 4800 | 4800 | C2015-07 Industrial Complex (2).xlsx
51 | 45 | Onderfundering betonvloer + vloerisolatie rondom | 2013-06-06 08:00 | 2013-06-13 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 | 2013-06-06 08:00 | 6d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 1 | Finished | 28800 | 28800 | C2015-07 Industrial Complex (2).xlsx
52 | 46 | Veiligheidsnetten + steeldeck | 2013-06-14 08:00 | 2013-06-20 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-14 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 1 | Finished | 24000 | 24000 | C2015-07 Industrial Complex (2).xlsx
53 | 47 | Paaltjes leeflijn | 2013-06-21 08:00 | 2013-06-21 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-21 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 1 | Finished | 4800 | 4800 | C2015-07 Industrial Complex (2).xlsx
54 | 48 | Isolatie + dakbedeking + RWA | 2013-06-24 08:00 | 2013-07-03 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-24 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 1 | Finished | 38400 | 38400 | C2015-07 Industrial Complex (2).xlsx
55 | 49 | Netbewapening + polybetonvloer | 2013-07-04 08:00 | 2013-07-12 17:00 | 7d |  | 0 | 0 | 600 | 33600 | 33600 | 2013-07-04 08:00 | 7d | 33600 | 0 | 0 | 0 | 0 | 33600 | 0 | 1 | Finished | 33600 | 33600 | C2015-07 Industrial Complex (2).xlsx
56 | 50 | Brandwerende schildering | 2013-08-13 08:00 | 2013-08-15 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2013-08-13 08:00 | 3d | 14400 | 0 | 0 | 0 | 0 | 14400 | 0 | 1 | Finished | 14400 | 14400 | C2015-07 Industrial Complex (2).xlsx
57 | 54 | Gevelbekledingen stockruimte | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  |  | 0 |  |  | 15488 |  | 3d | [5 empty] | 15488 |  | 1 |  | 15488 | 15488 | C2015-07 Industrial Complex (2).xlsx
58 | 52 | Alu buitenschrijnwerk + beglazing | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-09-19 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 1 | Finished | 3872 | 3872 | C2015-07 Industrial Complex (2).xlsx
59 | 53 | Montage poorten | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  | 0 | 0 | 484 | 11616 | 11616 | 2013-09-18 08:00 | 3d | 11616 | 0 | 0 | 0 | 0 | 11616 | 0 | 1 | Finished | 11616 | 11616 | C2015-07 Industrial Complex (2).xlsx
60 | 59 | technieken stockruimte | 2013-05-08 08:00 | 2013-11-12 17:00 | 135d |  |  | 0 |  |  | 504664 |  | 136d | [5 empty] | 373120 |  | 1 |  | 504664 | 504664 | C2015-07 Industrial Complex (2).xlsx
61 | 55 | Afbraakwerken | 2013-05-08 08:00 | 2013-05-08 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-03-26 08:00 | 4d | 15008 | 0 | 0 | 0 | 0 | 15008 | 0 | 1 | Finished | 3752 | 3752 | C2015-07 Industrial Complex (2).xlsx
62 | 56 | HVAC | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 720 | 178560 | 178560 | 2013-08-20 08:00 | 31d | 178560 | 0 | 0 | 0 | 0 | 178560 | 0 | 1 | Finished | 178560 | 178560 | C2015-07 Industrial Complex (2).xlsx
63 | 57 | Sanitair | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 129 | 31992 | 31992 | 2013-08-20 08:00 | 31d | 31992 | 0 | 0 | 0 | 0 | 31992 | 0 | 1 | Finished | 31992 | 31992 | C2015-07 Industrial Complex (2).xlsx
64 | 58 | Elektriciteit | 2013-08-20 08:00 | 2013-11-12 17:00 | 61d |  | 0 | 0 | 595 | 290360 | 290360 | 2013-08-20 08:00 | 31d | 147560 | 0 | 0 | 0 | 0 | 147560 | 0 | 1 | Finished | 290360 | 290360 | C2015-07 Industrial Complex (2).xlsx
65 | 79 | Straalcabine | 2013-05-22 08:00 | 2013-09-05 17:00 | 77d |  |  | 0 |  |  | 710216 |  | 83d | [5 empty] | 714720 |  | 1 |  | 710216 | 710216 | C2015-07 Industrial Complex (2).xlsx
66 | 61 | Funderingswerken | 2013-05-22 08:00 | 2013-05-27 17:00 | 4d |  | 0 | 0 | 563 | 18016 | 18016 | 2013-05-14 08:00 | 5d | 22520 | 0 | 0 | 0 | 0 | 22520 | 0 | 1 | Finished | 18016 | 18016 | C2015-07 Industrial Complex (2).xlsx
67 | 67 | Ruwbouwwerken + straalcabine | 2013-05-28 08:00 | 2013-06-28 17:00 | 24d |  |  | 0 |  |  | 48000 |  | 28d | [5 empty] | 48000 |  | 1 |  | 48000 | 48000 | C2015-07 Industrial Complex (2).xlsx
68 | 62 | Uitbraak bestaande gevelelementen + onderfundering + riolering + vloerisolatie rondom | 2013-05-28 08:00 | 2013-05-29 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-05-22 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 1 | Finished | 9600 | 9600 | C2015-07 Industrial Complex (2).xlsx
69 | 63 | Kolommen + balken + betonwanden + staalconstructie | 2013-06-06 08:00 | 2013-06-11 17:00 | 4d |  | 0 | 0 | 600 | 19200 | 19200 | 2013-06-06 08:00 | 4d | 19200 | 0 | 0 | 0 | 0 | 19200 | 0 | 1 | Finished | 19200 | 19200 | C2015-07 Industrial Complex (2).xlsx
70 | 64 | Welfsels + opstort | 2013-06-12 08:00 | 2013-06-12 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-12 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 1 | Finished | 4800 | 4800 | C2015-07 Industrial Complex (2).xlsx
71 | 65 | Netwapening + polybetonvloer | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-19 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 1 | Finished | 9600 | 9600 | C2015-07 Industrial Complex (2).xlsx
72 | 66 | Brandwerende schildering | 2013-06-28 08:00 | 2013-06-28 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-28 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 1 | Finished | 4800 | 4800 | C2015-07 Industrial Complex (2).xlsx
73 | 70 | Gevelbekledingen straalcabine | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  |  | 0 |  |  | 7744 |  | 1d | [5 empty] | 7744 |  | 1 |  | 7744 | 7744 | C2015-07 Industrial Complex (2).xlsx
74 | 68 | Alu buitenschrijnwerk + beglazing | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-08-28 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 1 | Finished | 3872 | 3872 | C2015-07 Industrial Complex (2).xlsx
75 | 69 | Montage poorten | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-08-28 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 1 | Finished | 3872 | 3872 | C2015-07 Industrial Complex (2).xlsx
76 | 73 | Dakwerken | 2013-06-13 08:00 | 2013-06-18 17:00 | 4d |  |  | 0 |  |  | 66656 |  | 4d | [5 empty] | 66656 |  | 1 |  | 66656 | 66656 | C2015-07 Industrial Complex (2).xlsx
77 | 72 | Isolatie + roofing | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 2083 | 49992 | 49992 | 2013-06-14 08:00 | 3d | 49992 | 0 | 0 | 0 | 0 | 49992 | 0 | 1 | Finished | 49992 | 49992 | C2015-07 Industrial Complex (2).xlsx
78 | 71 | paaltjes leeflijn | 2013-06-13 08:00 | 2013-06-13 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 | 2013-06-13 08:00 | 1d | 16664 | 0 | 0 | 0 | 0 | 16664 | 0 | 1 | Finished | 16664 | 16664 | C2015-07 Industrial Complex (2).xlsx
79 | 78 | Technieken straalcabine | 2013-05-27 08:00 | 2013-09-05 17:00 | 74d |  |  | 0 |  |  | 569800 |  | 78d | [5 empty] | 569800 |  | 1 |  | 569800 | 569800 | C2015-07 Industrial Complex (2).xlsx
80 | 77 | Elektriciteit | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 595 | 233240 | 233240 | 2013-07-01 08:00 | 49d | 233240 | 0 | 0 | 0 | 0 | 233240 | 0 | 1 | Finished | 233240 | 233240 | C2015-07 Industrial Complex (2).xlsx
81 | 74 | Afbraakwerken | 2013-05-27 08:00 | 2013-05-27 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-05-21 08:00 | 1d | 3752 | 0 | 0 | 0 | 0 | 3752 | 0 | 1 | Finished | 3752 | 3752 | C2015-07 Industrial Complex (2).xlsx
82 | 75 | HVAC | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 720 | 282240 | 282240 | 2013-07-01 08:00 | 49d | 282240 | 0 | 0 | 0 | 0 | 282240 | 0 | 1 | Finished | 282240 | 282240 | C2015-07 Industrial Complex (2).xlsx
83 | 76 | Sanitair | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 129 | 50568 | 50568 | 2013-07-01 08:00 | 49d | 50568 | 0 | 0 | 0 | 0 | 50568 | 0 | 1 | Finished | 50568 | 50568 | C2015-07 Industrial Complex (2).xlsx
84 | 80 | Opkuis | 2013-09-23 08:00 | 2013-10-01 17:00 | 7d |  | 0 | 0 | 25 | 1400 | 1400 | 2013-09-23 08:00 | 7d | 1400 | 0 | 0 | 0 | 0 | 1400 | 0 | 1 | Finished | 1400 | 1400 | C2015-07 Industrial Complex (2).xlsx
85 | 83 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-14 17:00 | 18d |  |  | 0 |  |  | 107560 |  | 15d | [5 empty] | 107560 |  | 1 |  | 107560 | 107560 | C2015-07 Industrial Complex (2).xlsx
86 | 81 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-11 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-04-15 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 1 | Finished | 67560 | 67560 | C2015-07 Industrial Complex (2).xlsx
87 | 82 | Rioleringswerken kantoor + aanvulling stabilisé + steenslag | 2013-06-05 08:00 | 2013-06-14 17:00 | 8d |  | 0 | 0 | 625 | 40000 | 40000 | 2013-04-15 08:00 | 8d | 40000 | 0 | 0 | 0 | 0 | 40000 | 0 | 1 | Finished | 40000 | 40000 | C2015-07 Industrial Complex (2).xlsx
88 | 88 | Ruwbouw kantoor niv 0 | 2013-06-13 08:00 | 2013-07-12 17:00 | 22d |  |  | 0 |  |  | 187200 |  | 21d | [5 empty] | 187200 |  | 1 |  | 187200 | 187200 | C2015-07 Industrial Complex (2).xlsx
89 | 84 | Vloerplaat gelijkvloers | 2013-06-13 08:00 | 2013-06-19 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-31 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 1 | Finished | 24000 | 24000 | C2015-07 Industrial Complex (2).xlsx
90 | 85 | Kolommen + balken gelijkvloers | 2013-06-20 08:00 | 2013-07-05 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-06-06 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 1 | Finished | 57600 | 57600 | C2015-07 Industrial Complex (2).xlsx
91 | 86 | Metselwerken gelijkvloers | 2013-06-20 08:00 | 2013-07-09 17:00 | 14d |  | 0 | 0 | 600 | 67200 | 67200 | 2013-06-06 08:00 | 14d | 67200 | 0 | 0 | 0 | 0 | 67200 | 0 | 1 | Finished | 67200 | 67200 | C2015-07 Industrial Complex (2).xlsx
92 | 87 | Afdek 0 + wapenen + opstort | 2013-07-03 08:00 | 2013-07-12 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-19 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 1 | Finished | 38400 | 38400 | C2015-07 Industrial Complex (2).xlsx
93 | 92 | Ruwbouw kantoor niv +1 | 2013-08-06 08:00 | 2013-09-04 17:00 | 22d |  |  | 0 |  |  | 144000 |  | 21d | [5 empty] | 144000 |  | 1 |  | 144000 | 144000 | C2015-07 Industrial Complex (2).xlsx
94 | 89 | Kolommen + balken 1ste | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-07-03 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 1 | Finished | 57600 | 57600 | C2015-07 Industrial Complex (2).xlsx
95 | 90 | Metselwerken 1ste | 2013-08-06 08:00 | 2013-08-19 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-07-03 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 1 | Finished | 48000 | 48000 | C2015-07 Industrial Complex (2).xlsx
96 | 91 | Afdek 1 + wapenen + opstort | 2013-08-26 08:00 | 2013-09-04 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-07-22 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 1 | Finished | 38400 | 38400 | C2015-07 Industrial Complex (2).xlsx
97 | 93 | Metselwerken dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2013-07-29 08:00 | 3d | 14400 | 0 | 0 | 0 | 0 | 14400 | 0 | 1 | Finished | 14400 | 14400 | C2015-07 Industrial Complex (2).xlsx
98 | 97 | Gevelbekledingen kantoor | 2013-09-05 08:00 | 2013-11-01 17:00 | 42d |  |  | 0 |  |  | 123904 |  | 51d | [5 empty] | 104544 |  | 1 |  | 123904 | 123904 | C2015-07 Industrial Complex (2).xlsx
99 | 94 | Buitenschrijnwerk + beglazing gelijkvloers | 2013-10-03 08:00 | 2013-10-18 17:00 | 12d |  | 0 | 0 | 484 | 46464 | 46464 | 2014-03-26 08:00 | 12d | 46464 | 0 | 0 | 0 | 0 | 46464 | 0 | 1 | Finished | 46464 | 46464 | C2015-07 Industrial Complex (2).xlsx
100 | 95 | Buitenschrijnwerk + beglazing 1ste | 2013-09-05 08:00 | 2013-09-18 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2014-03-13 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 1 | Finished | 38720 | 38720 | C2015-07 Industrial Complex (2).xlsx
101 | 96 | Gevelbekleding metaalcasettes | 2013-10-21 08:00 | 2013-11-01 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2014-01-30 08:00 | 5d | 19360 | 0 | 0 | 0 | 0 | 19360 | 0 | 1 | Finished | 38720 | 38720 | C2015-07 Industrial Complex (2).xlsx
102 | 102 | Dakwerken kantoor | 2013-09-10 08:00 | 2013-10-08 17:00 | 21d |  |  | 0 |  |  | 333280 |  | 19d | [5 empty] | 333280 |  | 1 |  | 333280 | 333280 | C2015-07 Industrial Complex (2).xlsx
103 | 98 | Hellingsbeton | 2013-09-10 08:00 | 2013-09-10 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 | 2014-01-28 08:00 | 1d | 16664 | 0 | 0 | 0 | 0 | 16664 | 0 | 1 | Finished | 16664 | 16664 | C2015-07 Industrial Complex (2).xlsx
104 | 99 | isolatie + dakbedekking + ballast | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 2083 | 166640 | 166640 | 2014-02-05 08:00 | 10d | 166640 | 0 | 0 | 0 | 0 | 166640 | 0 | 1 | Finished | 166640 | 166640 | C2015-07 Industrial Complex (2).xlsx
105 | 100 | RW-afvoeren | 2013-09-30 08:00 | 2013-10-03 17:00 | 4d |  | 0 | 0 | 2083 | 66656 | 66656 | 2014-02-17 08:00 | 4d | 66656 | 0 | 0 | 0 | 0 | 66656 | 0 | 1 | Finished | 66656 | 66656 | C2015-07 Industrial Complex (2).xlsx
106 | 101 | Lichtstraat | 2013-10-02 08:00 | 2013-10-08 17:00 | 5d |  | 0 | 0 | 2083 | 83320 | 83320 | 2014-02-17 08:00 | 5d | 83320 | 0 | 0 | 0 | 0 | 83320 | 0 | 1 | Finished | 83320 | 83320 | C2015-07 Industrial Complex (2).xlsx
107 | 123 | Niv 0 | 2013-10-11 08:00 | 2014-04-01 17:00 | 123d |  |  | 0 |  |  | 507520 |  | 68d | [5 empty] | 378688 |  | 1 |  | 507520 | 507520 | C2015-07 Industrial Complex (2).xlsx
108 | 103 | Cementage | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-01-27 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 1 | Finished | 3904 | 3904 | C2015-07 Industrial Complex (2).xlsx
109 | 104 | Pleisterwerken | 2013-10-11 08:00 | 2013-10-24 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-01-27 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 1 | Finished | 39040 | 39040 | C2015-07 Industrial Complex (2).xlsx
110 | 105 | Uitvullingslaag polystyreenkorrels | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-02-10 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 1 | Finished | 3904 | 3904 | C2015-07 Industrial Complex (2).xlsx
111 | 106 | Vloerisolatie PU platen | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-11 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 1 | Finished | 19520 | 19520 | C2015-07 Industrial Complex (2).xlsx
112 | 107 | Chape | 2013-11-05 08:00 | 2013-11-11 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-12 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 1 | Finished | 19520 | 19520 | C2015-07 Industrial Complex (2).xlsx
113 | 108 | Polybetonvloer | 2013-11-15 08:00 | 2013-11-15 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-02-24 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 1 | Finished | 3904 | 3904 | C2015-07 Industrial Complex (2).xlsx
114 | 109 | Stalen trappen kantoor | 2014-01-13 08:00 | 2014-01-22 17:00 | 8d |  | 0 | 0 | 488 | 31232 | 31232 | 2014-01-30 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 1 | Finished | 31232 | 31232 | C2015-07 Industrial Complex (2).xlsx
115 | 110 | Lichte scheidingswanden en voorzetwanden | 2013-11-19 08:00 | 2013-12-02 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-26 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 1 | Finished | 39040 | 39040 | C2015-07 Industrial Complex (2).xlsx
116 | 111 | Vloerbekleding keramische tegels | 2013-12-03 08:00 | 2013-12-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2014-01-27 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 1 | Finished | 11712 | 11712 | C2015-07 Industrial Complex (2).xlsx
117 | 112 | Faience | 2013-12-06 08:00 | 2013-12-19 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-04 08:00 | 8d | 31232 | 0 | 0 | 0 | 0 | 31232 | 0 | 1 | Finished | 39040 | 39040 | C2015-07 Industrial Complex (2).xlsx
118 | 113 | Binnendeuren en binnenramen | 2013-12-03 08:00 | 2013-12-16 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-27 08:00 | 2d | 7808 | 0 | 0 | 0 | 0 | 7808 | 0 | 1 | Finished | 39040 | 39040 | C2015-07 Industrial Complex (2).xlsx
119 | 114 | Zichtwanden op binnenwanden | 2013-12-17 08:00 | 2013-12-25 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-03-17 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 1 | Finished | 27328 | 27328 | C2015-07 Industrial Complex (2).xlsx
120 | 115 | Vast meubilair | 2014-01-09 08:00 | 2014-01-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-03-17 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 1 | Finished | 19520 | 19520 | C2015-07 Industrial Complex (2).xlsx
121 | 116 | Plafonds | 2014-01-16 08:00 | 2014-01-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 | 2014-02-27 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 1 | Finished | 46848 | 46848 | C2015-07 Industrial Complex (2).xlsx
122 | 117 | Vloerbekleding tapijt | 2014-02-03 08:00 | 2014-02-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2014-04-30 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 1 | Finished | 11712 | 11712 | C2015-07 Industrial Complex (2).xlsx
123 | 118 | Plinten | 2014-02-06 08:00 | 2014-02-10 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2014-04-30 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 1 | Finished | 11712 | 11712 | C2015-07 Industrial Complex (2).xlsx
124 | 119 | Schilderwerken | 2014-02-11 08:00 | 2014-03-05 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 | 2014-04-01 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 1 | Finished | 66368 | 66368 | C2015-07 Industrial Complex (2).xlsx
125 | 120 | Binnenzonnewering | 2014-03-06 08:00 | 2014-03-07 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 | 2014-04-30 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 1 | Finished | 7808 | 7808 | C2015-07 Industrial Complex (2).xlsx
126 | 121 | Allerhande aanwerkingen | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-04-30 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 1 | Finished | 39040 | 39040 | C2015-07 Industrial Complex (2).xlsx
127 | 122 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-04-22 08:00 | 4d | 15616 | 0 | 0 | 0 | 0 | 15616 | 0 | 1 | Finished | 27328 | 27328 | C2015-07 Industrial Complex (2).xlsx
128 | 142 | Niv +1 | 2013-10-02 08:00 | 2014-04-01 17:00 | 130d |  |  | 0 |  |  | 452864 |  | 68d | [5 empty] | 390400 |  | 1 |  | 452864 | 452864 | C2015-07 Industrial Complex (2).xlsx
129 | 124 | Pleisterwerken | 2013-10-02 08:00 | 2013-10-07 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 | 2014-01-27 08:00 | 4d | 15616 | 0 | 0 | 0 | 0 | 15616 | 0 | 1 | Finished | 15616 | 15616 | C2015-07 Industrial Complex (2).xlsx
130 | 125 | Pur uitvullingslaag | 2013-10-08 08:00 | 2013-10-08 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-01-31 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 1 | Finished | 3904 | 3904 | C2015-07 Industrial Complex (2).xlsx
131 | 126 | Chape | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-03 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 1 | Finished | 19520 | 19520 | C2015-07 Industrial Complex (2).xlsx
132 | 127 | Polybetonvloer | 2013-10-18 08:00 | 2013-10-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-02-12 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 1 | Finished | 3904 | 3904 | C2015-07 Industrial Complex (2).xlsx
133 | 128 | Lichte scheidingswanden en voorzetwanden | 2013-10-21 08:00 | 2013-11-11 17:00 | 16d |  | 0 | 0 | 488 | 62464 | 62464 | 2014-02-12 08:00 | 16d | 62464 | 0 | 0 | 0 | 0 | 62464 | 0 | 1 | Finished | 62464 | 62464 | C2015-07 Industrial Complex (2).xlsx
134 | 129 | Vloerbekleding keramische tegels | 2013-11-14 08:00 | 2013-11-18 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2014-01-27 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 1 | Finished | 11712 | 11712 | C2015-07 Industrial Complex (2).xlsx
135 | 130 | Faience | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 | 2014-01-30 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 1 | Finished | 7808 | 7808 | C2015-07 Industrial Complex (2).xlsx
136 | 131 | Binnendeuren en binnenramen | 2013-11-14 08:00 | 2013-11-27 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-04 08:00 | 2d | 7808 | 0 | 0 | 0 | 0 | 7808 | 0 | 1 | Finished | 39040 | 39040 | C2015-07 Industrial Complex (2).xlsx
137 | 132 | Zichtwanden op binnenwanden | 2013-11-28 08:00 | 2013-12-06 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-02-27 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 1 | Finished | 27328 | 27328 | C2015-07 Industrial Complex (2).xlsx
138 | 133 | Vast meubilair | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-27 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 1 | Finished | 19520 | 19520 | C2015-07 Industrial Complex (2).xlsx
139 | 134 | Plafonds | 2013-12-16 08:00 | 2013-12-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 | 2014-02-11 08:00 | 12d | 46848 | 0 | 0 | 0 | 0 | 46848 | 0 | 1 | Finished | 46848 | 46848 | C2015-07 Industrial Complex (2).xlsx
140 | 135 | Vloerbekleding tapijt | 2014-01-15 08:00 | 2014-01-23 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-03-17 08:00 | 7d | 27328 | 0 | 0 | 0 | 0 | 27328 | 0 | 1 | Finished | 27328 | 27328 | C2015-07 Industrial Complex (2).xlsx
141 | 136 | Plinten | 2014-01-24 08:00 | 2014-01-28 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2014-03-26 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 1 | Finished | 11712 | 11712 | C2015-07 Industrial Complex (2).xlsx
142 | 137 | Borstweringen | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 | 2014-04-07 08:00 | 4d | 15616 | 0 | 0 | 0 | 0 | 15616 | 0 | 1 | Finished | 15616 | 15616 | C2015-07 Industrial Complex (2).xlsx
143 | 138 | Schilderwerken | 2014-01-24 08:00 | 2014-02-17 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 | 2014-03-26 08:00 | 13d | 50752 | 0 | 0 | 0 | 0 | 50752 | 0 | 1 | Finished | 66368 | 66368 | C2015-07 Industrial Complex (2).xlsx
144 | 139 | Binnenzonneweringen en gordijnen | 2014-02-18 08:00 | 2014-02-19 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 | 2014-04-30 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 1 | Finished | 7808 | 7808 | C2015-07 Industrial Complex (2).xlsx
145 | 140 | Allerhande aanwerkingen | 2014-02-20 08:00 | 2014-03-05 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-04-30 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 1 | Finished | 39040 | 39040 | C2015-07 Industrial Complex (2).xlsx
146 | 141 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-04-24 08:00 | 4d | 15616 | 0 | 0 | 0 | 0 | 15616 | 0 | 1 | Finished | 27328 | 27328 | C2015-07 Industrial Complex (2).xlsx
147 | 147 | HVAC | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 345600 |  | 41d | [5 empty] | 138240 |  | 1 |  | 345600 | 345600 | C2015-07 Industrial Complex (2).xlsx
148 | 143 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 | 2014-03-17 08:00 | 2d | 11520 | 0 | 0 | 0 | 0 | 11520 | 0 | 1 | Finished | 57600 | 57600 | C2015-07 Industrial Complex (2).xlsx
149 | 144 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 | 2014-03-17 08:00 | 2d | 11520 | 0 | 0 | 0 | 0 | 11520 | 0 | 1 | Finished | 57600 | 57600 | C2015-07 Industrial Complex (2).xlsx
150 | 145 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 720 | 86400 | 86400 | 2014-01-21 08:00 | 10d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 1 | Finished | 86400 | 86400 | C2015-07 Industrial Complex (2).xlsx
151 | 146 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 720 | 144000 | 144000 | 2014-02-06 08:00 | 10d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 1 | Finished | 144000 | 144000 | C2015-07 Industrial Complex (2).xlsx
152 | 152 | Sanitair | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 61920 |  | 70d | [5 empty] | 41280 |  | 1 |  | 61920 | 61920 | C2015-07 Industrial Complex (2).xlsx
153 | 148 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 | 2014-04-15 08:00 | 10d | 10320 | 0 | 0 | 0 | 0 | 10320 | 0 | 1 | Finished | 10320 | 10320 | C2015-07 Industrial Complex (2).xlsx
154 | 149 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 | 2014-04-15 08:00 | 10d | 10320 | 0 | 0 | 0 | 0 | 10320 | 0 | 1 | Finished | 10320 | 10320 | C2015-07 Industrial Complex (2).xlsx
155 | 150 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 129 | 15480 | 15480 | 2014-01-21 08:00 | 10d | 10320 | 0 | 0 | 0 | 0 | 10320 | 0 | 1 | Finished | 15480 | 15480 | C2015-07 Industrial Complex (2).xlsx
156 | 151 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 129 | 25800 | 25800 | 2014-02-06 08:00 | 10d | 10320 | 0 | 0 | 0 | 0 | 10320 | 0 | 1 | Finished | 25800 | 25800 | C2015-07 Industrial Complex (2).xlsx
157 | 158 | Elektriciteit | 2013-09-05 08:00 | 2014-01-22 17:00 | 100d |  |  | 0 |  |  | 299880 |  | 20d | [5 empty] | 138040 |  | 1 |  | 299880 | 299880 | C2015-07 Industrial Complex (2).xlsx
158 | 153 | Leidingen op dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 595 | 14280 | 14280 | 2014-02-26 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 1 | Finished | 14280 | 14280 | C2015-07 Industrial Complex (2).xlsx
159 | 154 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 | 2014-02-27 08:00 | 7d | 33320 | 0 | 0 | 0 | 0 | 33320 | 0 | 1 | Finished | 47600 | 47600 | C2015-07 Industrial Complex (2).xlsx
160 | 155 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 | 2014-03-17 08:00 | 7d | 33320 | 0 | 0 | 0 | 0 | 33320 | 0 | 1 | Finished | 47600 | 47600 | C2015-07 Industrial Complex (2).xlsx
161 | 156 | Leidingen in plafonds 1ste | 2013-12-02 08:00 | 2013-12-20 17:00 | 15d |  | 0 | 0 | 595 | 71400 | 71400 | 2014-02-27 08:00 | 7d | 33320 | 0 | 0 | 0 | 0 | 33320 | 0 | 1 | Finished | 71400 | 71400 | C2015-07 Industrial Complex (2).xlsx
162 | 157 | Leidingen in plafonds gelijkvloers | 2013-12-19 08:00 | 2014-01-22 17:00 | 25d |  | 0 | 0 | 595 | 119000 | 119000 | 2014-03-17 08:00 | 7d | 33320 | 0 | 0 | 0 | 0 | 33320 | 0 | 1 | Finished | 119000 | 119000 | C2015-07 Industrial Complex (2).xlsx
163 | 161 | Bestaande loods | 2013-09-10 08:00 | 2013-10-03 17:00 | 18d |  |  | 0 |  |  | 86400 |  | 19d | [5 empty] | 86400 |  | 1 |  | 86400 | 86400 | C2015-07 Industrial Complex (2).xlsx
164 | 159 | Kolommen + balken + welfsels | 2013-09-10 08:00 | 2013-09-17 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 | 2014-01-27 08:00 | 6d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 1 | Finished | 28800 | 28800 | C2015-07 Industrial Complex (2).xlsx
165 | 160 | Metselwerken | 2013-09-18 08:00 | 2013-10-03 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2014-02-05 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 1 | Finished | 57600 | 57600 | C2015-07 Industrial Complex (2).xlsx
166 | 162 | Bestaande kantoren | 2014-02-12 08:00 | 2014-04-08 17:00 | 40d |  | 0 | 0 | 600 | 192000 | 192000 | 2014-01-27 08:00 | 35d | 168000 | 0 | 0 | 0 | 0 | 168000 | 0 | 1 | Finished | 192000 | 192000 | C2015-07 Industrial Complex (2).xlsx
167 | 166 | Omgevingswerken | 2013-10-04 08:00 | 2014-04-01 17:00 | 128d |  |  | 0 |  |  | 99840 |  | 62d | [5 empty] | 99840 |  | 1 |  | 99840 | 99840 | C2015-07 Industrial Complex (2).xlsx
168 | 163 | Laadkade | 2013-10-04 08:00 | 2013-10-24 17:00 | 15d |  | 0 | 0 | 240 | 28800 | 28800 | 2014-01-31 08:00 | 15d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 1 | Finished | 28800 | 28800 | C2015-07 Industrial Complex (2).xlsx
169 | 164 | Dockleveler | 2013-12-10 08:00 | 2013-12-11 17:00 | 2d |  | 0 | 0 | 240 | 3840 | 3840 | 2014-02-17 08:00 | 2d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 1 | Finished | 3840 | 3840 | C2015-07 Industrial Complex (2).xlsx
170 | 165 | Buitenaanleg | 2014-02-12 08:00 | 2014-04-01 17:00 | 35d |  | 0 | 0 | 240 | 67200 | 67200 | 2014-03-11 08:00 | 35d | 67200 | 0 | 0 | 0 | 0 | 67200 | 0 | 1 | Finished | 67200 | 67200 | C2015-07 Industrial Complex (2).xlsx
4 | 0 | Garden Center | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 467297.2052 |  | 186d | [5 empty] | 461900.1651 |  | 1 |  | 467297.2052 | 467297.2052 | C2015-08 Garden Center.xlsx
5 | 22 | Montagewerken | 2014-06-04 08:00 | 2014-08-20 17:00 | 56d |  |  | 0 |  |  | 60882.2407 |  | 65d | [5 empty] | 57214.7207 |  | 1 |  | 60882.2407 | 60882.2407 | C2015-08 Garden Center.xlsx
6 | 1 | Voorlopige plint | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-04 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 1 | Finished | 2659.04 | 2659.04 | C2015-08 Garden Center.xlsx
7 | 2 | prefabplint inkom sluiten | 2014-08-12 08:00 | 2014-08-13 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-12 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 1 | Finished | 2659.04 | 2659.04 | C2015-08 Garden Center.xlsx
8 | 3 | sandwich laagbouw | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 166.19 | 6647.6001 | 6647.6001 | 2014-06-04 08:00 | 5d | 6647.6001 | 0 | 0 | 0 | 0 | 6647.6001 | 0 | 1 | Finished | 6647.6001 | 6647.6001 | C2015-08 Garden Center.xlsx
9 | 4 | dakdekking voorbereiding | 2014-07-07 08:00 | 2014-07-09 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-07 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 1 | Finished | 3988.5601 | 3988.5601 | C2015-08 Garden Center.xlsx
10 | 5 | start dakdekking | 2014-08-05 08:00 | 2014-08-20 17:00 | 12d |  | 0 | 0 | 166.19 | 15954.2402 | 15954.2402 | 2014-07-07 08:00 | 12d | 15954.2402 | 0 | 0 | 0 | 0 | 15954.2402 | 0 | 1 | Finished | 15954.2402 | 15954.2402 | C2015-08 Garden Center.xlsx
11 | 6 | maken resterende doorvoerer | 2014-07-09 08:00 | 2014-07-11 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-09 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 1 | Finished | 3988.5601 | 3988.5601 | C2015-08 Garden Center.xlsx
12 | 7 | diverse dakdoorvoeren | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-11 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 1 | Finished | 1329.52 | 1329.52 | C2015-08 Garden Center.xlsx
13 | 8 | welfsels tellerlokaal | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-02 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 1 | Finished | 1329.52 | 1329.52 | C2015-08 Garden Center.xlsx
14 | 9 | andere welfsels | 2014-07-03 08:00 | 2014-07-03 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-03 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 1 | Finished | 1329.52 | 1329.52 | C2015-08 Garden Center.xlsx
15 | 10 | afmontage staal hoogbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 1 | Finished | 1329.52 | 1329.52 | C2015-08 Garden Center.xlsx
16 | 11 | randbeveiliging tussenvloeren | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 1 | Finished | 1329.52 | 1329.52 | C2015-08 Garden Center.xlsx
17 | 19 | Buitenwanden kantoor | 2014-06-04 08:00 | 2014-08-19 17:00 | 55d |  |  | 0 |  |  | 15586.9601 |  | 65d | [5 empty] | 11919.4401 |  | 1 |  | 15586.9601 | 15586.9601 | C2015-08 Garden Center.xlsx
18 | 12 | Aanvullen en grondwerken | 2014-06-04 08:00 | 2014-06-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-06-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 1 | Finished | 916.88 | 916.88 | C2015-08 Garden Center.xlsx
19 | 13 | sandwichpanelen inkom | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 114.61 | 4584.4 | 4584.4 | 2014-06-04 08:00 | 5d | 4584.4 | 0 | 0 | 0 | 0 | 4584.4 | 0 | 1 | Finished | 4584.4 | 4584.4 | C2015-08 Garden Center.xlsx
20 | 14 | netten demonteren lage zone | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 1 | Finished | 916.88 | 916.88 | C2015-08 Garden Center.xlsx
21 | 15 | beveiliging hoge dak | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 1 | Finished | 916.88 | 916.88 | C2015-08 Garden Center.xlsx
22 | 16 | welfsels traphal | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-08-29 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 1 | Finished | 916.88 | 916.88 | C2015-08 Garden Center.xlsx
23 | 17 | steeldeck hoogbouw-inkom | 2014-07-08 08:00 | 2014-07-09 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 1 | Finished | 1833.76 | 1833.76 | C2015-08 Garden Center.xlsx
24 | 18 | dakbedekking hoogbouw | 2014-08-12 08:00 | 2014-08-19 17:00 | 6d |  | 0 | 0 | 114.61 | 5501.28 | 5501.28 | 2014-09-01 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 1 | Finished | 5501.28 | 5501.28 | C2015-08 Garden Center.xlsx
25 | 20 | regenwaterafvoer laagbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 1 | Finished | 916.88 | 916.88 | C2015-08 Garden Center.xlsx
26 | 21 | regenwaterafvoer hoogbouw | 2014-07-09 08:00 | 2014-07-10 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 1 | Finished | 1833.76 | 1833.76 | C2015-08 Garden Center.xlsx
27 | 52 | Ruwbouwwerken | 2014-06-23 08:00 | 2014-08-22 17:00 | 45d |  |  | 0 |  |  | 126492.3207 |  | 71d | [5 empty] | 126492.3207 |  | 1 |  | 126492.3207 | 126492.3207 | C2015-08 Garden Center.xlsx
28 | 23 | Wachtbuizen | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
29 | 24 | grondwerken | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
30 | 25 | metselwerken tellerlokaal | 2014-06-27 08:00 | 2014-07-11 17:00 | 11d |  | 0 | 0 | 159.86 | 14067.6801 | 14067.6801 | 2014-06-27 08:00 | 11d | 14067.6801 | 0 | 0 | 0 | 0 | 14067.6801 | 0 | 1 | Finished | 14067.6801 | 14067.6801 | C2015-08 Garden Center.xlsx
31 | 26 | metselwerken kantoren | 2014-06-23 08:00 | 2014-07-01 17:00 | 7d |  | 0 | 0 | 159.86 | 8952.16 | 8952.16 | 2014-06-23 08:00 | 7d | 8952.16 | 0 | 0 | 0 | 0 | 8952.16 | 0 | 1 | Finished | 8952.16 | 8952.16 | C2015-08 Garden Center.xlsx
32 | 27 | metselwerken traphal | 2014-06-23 08:00 | 2014-08-06 17:00 | 33d |  | 0 | 0 | 159.86 | 42203.0402 | 42203.0402 | 2014-06-23 08:00 | 33d | 42203.0402 | 0 | 0 | 0 | 0 | 42203.0402 | 0 | 1 | Finished | 42203.0402 | 42203.0402 | C2015-08 Garden Center.xlsx
33 | 28 | prefab bordessen | 2014-06-30 08:00 | 2014-07-11 17:00 | 10d |  | 0 | 0 | 159.86 | 12788.8 | 12788.8 | 2014-06-30 08:00 | 10d | 12788.8 | 0 | 0 | 0 | 0 | 12788.8 | 0 | 1 | Finished | 12788.8 | 12788.8 | C2015-08 Garden Center.xlsx
34 | 29 | trapsledes | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-28 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
35 | 30 | welfsels traphal | 2014-08-08 08:00 | 2014-08-11 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-29 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 1 | Finished | 2557.76 | 2557.76 | C2015-08 Garden Center.xlsx
36 | 31 | voegwerken metselwerken | 2014-08-12 08:00 | 2014-08-14 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-06-30 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 1 | Finished | 3836.64 | 3836.64 | C2015-08 Garden Center.xlsx
37 | 32 | schilderwerken metselwerken | 2014-08-18 08:00 | 2014-08-20 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-09-08 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 1 | Finished | 3836.64 | 3836.64 | C2015-08 Garden Center.xlsx
38 | 33 | koepsels traphal | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
39 | 34 | koepsels laag dak | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
40 | 35 | riolering overloop | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 1 | Finished | 1241.6801 | 1241.6801 | C2015-08 Garden Center.xlsx
41 | 36 | riolering overloop recup | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 1 | Finished | 1241.6801 | 1241.6801 | C2015-08 Garden Center.xlsx
42 | 37 | riolering inkom | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 1 | Finished | 1241.6801 | 1241.6801 | C2015-08 Garden Center.xlsx
43 | 38 | arduinen dorpels | 2014-08-14 08:00 | 2014-08-14 17:00 | 1d |  | 0 | 0 | 159.21 | 1273.6801 | 1273.6801 | 2014-07-04 08:00 | 1d | 1273.6801 | 0 | 0 | 0 | 0 | 1273.6801 | 0 | 1 | Finished | 1273.6801 | 1273.6801 | C2015-08 Garden Center.xlsx
44 | 51 | Buitenschrijnwerk | 2014-07-07 08:00 | 2014-08-22 17:00 | 35d |  |  | 0 |  |  | 26856.4801 |  | 61d | [5 empty] | 26856.4801 |  | 1 |  | 26856.4801 | 26856.4801 | C2015-08 Garden Center.xlsx
45 | 39 | atelier alu | 2014-07-07 08:00 | 2014-07-11 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-07-07 08:00 | 5d | 6394.4 | 0 | 0 | 0 | 0 | 6394.4 | 0 | 1 | Finished | 6394.4 | 6394.4 | C2015-08 Garden Center.xlsx
46 | 40 | plaatsing alu | 2014-08-14 08:00 | 2014-08-15 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-07 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 1 | Finished | 2557.76 | 2557.76 | C2015-08 Garden Center.xlsx
47 | 41 | plaatsing glas deel 1 | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-11 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
48 | 42 | opmeting restant | 2014-08-06 08:00 | 2014-08-06 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-06 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
49 | 43 | plaatsing alu restant | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-18 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
50 | 44 | alu raam | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-19 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 1 | Finished | 2557.76 | 2557.76 | C2015-08 Garden Center.xlsx
51 | 45 | plaatsing glas restant | 2014-08-20 08:00 | 2014-08-20 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-19 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
52 | 46 | sectionaal poorten | 2014-08-15 08:00 | 2014-08-18 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-25 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 1 | Finished | 2557.76 | 2557.76 | C2015-08 Garden Center.xlsx
53 | 47 | poorten berging en tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
54 | 48 | RF behandeling laagbouw | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-13 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 1 | Finished | 2557.76 | 2557.76 | C2015-08 Garden Center.xlsx
55 | 49 | RF behandeling hoogbouw | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-13 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 1 | Finished | 2557.76 | 2557.76 | C2015-08 Garden Center.xlsx
56 | 50 | Retouche staalconstructie | 2014-08-21 08:00 | 2014-08-21 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-29 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
57 | 66 | Betonvloer | 2014-07-02 08:00 | 2014-09-26 17:00 | 63d |  |  | 0 |  |  | 35808.6401 |  | 64d | [5 empty] | 35808.6401 |  | 1 |  | 35808.6401 | 35808.6401 | C2015-08 Garden Center.xlsx
58 | 53 | druklaag welfsels kelder | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
59 | 54 | grondwerk inkomzone | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
60 | 55 | ondervloer inkom | 2014-08-15 08:00 | 2014-08-15 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
61 | 56 | arduin inkom | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
62 | 57 | overige arduinen dorpels | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-07-09 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 1 | Finished | 2557.76 | 2557.76 | C2015-08 Garden Center.xlsx
63 | 58 | polivloer tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
64 | 59 | polivloer berging | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
65 | 60 | vloerisolatie | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-08-22 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 1 | Finished | 3836.64 | 3836.64 | C2015-08 Garden Center.xlsx
66 | 61 | folie en vloerverwarming | 2014-08-28 08:00 | 2014-09-03 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-08-28 08:00 | 5d | 6394.4 | 0 | 0 | 0 | 0 | 6394.4 | 0 | 1 | Finished | 6394.4 | 6394.4 | C2015-08 Garden Center.xlsx
67 | 62 | druklaag welfsels | 2014-07-04 08:00 | 2014-07-11 17:00 | 6d |  | 0 | 0 | 159.86 | 7673.28 | 7673.28 | 2014-07-04 08:00 | 6d | 7673.28 | 0 | 0 | 0 | 0 | 7673.28 | 0 | 1 | Finished | 7673.28 | 7673.28 | C2015-08 Garden Center.xlsx
68 | 63 | polivloer winkel en inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 1 | Finished | 1278.88 | 1278.88 | C2015-08 Garden Center.xlsx
69 | 64 | nabehandeling polivloer | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-09-26 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 1 | Finished | 2557.76 | 2557.76 | C2015-08 Garden Center.xlsx
70 | 65 | binnenwand berging | 2014-08-05 08:00 | 2014-08-07 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-08-05 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 1 | Finished | 3836.64 | 3836.64 | C2015-08 Garden Center.xlsx
71 | 77 | Wegeniswerken achter | 2014-07-10 08:00 | 2014-08-25 17:00 | 33d |  |  | 0 |  |  | 17427.76 |  | 33d | [5 empty] | 17427.76 |  | 1 |  | 17427.76 | 17427.76 | C2015-08 Garden Center.xlsx
72 | 67 | opruimen werfkeet | 2014-07-10 08:00 | 2014-07-10 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 2014-07-10 08:00 | 1d | 251.6 | 0 | 0 | 0 | 0 | 251.6 | 0 | 1 | Finished | 251.6 | 251.6 | C2015-08 Garden Center.xlsx
73 | 68 | riolering naar hangar | 2014-07-11 08:00 | 2014-07-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 2014-07-11 08:00 | 2d | 2483.3601 | 0 | 0 | 0 | 0 | 2483.3601 | 0 | 1 | Finished | 2483.3601 | 2483.3601 | C2015-08 Garden Center.xlsx
74 | 69 | nutsleidingen ondergronds | 2014-07-14 08:00 | 2014-07-14 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-14 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 1 | Finished | 1241.6801 | 1241.6801 | C2015-08 Garden Center.xlsx
75 | 70 | riolering bestrating | 2014-07-15 08:00 | 2014-07-15 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-15 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 1 | Finished | 1241.6801 | 1241.6801 | C2015-08 Garden Center.xlsx
76 | 71 | funderingskoffer | 2014-07-16 08:00 | 2014-07-16 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-16 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 1 | Finished | 1329.52 | 1329.52 | C2015-08 Garden Center.xlsx
77 | 72 | fijnnivelleren funderingskoffer | 2014-07-18 08:00 | 2014-07-18 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-18 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 1 | Finished | 1329.52 | 1329.52 | C2015-08 Garden Center.xlsx
78 | 73 | klinkerverharding | 2014-07-21 08:00 | 2014-07-21 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-21 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 1 | Finished | 477.52 | 477.52 | C2015-08 Garden Center.xlsx
79 | 74 | Asfaltverharding | 2014-07-21 08:00 | 2014-07-22 17:00 | 2d |  | 0 | 0 | 59.69 | 955.04 | 955.04 | 2014-07-21 08:00 | 2d | 955.04 | 0 | 0 | 0 | 0 | 955.04 | 0 | 1 | Finished | 955.04 | 955.04 | C2015-08 Garden Center.xlsx
80 | 75 | herkwerken | 2014-07-28 08:00 | 2014-07-28 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-28 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 1 | Finished | 477.52 | 477.52 | C2015-08 Garden Center.xlsx
81 | 76 | Afwerken groenzones | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  | 0 | 0 | 59.69 | 7640.3198 | 7640.3198 | 2014-08-04 08:00 | 16d | 7640.3198 | 0 | 0 | 0 | 0 | 7640.3198 | 0 | 1 | Finished | 7640.3198 | 7640.3198 | C2015-08 Garden Center.xlsx
82 | 91 | Wegeniswerken voor | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  |  | 0 |  |  | 12790.3203 |  | 20d | [5 empty] | 12790.3203 |  | 1 |  | 12790.3203 | 12790.3203 | C2015-08 Garden Center.xlsx
83 | 78 | opruimen voorterrein | 2014-08-04 08:00 | 2014-08-05 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 | 2014-09-08 08:00 | 2d | 503.2 | 0 | 0 | 0 | 0 | 503.2 | 0 | 1 | Finished | 503.2 | 503.2 | C2015-08 Garden Center.xlsx
84 | 79 | grondwerken/braakwerken | 2014-08-06 08:00 | 2014-08-12 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-09-08 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 1 | Finished | 1258 | 1258 | C2015-08 Garden Center.xlsx
85 | 80 | herinrichting werf | 2014-08-05 08:00 | 2014-08-05 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 2014-09-08 08:00 | 1d | 251.6 | 0 | 0 | 0 | 0 | 251.6 | 0 | 1 | Finished | 251.6 | 251.6 | C2015-08 Garden Center.xlsx
86 | 81 | plaatsing riolering | 2014-08-13 08:00 | 2014-08-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 2014-09-18 08:00 | 2d | 2483.3601 | 0 | 0 | 0 | 0 | 2483.3601 | 0 | 1 | Finished | 2483.3601 | 2483.3601 | C2015-08 Garden Center.xlsx
87 | 82 | nutsleidingen fase 1 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 1 | Finished | 1241.6801 | 1241.6801 | C2015-08 Garden Center.xlsx
88 | 83 | nutsleidingen fase 2 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 1 | Finished | 1241.6801 | 1241.6801 | C2015-08 Garden Center.xlsx
89 | 84 | riolering bestrating | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 1 | Finished | 1241.6801 | 1241.6801 | C2015-08 Garden Center.xlsx
90 | 85 | funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-25 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 1 | Finished | 1329.52 | 1329.52 | C2015-08 Garden Center.xlsx
91 | 86 | fijnniverllerinn funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-25 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 1 | Finished | 1329.52 | 1329.52 | C2015-08 Garden Center.xlsx
92 | 87 | klinkerverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 1 | Finished | 477.52 | 477.52 | C2015-08 Garden Center.xlsx
93 | 88 | asfaltverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 1 | Finished | 477.52 | 477.52 | C2015-08 Garden Center.xlsx
94 | 89 | herkwerken | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 1 | Finished | 477.52 | 477.52 | C2015-08 Garden Center.xlsx
95 | 90 | afwerken groenzones | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 1 | Finished | 477.52 | 477.52 | C2015-08 Garden Center.xlsx
96 | 115 | afbouw +2 | 2014-08-15 08:00 | 2014-09-30 17:00 | 33d |  |  | 0 |  |  | 43914.6408 |  | 36d | [5 empty] | 43914.6408 |  | 1 |  | 43914.6408 | 43914.6408 | C2015-08 Garden Center.xlsx
97 | 92 | voorbereid werk wanden | 2014-08-15 08:00 | 2014-08-21 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-08-22 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 1 | Finished | 1258 | 1258 | C2015-08 Garden Center.xlsx
98 | 93 | technieken in holle wanden | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 118.75 | 2850 | 2850 | 2014-08-26 08:00 | 3d | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 1 | Finished | 2850 | 2850 | C2015-08 Garden Center.xlsx
99 | 94 | wanden sluiten | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-08-29 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 1 | Finished | 3623.2001 | 3623.2001 | C2015-08 Garden Center.xlsx
100 | 95 | wanden afwerken | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-08-29 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 1 | Finished | 3623.2001 | 3623.2001 | C2015-08 Garden Center.xlsx
101 | 96 | technieken boven gyproc | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-28 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 1 | Finished | 1900 | 1900 | C2015-08 Garden Center.xlsx
102 | 97 | technieken boven plafond | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 2014-09-01 08:00 | 1d | 950 | 0 | 0 | 0 | 0 | 950 | 0 | 1 | Finished | 950 | 950 | C2015-08 Garden Center.xlsx
103 | 98 | gyproc plafond | 2014-08-26 08:00 | 2014-08-28 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-01 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 1 | Finished | 2173.92 | 2173.92 | C2015-08 Garden Center.xlsx
104 | 99 | pur isolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-09 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
105 | 100 | folie en vloerverwarming | 2014-09-01 08:00 | 2014-09-02 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-10 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
106 | 101 | chappewerken | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-12 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
107 | 102 | vloer tegelwerken | 2014-09-08 08:00 | 2014-09-11 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-09-18 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 1 | Finished | 2898.5601 | 2898.5601 | C2015-08 Garden Center.xlsx
108 | 103 | vloertegelplinten | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
109 | 104 | binnendeuren | 2014-09-12 08:00 | 2014-09-15 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-24 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
110 | 105 | afwerking met plinten | 2014-09-16 08:00 | 2014-09-16 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-26 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
111 | 106 | schilderwerken | 2014-09-10 08:00 | 2014-09-16 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-09-18 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 1 | Finished | 3623.2001 | 3623.2001 | C2015-08 Garden Center.xlsx
112 | 107 | afbouw technieken wanden | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-29 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
113 | 108 | plaatsing keuken | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
114 | 109 | plaatsing wandtegels keuken | 2014-09-15 08:00 | 2014-09-15 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-25 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
115 | 110 | plaatsing wandtegels sanitair | 2014-09-12 08:00 | 2014-09-17 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-09-24 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 1 | Finished | 2898.5601 | 2898.5601 | C2015-08 Garden Center.xlsx
116 | 111 | restant raster en plafondtegel | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-30 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 1 | Finished | 2173.92 | 2173.92 | C2015-08 Garden Center.xlsx
117 | 112 | afbouw plafonds | 2014-09-23 08:00 | 2014-09-24 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-06 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
118 | 113 | afbouw sanitair | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-02 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
119 | 114 | inrichting kantoren | 2014-09-24 08:00 | 2014-09-30 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-10-06 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 1 | Finished | 3623.2001 | 3623.2001 | C2015-08 Garden Center.xlsx
120 | 134 | gyprocwerken gvl | 2014-08-05 08:00 | 2014-10-06 17:00 | 45d |  |  | 0 |  |  | 25989.9204 |  | 44d | [5 empty] | 30337.7605 |  | 1 |  | 25989.9204 | 25989.9204 | C2015-08 Garden Center.xlsx
121 | 116 | technieken in betonblokken | 2014-08-05 08:00 | 2014-08-06 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-21 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 1 | Finished | 1900 | 1900 | C2015-08 Garden Center.xlsx
122 | 117 | pleisterwerken betonblokken | 2014-08-11 08:00 | 2014-08-13 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-25 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 1 | Finished | 2173.92 | 2173.92 | C2015-08 Garden Center.xlsx
123 | 118 | voorbereidend werk gyproc | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-18 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
124 | 119 | technieken in wanden | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-19 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 1 | Finished | 1900 | 1900 | C2015-08 Garden Center.xlsx
125 | 120 | technieken plafonds | 2014-08-26 08:00 | 2014-08-27 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-21 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 1 | Finished | 1900 | 1900 | C2015-08 Garden Center.xlsx
126 | 121 | wanden dicht | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-21 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
127 | 122 | vloerisolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-27 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
128 | 123 | folie en vloerverwarming | 2014-09-02 08:00 | 2014-09-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-28 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
129 | 124 | chappevloer | 2014-09-08 08:00 | 2014-09-08 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-08 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
130 | 125 | wanden afwerken | 2014-08-27 08:00 | 2014-08-28 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-22 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
131 | 126 | vloertegelwerken | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-30 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 1 | Finished | 2173.92 | 2173.92 | C2015-08 Garden Center.xlsx
132 | 127 | afwerking met plinten | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-03 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
133 | 128 | binnendeuren | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-03 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
134 | 129 | restant plinten | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-06 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
135 | 130 | schilderwerken | 2014-09-23 08:00 | 2014-09-25 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-10-03 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 1 | Finished | 2173.92 | 2173.92 | C2015-08 Garden Center.xlsx
136 | 131 | plafondraster | 2014-09-26 08:00 | 2014-09-29 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-08 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
137 | 132 | afbouw technieken | 2014-09-30 08:00 | 2014-10-01 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-10 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
138 | 133 | inrichting kantoren gvl | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-10-14 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 1 | Finished | 2173.92 | 2173.92 | C2015-08 Garden Center.xlsx
139 | 151 | gyprocwerken inkomzone | 2014-06-04 08:00 | 2014-10-09 17:00 | 92d |  |  | 0 |  |  | 23409.6003 |  | 33d | [5 empty] | 29975.6804 |  | 1 |  | 23409.6003 | 23409.6003 | C2015-08 Garden Center.xlsx
140 | 135 | sandwich deel 1 | 2014-08-18 08:00 | 2014-08-19 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-08-19 08:00 | 6d | 5501.28 | 0 | 0 | 0 | 0 | 5501.28 | 0 | 1 | Finished | 1833.76 | 1833.76 | C2015-08 Garden Center.xlsx
141 | 136 | vloerisolatie | 2014-10-02 08:00 | 2014-10-02 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-26 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
142 | 137 | folie en vloerverwarming | 2014-10-03 08:00 | 2014-10-03 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-27 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
143 | 138 | polivloer inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-09 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
144 | 139 | sandwich deel 2 | 2014-09-16 08:00 | 2014-09-17 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-09-05 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 1 | Finished | 1833.76 | 1833.76 | C2015-08 Garden Center.xlsx
145 | 140 | voorbereid werk gyproc | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-15 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 1 | Finished | 2173.92 | 2173.92 | C2015-08 Garden Center.xlsx
146 | 141 | technieken in wanden | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-19 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 1 | Finished | 1900 | 1900 | C2015-08 Garden Center.xlsx
147 | 142 | wanden dicht | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-22 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
148 | 143 | wanden afwerken | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-22 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
149 | 144 | technieken boven plafonds | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-26 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 1 | Finished | 1900 | 1900 | C2015-08 Garden Center.xlsx
150 | 145 | plafond sanitair | 2014-09-29 08:00 | 2014-10-01 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-26 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 1 | Finished | 2173.92 | 2173.92 | C2015-08 Garden Center.xlsx
151 | 146 | wandtegelwerken sanitair | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-15 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 1 | Finished | 2173.92 | 2173.92 | C2015-08 Garden Center.xlsx
152 | 147 | binnnenschrijnwerk | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-18 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
153 | 148 | schilderwerk binnenschrijnwerk | 2014-10-08 08:00 | 2014-10-09 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-23 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
154 | 149 | schilderwerk wanden | 2014-10-02 08:00 | 2014-10-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-25 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
155 | 150 | afbouw sanitaire ruimten | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-29 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
156 | 164 | traphal afwerking | 2014-08-11 08:00 | 2014-10-07 17:00 | 42d |  |  | 0 |  |  | 19516.7203 |  | 44d | [5 empty] | 21416.7203 |  | 1 |  | 19516.7203 | 19516.7203 | C2015-08 Garden Center.xlsx
157 | 152 | technieken ingewerkt in beton | 2014-08-11 08:00 | 2014-08-12 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-25 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 1 | Finished | 1900 | 1900 | C2015-08 Garden Center.xlsx
158 | 153 | technieken in spouw | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 2014-08-26 08:00 | 3d | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 1 | Finished | 950 | 950 | C2015-08 Garden Center.xlsx
159 | 154 | raam en deur in traphal | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-25 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
160 | 155 | pleisterwerk betonblokken | 2014-08-13 08:00 | 2014-08-19 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-09-01 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 1 | Finished | 3623.2001 | 3623.2001 | C2015-08 Garden Center.xlsx
161 | 156 | tegelplinten betontrappen | 2014-09-09 08:00 | 2014-09-10 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-19 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
162 | 157 | vloertegels inkom en plinten | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-08 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
163 | 158 | opmeting leuning | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-02 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
164 | 159 | plaatsing leuningen | 2014-09-01 08:00 | 2014-09-01 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-01 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
165 | 160 | rolstoellift | 2014-09-02 08:00 | 2014-09-05 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-10-02 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 1 | Finished | 2898.5601 | 2898.5601 | C2015-08 Garden Center.xlsx
166 | 161 | plafondraster en bekleding | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-22 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
167 | 162 | schilderwerk pleisterwerk | 2014-10-01 08:00 | 2014-10-06 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-10-20 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 1 | Finished | 2898.5601 | 2898.5601 | C2015-08 Garden Center.xlsx
168 | 163 | plafondtegels | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
169 | 198 | Fase 2 | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 101065.0415 |  | 102d | [5 empty] | 86521.6012 |  | 1 |  | 101065.0415 | 101065.0415 | C2015-08 Garden Center.xlsx
170 | 165 | inrichting winkel | 2014-09-29 08:00 | 2014-10-10 17:00 | 10d |  | 0 | 0 | 31.45 | 2516.0001 | 2516.0001 | 2014-09-30 08:00 | 10d | 2516.0001 | 0 | 0 | 0 | 0 | 2516.0001 | 0 | 1 | Finished | 2516.0001 | 2516.0001 | C2015-08 Garden Center.xlsx
171 | 166 | inrichting kantoor | 2014-10-08 08:00 | 2014-10-14 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-09 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 1 | Finished | 1258 | 1258 | C2015-08 Garden Center.xlsx
172 | 167 | ontmanteling bestaande winkel | 2014-10-13 08:00 | 2014-10-17 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-14 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 1 | Finished | 1258 | 1258 | C2015-08 Garden Center.xlsx
173 | 168 | sloop bestaande winkel | 2014-10-20 08:00 | 2014-10-24 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-21 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 1 | Finished | 1258 | 1258 | C2015-08 Garden Center.xlsx
174 | 169 | voorlopige wand te behouden | 2014-10-21 08:00 | 2014-10-22 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 | 2014-10-22 08:00 | 2d | 503.2 | 0 | 0 | 0 | 0 | 503.2 | 0 | 1 | Finished | 503.2 | 503.2 | C2015-08 Garden Center.xlsx
175 | 170 | uitzetten assen en grondwerk | 2014-10-27 08:00 | 2014-10-27 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-11-12 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 1 | Finished | 1329.52 | 1329.52 | C2015-08 Garden Center.xlsx
176 | 171 | inzagen van bestaande beton | 2014-10-28 08:00 | 2014-10-29 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-11-13 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 1 | Finished | 2659.04 | 2659.04 | C2015-08 Garden Center.xlsx
177 | 172 | uitzetten paalfundering | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-11-17 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 1 | Finished | 1329.52 | 1329.52 | C2015-08 Garden Center.xlsx
178 | 173 | maken van paalfundering | 2014-11-04 08:00 | 2014-11-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-11-19 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 1 | Finished | 2659.04 | 2659.04 | C2015-08 Garden Center.xlsx
179 | 174 | akoestisch doormeten | 2014-11-13 08:00 | 2014-11-13 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-11-21 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 1 | Finished | 1329.52 | 1329.52 | C2015-08 Garden Center.xlsx
180 | 175 | maken van fundering | 2014-11-17 08:00 | 2014-11-18 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-11-24 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 1 | Finished | 2659.04 | 2659.04 | C2015-08 Garden Center.xlsx
181 | 176 | staalconstructie fase 2 | 2014-11-21 08:00 | 2014-11-24 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-11-28 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 1 | Finished | 2557.76 | 2557.76 | C2015-08 Garden Center.xlsx
182 | 177 | houten spanten | 2014-11-25 08:00 | 2014-11-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-12-02 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 1 | Finished | 2557.76 | 2557.76 | C2015-08 Garden Center.xlsx
183 | 178 | afmontage staal | 2014-11-27 08:00 | 2014-11-28 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-12-04 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 1 | Finished | 2557.76 | 2557.76 | C2015-08 Garden Center.xlsx
184 | 179 | prefabplinten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-12-09 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 1 | Finished | 2557.76 | 2557.76 | C2015-08 Garden Center.xlsx
185 | 180 | voorbereidingen wand | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-12-11 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 1 | Finished | 1833.76 | 1833.76 | C2015-08 Garden Center.xlsx
186 | 181 | sandwichwand | 2014-12-05 08:00 | 2014-12-10 17:00 | 4d |  | 0 | 0 | 114.61 | 3667.52 | 3667.52 | 2014-12-15 08:00 | 4d | 3667.52 | 0 | 0 | 0 | 0 | 3667.52 | 0 | 1 | Finished | 3667.52 | 3667.52 | C2015-08 Garden Center.xlsx
187 | 182 | veiligheidsnetten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-12-09 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 1 | Finished | 2659.04 | 2659.04 | C2015-08 Garden Center.xlsx
188 | 183 | dakplaten plaatsen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-12-10 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 1 | Finished | 3988.5601 | 3988.5601 | C2015-08 Garden Center.xlsx
189 | 184 | dakbedekking | 2014-12-04 08:00 | 2014-12-17 17:00 | 10d |  | 0 | 0 | 166.19 | 13295.2002 | 13295.2002 | 2014-12-15 08:00 | 10d | 13295.2002 | 0 | 0 | 0 | 0 | 13295.2002 | 0 | 1 | Finished | 13295.2002 | 13295.2002 | C2015-08 Garden Center.xlsx
190 | 185 | plaatsing rookluiken | 2014-12-25 08:00 | 2014-12-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2015-02-12 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
191 | 186 | plaatsing rookscherm | 2014-12-29 08:00 | 2014-12-30 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2015-02-16 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
192 | 187 | grondwerk blinde vlek | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-12-11 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 1 | Finished | 2659.04 | 2659.04 | C2015-08 Garden Center.xlsx
193 | 188 | ondervloer tussen gebouwen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-12-11 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 1 | Finished | 3988.5601 | 3988.5601 | C2015-08 Garden Center.xlsx
194 | 189 | technieken onder dak | 2014-06-04 08:00 | 2014-06-12 17:00 | 7d |  | 0 | 0 | 118.75 | 6650 | 6650 | 2014-12-15 08:00 | 7d | 6650 | 0 | 0 | 0 | 0 | 6650 | 0 | 1 | Finished | 6650 | 6650 | C2015-08 Garden Center.xlsx
195 | 190 | uitvullaag | 2015-01-05 08:00 | 2015-01-06 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2015-01-05 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 1449.28 | 1449.28 | C2015-08 Garden Center.xlsx
196 | 191 | stellen dillatieprofielen | 2015-01-14 08:00 | 2015-01-16 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2015-01-14 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 1 | Finished | 2173.92 | 2173.92 | C2015-08 Garden Center.xlsx
197 | 192 | folie en vloerverwarming | 2015-01-14 08:00 | 2015-01-20 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2015-01-14 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 1 | Finished | 3623.2001 | 3623.2001 | C2015-08 Garden Center.xlsx
198 | 193 | polybetonvloer | 2015-01-21 08:00 | 2015-01-21 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2015-01-21 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
199 | 194 | afwerkingsformule beton | 2015-01-22 08:00 | 2015-01-22 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2015-01-22 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 724.64 | 724.64 | C2015-08 Garden Center.xlsx
200 | 195 | afwerkingslaag beton | 2015-01-22 08:00 | 2015-02-18 17:00 | 20d |  | 0 | 0 | 90.58 | 14492.8003 | 14492.8003 | 2015-02-11 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 1 | Finished | 14492.8003 | 14492.8003 | C2015-08 Garden Center.xlsx
201 | 196 | afbouw technieken dak | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2015-02-12 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 1 | Finished | 3623.2001 | 3623.2001 | C2015-08 Garden Center.xlsx
202 | 197 | winkelinrichting | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2015-02-12 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 1 | Finished | 3623.2001 | 3623.2001 | C2015-08 Garden Center.xlsx
4 | 0 | Railway Station (2) | 2012-11-05 08:00 | 2014-03-13 17:00 | 354d |  |  | 0 |  |  | 1457423.999 |  | 569d 1h | [5 empty] | 2145682.2591 |  | 1 |  | 1457423.999 | 1457423.999 | C2015-09 Railway Station (2).xlsx
5 | 13 | voorbereidende werken | 2012-11-05 08:00 | 2012-12-14 17:00 | 30d |  |  | 0 |  |  | 155859.5994 |  | 118d | [5 empty] | 208523.269 |  | 1 |  | 155859.5994 | 155859.5994 | C2015-09 Railway Station (2).xlsx
6 | 1 | beschoeide sleuf | 2012-11-05 08:00 | 2012-11-19 17:00 | 11d |  | 0 | 0 | 263.31 | 23171.2798 | 23171.2798 | 2012-11-05 08:00 | 11d | 23171.2798 | 0 | 0 | 0 | 0 | 23171.2798 | 0 | 1 | Finished | 23171.2798 | 23171.2798 | C2015-09 Railway Station (2).xlsx
7 | 2 | funderingen voor tijdelijke structuur bovenleidingen | 2012-11-08 08:00 | 2012-11-19 17:00 | 8d |  | 0 | 0 | 263.31 | 16851.8398 | 16851.8398 | 2012-11-08 08:00 | 8d | 16851.8398 | 0 | 0 | 0 | 0 | 16851.8398 | 0 | 1 | Finished | 16851.8398 | 16851.8398 | C2015-09 Railway Station (2).xlsx
8 | 3 | tijdelijke structuur overname bovenleiding | 2012-11-09 08:00 | 2012-11-19 17:00 | 7d |  | 0 | 0 | 263.31 | 14745.3599 | 14745.3599 | 2012-11-09 08:00 | 7d | 14745.3599 | 0 | 0 | 0 | 0 | 14745.3599 | 0 | 1 | Finished | 14745.3599 | 14745.3599 | C2015-09 Railway Station (2).xlsx
9 | 4 | aanpassing doorgang mindervaliden perron A | 2012-11-12 08:00 | 2012-11-20 17:00 | 7d |  | 0 | 0 | 263.31 | 14745.3599 | 14745.3599 | 2012-11-12 08:00 | 7d | 14745.3599 | 0 | 0 | 0 | 0 | 14745.3599 | 0 | 1 | Finished | 14745.3599 | 14745.3599 | C2015-09 Railway Station (2).xlsx
10 | 5 | overdracht spoor D | 2012-11-09 08:00 | 2012-11-09 17:00 | 1d |  | 0 | 0 | 263.31 | 2106.48 | 2106.48 | 2012-11-09 08:00 | 1d | 2106.48 | 0 | 0 | 0 | 0 | 2106.48 | 0 | 1 | Finished | 2106.48 | 2106.48 | C2015-09 Railway Station (2).xlsx
11 | 6 | plaatsing oranje veiligheidsnet | 2012-11-12 08:00 | 2012-11-19 17:00 | 6d |  | 0 | 0 | 263.31 | 12638.8799 | 12638.8799 | 2012-11-12 08:00 | 6d | 12638.8799 | 0 | 0 | 0 | 0 | 12638.8799 | 0 | 1 | Finished | 12638.8799 | 12638.8799 | C2015-09 Railway Station (2).xlsx
12 | 7 | aanpassing signalisatie perron A | 2012-11-26 08:00 | 2012-12-07 17:00 | 10d |  | 0 | 0 | 263.31 | 21064.7998 | 21064.7998 | 2012-11-26 08:00 | 10d | 21064.7998 | 0 | 0 | 0 | 0 | 21064.7998 | 0 | 1 | Finished | 21064.7998 | 21064.7998 | C2015-09 Railway Station (2).xlsx
13 | 8 | opritten toegang spoorniveau | 2012-11-26 08:00 | 2012-12-11 17:00 | 12d |  | 0 | 0 | 263.1 | 25257.6006 | 25257.6006 | 2012-11-26 08:00 | 12d | 25257.6006 | 0 | 0 | 0 | 0 | 25257.6006 | 0 | 1 | Finished | 25257.6006 | 25257.6006 | C2015-09 Railway Station (2).xlsx
14 | 9 | Afsluiting zone werf (perron A) | 2012-11-29 08:00 | 2012-12-14 17:00 | 12d |  | 0 | 0 | 263.31 | 25277.7598 | 25277.7598 | 2012-11-29 08:00 | 12d | 25277.7598 | 0 | 0 | 0 | 0 | 25277.7598 | 0 | 1 | Finished | 25277.7598 | 25277.7598 | C2015-09 Railway Station (2).xlsx
15 | 10 | nieuwe verlichting perron A | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-12-07 08:00 | 1d | 0.08 | 0 | 0 | 2106.3999 | 0 | 2106.4799 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
16 | 11 | Fundering voor torenkraan | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-03-18 08:00 | 15d | 1.2 | 0 | 0 | 31597.1992 | 0 | 31598.3992 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
17 | 12 | Installatie torenkraan | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-04-05 08:00 | 9d | 0.72 | 0 | 0 | 18958.3105 | 0 | 18959.0305 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
18 | 65 | Grondwerken | 2012-11-05 08:00 | 2013-06-07 17:00 | 155d |  |  | 0 |  |  | 69219.9192 |  | 563d 1h | [5 empty] | 38603.9796 |  | 1 |  | 69219.9192 | 69219.9192 | C2015-09 Railway Station (2).xlsx
19 | 24 | Zone 1 | 2012-11-05 08:00 | 2013-02-26 17:00 | 82d |  |  | 0 |  |  | 12281.5999 |  | 113d | [5 empty] | 10815.4399 |  | 1 |  | 12281.5999 | 12281.5999 | C2015-09 Railway Station (2).xlsx
20 | 14 | opbraakwerken perron | 2012-12-03 08:00 | 2012-12-18 17:00 | 12d |  | 0 | 0 | 6.12 | 587.52 | 587.52 | 2012-12-03 08:00 | 12d | 587.52 | 0 | 0 | 0 | 0 | 587.52 | 0 | 1 | Finished | 587.52 | 587.52 | C2015-09 Railway Station (2).xlsx
21 | 15 | beschoeiing | 2012-12-10 08:00 | 2013-01-17 17:00 | 29d |  | 0 | 0 | 14.41 | 3343.12 | 3343.12 | 2013-01-17 08:00 | 18d | 2075.04 | 0 | 0 | 0 | 0 | 2075.04 | 0 | 1 | Finished | 3343.12 | 3343.12 | C2015-09 Railway Station (2).xlsx
22 | 16 | afbraakwerken luifel | 2012-12-14 08:00 | 2013-01-14 17:00 | 22d |  | 0 | 0 | 6.12 | 1077.12 | 1077.12 | 2013-01-14 08:00 | 12d | 587.52 | 0 | 0 | 0 | 0 | 587.52 | 0 | 1 | Finished | 1077.12 | 1077.12 | C2015-09 Railway Station (2).xlsx
23 | 17 | beschoeiing | 2013-01-07 08:00 | 2013-01-31 17:00 | 19d |  | 0 | 0 | 14.41 | 2190.32 | 2190.32 | 2013-01-29 08:00 | 19d | 2190.32 | 0 | 0 | 0 | 0 | 2190.32 | 0 | 1 | Finished | 2190.32 | 2190.32 | C2015-09 Railway Station (2).xlsx
24 | 18 | grondwerken | 2013-01-18 08:00 | 2013-01-31 17:00 | 10d |  | 0 | 0 | 14.41 | 1152.8 | 1152.8 | 2013-01-31 08:00 | 9d | 1037.52 | 0 | 0 | 0 | 0 | 1037.52 | 0 | 1 | Finished | 1152.8 | 1152.8 | C2015-09 Railway Station (2).xlsx
25 | 19 | verankering beschoeiing | 2013-01-24 08:00 | 2013-01-29 17:00 | 4d |  | 0 | 0 | 14.41 | 461.12 | 461.12 | 2013-02-07 08:00 | 4d | 461.12 | 0 | 0 | 0 | 0 | 461.12 | 0 | 1 | Finished | 461.12 | 461.12 | C2015-09 Railway Station (2).xlsx
26 | 20 | grondwerken | 2013-01-28 08:00 | 2013-02-12 17:00 | 12d |  | 0 | 0 | 14.41 | 1383.36 | 1383.36 | 2013-02-11 08:00 | 12d | 1383.36 | 0 | 0 | 0 | 0 | 1383.36 | 0 | 1 | Finished | 1383.36 | 1383.36 | C2015-09 Railway Station (2).xlsx
27 | 21 | aanpassing oprit toegang naar spoor | 2013-02-05 08:00 | 2013-02-21 17:00 | 13d |  | 0 | 0 | 14.41 | 1498.64 | 1498.64 | 2013-04-24 08:00 | 11d | 1268.08 | 0 | 0 | 0 | 0 | 1268.08 | 0 | 1 | Finished | 1498.64 | 1498.64 | C2015-09 Railway Station (2).xlsx
28 | 22 | afbraak wegtunnel | 2013-02-11 08:00 | 2013-02-26 17:00 | 12d |  | 0 | 0 | 6.12 | 587.52 | 587.52 | 2013-03-21 08:00 | 12d | 587.52 | 0 | 0 | 0 | 0 | 587.52 | 0 | 1 | Finished | 587.52 | 587.52 | C2015-09 Railway Station (2).xlsx
29 | 23 | afbraak wegtunnel | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-02-19 08:00 | 13d | 1.04 | 0 | 0 | 636.4 | 0 | 637.44 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
30 | 41 | Zone 2 | 2012-11-05 08:00 | 2013-06-07 17:00 | 155d |  |  | 0 |  |  | 39355.0396 |  | 563d 1h | [5 empty] | 13920.2299 |  | 1 |  | 39355.0396 | 39355.0396 | C2015-09 Railway Station (2).xlsx
31 | 25 | beschoeide sleuf | 2012-11-13 08:00 | 2012-12-06 17:00 | 18d |  | 0 | 0 | 14.41 | 2075.04 | 2075.04 | 2012-11-13 08:00 | 18d | 2075.04 | 0 | 0 | 0 | 0 | 2075.04 | 0 | 1 | Finished | 2075.04 | 2075.04 | C2015-09 Railway Station (2).xlsx
32 | 26 | opbraakwerken perron | 2012-12-11 08:00 | 2013-01-18 17:00 | 29d |  | 0 | 0 | 6.12 | 1419.84 | 1419.84 | 2013-01-21 08:00 | 19d | 930.24 | 0 | 0 | 0 | 0 | 930.24 | 0 | 1 | Finished | 1419.84 | 1419.84 | C2015-09 Railway Station (2).xlsx
33 | 27 | afbraakwerken luifel | 2013-01-07 08:00 | 2013-01-31 17:00 | 19d |  | 0 | 0 | 6.12 | 930.24 | 930.24 | 2013-01-24 08:00 | 16d | 783.36 | 0 | 0 | 0 | 0 | 783.36 | 0 | 1 | Finished | 930.24 | 930.24 | C2015-09 Railway Station (2).xlsx
34 | 28 | beschoeide sleuf | 2012-12-03 08:00 | 2013-01-10 17:00 | 29d |  | 0 | 0 | 14.41 | 3343.12 | 3343.12 | 2013-01-31 08:00 | 18d | 2075.04 | 0 | 0 | 0 | 0 | 2075.04 | 0 | 1 | Finished | 3343.12 | 3343.12 | C2015-09 Railway Station (2).xlsx
35 | 29 | grondwerken perron op volle grond | 2012-12-11 08:00 | 2013-01-28 17:00 | 35d |  | 0 | 0 | 14.41 | 4034.8 | 4034.8 | 2015-01-09 08:00 | 1h | 14.41 | 0 | 0 | 0 | 0 | 14.41 | 0 | 1 | Finished | 4034.8 | 4034.8 | C2015-09 Railway Station (2).xlsx
36 | 30 | eerste wand koker in perron op volle grond | 2012-12-20 08:00 | 2013-02-14 17:00 | 41d |  | 0 | 0 | 14.41 | 4726.4799 | 4726.4799 | 2015-01-09 08:00 | 1h | 14.41 | 0 | 0 | 0 | 0 | 14.41 | 0 | 1 | Finished | 4726.4799 | 4726.4799 | C2015-09 Railway Station (2).xlsx
37 | 31 | beschoeiiing funderingen palen bovenleiding | 2013-01-11 08:00 | 2013-01-28 17:00 | 12d |  | 0 | 0 | 14.41 | 1383.36 | 1383.36 | 2015-01-09 08:00 | 1h | 14.41 | 0 | 0 | 0 | 0 | 14.41 | 0 | 1 | Finished | 1383.36 | 1383.36 | C2015-09 Railway Station (2).xlsx
38 | 32 | funderingsmassieven in perron | 2013-01-29 08:00 | 2013-03-04 17:00 | 25d |  | 0 | 0 | 14.41 | 2882 | 2882 | 2015-01-09 08:00 | 1h | 14.41 | 0 | 0 | 0 | 0 | 14.41 | 0 | 1 | Finished | 2882 | 2882 | C2015-09 Railway Station (2).xlsx
39 | 33 | perron volle grond | 2013-02-15 08:00 | 2013-04-15 17:00 | 42d |  | 0 | 0 | 14.41 | 4841.7599 | 4841.7599 | 2015-01-09 08:00 | 1h | 14.41 | 0 | 0 | 0 | 0 | 14.41 | 0 | 1 | Finished | 4841.7599 | 4841.7599 | C2015-09 Railway Station (2).xlsx
40 | 34 | eerste wand koker in perron volle grond | 2013-03-22 08:00 | 2013-04-29 17:00 | 27d |  | 0 | 0 | 14.41 | 3112.56 | 3112.56 | 2015-01-09 08:00 | 1h | 14.41 | 0 | 0 | 0 | 0 | 14.41 | 0 | 1 | Finished | 3112.56 | 3112.56 | C2015-09 Railway Station (2).xlsx
41 | 35 | perron volle grond | 2013-04-18 08:00 | 2013-06-07 17:00 | 37d |  | 0 | 0 | 14.41 | 4265.36 | 4265.36 | 2015-01-09 08:00 | 1h | 14.41 | 0 | 0 | 0 | 0 | 14.41 | 0 | 1 | Finished | 4265.36 | 4265.36 | C2015-09 Railway Station (2).xlsx
42 | 36 | beschoeiing | 2013-01-18 08:00 | 2013-02-12 17:00 | 18d |  | 0 | 0 | 14.41 | 2075.04 | 2075.04 | 2013-03-04 08:00 | 18d | 2075.04 | 0 | 0 | 0 | 0 | 2075.04 | 0 | 1 | Finished | 2075.04 | 2075.04 | C2015-09 Railway Station (2).xlsx
43 | 37 | grondwerken | 2013-02-05 08:00 | 2013-02-21 17:00 | 13d |  | 0 | 0 | 14.41 | 1498.64 | 1498.64 | 2013-03-25 08:00 | 12d | 1383.36 | 0 | 0 | 0 | 0 | 1383.36 | 0 | 1 | Finished | 1498.64 | 1498.64 | C2015-09 Railway Station (2).xlsx
44 | 38 | verankering beschoeiing | 2013-02-11 08:00 | 2013-02-18 17:00 | 6d |  | 0 | 0 | 14.41 | 691.68 | 691.68 | 2013-03-28 08:00 | 7d | 806.96 | 0 | 0 | 0 | 0 | 806.96 | 0 | 1 | Finished | 691.68 | 691.68 | C2015-09 Railway Station (2).xlsx
45 | 39 | grondwerken | 2013-02-14 08:00 | 2013-03-11 17:00 | 18d |  | 0 | 0 | 14.41 | 2075.04 | 2075.04 | 2013-04-08 08:00 | 15d | 1729.2 | 0 | 0 | 0 | 0 | 1729.2 | 0 | 1 | Finished | 2075.04 | 2075.04 | C2015-09 Railway Station (2).xlsx
46 | 40 | Afbraakwerken wegtunnel | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-03-28 08:00 | 17d | 1.36 | 0 | 0 | 1959.76 | 0 | 1961.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
47 | 50 | Zone 3 | 2012-12-21 08:00 | 2013-03-26 17:00 | 68d |  |  | 0 |  |  | 6402.2399 |  | 506d 1h | [5 empty] | 1469.19 |  | 1 |  | 6402.2399 | 6402.2399 | C2015-09 Railway Station (2).xlsx
48 | 42 | Opbraakwerken perron | 2012-12-21 08:00 | 2013-01-21 17:00 | 22d |  | 0 | 0 | 6.12 | 1077.12 | 1077.12 | 2013-01-31 08:00 | 12d | 587.52 | 0 | 0 | 0 | 0 | 587.52 | 0 | 1 | Finished | 1077.12 | 1077.12 | C2015-09 Railway Station (2).xlsx
49 | 43 | afbraakwerken luifel | 2013-01-17 08:00 | 2013-02-01 17:00 | 12d |  | 0 | 0 | 6.12 | 587.52 | 587.52 | 2013-02-04 08:00 | 12d | 587.52 | 0 | 0 | 0 | 0 | 587.52 | 0 | 1 | Finished | 587.52 | 587.52 | C2015-09 Railway Station (2).xlsx
50 | 44 | Afbraakwerken reizigerstunnel | 2013-02-18 08:00 | 2013-02-21 17:00 | 4d |  | 0 | 0 | 6.12 | 195.84 | 195.84 | 2013-03-25 08:00 | 2d | 97.92 | 0 | 0 | 0 | 0 | 97.92 | 0 | 1 | Finished | 195.84 | 195.84 | C2015-09 Railway Station (2).xlsx
51 | 45 | Voorlopige trap toegang perron A | 2013-02-18 08:00 | 2013-03-05 17:00 | 12d |  | 0 | 0 | 14.41 | 1383.36 | 1383.36 | 2015-01-09 08:00 | 1h | 14.41 | 0 | 0 | 0 | 0 | 14.41 | 0 | 1 | Finished | 1383.36 | 1383.36 | C2015-09 Railway Station (2).xlsx
52 | 46 | Afbraakwerken reizigerstunnel | 2013-03-04 08:00 | 2013-03-07 17:00 | 4d |  | 0 | 0 | 6.12 | 195.84 | 195.84 | 2013-04-17 08:00 | 3d | 146.88 | 0 | 0 | 0 | 0 | 146.88 | 0 | 1 | Finished | 195.84 | 195.84 | C2015-09 Railway Station (2).xlsx
53 | 47 | Voorlopige toegang perron A | 2013-03-04 08:00 | 2013-03-19 17:00 | 12d |  | 0 | 0 | 14.41 | 1383.36 | 1383.36 | 2015-01-09 08:00 | 1h | 14.41 | 0 | 0 | 0 | 0 | 14.41 | 0 | 1 | Finished | 1383.36 | 1383.36 | C2015-09 Railway Station (2).xlsx
54 | 48 | Afbraakwerken reizigerstunnel | 2013-03-11 08:00 | 2013-03-14 17:00 | 4d |  | 0 | 0 | 6.12 | 195.84 | 195.84 | 2015-01-09 08:00 | 1h | 6.12 | 0 | 0 | 0 | 0 | 6.12 | 0 | 1 | Finished | 195.84 | 195.84 | C2015-09 Railway Station (2).xlsx
55 | 49 | grondwerken onder reizigerstunnel | 2013-03-11 08:00 | 2013-03-26 17:00 | 12d |  | 0 | 0 | 14.41 | 1383.36 | 1383.36 | 2015-01-09 08:00 | 1h | 14.41 | 0 | 0 | 0 | 0 | 14.41 | 0 | 1 | Finished | 1383.36 | 1383.36 | C2015-09 Railway Station (2).xlsx
56 | 64 | Zone 4 | 2012-11-05 08:00 | 2013-04-03 17:00 | 108d |  |  | 0 |  |  | 11181.0399 |  | 207d | [5 empty] | 12399.1199 |  | 1 |  | 11181.0399 | 11181.0399 | C2015-09 Railway Station (2).xlsx
57 | 51 | opbraakwerken perron | 2013-01-11 08:00 | 2013-02-05 17:00 | 18d |  | 0 | 0 | 6.12 | 881.28 | 881.28 | 2013-02-04 08:00 | 19d | 930.24 | 0 | 0 | 0 | 0 | 930.24 | 0 | 1 | Finished | 881.28 | 881.28 | C2015-09 Railway Station (2).xlsx
58 | 52 | afbraakwerken luifel | 2013-01-24 08:00 | 2013-02-08 17:00 | 12d |  | 0 | 0 | 6.12 | 587.52 | 587.52 | 2013-02-11 08:00 | 12d | 587.52 | 0 | 0 | 0 | 0 | 587.52 | 0 | 1 | Finished | 587.52 | 587.52 | C2015-09 Railway Station (2).xlsx
59 | 53 | beschoeiing luifel | 2013-02-01 08:00 | 2013-03-07 17:00 | 25d |  | 0 | 0 | 14.41 | 2882 | 2882 | 2013-03-25 08:00 | 22d | 2536.16 | 0 | 0 | 0 | 0 | 2536.16 | 0 | 1 | Finished | 2882 | 2882 | C2015-09 Railway Station (2).xlsx
60 | 54 | grondwerken | 2013-02-19 08:00 | 2013-03-07 17:00 | 13d |  | 0 | 0 | 14.41 | 1498.64 | 1498.64 | 2013-04-04 08:00 | 10d | 1152.8 | 0 | 0 | 0 | 0 | 1152.8 | 0 | 1 | Finished | 1498.64 | 1498.64 | C2015-09 Railway Station (2).xlsx
61 | 55 | verankering beschoeiing | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 14.41 | 576.4 | 576.4 | 2013-04-09 08:00 | 4d | 461.12 | 0 | 0 | 0 | 0 | 461.12 | 0 | 1 | Finished | 576.4 | 576.4 | C2015-09 Railway Station (2).xlsx
62 | 56 | grondwerken tussen reizigers/dienst tunnel | 2013-02-28 08:00 | 2013-03-15 17:00 | 12d |  | 0 | 0 | 14.41 | 1383.36 | 1383.36 | 2013-04-11 08:00 | 10d | 1152.8 | 0 | 0 | 0 | 0 | 1152.8 | 0 | 1 | Finished | 1383.36 | 1383.36 | C2015-09 Railway Station (2).xlsx
63 | 57 | grondwerken tussen dienst/tram tunnel | 2013-03-07 08:00 | 2013-03-22 17:00 | 12d |  | 0 | 0 | 14.41 | 1383.36 | 1383.36 | 2013-04-17 08:00 | 10d | 1152.8 | 0 | 0 | 0 | 0 | 1152.8 | 0 | 1 | Finished | 1383.36 | 1383.36 | C2015-09 Railway Station (2).xlsx
64 | 58 | afbraakwerken diensttunnel | 2013-03-15 08:00 | 2013-03-21 17:00 | 5d |  | 0 | 0 | 6.12 | 244.8 | 244.8 | 2013-04-24 08:00 | 4d | 195.84 | 0 | 0 | 0 | 0 | 195.84 | 0 | 1 | Finished | 244.8 | 244.8 | C2015-09 Railway Station (2).xlsx
65 | 59 | afbraakwerken tramtunnel | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 6.12 | 244.8 | 244.8 | 2013-04-15 08:00 | 2d | 97.92 | 0 | 0 | 0 | 0 | 97.92 | 0 | 1 | Finished | 244.8 | 244.8 | C2015-09 Railway Station (2).xlsx
66 | 60 | voorlopige toegang perron A | 2013-03-18 08:00 | 2013-04-03 17:00 | 13d |  | 0 | 0 | 14.41 | 1498.64 | 1498.64 | 2013-11-04 08:00 | 12d | 1383.36 | 0 | 0 | 0 | 0 | 1383.36 | 0 | 1 | Finished | 1498.64 | 1498.64 | C2015-09 Railway Station (2).xlsx
67 | 61 | beschoeiing aansluitend diensttunnel | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-04-12 08:00 | 12d | 0.96 | 0 | 0 | 1383.36 | 0 | 1384.32 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
68 | 62 | Afbraakwerken wand en vloerplaat tramtunnel | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-04-15 08:00 | 8d | 0.64 | 0 | 0 | 922.24 | 0 | 922.88 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
69 | 63 | Afbraakwerken wand en vloerplaat tramtunnel | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-04-22 08:00 | 9d | 0.72 | 0 | 0 | 440.64 | 0 | 441.36 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
70 | 89 | Funderingen | 2013-01-28 08:00 | 2013-06-28 10:00 | 109d 2h |  |  | 0 |  |  | 29034.7197 |  | 125d | [5 empty] | 28142.3997 |  | 1 |  | 29034.7197 | 29034.7197 | C2015-09 Railway Station (2).xlsx
71 | 70 | Zone 1 | 2013-02-07 08:00 | 2013-04-18 17:00 | 51d |  |  | 0 |  |  | 5971.6799 |  | 70d | [5 empty] | 5834.3999 |  | 1 |  | 5971.6799 | 5971.6799 | C2015-09 Railway Station (2).xlsx
72 | 66 | Diepe funderingen | 2013-02-07 08:00 | 2013-03-04 17:00 | 18d |  | 0 | 0 | 8.58 | 1235.52 | 1235.52 | 2013-03-05 08:00 | 18d | 1235.52 | 0 | 0 | 0 | 0 | 1235.52 | 0 | 1 | Finished | 1235.52 | 1235.52 | C2015-09 Railway Station (2).xlsx
73 | 67 | Funderingsmassieven | 2013-02-14 08:00 | 2013-03-22 17:00 | 27d |  | 0 | 0 | 8.58 | 1853.28 | 1853.28 | 2013-04-03 08:00 | 23d | 1578.72 | 0 | 0 | 0 | 0 | 1578.72 | 0 | 1 | Finished | 1853.28 | 1853.28 | C2015-09 Railway Station (2).xlsx
74 | 68 | Diepe funderingen | 2013-03-07 08:00 | 2013-03-29 17:00 | 17d |  | 0 | 0 | 8.58 | 1166.88 | 1166.88 | 2013-04-29 08:00 | 19d | 1304.16 | 0 | 0 | 0 | 0 | 1304.16 | 0 | 1 | Finished | 1166.88 | 1166.88 | C2015-09 Railway Station (2).xlsx
75 | 69 | Funderingsmassieven | 2013-03-15 08:00 | 2013-04-18 17:00 | 25d |  | 0 | 0 | 8.58 | 1716 | 1716 | 2013-05-07 08:00 | 25d | 1716 | 0 | 0 | 0 | 0 | 1716 | 0 | 1 | Finished | 1716 | 1716 | C2015-09 Railway Station (2).xlsx
76 | 81 | Zone 2 | 2013-01-28 08:00 | 2013-06-28 10:00 | 109d 2h |  |  | 0 |  |  | 13522.0799 |  | 125d | [5 empty] | 13178.8799 |  | 1 |  | 13522.0799 | 13522.0799 | C2015-09 Railway Station (2).xlsx
77 | 71 | VP GV onder lichtstraat | 2013-01-28 08:00 | 2013-02-21 17:00 | 19d |  | 0 | 0 | 8.58 | 1304.16 | 1304.16 | 2013-02-28 08:00 | 16d | 1098.24 | 0 | 0 | 0 | 0 | 1098.24 | 0 | 1 | Finished | 1304.16 | 1304.16 | C2015-09 Railway Station (2).xlsx
78 | 72 | VP GV onder lichtstraat (deel 2) | 2013-02-15 08:00 | 2013-03-12 17:00 | 18d |  | 0 | 0 | 8.58 | 1235.52 | 1235.52 | 2013-05-21 08:00 | 15d | 1029.6 | 0 | 0 | 0 | 0 | 1029.6 | 0 | 1 | Finished | 1235.52 | 1235.52 | C2015-09 Railway Station (2).xlsx
79 | 73 | VP GV onder lichtstraat (deel 3) | 2013-03-01 08:00 | 2013-03-26 17:00 | 18d |  | 0 | 0 | 8.58 | 1235.52 | 1235.52 | 2013-05-13 08:00 | 16d | 1098.24 | 0 | 0 | 0 | 0 | 1098.24 | 0 | 1 | Finished | 1235.52 | 1235.52 | C2015-09 Railway Station (2).xlsx
80 | 74 | VP GV onder lichtstraat (deel 4) | 2013-03-05 08:00 | 2013-04-08 17:00 | 25d |  | 0 | 0 | 8.58 | 1716 | 1716 | 2013-05-02 08:00 | 23d | 1578.72 | 0 | 0 | 0 | 0 | 1578.72 | 0 | 1 | Finished | 1716 | 1716 | C2015-09 Railway Station (2).xlsx
81 | 75 | Installaties voor baretten | 2013-02-19 08:00 | 2013-02-26 17:00 | 6d |  | 0 | 0 | 8.58 | 411.84 | 411.84 | 2013-04-11 08:00 | 5d | 343.2 | 0 | 0 | 0 | 0 | 343.2 | 0 | 1 | Finished | 411.84 | 411.84 | C2015-09 Railway Station (2).xlsx
82 | 76 | Baretten | 2013-02-28 08:00 | 2013-04-04 17:00 | 26d |  | 0 | 0 | 8.58 | 1784.64 | 1784.64 | 2013-04-18 08:00 | 25d | 1716 | 0 | 0 | 0 | 0 | 1716 | 0 | 1 | Finished | 1784.64 | 1784.64 | C2015-09 Railway Station (2).xlsx
83 | 77 | VP op stross 1 | 2013-04-04 08:00 | 2013-05-13 17:00 | 28d |  | 0 | 0 | 8.58 | 1921.92 | 1921.92 | 2013-05-21 08:00 | 25d | 1716 | 0 | 0 | 0 | 0 | 1716 | 0 | 1 | Finished | 1921.92 | 1921.92 | C2015-09 Railway Station (2).xlsx
84 | 78 | VP op stross 2 | 2013-04-30 10:00 | 2013-05-24 10:00 | 18d |  | 0 | 0 | 8.58 | 1235.52 | 1235.52 | 2013-06-27 08:00 | 15d | 1029.6 | 0 | 0 | 0 | 0 | 1029.6 | 0 | 1 | Finished | 1235.52 | 1235.52 | C2015-09 Railway Station (2).xlsx
85 | 79 | VP op stross 3 | 2013-05-15 10:00 | 2013-06-12 10:00 | 20d |  | 0 | 0 | 8.58 | 1372.8 | 1372.8 | 2013-07-09 08:00 | 32d | 2196.48 | 0 | 0 | 0 | 0 | 2196.48 | 0 | 1 | Finished | 1372.8 | 1372.8 | C2015-09 Railway Station (2).xlsx
86 | 80 | VP op stross 4 | 2013-06-03 10:00 | 2013-06-28 10:00 | 19d |  | 0 | 0 | 8.58 | 1304.16 | 1304.16 | 2013-06-11 08:00 | 20d | 1372.8 | 0 | 0 | 0 | 0 | 1372.8 | 0 | 1 | Finished | 1304.16 | 1304.16 | C2015-09 Railway Station (2).xlsx
87 | 88 | Zone 3 | 2013-03-21 08:00 | 2013-06-11 17:00 | 59d |  |  | 0 |  |  | 9540.9599 |  | 64d | [5 empty] | 9129.1199 |  | 1 |  | 9540.9599 | 9540.9599 | C2015-09 Railway Station (2).xlsx
88 | 82 | VP GV onder lichtstraat (deel 5) | 2013-03-26 08:00 | 2013-04-17 17:00 | 17d |  | 0 | 0 | 8.58 | 1166.88 | 1166.88 | 2013-05-28 08:00 | 15d | 1029.6 | 0 | 0 | 0 | 0 | 1029.6 | 0 | 1 | Finished | 1166.88 | 1166.88 | C2015-09 Railway Station (2).xlsx
89 | 83 | VP GV onder lichtstraat (deel 6) | 2013-03-29 08:00 | 2013-05-02 17:00 | 25d |  | 0 | 0 | 8.58 | 1716 | 1716 | 2013-05-30 08:00 | 22d | 1510.08 | 0 | 0 | 0 | 0 | 1510.08 | 0 | 1 | Finished | 1716 | 1716 | C2015-09 Railway Station (2).xlsx
90 | 84 | Baretten | 2013-03-21 08:00 | 2013-04-19 17:00 | 22d |  | 0 | 0 | 8.58 | 1510.08 | 1510.08 | 2013-05-17 08:00 | 21d | 1441.44 | 0 | 0 | 0 | 0 | 1441.44 | 0 | 1 | Finished | 1510.08 | 1510.08 | C2015-09 Railway Station (2).xlsx
91 | 85 | VP op stross 5 | 2013-04-24 08:00 | 2013-06-03 17:00 | 29d |  | 0 | 0 | 8.58 | 1990.56 | 1990.56 | 2013-06-11 08:00 | 25d | 1716 | 0 | 0 | 0 | 0 | 1716 | 0 | 1 | Finished | 1990.56 | 1990.56 | C2015-09 Railway Station (2).xlsx
92 | 86 | VP op stross 6 | 2013-04-24 08:00 | 2013-05-17 17:00 | 18d |  | 0 | 0 | 8.58 | 1235.52 | 1235.52 | 2013-06-27 08:00 | 15d | 1029.6 | 0 | 0 | 0 | 0 | 1029.6 | 0 | 1 | Finished | 1235.52 | 1235.52 | C2015-09 Railway Station (2).xlsx
93 | 87 | VP op stross 7 | 2013-05-03 08:00 | 2013-06-11 17:00 | 28d |  | 0 | 0 | 8.58 | 1921.92 | 1921.92 | 2013-06-27 08:00 | 35d | 2402.4 | 0 | 0 | 0 | 0 | 2402.4 | 0 | 1 | Finished | 1921.92 | 1921.92 | C2015-09 Railway Station (2).xlsx
94 | 160 | Superstructuur | 2012-11-05 08:00 | 2013-10-03 17:00 | 239d |  |  | 0 |  |  | 130823.1934 |  | 440d 1h | [5 empty] | 157243.2448 |  | 1 |  | 130823.1934 | 130823.1934 | C2015-09 Railway Station (2).xlsx
95 | 106 | Zone 1 | 2012-11-05 08:00 | 2013-06-21 17:00 | 165d |  |  | 0 |  |  | 35109.3582 |  | 205d | [5 empty] | 43124.9581 |  | 1 |  | 35109.3582 | 35109.3582 | C2015-09 Railway Station (2).xlsx
96 | 90 | Brugligger 1 | 2013-02-26 08:00 | 2013-04-09 17:00 | 31d |  | 0 | 0 | 18.21 | 4516.0798 | 4516.0798 | 2013-05-21 08:00 | 32d | 4661.7598 | 0 | 0 | 0 | 0 | 4661.7598 | 0 | 1 | Finished | 4516.0798 | 4516.0798 | C2015-09 Railway Station (2).xlsx
97 | 91 | Brugligger 2 | 2013-03-08 08:00 | 2013-04-11 17:00 | 25d |  | 0 | 0 | 18.21 | 3641.9998 | 3641.9998 | 2013-06-11 08:00 | 40d | 5827.1997 | 0 | 0 | 0 | 0 | 5827.1997 | 0 | 1 | Finished | 3641.9998 | 3641.9998 | C2015-09 Railway Station (2).xlsx
98 | 92 | Brugligger 3 | 2013-03-08 08:00 | 2013-04-11 17:00 | 25d |  | 0 | 0 | 18.21 | 3641.9998 | 3641.9998 | 2013-08-08 08:00 | 28d | 4079.0398 | 0 | 0 | 0 | 0 | 4079.0398 | 0 | 1 | Finished | 3641.9998 | 3641.9998 | C2015-09 Railway Station (2).xlsx
99 | 93 | Brugligger 4 | 2013-04-09 08:00 | 2013-05-14 17:00 | 26d |  | 0 | 0 | 18.21 | 3787.6798 | 3787.6798 | 2013-11-15 08:00 | 34d | 4953.1198 | 0 | 0 | 0 | 0 | 4953.1198 | 0 | 1 | Finished | 3787.6798 | 3787.6798 | C2015-09 Railway Station (2).xlsx
100 | 94 | Brugligger 5 | 2013-04-09 08:00 | 2013-05-14 17:00 | 26d |  | 0 | 0 | 18.21 | 3787.6798 | 3787.6798 | 2013-11-15 08:00 | 34d | 4953.1198 | 0 | 0 | 0 | 0 | 4953.1198 | 0 | 1 | Finished | 3787.6798 | 3787.6798 | C2015-09 Railway Station (2).xlsx
101 | 95 | Beton structuur 1 | 2013-04-09 08:00 | 2013-05-07 17:00 | 21d |  | 0 | 0 | 18.21 | 3059.2798 | 3059.2798 | 2013-10-02 08:00 | 15d | 2185.1999 | 0 | 0 | 0 | 0 | 2185.1999 | 0 | 1 | Finished | 3059.2798 | 3059.2798 | C2015-09 Railway Station (2).xlsx
102 | 96 | Beton structuur 2 | 2013-04-09 08:00 | 2013-05-07 17:00 | 21d |  | 0 | 0 | 18.21 | 3059.2798 | 3059.2798 | 2013-09-30 08:00 | 15d | 2185.1999 | 0 | 0 | 0 | 0 | 2185.1999 | 0 | 1 | Finished | 3059.2798 | 3059.2798 | C2015-09 Railway Station (2).xlsx
103 | 97 | Beton structuur 3 | 2013-05-08 08:00 | 2013-06-07 17:00 | 23d |  | 0 | 0 | 18.21 | 3350.6398 | 3350.6398 | 2014-01-07 08:00 | 18d | 2622.2399 | 0 | 0 | 0 | 0 | 2622.2399 | 0 | 1 | Finished | 3350.6398 | 3350.6398 | C2015-09 Railway Station (2).xlsx
104 | 98 | Beton structuur 4 | 2013-05-08 08:00 | 2013-06-07 17:00 | 23d |  | 0 | 0 | 18.21 | 3350.6398 | 3350.6398 | 2014-01-06 08:00 | 17d | 2476.5599 | 0 | 0 | 0 | 0 | 2476.5599 | 0 | 1 | Finished | 3350.6398 | 3350.6398 | C2015-09 Railway Station (2).xlsx
105 | 99 | Beton structuur 5 | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 18.21 | 2913.5999 | 2913.5999 | 2014-01-06 08:00 | 17d | 2476.5599 | 0 | 0 | 0 | 0 | 2476.5599 | 0 | 1 | Finished | 2913.5999 | 2913.5999 | C2015-09 Railway Station (2).xlsx
106 | 100 | K1 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-05-03 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
107 | 101 | K2 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-05-07 08:00 | 6d | 0.48 | 0 | 0 | 874.08 | 0 | 874.56 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
108 | 102 | K3 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-06-14 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
109 | 103 | K4 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-06-19 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
110 | 104 | K5 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-06-25 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
111 | 105 | perron op volle grond | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-01-13 08:00 | 24d | 1.92 | 0 | 0 | 3496.3201 | 0 | 3498.2401 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
112 | 131 | Zone 2 | 2012-11-05 08:00 | 2013-09-25 17:00 | 233d |  |  | 0 |  |  | 36275.4382 |  | 172d | [5 empty] | 53197.679 |  | 1 |  | 36275.4382 | 36275.4382 | C2015-09 Railway Station (2).xlsx
113 | 107 | Brugligger 6 | 2013-05-08 08:00 | 2013-06-11 17:00 | 25d |  | 0 | 0 | 18.21 | 3641.9998 | 3641.9998 | 2013-08-06 08:00 | 24d | 3496.3198 | 0 | 0 | 0 | 0 | 3496.3198 | 0 | 1 | Finished | 3641.9998 | 3641.9998 | C2015-09 Railway Station (2).xlsx
114 | 108 | Brugligger 7 | 2013-06-06 08:00 | 2013-07-02 17:00 | 19d |  | 0 | 0 | 18.21 | 2767.9199 | 2767.9199 | 2013-09-16 08:00 | 19d | 2767.9199 | 0 | 0 | 0 | 0 | 2767.9199 | 0 | 1 | Finished | 2767.9199 | 2767.9199 | C2015-09 Railway Station (2).xlsx
115 | 109 | Brugligger 8 | 2013-06-27 08:00 | 2013-08-06 17:00 | 29d |  | 0 | 0 | 18.21 | 4224.7198 | 4224.7198 | 2013-10-17 08:00 | 22d | 3204.9598 | 0 | 0 | 0 | 0 | 3204.9598 | 0 | 1 | Finished | 4224.7198 | 4224.7198 | C2015-09 Railway Station (2).xlsx
116 | 110 | Brugligger 9 | 2013-07-18 08:00 | 2013-09-03 17:00 | 34d |  | 0 | 0 | 18.21 | 4953.1198 | 4953.1198 | 2013-09-23 08:00 | 22d | 3204.9598 | 0 | 0 | 0 | 0 | 3204.9598 | 0 | 1 | Finished | 4953.1198 | 4953.1198 | C2015-09 Railway Station (2).xlsx
117 | 111 | Beton structuur 6 | 2013-06-06 08:00 | 2013-07-03 17:00 | 20d |  | 0 | 0 | 18.21 | 2913.5999 | 2913.5999 | 2013-09-30 08:00 | 15d | 2185.1999 | 0 | 0 | 0 | 0 | 2185.1999 | 0 | 1 | Finished | 2913.5999 | 2913.5999 | C2015-09 Railway Station (2).xlsx
118 | 112 | Beton structuur 7 | 2013-06-27 08:00 | 2013-08-07 17:00 | 30d |  | 0 | 0 | 18.21 | 4370.3998 | 4370.3998 | 2013-10-08 08:00 | 15d | 2185.1999 | 0 | 0 | 0 | 0 | 2185.1999 | 0 | 1 | Finished | 4370.3998 | 4370.3998 | C2015-09 Railway Station (2).xlsx
119 | 113 | Beton structuur 8 | 2013-07-18 08:00 | 2013-08-30 17:00 | 32d |  | 0 | 0 | 18.21 | 4661.7598 | 4661.7598 | 2013-11-18 08:00 | 17d | 2476.5599 | 0 | 0 | 0 | 0 | 2476.5599 | 0 | 1 | Finished | 4661.7598 | 4661.7598 | C2015-09 Railway Station (2).xlsx
120 | 114 | Beton structuur 9 | 2013-08-29 08:00 | 2013-09-25 17:00 | 20d |  | 0 | 0 | 18.21 | 2913.5999 | 2913.5999 | 2013-11-18 08:00 | 17d | 2476.5599 | 0 | 0 | 0 | 0 | 2476.5599 | 0 | 1 | Finished | 2913.5999 | 2913.5999 | C2015-09 Railway Station (2).xlsx
121 | 115 | Beton structuur 10 | 2013-06-20 08:00 | 2013-07-17 17:00 | 20d |  | 0 | 0 | 18.21 | 2913.5999 | 2913.5999 | 2013-09-30 08:00 | 15d | 2185.1999 | 0 | 0 | 0 | 0 | 2185.1999 | 0 | 1 | Finished | 2913.5999 | 2913.5999 | C2015-09 Railway Station (2).xlsx
122 | 116 | Beton structuur 11 | 2013-08-29 08:00 | 2013-09-25 17:00 | 20d |  | 0 | 0 | 18.21 | 2913.5999 | 2913.5999 | 2013-10-22 08:00 | 18d | 2622.2399 | 0 | 0 | 0 | 0 | 2622.2399 | 0 | 1 | Finished | 2913.5999 | 2913.5999 | C2015-09 Railway Station (2).xlsx
123 | 117 | K6 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-06-12 08:00 | 18d | 1.44 | 0 | 0 | 2622.24 | 0 | 2623.68 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
124 | 118 | K7 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-06-25 08:00 | 10d | 0.8 | 0 | 0 | 1456.8 | 0 | 1457.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
125 | 119 | K8 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-08-05 08:00 | 12d | 0.96 | 0 | 0 | 1748.16 | 0 | 1749.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
126 | 120 | K9 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-08-12 08:00 | 12d | 0.96 | 0 | 0 | 1748.16 | 0 | 1749.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
127 | 121 | K10 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-06-10 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
128 | 122 | VP1 - VP GV tussen | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-06-11 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
129 | 123 | VP2 - VP GV tussen 1 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-06-11 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
130 | 124 | VP2 - VP GV tussen 2 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-06-12 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
131 | 125 | VP2 - VP GV tussen 3 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-06-28 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
132 | 126 | Voorzetwand langs lokaal | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-09-23 08:00 | 20d | 1.6 | 0 | 0 | 2913.6001 | 0 | 2915.2001 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
133 | 127 | Vloerplaat boven voorzetwand (deel 2) | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-10-11 08:00 | 12d | 0.96 | 0 | 0 | 1748.16 | 0 | 1749.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
134 | 128 | Perron op volle grond - riolering en L-wanden | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-11-19 08:00 | 51d | 4.08 | 0 | 0 | 7439.6802 | 0 | 7443.7602 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
135 | 129 | Trap wanden | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-01-06 08:00 | 17d | 1.36 | 0 | 0 | 2476.5601 | 0 | 2477.9201 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
136 | 130 | Trap plaatsing prefab | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-01-23 08:00 | 9d | 0.72 | 0 | 0 | 1311.12 | 0 | 1311.84 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
137 | 159 | Zone 3 | 2012-11-05 08:00 | 2013-10-03 17:00 | 239d |  |  | 0 |  |  | 59438.397 |  | 406d 1h | [5 empty] | 60920.6077 |  | 1 |  | 59438.397 | 59438.397 | C2015-09 Railway Station (2).xlsx
138 | 132 | Brugligger 10 | 2013-06-04 08:00 | 2013-08-05 17:00 | 45d |  | 0 | 0 | 18.21 | 6555.5997 | 6555.5997 | 2013-09-23 08:00 | 31d | 4516.0798 | 0 | 0 | 0 | 0 | 4516.0798 | 0 | 1 | Finished | 6555.5997 | 6555.5997 | C2015-09 Railway Station (2).xlsx
139 | 133 | Brugligger 11 | 2013-05-21 08:00 | 2013-06-19 17:00 | 22d |  | 0 | 0 | 18.21 | 3204.9598 | 3204.9598 | 2013-09-30 08:00 | 22d | 3204.9598 | 0 | 0 | 0 | 0 | 3204.9598 | 0 | 1 | Finished | 3204.9598 | 3204.9598 | C2015-09 Railway Station (2).xlsx
140 | 134 | Brugligger 12 | 2013-06-14 08:00 | 2013-07-10 17:00 | 19d |  | 0 | 0 | 18.21 | 2767.9199 | 2767.9199 | 2013-10-17 08:00 | 22d | 3204.9598 | 0 | 0 | 0 | 0 | 3204.9598 | 0 | 1 | Finished | 2767.9199 | 2767.9199 | C2015-09 Railway Station (2).xlsx
141 | 135 | Brugligger 13 | 2013-07-05 08:00 | 2013-08-14 17:00 | 29d |  | 0 | 0 | 18.21 | 4224.7198 | 4224.7198 | 2013-10-17 08:00 | 22d | 3204.9598 | 0 | 0 | 0 | 0 | 3204.9598 | 0 | 1 | Finished | 4224.7198 | 4224.7198 | C2015-09 Railway Station (2).xlsx
142 | 136 | Brugligger 14 | 2013-08-09 08:00 | 2013-09-06 17:00 | 21d |  | 0 | 0 | 18.21 | 3059.2798 | 3059.2798 | 2013-11-04 08:00 | 12d | 1748.1599 | 0 | 0 | 0 | 0 | 1748.1599 | 0 | 1 | Finished | 3059.2798 | 3059.2798 | C2015-09 Railway Station (2).xlsx
143 | 137 | Beton structuur 12 | 2013-07-16 08:00 | 2013-08-28 17:00 | 32d |  | 0 | 0 | 18.21 | 4661.7598 | 4661.7598 | 2013-12-05 08:00 | 26d | 3787.6798 | 0 | 0 | 0 | 0 | 3787.6798 | 0 | 1 | Finished | 4661.7598 | 4661.7598 | C2015-09 Railway Station (2).xlsx
144 | 138 | Beton structuur 13 | 2013-07-16 08:00 | 2013-08-28 17:00 | 32d |  | 0 | 0 | 18.21 | 4661.7598 | 4661.7598 | 2013-12-19 08:00 | 27d | 3933.3598 | 0 | 0 | 0 | 0 | 3933.3598 | 0 | 1 | Finished | 4661.7598 | 4661.7598 | C2015-09 Railway Station (2).xlsx
145 | 139 | Beton structuur 14 | 2013-06-14 08:00 | 2013-07-11 17:00 | 20d |  | 0 | 0 | 18.21 | 2913.5999 | 2913.5999 | 2013-10-23 08:00 | 18d | 2622.2399 | 0 | 0 | 0 | 0 | 2622.2399 | 0 | 1 | Finished | 2913.5999 | 2913.5999 | C2015-09 Railway Station (2).xlsx
146 | 140 | Beton structuur 15 | 2013-07-05 08:00 | 2013-08-19 17:00 | 32d |  | 0 | 0 | 18.21 | 4661.7598 | 4661.7598 | 2014-02-25 08:00 | 17d | 2476.5599 | 0 | 0 | 0 | 0 | 2476.5599 | 0 | 1 | Finished | 4661.7598 | 4661.7598 | C2015-09 Railway Station (2).xlsx
147 | 141 | Beton structuur 16 | 2013-08-09 08:00 | 2013-09-09 17:00 | 22d |  | 0 | 0 | 18.21 | 3204.9598 | 3204.9598 | 2013-12-06 08:00 | 23d | 3350.6398 | 0 | 0 | 0 | 0 | 3350.6398 | 0 | 1 | Finished | 3204.9598 | 3204.9598 | C2015-09 Railway Station (2).xlsx
148 | 142 | Beton structuur 17 | 2013-07-16 08:00 | 2013-08-28 17:00 | 32d |  | 0 | 0 | 18.21 | 4661.7598 | 4661.7598 | 2013-12-05 08:00 | 23d | 3350.6398 | 0 | 0 | 0 | 0 | 3350.6398 | 0 | 1 | Finished | 4661.7598 | 4661.7598 | C2015-09 Railway Station (2).xlsx
149 | 143 | Beton structuur 18 | 2013-07-16 08:00 | 2013-08-28 17:00 | 32d |  | 0 | 0 | 18.21 | 4661.7598 | 4661.7598 | 2013-12-19 08:00 | 27d | 3933.3598 | 0 | 0 | 0 | 0 | 3933.3598 | 0 | 1 | Finished | 4661.7598 | 4661.7598 | C2015-09 Railway Station (2).xlsx
150 | 144 | Beton structuur 19 | 2013-06-28 08:00 | 2013-08-08 17:00 | 30d |  | 0 | 0 | 18.21 | 4370.3998 | 4370.3998 | 2015-01-09 08:00 | 1h | 18.21 | 0 | 0 | 0 | 0 | 18.21 | 0 | 1 | Finished | 4370.3998 | 4370.3998 | C2015-09 Railway Station (2).xlsx
151 | 145 | Beton structuur 20 | 2013-08-20 08:00 | 2013-09-16 17:00 | 20d |  | 0 | 0 | 18.21 | 2913.5999 | 2913.5999 | 2013-12-06 08:00 | 23d | 3350.6398 | 0 | 0 | 0 | 0 | 3350.6398 | 0 | 1 | Finished | 2913.5999 | 2913.5999 | C2015-09 Railway Station (2).xlsx
152 | 146 | Beton structuur 21 | 2013-09-06 08:00 | 2013-10-03 17:00 | 20d |  | 0 | 0 | 18.21 | 2913.5999 | 2913.5999 | 2013-12-06 08:00 | 23d | 3350.6398 | 0 | 0 | 0 | 0 | 3350.6398 | 0 | 1 | Finished | 2913.5999 | 2913.5999 | C2015-09 Railway Station (2).xlsx
153 | 147 | K11 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-08-19 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
154 | 148 | K12 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-08-19 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
155 | 149 | K13 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-08-19 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
156 | 150 | K14 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-08-20 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
157 | 151 | K15 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-08-20 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
158 | 152 | K16 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-08-21 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
159 | 153 | Aanpassing toegang reizigers perron A | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-11-04 08:00 | 12d | 0.96 | 0 | 0 | 1748.16 | 0 | 1749.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
160 | 154 | Plaatsing bekisting | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-10-11 08:00 | 4d | 0.32 | 0 | 0 | 582.72 | 0 | 583.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
161 | 155 | Zolen en kolommen | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-08-08 08:00 | 17d | 1.36 | 0 | 0 | 2476.5601 | 0 | 2477.9201 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
162 | 156 | Verankering beschoeiing | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-06-20 08:00 | 10d | 0.8 | 0 | 0 | 1456.8 | 0 | 1457.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
163 | 157 | VP3 - VP GV tussen | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-08-19 08:00 | 20d | 1.6 | 0 | 0 | 2913.6001 | 0 | 2915.2001 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
164 | 158 | VP4 - VP GV tussen | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2013-08-22 08:00 | 15d | 1.2 | 0 | 0 | 2185.2 | 0 | 2186.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
165 | 167 | Waterdichting | 2013-05-15 08:00 | 2013-09-06 17:00 | 83d |  |  | 0 |  |  | 8276.6398 |  | 133d | [5 empty] | 7217.9998 |  | 1 |  | 8276.6398 | 8276.6398 | C2015-09 Railway Station (2).xlsx
166 | 161 | Waterdichting + gietasfalt | 2013-05-15 08:00 | 2013-06-05 17:00 | 16d |  | 0 | 0 | 12.03 | 1539.84 | 1539.84 | 2014-03-21 08:00 | 12d | 1154.88 | 0 | 0 | 0 | 0 | 1154.88 | 0 | 1 | Finished | 1539.84 | 1539.84 | C2015-09 Railway Station (2).xlsx
167 | 162 | Ballastmatten | 2013-05-30 08:00 | 2013-06-19 17:00 | 15d |  | 0 | 0 | 12.03 | 1443.6 | 1443.6 | 2014-08-21 08:00 | 17d | 1636.08 | 0 | 0 | 0 | 0 | 1636.08 | 0 | 1 | Finished | 1443.6 | 1443.6 | C2015-09 Railway Station (2).xlsx
168 | 163 | Ballast | 2013-06-13 08:00 | 2013-06-26 17:00 | 10d |  | 0 | 0 | 12.03 | 962.4 | 962.4 | 2014-09-08 09:00 | 10d | 962.4 | 0 | 0 | 0 | 0 | 962.4 | 0 | 1 | Finished | 962.4 | 962.4 | C2015-09 Railway Station (2).xlsx
169 | 164 | Waterdichting + gietasfalt | 2013-07-18 08:00 | 2013-08-23 17:00 | 27d |  | 0 | 0 | 12.03 | 2598.4799 | 2598.4799 | 2014-04-02 08:00 | 17d | 1636.08 | 0 | 0 | 0 | 0 | 1636.08 | 0 | 1 | Finished | 2598.4799 | 2598.4799 | C2015-09 Railway Station (2).xlsx
170 | 165 | Ballastmatten | 2013-08-19 08:00 | 2013-08-28 17:00 | 8d |  | 0 | 0 | 12.03 | 769.92 | 769.92 | 2014-09-04 08:00 | 10d | 962.4 | 0 | 0 | 0 | 0 | 962.4 | 0 | 1 | Finished | 769.92 | 769.92 | C2015-09 Railway Station (2).xlsx
171 | 166 | Ballast | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 12.03 | 962.4 | 962.4 | 2014-09-11 08:00 | 9d | 866.16 | 0 | 0 | 0 | 0 | 866.16 | 0 | 1 | Finished | 962.4 | 962.4 | C2015-09 Railway Station (2).xlsx
172 | 193 | Infrastructuur | 2012-11-05 08:00 | 2013-12-12 17:00 | 289d |  |  | 0 |  |  | 51069.5995 |  | 167d | [5 empty] | 60298.3997 |  | 1 |  | 51069.5995 | 51069.5995 | C2015-09 Railway Station (2).xlsx
173 | 168 | Structuur bufferbekken | 2013-05-27 08:00 | 2013-07-19 17:00 | 40d |  | 0 | 0 | 14.41 | 4611.2 | 4611.2 | 2013-10-29 08:00 | 59d | 6801.5199 | 0 | 0 | 0 | 0 | 6801.5199 | 0 | 1 | Finished | 4611.2 | 4611.2 | C2015-09 Railway Station (2).xlsx
174 | 169 | Liftput 1 | 2013-06-10 08:00 | 2013-07-19 17:00 | 30d |  | 0 | 0 | 14.41 | 3458.4 | 3458.4 | 2013-11-04 08:00 | 30d | 3458.4 | 0 | 0 | 0 | 0 | 3458.4 | 0 | 1 | Finished | 3458.4 | 3458.4 | C2015-09 Railway Station (2).xlsx
175 | 170 | Liftput 2 | 2013-08-13 08:00 | 2013-09-25 17:00 | 32d |  | 0 | 0 | 14.41 | 3688.96 | 3688.96 | 2013-12-05 08:00 | 39d | 4495.92 | 0 | 0 | 0 | 0 | 4495.92 | 0 | 1 | Finished | 3688.96 | 3688.96 | C2015-09 Railway Station (2).xlsx
176 | 171 | Structuur bufferbekken | 2013-10-24 08:00 | 2013-12-03 17:00 | 29d |  | 0 | 0 | 14.41 | 3343.12 | 3343.12 | 2014-04-10 08:00 | 30d | 3458.4 | 0 | 0 | 0 | 0 | 3458.4 | 0 | 1 | Finished | 3343.12 | 3343.12 | C2015-09 Railway Station (2).xlsx
177 | 172 | Ophanging VP GV aan brugdek 1 | 2013-09-10 08:00 | 2013-09-23 17:00 | 10d |  | 0 | 0 | 14.41 | 1152.8 | 1152.8 | 2013-10-17 08:00 | 10d | 1152.8 | 0 | 0 | 0 | 0 | 1152.8 | 0 | 1 | Finished | 1152.8 | 1152.8 | C2015-09 Railway Station (2).xlsx
178 | 173 | Ophanging VP GV aan brugdek 2 | 2013-07-18 08:00 | 2013-08-14 17:00 | 20d |  | 0 | 0 | 14.41 | 2305.6 | 2305.6 | 2013-11-04 08:00 | 12d | 1383.36 | 0 | 0 | 0 | 0 | 1383.36 | 0 | 1 | Finished | 2305.6 | 2305.6 | C2015-09 Railway Station (2).xlsx
179 | 174 | Ophanging VP GV aan brugdek 3 | 2013-09-02 08:00 | 2013-09-13 17:00 | 10d |  | 0 | 0 | 14.41 | 1152.8 | 1152.8 | 2013-11-14 08:00 | 11d | 1268.08 | 0 | 0 | 0 | 0 | 1268.08 | 0 | 1 | Finished | 1152.8 | 1152.8 | C2015-09 Railway Station (2).xlsx
180 | 175 | Grondwerken stross | 2013-09-13 08:00 | 2013-10-17 17:00 | 25d |  | 0 | 0 | 14.41 | 2882 | 2882 | 2014-01-10 08:00 | 17d | 1959.76 | 0 | 0 | 0 | 0 | 1959.76 | 0 | 1 | Finished | 2882 | 2882 | C2015-09 Railway Station (2).xlsx
181 | 176 | Vloerplaat -1 | 2013-09-27 08:00 | 2013-11-26 17:00 | 43d |  | 0 | 0 | 14.41 | 4957.0399 | 4957.0399 | 2014-04-01 08:00 | 31d | 3573.68 | 0 | 0 | 0 | 0 | 3573.68 | 0 | 1 | Finished | 4957.0399 | 4957.0399 | C2015-09 Railway Station (2).xlsx
182 | 177 | Beton bak voor roltrap | 2013-10-04 08:00 | 2013-10-24 17:00 | 15d |  | 0 | 0 | 14.41 | 1729.2 | 1729.2 | 2013-12-05 08:00 | 32d | 3688.96 | 0 | 0 | 0 | 0 | 3688.96 | 0 | 1 | Finished | 1729.2 | 1729.2 | C2015-09 Railway Station (2).xlsx
183 | 178 | Kolommen en wanden -1 | 2013-10-17 08:00 | 2013-12-12 17:00 | 41d |  | 0 | 0 | 14.41 | 4726.4799 | 4726.4799 | 2014-04-23 08:00 | 23d | 2651.44 | 0 | 0 | 0 | 0 | 2651.44 | 0 | 1 | Finished | 4726.4799 | 4726.4799 | C2015-09 Railway Station (2).xlsx
184 | 179 | Grondwerken stross | 2013-08-06 08:00 | 2013-09-11 17:00 | 27d |  | 0 | 0 | 14.41 | 3112.56 | 3112.56 | 2013-12-02 08:00 | 31d | 3573.68 | 0 | 0 | 0 | 0 | 3573.68 | 0 | 1 | Finished | 3112.56 | 3112.56 | C2015-09 Railway Station (2).xlsx
185 | 180 | Vloerplaat -1 | 2013-08-29 08:00 | 2013-10-16 17:00 | 35d |  | 0 | 0 | 14.41 | 4034.8 | 4034.8 | 2014-03-03 08:00 | 26d | 2997.28 | 0 | 0 | 0 | 0 | 2997.28 | 0 | 1 | Finished | 4034.8 | 4034.8 | C2015-09 Railway Station (2).xlsx
186 | 181 | Kolommen en wanden | 2013-10-04 08:00 | 2013-10-31 17:00 | 20d |  | 0 | 0 | 14.41 | 2305.6 | 2305.6 | 2014-04-01 08:00 | 21d | 2420.88 | 0 | 0 | 0 | 0 | 2420.88 | 0 | 1 | Finished | 2305.6 | 2305.6 | C2015-09 Railway Station (2).xlsx
187 | 182 | Beton bak voor roltrap | 2013-10-08 08:00 | 2013-10-28 17:00 | 15d |  | 0 | 0 | 14.41 | 1729.2 | 1729.2 | 2014-04-03 08:00 | 7d | 806.96 | 0 | 0 | 0 | 0 | 806.96 | 0 | 1 | Finished | 1729.2 | 1729.2 | C2015-09 Railway Station (2).xlsx
188 | 183 | Grondwerken in stross | 2013-09-13 08:00 | 2013-10-03 17:00 | 15d |  | 0 | 0 | 14.41 | 1729.2 | 1729.2 | 2014-01-22 08:00 | 15d | 1729.2 | 0 | 0 | 0 | 0 | 1729.2 | 0 | 1 | Finished | 1729.2 | 1729.2 | C2015-09 Railway Station (2).xlsx
189 | 184 | Kolommen en wanden | 2013-09-24 08:00 | 2013-09-30 17:00 | 5d |  | 0 | 0 | 14.41 | 576.4 | 576.4 | 2014-03-26 08:00 | 15d | 1729.2 | 0 | 0 | 0 | 0 | 1729.2 | 0 | 1 | Finished | 576.4 | 576.4 | C2015-09 Railway Station (2).xlsx
190 | 185 | Vloerplaat -1 | 2013-09-26 08:00 | 2013-11-07 17:00 | 31d |  | 0 | 0 | 14.41 | 3573.68 | 3573.68 | 2014-03-03 08:00 | 27d | 3112.56 | 0 | 0 | 0 | 0 | 3112.56 | 0 | 1 | Finished | 3573.68 | 3573.68 | C2015-09 Railway Station (2).xlsx
191 | 186 | Verwijdering ophanging VP aan brugdek | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-05-07 08:00 | 13d | 1.04 | 0 | 0 | 1498.64 | 0 | 1499.68 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
192 | 187 | Onderschoeiing reizigerstunnel | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-04-04 08:00 | 10d | 0.8 | 0 | 0 | 1152.8 | 0 | 1153.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
193 | 188 | VP5 - VP GV tussen | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-01-06 08:00 | 20d | 1.6 | 0 | 0 | 2305.6001 | 0 | 2307.2001 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
194 | 189 | Funderingsmassieven en tech. putten | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-02-04 08:00 | 10d | 0.8 | 0 | 0 | 1152.8 | 0 | 1153.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
195 | 190 | Spanning sankers | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-05-07 08:00 | 12d | 0.96 | 0 | 0 | 1383.36 | 0 | 1384.32 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
196 | 191 | Waterdichting plaat GV | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-05-15 08:00 | 10d | 0.8 | 0 | 0 | 1152.8 | 0 | 1153.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
197 | 192 | Betonplaat op waterdichting GV | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-05-22 08:00 | 12d | 0.96 | 0 | 0 | 1383.36 | 0 | 1384.32 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
198 | 221 | Technische installaties | 2012-11-05 08:00 | 2014-03-04 17:00 | 347d |  |  | 0 |  |  | 728933.1277 |  | 259d 1h | [5 empty] | 1158736.1248 |  | 1 |  | 728933.1277 | 728933.1277 | C2015-09 Railway Station (2).xlsx
199 | 194 | Kabels, verlichting en branddetectie | 2013-11-08 08:00 | 2014-01-30 17:00 | 60d |  | 0 | 0 | 232.44 | 111571.2012 | 111571.2012 | 2014-04-30 08:00 | 40d | 74380.8008 | 0 | 0 | 0 | 0 | 74380.8008 | 0 | 1 | Finished | 111571.2012 | 111571.2012 | C2015-09 Railway Station (2).xlsx
200 | 195 | Metselwerk -1 | 2013-10-31 08:00 | 2014-01-21 17:00 | 59d |  | 0 | 0 | 232.44 | 109711.6812 | 109711.6812 | 2014-03-31 08:00 | 37d | 68802.2407 | 0 | 0 | 0 | 0 | 68802.2407 | 0 | 1 | Finished | 109711.6812 | 109711.6812 | C2015-09 Railway Station (2).xlsx
201 | 196 | Installaties in techn lokalen | 2013-12-05 08:00 | 2014-03-04 17:00 | 64d |  | 0 | 0 | 232.44 | 119009.2812 | 119009.2812 | 2014-04-22 08:00 | 64d | 119009.2812 | 0 | 0 | 0 | 0 | 119009.2812 | 0 | 1 | Finished | 119009.2812 | 119009.2812 | C2015-09 Railway Station (2).xlsx
202 | 197 | Kabels, verlichting in koker | 2013-09-05 08:00 | 2013-10-30 17:00 | 40d |  | 0 | 0 | 232.44 | 74380.8008 | 74380.8008 | 2014-01-13 08:00 | 62d | 115290.2412 | 0 | 0 | 0 | 0 | 115290.2412 | 0 | 1 | Finished | 74380.8008 | 74380.8008 | C2015-09 Railway Station (2).xlsx
203 | 198 | Plaatsing structuur roltrap | 2013-10-23 08:00 | 2013-11-06 17:00 | 11d |  | 0 | 0 | 232.44 | 20454.7202 | 20454.7202 | 2014-03-25 08:00 | 8d | 14876.1602 | 0 | 0 | 0 | 0 | 14876.1602 | 0 | 1 | Finished | 20454.7202 | 20454.7202 | C2015-09 Railway Station (2).xlsx
204 | 199 | Technische uitrusting roltrap | 2013-10-30 08:00 | 2013-11-22 17:00 | 18d |  | 0 | 0 | 232.44 | 33471.3604 | 33471.3604 | 2014-03-31 08:00 | 8d | 14876.1602 | 0 | 0 | 0 | 0 | 14876.1602 | 0 | 1 | Finished | 33471.3604 | 33471.3604 | C2015-09 Railway Station (2).xlsx
205 | 200 | Bekleding onderkant roltrap | 2013-11-18 08:00 | 2013-12-10 17:00 | 17d |  | 0 | 0 | 232.44 | 31611.8403 | 31611.8403 | 2014-09-01 08:00 | 50d | 92976.001 | 0 | 0 | 0 | 0 | 92976.001 | 0 | 1 | Finished | 31611.8403 | 31611.8403 | C2015-09 Railway Station (2).xlsx
206 | 201 | Plaatsing structuur roltrap | 2013-10-22 08:00 | 2013-11-05 17:00 | 11d |  | 0 | 0 | 232.44 | 20454.7202 | 20454.7202 | 2014-05-05 08:00 | 10d | 18595.2002 | 0 | 0 | 0 | 0 | 18595.2002 | 0 | 1 | Finished | 20454.7202 | 20454.7202 | C2015-09 Railway Station (2).xlsx
207 | 202 | Technische uitrusting roltrap | 2013-10-29 08:00 | 2013-11-21 17:00 | 18d |  | 0 | 0 | 232.44 | 33471.3604 | 33471.3604 | 2014-05-07 08:00 | 10d | 18595.2002 | 0 | 0 | 0 | 0 | 18595.2002 | 0 | 1 | Finished | 33471.3604 | 33471.3604 | C2015-09 Railway Station (2).xlsx
208 | 203 | Bekleding onderkant roltrap | 2013-11-15 08:00 | 2013-12-09 17:00 | 17d |  | 0 | 0 | 232.44 | 31611.8403 | 31611.8403 | 2014-09-01 08:00 | 50d | 92976.001 | 0 | 0 | 0 | 0 | 92976.001 | 0 | 1 | Finished | 31611.8403 | 31611.8403 | C2015-09 Railway Station (2).xlsx
209 | 204 | Installatie lift | 2013-07-08 08:00 | 2013-10-22 17:00 | 77d |  | 0 | 0 | 232.44 | 143183.0415 | 143183.0415 | 2015-01-09 08:00 | 1h | 232.44 | 0 | 0 | 0 | 0 | 232.44 | 0 | 1 | Finished | 143183.0415 | 143183.0415 | C2015-09 Railway Station (2).xlsx
210 | 205 | Technische installaties in bufferbekken | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-10-13 08:00 | 24d | 1.92 | 0 | 0 | 44628.4805 | 0 | 44630.4005 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
211 | 206 | Plaatsing roltrap | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-05-12 08:00 | 10d | 0.8 | 0 | 0 | 18595.1992 | 0 | 18595.9992 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
212 | 207 | Plaatsing glas kanten roltrap | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-15 08:00 | 47d | 3.76 | 0 | 0 | 87397.4375 | 0 | 87401.1975 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
213 | 208 | Plaatsing structuur kanten roltrap | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-05-19 08:00 | 7d | 0.56 | 0 | 0 | 13016.6396 | 0 | 13017.1996 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
214 | 209 | Plaatsing roltrap | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-05-12 08:00 | 10d | 0.8 | 0 | 0 | 18595.1992 | 0 | 18595.9992 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
215 | 210 | Plaatsing glas kanten roltrap | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-15 08:00 | 48d | 3.84 | 0 | 0 | 89256.9609 | 0 | 89260.8009 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
216 | 211 | Metselwerk lokalen | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-06-19 08:00 | 12d | 0.96 | 0 | 0 | 22314.2402 | 0 | 22315.2002 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
217 | 212 | Deuren voor technische lokalen | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-06-02 08:00 | 11d | 0.88 | 0 | 0 | 20454.7207 | 0 | 20455.6007 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
218 | 213 | Trap 1 - perron C-D | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-04-07 08:00 | 1d | 0.08 | 0 | 0 | 1859.52 | 0 | 1859.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
219 | 214 | Trap 2 - perron C-D | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-04-23 08:00 | 10d | 0.8 | 0 | 0 | 18595.1992 | 0 | 18595.9992 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
220 | 215 | Aaanvulling en geo textiel | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-04-14 08:00 | 46d | 3.68 | 0 | 0 | 85537.9219 | 0 | 85541.6019 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
221 | 216 | Leidingen en wachtbuizen aanvoer/afvoer | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-05-08 08:00 | 22d | 1.76 | 0 | 0 | 40909.4414 | 0 | 40911.2014 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
222 | 217 | Waterdichting in bufferbekken | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-29 08:00 | 20d | 1.6 | 0 | 0 | 37190.3984 | 0 | 37191.9984 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
223 | 218 | Sluitwand beton in roltrap | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-03-31 08:00 | 4d | 0.32 | 0 | 0 | 7438.0801 | 0 | 7438.4001 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
224 | 219 | Integratie technieken in portiek | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-07-01 08:00 | 7d | 0.56 | 0 | 0 | 13016.6396 | 0 | 13017.1996 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
225 | 220 | Plaatsing rolluik in portiek roltrap | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-07-01 08:00 | 5d | 0.4 | 0 | 0 | 9297.5996 | 0 | 9297.9996 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
226 | 280 | GOK | 2012-11-05 08:00 | 2014-02-19 17:00 | 338d |  |  | 0 |  |  | 139054.4013 |  | 214d 1h | [5 empty] | 249217.6625 |  | 1 |  | 139054.4013 | 139054.4013 | C2015-09 Railway Station (2).xlsx
227 | 222 | Staalstructuur overkapping | 2013-09-03 08:00 | 2013-10-21 17:00 | 35d |  | 0 | 0 | 24.76 | 6932.8001 | 6932.8001 | 2014-04-28 08:00 | 64d | 12677.1201 | 0 | 0 | 0 | 0 | 12677.1201 | 0 | 1 | Finished | 6932.8001 | 6932.8001 | C2015-09 Railway Station (2).xlsx
228 | 223 | Wegnemen tijdelijke staalstructuur | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 24.76 | 1980.8 | 1980.8 | 2014-08-08 08:00 | 11d | 2178.88 | 0 | 0 | 0 | 0 | 2178.88 | 0 | 1 | Finished | 1980.8 | 1980.8 | C2015-09 Railway Station (2).xlsx
229 | 224 | Herstellingen staalstructuur spoor D | 2013-10-21 08:00 | 2013-11-20 17:00 | 23d |  | 0 | 0 | 24.76 | 4555.84 | 4555.84 | 2014-08-12 08:00 | 63d | 12479.0401 | 0 | 0 | 0 | 0 | 12479.0401 | 0 | 1 | Finished | 4555.84 | 4555.84 | C2015-09 Railway Station (2).xlsx
230 | 225 | Onderhoudsgondel op dak boven spoor D | 2013-11-05 08:00 | 2013-11-28 17:00 | 18d |  | 0 | 0 | 24.76 | 3565.44 | 3565.44 | 2014-08-25 08:00 | 65d | 12875.2001 | 0 | 0 | 0 | 0 | 12875.2001 | 0 | 1 | Finished | 3565.44 | 3565.44 | C2015-09 Railway Station (2).xlsx
231 | 226 | Platen en goten hoog dak | 2013-09-30 08:00 | 2013-11-04 17:00 | 26d |  | 0 | 0 | 24.76 | 5150.08 | 5150.08 | 2014-07-09 08:00 | 26d | 5150.08 | 0 | 0 | 0 | 0 | 5150.08 | 0 | 1 | Finished | 5150.08 | 5150.08 | C2015-09 Railway Station (2).xlsx
232 | 227 | Platen en goten laag dak | 2013-09-30 08:00 | 2013-11-12 17:00 | 32d |  | 0 | 0 | 24.76 | 6338.5601 | 6338.5601 | 2014-07-22 08:00 | 31d | 6140.4801 | 0 | 0 | 0 | 0 | 6140.4801 | 0 | 1 | Finished | 6338.5601 | 6338.5601 | C2015-09 Railway Station (2).xlsx
233 | 228 | Staalstructuur gevel spoor C | 2013-10-14 08:00 | 2013-11-12 17:00 | 22d |  | 0 | 0 | 24.76 | 4357.76 | 4357.76 | 2014-06-25 08:00 | 21d | 4159.68 | 0 | 0 | 0 | 0 | 4159.68 | 0 | 1 | Finished | 4357.76 | 4357.76 | C2015-09 Railway Station (2).xlsx
234 | 229 | Staalstructuur gevel spoor B | 2013-11-05 08:00 | 2013-12-06 17:00 | 24d |  | 0 | 0 | 24.76 | 4753.92 | 4753.92 | 2014-07-16 08:00 | 21d | 4159.68 | 0 | 0 | 0 | 0 | 4159.68 | 0 | 1 | Finished | 4753.92 | 4753.92 | C2015-09 Railway Station (2).xlsx
235 | 230 | Beglazing gevel - spoor D | 2013-09-24 08:00 | 2013-11-05 17:00 | 31d |  | 0 | 0 | 24.76 | 6140.4801 | 6140.4801 | 2015-01-09 08:00 | 1h | 24.76 | 0 | 0 | 0 | 0 | 24.76 | 0 | 1 | Finished | 6140.4801 | 6140.4801 | C2015-09 Railway Station (2).xlsx
236 | 231 | Beglazing gevel - spoor C | 2013-10-21 08:00 | 2013-12-06 17:00 | 35d |  | 0 | 0 | 24.76 | 6932.8001 | 6932.8001 | 2014-09-08 09:00 | 31d | 6140.4801 | 0 | 0 | 0 | 0 | 6140.4801 | 0 | 1 | Finished | 6932.8001 | 6932.8001 | C2015-09 Railway Station (2).xlsx
237 | 232 | Waterdichting hoog dak | 2013-10-21 08:00 | 2013-11-22 17:00 | 25d |  | 0 | 0 | 24.76 | 4952 | 4952 | 2014-08-25 08:00 | 25d | 4952 | 0 | 0 | 0 | 0 | 4952 | 0 | 1 | Finished | 4952 | 4952 | C2015-09 Railway Station (2).xlsx
238 | 233 | Waterdichting laag dak | 2013-11-05 08:00 | 2013-12-10 17:00 | 26d |  | 0 | 0 | 24.76 | 5150.08 | 5150.08 | 2014-08-13 08:00 | 26d | 5150.08 | 0 | 0 | 0 | 0 | 5150.08 | 0 | 1 | Finished | 5150.08 | 5150.08 | C2015-09 Railway Station (2).xlsx
239 | 234 | Integratie technieken hoog dak | 2013-10-07 08:00 | 2013-11-14 17:00 | 29d |  | 0 | 0 | 24.76 | 5744.3201 | 5744.3201 | 2014-07-30 08:00 | 82d | 16242.5602 | 0 | 0 | 0 | 0 | 16242.5602 | 0 | 1 | Finished | 5744.3201 | 5744.3201 | C2015-09 Railway Station (2).xlsx
240 | 235 | Integratie technieken laag dak | 2013-10-21 08:00 | 2013-11-28 17:00 | 29d |  | 0 | 0 | 24.76 | 5744.3201 | 5744.3201 | 2014-08-04 08:00 | 23d | 4555.84 | 0 | 0 | 0 | 0 | 4555.84 | 0 | 1 | Finished | 5744.3201 | 5744.3201 | C2015-09 Railway Station (2).xlsx
241 | 236 | Beplating plafond staalstructuur hoog dak | 2013-10-24 08:00 | 2013-12-03 17:00 | 29d |  | 0 | 0 | 24.76 | 5744.3201 | 5744.3201 | 2014-08-11 08:00 | 74d | 14657.9201 | 0 | 0 | 0 | 0 | 14657.9201 | 0 | 1 | Finished | 5744.3201 | 5744.3201 | C2015-09 Railway Station (2).xlsx
242 | 237 | Beplating plafond staalstructuur laag dak | 2013-11-14 08:00 | 2013-12-16 17:00 | 23d |  | 0 | 0 | 24.76 | 4555.84 | 4555.84 | 2014-08-11 08:00 | 74d | 14657.9201 | 0 | 0 | 0 | 0 | 14657.9201 | 0 | 1 | Finished | 4555.84 | 4555.84 | C2015-09 Railway Station (2).xlsx
243 | 238 | Trap 1 | 2013-07-12 08:00 | 2013-08-19 17:00 | 27d |  | 0 | 0 | 24.76 | 5348.16 | 5348.16 | 2014-05-23 08:00 | 36d | 7130.8801 | 0 | 0 | 0 | 0 | 7130.8801 | 0 | 1 | Finished | 5348.16 | 5348.16 | C2015-09 Railway Station (2).xlsx
244 | 239 | Trap 2 | 2013-09-12 08:00 | 2013-10-02 17:00 | 15d |  | 0 | 0 | 24.76 | 2971.2 | 2971.2 | 2014-03-17 08:00 | 69d | 13667.5201 | 0 | 0 | 0 | 0 | 13667.5201 | 0 | 1 | Finished | 2971.2 | 2971.2 | C2015-09 Railway Station (2).xlsx
245 | 240 | Staalstructuur lichtstraat | 2013-09-19 08:00 | 2013-10-09 17:00 | 15d |  | 0 | 0 | 24.76 | 2971.2 | 2971.2 | 2014-04-22 08:00 | 17d | 3367.36 | 0 | 0 | 0 | 0 | 3367.36 | 0 | 1 | Finished | 2971.2 | 2971.2 | C2015-09 Railway Station (2).xlsx
246 | 241 | Integratie technieken in lichtstraat | 2013-09-26 08:00 | 2013-10-16 17:00 | 15d |  | 0 | 0 | 24.76 | 2971.2 | 2971.2 | 2014-04-29 08:00 | 17d | 3367.36 | 0 | 0 | 0 | 0 | 3367.36 | 0 | 1 | Finished | 2971.2 | 2971.2 | C2015-09 Railway Station (2).xlsx
247 | 242 | Beglazing lichtstraat | 2013-10-03 08:00 | 2013-11-18 17:00 | 33d |  | 0 | 0 | 24.76 | 6536.6401 | 6536.6401 | 2014-05-15 08:00 | 14d | 2773.12 | 0 | 0 | 0 | 0 | 2773.12 | 0 | 1 | Finished | 6536.6401 | 6536.6401 | C2015-09 Railway Station (2).xlsx
248 | 243 | Beplating lichtstraat | 2013-10-24 08:00 | 2013-11-25 17:00 | 23d |  | 0 | 0 | 24.76 | 4555.84 | 4555.84 | 2014-05-15 08:00 | 14d | 2773.12 | 0 | 0 | 0 | 0 | 2773.12 | 0 | 1 | Finished | 4555.84 | 4555.84 | C2015-09 Railway Station (2).xlsx
249 | 244 | Staalstructuur lichtstraat boven roltrap | 2013-10-29 08:00 | 2013-11-14 17:00 | 13d |  | 0 | 0 | 24.76 | 2575.04 | 2575.04 | 2015-01-09 08:00 | 1h | 24.76 | 0 | 0 | 0 | 0 | 24.76 | 0 | 1 | Finished | 2575.04 | 2575.04 | C2015-09 Railway Station (2).xlsx
250 | 245 | Beglazing lichtstraat boven roltrap | 2013-11-04 08:00 | 2013-11-19 17:00 | 12d |  | 0 | 0 | 24.76 | 2376.96 | 2376.96 | 2015-01-09 08:00 | 1h | 24.76 | 0 | 0 | 0 | 0 | 24.76 | 0 | 1 | Finished | 2376.96 | 2376.96 | C2015-09 Railway Station (2).xlsx
251 | 246 | Staalstructuur lichtstraat boven roltrap | 2013-10-30 08:00 | 2013-11-15 17:00 | 13d |  | 0 | 0 | 24.76 | 2575.04 | 2575.04 | 2015-01-09 08:00 | 1h | 24.76 | 0 | 0 | 0 | 0 | 24.76 | 0 | 1 | Finished | 2575.04 | 2575.04 | C2015-09 Railway Station (2).xlsx
252 | 247 | Beglazing lichtstraat boven roltrap | 2013-11-05 08:00 | 2013-11-20 17:00 | 12d |  | 0 | 0 | 24.76 | 2376.96 | 2376.96 | 2015-01-09 08:00 | 1h | 24.76 | 0 | 0 | 0 | 0 | 24.76 | 0 | 1 | Finished | 2376.96 | 2376.96 | C2015-09 Railway Station (2).xlsx
253 | 248 | Bevloering perron | 2013-11-08 08:00 | 2013-12-03 17:00 | 18d |  | 0 | 0 | 24.76 | 3565.44 | 3565.44 | 2014-08-20 08:00 | 52d | 10300.1601 | 0 | 0 | 0 | 0 | 10300.1601 | 0 | 1 | Finished | 3565.44 | 3565.44 | C2015-09 Railway Station (2).xlsx
254 | 249 | Afwerking bevloering perron D | 2013-11-19 08:00 | 2013-12-12 17:00 | 18d |  | 0 | 0 | 24.76 | 3565.44 | 3565.44 | 2015-01-09 08:00 | 1h | 24.76 | 0 | 0 | 0 | 0 | 24.76 | 0 | 1 | Finished | 3565.44 | 3565.44 | C2015-09 Railway Station (2).xlsx
255 | 250 | Ophangtoestellen perron | 2013-11-19 08:00 | 2013-12-12 17:00 | 18d |  | 0 | 0 | 24.76 | 3565.44 | 3565.44 | 2015-01-09 08:00 | 1h | 24.76 | 0 | 0 | 0 | 0 | 24.76 | 0 | 1 | Finished | 3565.44 | 3565.44 | C2015-09 Railway Station (2).xlsx
256 | 251 | Bevloering perron | 2013-12-09 08:00 | 2014-02-19 17:00 | 53d |  | 0 | 0 | 24.76 | 10498.2401 | 10498.2401 | 2015-01-09 08:00 | 1h | 24.76 | 0 | 0 | 0 | 0 | 24.76 | 0 | 1 | Finished | 10498.2401 | 10498.2401 | C2015-09 Railway Station (2).xlsx
257 | 252 | Structuur levenslijn | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-22 08:00 | 20d | 1.6 | 0 | 0 | 3961.6001 | 0 | 3963.2001 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
258 | 253 | Electrische installaties op dak | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-11 08:00 | 37d | 2.96 | 0 | 0 | 7328.96 | 0 | 7331.92 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
259 | 254 | Extractoren op dak | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-11 08:00 | 15d | 1.2 | 0 | 0 | 2971.2 | 0 | 2972.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
260 | 255 | Onderhoudsuitrusting gevel | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-08-11 08:00 | 19d | 1.52 | 0 | 0 | 3763.52 | 0 | 3765.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
261 | 256 | Staalstructuur overkapping 1 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2015-01-09 08:00 | 1h | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
262 | 257 | Staalstructuur overkapping 2 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2015-01-09 08:00 | 1h | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
263 | 258 | Staalstructuur overkapping 3 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2015-01-09 08:00 | 1h | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
264 | 259 | Staalstructuur overkapping 4 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2015-01-09 08:00 | 1h | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
265 | 260 | Staalstructuur overkapping 5 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2015-01-09 08:00 | 1h | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
266 | 261 | Plaatsing standleidingen | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-08-07 08:00 | 19d | 1.52 | 0 | 0 | 3763.52 | 0 | 3765.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
267 | 262 | Plaatsing overstorten | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-10-13 08:00 | 10d | 0.8 | 0 | 0 | 1980.8 | 0 | 1981.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
268 | 263 | Profielen voor handgreep | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-03-27 08:00 | 10d | 0.8 | 0 | 0 | 1980.8 | 0 | 1981.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
269 | 264 | Kaders voor beglazing lichtstraat | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-05-08 08:00 | 15d | 1.2 | 0 | 0 | 2971.2 | 0 | 2972.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
270 | 265 | Waterdichting op perron | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-05-13 08:00 | 10d | 0.8 | 0 | 0 | 1980.8 | 0 | 1981.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
271 | 266 | Perronboorden | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-08-04 08:00 | 11d | 0.88 | 0 | 0 | 2178.8799 | 0 | 2179.7599 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
272 | 267 | Bekabeling in perronboorden | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-08-04 08:00 | 11d | 0.88 | 0 | 0 | 2178.8799 | 0 | 2179.7599 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
273 | 268 | Afwerken handgreep | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-10-20 08:00 | 9d | 0.72 | 0 | 0 | 1782.72 | 0 | 1783.44 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
274 | 269 | Staalstructuur gevel spoor C 1 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-06-25 08:00 | 21d | 1.68 | 0 | 0 | 4159.6802 | 0 | 4161.3602 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
275 | 270 | Staalstructuur gevel spoor C 2 | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-07-16 08:00 | 21d | 1.68 | 0 | 0 | 4159.6802 | 0 | 4161.3602 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
276 | 271 | Vervolledigen waterdichting spoor D | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-08-18 08:00 | 21d | 1.68 | 0 | 0 | 4159.6802 | 0 | 4161.3602 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
277 | 272 | Waterdichting en gietasfalt spoorbak | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-04-02 08:00 | 17d | 1.36 | 0 | 0 | 3367.3601 | 0 | 3368.7201 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
278 | 273 | Afwerking schilderwerken overkapping | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-02 08:00 | 48d | 3.84 | 0 | 0 | 6338.5601 | 0 | 6342.4001 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
279 | 274 | Tijdelijke structuur en afvoeren spoor D | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-08-13 08:00 | 16d | 1.28 | 0 | 0 | 3169.28 | 0 | 3170.56 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
280 | 275 | tijdelijke dichting gevel spoor D | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-15 08:00 | 34d | 2.72 | 0 | 0 | 7725.1201 | 0 | 7727.8401 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
281 | 276 | Onderhoudstoestellen gevel | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2015-01-09 08:00 | 1h | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
282 | 277 | Afwerking kopgevels | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-03 08:00 | 34d | 2.72 | 0 | 0 | 6734.7202 | 0 | 6737.4402 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
283 | 278 | Afwerking waterdichting op perron | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-10-20 08:00 | 5d | 0.4 | 0 | 0 | 990.4 | 0 | 990.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
284 | 279 | herstelling perronboorden | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-10-20 08:00 | 9d | 0.72 | 0 | 0 | 1782.72 | 0 | 1783.44 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
285 | 306 | KOK A - perron C | 2012-11-05 08:00 | 2013-12-13 17:00 | 290d |  |  | 0 |  |  | 20850.4004 |  | 221d 1h | [5 empty] | 48847.2403 |  | 1 |  | 20850.4004 | 20850.4004 | C2015-09 Railway Station (2).xlsx
286 | 281 | Staalstructuur | 2013-09-20 08:00 | 2013-10-10 17:00 | 15d |  | 0 | 0 | 12.01 | 1441.2 | 1441.2 | 2014-03-06 08:00 | 20d | 1921.6 | 0 | 0 | 0 | 0 | 1921.6 | 0 | 1 | Finished | 1441.2 | 1441.2 | C2015-09 Railway Station (2).xlsx
287 | 282 | Platen en goten dak staalstructuur | 2013-09-27 08:00 | 2013-10-24 17:00 | 20d |  | 0 | 0 | 12.01 | 1921.6 | 1921.6 | 2014-04-03 08:00 | 23d | 2209.84 | 0 | 0 | 0 | 0 | 2209.84 | 0 | 1 | Finished | 1921.6 | 1921.6 | C2015-09 Railway Station (2).xlsx
288 | 283 | Integratie technieken in KOK | 2013-10-04 08:00 | 2013-10-31 17:00 | 20d |  | 0 | 0 | 12.01 | 1921.6 | 1921.6 | 2014-05-06 08:00 | 15d | 1441.2 | 0 | 0 | 0 | 0 | 1441.2 | 0 | 1 | Finished | 1921.6 | 1921.6 | C2015-09 Railway Station (2).xlsx
289 | 284 | Beglazing gevel | 2013-10-18 08:00 | 2013-11-08 17:00 | 16d |  | 0 | 0 | 12.01 | 1537.28 | 1537.28 | 2014-05-12 08:00 | 17d | 1633.36 | 0 | 0 | 0 | 0 | 1633.36 | 0 | 1 | Finished | 1537.28 | 1537.28 | C2015-09 Railway Station (2).xlsx
290 | 285 | Waterdichting dak | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d |  | 0 | 0 | 12.01 | 2305.92 | 2305.92 | 2014-05-06 08:00 | 15d | 1441.2 | 0 | 0 | 0 | 0 | 1441.2 | 0 | 1 | Finished | 2305.92 | 2305.92 | C2015-09 Railway Station (2).xlsx
291 | 286 | Beplating onderkant dakstructuur | 2013-10-18 08:00 | 2013-11-08 17:00 | 16d |  | 0 | 0 | 12.01 | 1537.28 | 1537.28 | 2014-07-15 08:00 | 78d | 7494.2401 | 0 | 0 | 0 | 0 | 7494.2401 | 0 | 1 | Finished | 1537.28 | 1537.28 | C2015-09 Railway Station (2).xlsx
292 | 287 | Staalstructuur lichtstraat | 2013-10-04 08:00 | 2013-10-24 17:00 | 15d |  | 0 | 0 | 12.01 | 1441.2 | 1441.2 | 2014-05-12 08:00 | 17d | 1633.36 | 0 | 0 | 0 | 0 | 1633.36 | 0 | 1 | Finished | 1441.2 | 1441.2 | C2015-09 Railway Station (2).xlsx
293 | 288 | Integratie technieken in lichtstraat | 2013-10-11 08:00 | 2013-10-31 17:00 | 15d |  | 0 | 0 | 12.01 | 1441.2 | 1441.2 | 2014-05-19 08:00 | 18d | 1729.44 | 0 | 0 | 0 | 0 | 1729.44 | 0 | 1 | Finished | 1441.2 | 1441.2 | C2015-09 Railway Station (2).xlsx
294 | 289 | Beglazing lichtstraat | 2013-10-18 08:00 | 2013-11-08 17:00 | 16d |  | 0 | 0 | 12.01 | 1537.28 | 1537.28 | 2015-01-09 08:00 | 1h | 12.01 | 0 | 0 | 0 | 0 | 12.01 | 0 | 1 | Finished | 1537.28 | 1537.28 | C2015-09 Railway Station (2).xlsx
295 | 290 | Beplating lichtstraat | 2013-10-25 08:00 | 2013-11-19 17:00 | 18d |  | 0 | 0 | 12.01 | 1729.44 | 1729.44 | 2014-09-04 08:00 | 35d | 3362.8001 | 0 | 0 | 0 | 0 | 3362.8001 | 0 | 1 | Finished | 1729.44 | 1729.44 | C2015-09 Railway Station (2).xlsx
296 | 291 | Bevloering perron | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d |  | 0 | 0 | 12.01 | 2305.92 | 2305.92 | 2014-07-01 08:00 | 88d | 8455.0402 | 0 | 0 | 0 | 0 | 8455.0402 | 0 | 1 | Finished | 2305.92 | 2305.92 | C2015-09 Railway Station (2).xlsx
297 | 292 | Ophangtoestellen op perron | 2013-11-20 08:00 | 2013-12-13 17:00 | 18d |  | 0 | 0 | 12.01 | 1729.44 | 1729.44 | 2015-01-09 08:00 | 1h | 12.01 | 0 | 0 | 0 | 0 | 12.01 | 0 | 1 | Finished | 1729.44 | 1729.44 | C2015-09 Railway Station (2).xlsx
298 | 293 | Structuur levenslijn | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-10-20 08:00 | 11d | 0.88 | 0 | 0 | 1056.88 | 0 | 1057.76 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
299 | 294 | Plaatsing standleidingen | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-04-03 08:00 | 10d | 0.8 | 0 | 0 | 960.8 | 0 | 961.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
300 | 295 | Plaatsing overstorten | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-05-06 08:00 | 10d | 0.8 | 0 | 0 | 960.8 | 0 | 961.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
301 | 296 | Profielen ballustrades | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2015-01-09 08:00 | 1h | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
302 | 297 | Kaders voor beglazing lichtstraat | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-08-13 08:00 | 16d | 1.28 | 0 | 0 | 1537.28 | 0 | 1538.56 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
303 | 298 | Waterdichting op perron | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-06-13 08:00 | 10d | 0.8 | 0 | 0 | 960.8 | 0 | 961.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
304 | 299 | Perronboorden | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-06-20 08:00 | 10d | 0.8 | 0 | 0 | 960.8 | 0 | 961.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
305 | 300 | Bekabeling in perronboorden | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-06-20 08:00 | 10d | 0.8 | 0 | 0 | 960.8 | 0 | 961.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
306 | 301 | Afwerking ballustrades | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2015-01-09 08:00 | 1h | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
307 | 302 | Waterdichting en gietasfalt spoorbak | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-04-16 08:00 | 17d | 1.36 | 0 | 0 | 1633.36 | 0 | 1634.72 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
308 | 303 | Beglazing lichtstraat | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-08 09:00 | 66d | 5.28 | 0 | 0 | 6341.2798 | 0 | 6346.5598 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
309 | 304 | Afwerking glas zitbanken | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-10-01 08:00 | 10d | 0.8 | 0 | 0 | 960.8 | 0 | 961.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
310 | 305 | Afwerking zitbanken | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-11-27 08:00 | 12d | 0.96 | 0 | 0 | 1152.96 | 0 | 1153.92 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
311 | 314 | KOK A - perron B | 2013-10-04 08:00 | 2014-03-13 17:00 | 115d |  |  | 0 |  |  | 20272.8804 |  | 1h | [5 empty] | 84.07 |  | 1 |  | 20272.8804 | 20272.8804 | C2015-09 Railway Station (2).xlsx
312 | 307 | Staalstructuur | 2013-10-04 08:00 | 2013-10-31 17:00 | 20d |  | 0 | 0 | 12.01 | 1921.6 | 1921.6 | 2015-01-09 08:00 | 1h | 12.01 | 0 | 0 | 0 | 0 | 12.01 | 0 | 1 | Finished | 1921.6 | 1921.6 | C2015-09 Railway Station (2).xlsx
313 | 308 | Platen en gote dak staalstructuur | 2013-10-25 08:00 | 2013-11-26 17:00 | 23d |  | 0 | 0 | 12.01 | 2209.84 | 2209.84 | 2015-01-09 08:00 | 1h | 12.01 | 0 | 0 | 0 | 0 | 12.01 | 0 | 1 | Finished | 2209.84 | 2209.84 | C2015-09 Railway Station (2).xlsx
314 | 309 | Integratie technieken KOK | 2013-11-04 08:00 | 2013-12-13 17:00 | 30d |  | 0 | 0 | 12.01 | 2882.4001 | 2882.4001 | 2015-01-09 08:00 | 1h | 12.01 | 0 | 0 | 0 | 0 | 12.01 | 0 | 1 | Finished | 2882.4001 | 2882.4001 | C2015-09 Railway Station (2).xlsx
315 | 310 | Waterdichting dak | 2013-11-20 08:00 | 2013-12-20 17:00 | 23d |  | 0 | 0 | 12.01 | 2209.84 | 2209.84 | 2015-01-09 08:00 | 1h | 12.01 | 0 | 0 | 0 | 0 | 12.01 | 0 | 1 | Finished | 2209.84 | 2209.84 | C2015-09 Railway Station (2).xlsx
316 | 311 | Beplating onderkant dakstructuur | 2013-11-28 08:00 | 2014-01-14 17:00 | 34d |  | 0 | 0 | 12.01 | 3266.7201 | 3266.7201 | 2015-01-09 08:00 | 1h | 12.01 | 0 | 0 | 0 | 0 | 12.01 | 0 | 1 | Finished | 3266.7201 | 3266.7201 | C2015-09 Railway Station (2).xlsx
317 | 312 | Bevloering perron | 2013-12-16 08:00 | 2014-02-25 17:00 | 52d |  | 0 | 0 | 12.01 | 4996.1601 | 4996.1601 | 2015-01-09 08:00 | 1h | 12.01 | 0 | 0 | 0 | 0 | 12.01 | 0 | 1 | Finished | 4996.1601 | 4996.1601 | C2015-09 Railway Station (2).xlsx
318 | 313 | Ophangtoestellen op perron | 2014-02-03 08:00 | 2014-03-13 17:00 | 29d |  | 0 | 0 | 12.01 | 2786.3201 | 2786.3201 | 2015-01-09 08:00 | 1h | 12.01 | 0 | 0 | 0 | 0 | 12.01 | 0 | 1 | Finished | 2786.3201 | 2786.3201 | C2015-09 Railway Station (2).xlsx
319 | 341 | KOK B - perron C | 2012-11-05 08:00 | 2013-12-06 17:00 | 285d |  |  | 0 |  |  | 22579.12 |  | 224d 1h | [5 empty] | 41835.96 |  | 1 |  | 22579.12 | 22579.12 | C2015-09 Railway Station (2).xlsx
320 | 315 | Staalstructuur | 2013-09-02 08:00 | 2013-09-20 17:00 | 15d |  | 0 | 0 | 13.25 | 1590 | 1590 | 2014-03-03 08:00 | 16d | 1696 | 0 | 0 | 0 | 0 | 1696 | 0 | 1 | Finished | 1590 | 1590 | C2015-09 Railway Station (2).xlsx
321 | 316 | Platen en goten dak staalstructuur | 2013-09-09 08:00 | 2013-10-04 17:00 | 20d |  | 0 | 0 | 13.25 | 2120 | 2120 | 2014-03-28 08:00 | 21d | 2226 | 0 | 0 | 0 | 0 | 2226 | 0 | 1 | Finished | 2120 | 2120 | C2015-09 Railway Station (2).xlsx
322 | 317 | Integratie technieken in KOK | 2013-09-16 08:00 | 2013-10-18 17:00 | 25d |  | 0 | 0 | 13.25 | 2650 | 2650 | 2014-04-04 08:00 | 16d | 1696 | 0 | 0 | 0 | 0 | 1696 | 0 | 1 | Finished | 2650 | 2650 | C2015-09 Railway Station (2).xlsx
323 | 318 | Beglazing gevel | 2013-09-30 08:00 | 2013-10-18 17:00 | 15d |  | 0 | 0 | 13.25 | 1590 | 1590 | 2014-04-23 08:00 | 17d | 1802 | 0 | 0 | 0 | 0 | 1802 | 0 | 1 | Finished | 1590 | 1590 | C2015-09 Railway Station (2).xlsx
324 | 319 | Waterdichting dak | 2013-10-14 08:00 | 2013-11-04 17:00 | 16d |  | 0 | 0 | 13.25 | 1696 | 1696 | 2014-04-18 08:00 | 16d | 1696 | 0 | 0 | 0 | 0 | 1696 | 0 | 1 | Finished | 1696 | 1696 | C2015-09 Railway Station (2).xlsx
325 | 320 | Beplating onderkant dakstructuur | 2013-10-07 08:00 | 2013-10-25 17:00 | 15d |  | 0 | 0 | 13.25 | 1590 | 1590 | 2014-05-08 08:00 | 15d | 1590 | 0 | 0 | 0 | 0 | 1590 | 0 | 1 | Finished | 1590 | 1590 | C2015-09 Railway Station (2).xlsx
326 | 321 | Staalstructuur lichtstraat | 2013-09-16 08:00 | 2013-10-04 17:00 | 15d |  | 0 | 0 | 13.25 | 1590 | 1590 | 2015-01-09 08:00 | 1h | 13.25 | 0 | 0 | 0 | 0 | 13.25 | 0 | 1 | Finished | 1590 | 1590 | C2015-09 Railway Station (2).xlsx
327 | 322 | Integratie technieken in lichtstraat | 2013-09-23 08:00 | 2013-10-11 17:00 | 15d |  | 0 | 0 | 13.25 | 1590 | 1590 | 2015-01-09 08:00 | 1h | 13.25 | 0 | 0 | 0 | 0 | 13.25 | 0 | 1 | Finished | 1590 | 1590 | C2015-09 Railway Station (2).xlsx
328 | 323 | Beglazing lichtstraat | 2013-09-30 08:00 | 2013-10-18 17:00 | 15d |  | 0 | 0 | 13.25 | 1590 | 1590 | 2015-01-09 08:00 | 1h | 13.25 | 0 | 0 | 0 | 0 | 13.25 | 0 | 1 | Finished | 1590 | 1590 | C2015-09 Railway Station (2).xlsx
329 | 324 | Beplating lichtstraat | 2013-10-07 08:00 | 2013-10-25 17:00 | 15d |  | 0 | 0 | 13.25 | 1590 | 1590 | 2015-01-09 08:00 | 1h | 13.25 | 0 | 0 | 0 | 0 | 13.25 | 0 | 1 | Finished | 1590 | 1590 | C2015-09 Railway Station (2).xlsx
330 | 325 | Bevloering perron | 2013-10-21 08:00 | 2013-11-20 17:00 | 23d |  | 0 | 0 | 13.25 | 2438 | 2438 | 2014-05-20 08:00 | 12d | 1272 | 0 | 0 | 0 | 0 | 1272 | 0 | 1 | Finished | 2438 | 2438 | C2015-09 Railway Station (2).xlsx
331 | 326 | Ophangtoestellen op perron | 2013-11-05 08:00 | 2013-12-06 17:00 | 24d |  | 0 | 0 | 13.25 | 2544 | 2544 | 2014-09-01 08:00 | 44d | 4664 | 0 | 0 | 0 | 0 | 4664 | 0 | 1 | Finished | 2544 | 2544 | C2015-09 Railway Station (2).xlsx
332 | 327 | Structuur levenslijn | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-07-07 08:00 | 10d | 0.8 | 0 | 0 | 1060 | 0 | 1060.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
333 | 328 | Plaatsing standleidingen | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-04-04 08:00 | 10d | 0.8 | 0 | 0 | 1060 | 0 | 1060.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
334 | 329 | Plaatsing overstorten | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-04-11 08:00 | 11d | 0.88 | 0 | 0 | 1166 | 0 | 1166.88 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
335 | 330 | Waterdichting perron | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-05-07 08:00 | 10d | 0.8 | 0 | 0 | 1060 | 0 | 1060.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
336 | 331 | Perronboorden | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-05-13 08:00 | 10d | 0.8 | 0 | 0 | 1060 | 0 | 1060.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
337 | 332 | Bekabeling in perronboorden | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-05-13 08:00 | 10d | 0.8 | 0 | 0 | 1060 | 0 | 1060.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
338 | 333 | Afwerken ballustrades | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-05-26 08:00 | 10d | 0.8 | 0 | 0 | 1060 | 0 | 1060.8 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
339 | 334 | Integratie schouw voor technische lokaal | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-04-04 08:00 | 14d | 1.12 | 0 | 0 | 1484 | 0 | 1485.12 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
340 | 335 | Waterdichting en gietasfalt spoorbak | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-04-09 08:00 | 11d | 0.88 | 0 | 0 | 1166 | 0 | 1166.88 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
341 | 336 | Afwerking voegen vloer | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-08-21 08:00 | 45d | 3.6 | 0 | 0 | 4770 | 0 | 4773.6 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
342 | 337 | Afwerking beplating kolommen | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-08-21 08:00 | 40d | 3.2 | 0 | 0 | 4240 | 0 | 4243.2 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
343 | 338 | Afwerking luifels en vleugels | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-08 09:00 | 38d | 3.04 | 0 | 0 | 4028 | 0 | 4031.04 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
344 | 339 | Afwerking zitbanken | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-11-27 08:00 | 12d | 0.96 | 0 | 0 | 1272 | 0 | 1272.96 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
345 | 340 | Plaatsing afwerking schouw | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-12-01 08:00 | 6d | 0.48 | 0 | 0 | 636 | 0 | 636.48 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
346 | 349 | KOK B - perron B | 2013-05-17 08:00 | 2013-09-10 17:00 | 83d |  |  | 0 |  |  | 18550 |  | 1h | [5 empty] | 92.75 |  | 1 |  | 18550 | 18550 | C2015-09 Railway Station (2).xlsx
347 | 342 | Staalstructuur | 2013-05-17 08:00 | 2013-06-14 17:00 | 21d |  | 0 | 0 | 13.25 | 2226 | 2226 | 2015-01-09 08:00 | 1h | 13.25 | 0 | 0 | 0 | 0 | 13.25 | 0 | 1 | Finished | 2226 | 2226 | C2015-09 Railway Station (2).xlsx
348 | 343 | Platen en goten dak staalstructuur | 2013-06-03 08:00 | 2013-06-28 17:00 | 20d |  | 0 | 0 | 13.25 | 2120 | 2120 | 2015-01-09 08:00 | 1h | 13.25 | 0 | 0 | 0 | 0 | 13.25 | 0 | 1 | Finished | 2120 | 2120 | C2015-09 Railway Station (2).xlsx
349 | 344 | Integratie technieken in KOK | 2013-06-10 08:00 | 2013-07-12 17:00 | 25d |  | 0 | 0 | 13.25 | 2650 | 2650 | 2015-01-09 08:00 | 1h | 13.25 | 0 | 0 | 0 | 0 | 13.25 | 0 | 1 | Finished | 2650 | 2650 | C2015-09 Railway Station (2).xlsx
350 | 345 | Waterdichting dak | 2013-06-24 08:00 | 2013-07-19 17:00 | 20d |  | 0 | 0 | 13.25 | 2120 | 2120 | 2015-01-09 08:00 | 1h | 13.25 | 0 | 0 | 0 | 0 | 13.25 | 0 | 1 | Finished | 2120 | 2120 | C2015-09 Railway Station (2).xlsx
351 | 346 | Beplating onderkant dakstructuur | 2013-07-01 08:00 | 2013-08-09 17:00 | 30d |  | 0 | 0 | 13.25 | 3180 | 3180 | 2015-01-09 08:00 | 1h | 13.25 | 0 | 0 | 0 | 0 | 13.25 | 0 | 1 | Finished | 3180 | 3180 | C2015-09 Railway Station (2).xlsx
352 | 347 | Bevloering perron | 2013-07-15 08:00 | 2013-09-03 17:00 | 37d |  | 0 | 0 | 13.25 | 3922 | 3922 | 2015-01-09 08:00 | 1h | 13.25 | 0 | 0 | 0 | 0 | 13.25 | 0 | 1 | Finished | 3922 | 3922 | C2015-09 Railway Station (2).xlsx
353 | 348 | Ophangtoestellen op perron | 2013-08-12 08:00 | 2013-09-10 17:00 | 22d |  | 0 | 0 | 13.25 | 2332 | 2332 | 2015-01-09 08:00 | 1h | 13.25 | 0 | 0 | 0 | 0 | 13.25 | 0 | 1 | Finished | 2332 | 2332 | C2015-09 Railway Station (2).xlsx
354 | 371 | Accessoires | 2012-11-05 08:00 | 2013-12-19 17:00 | 294d |  |  | 0 |  |  | 62900.3982 |  | 171d 1h | [5 empty] | 146839.1588 |  | 1 |  | 62900.3982 | 62900.3982 | C2015-09 Railway Station (2).xlsx
355 | 350 | Lokaaltjes op perron | 2013-10-18 08:00 | 2013-12-05 17:00 | 35d |  | 0 | 0 | 54.6 | 15287.9996 | 15287.9996 | 2015-01-09 08:00 | 1h | 54.6 | 0 | 0 | 0 | 0 | 54.6 | 0 | 1 | Finished | 15287.9996 | 15287.9996 | C2015-09 Railway Station (2).xlsx
356 | 351 | Integratie technieken in accessoires | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d |  | 0 | 0 | 54.6 | 10483.1997 | 10483.1997 | 2014-09-18 08:00 | 22d | 9609.5997 | 0 | 0 | 0 | 0 | 9609.5997 | 0 | 1 | Finished | 10483.1997 | 10483.1997 | C2015-09 Railway Station (2).xlsx
357 | 352 | Omkasting drankautomaten | 2013-11-12 08:00 | 2013-12-13 17:00 | 24d |  | 0 | 0 | 54.6 | 10483.1997 | 10483.1997 | 2014-10-15 08:00 | 10d | 4367.9999 | 0 | 0 | 0 | 0 | 4367.9999 | 0 | 1 | Finished | 10483.1997 | 10483.1997 | C2015-09 Railway Station (2).xlsx
358 | 353 | Zitbanken | 2013-11-12 08:00 | 2013-12-13 17:00 | 24d |  | 0 | 0 | 54.6 | 10483.1997 | 10483.1997 | 2014-10-20 08:00 | 22d | 9609.5997 | 0 | 0 | 0 | 0 | 9609.5997 | 0 | 1 | Finished | 10483.1997 | 10483.1997 | C2015-09 Railway Station (2).xlsx
359 | 354 | Omkasting andere automaten | 2013-11-12 08:00 | 2013-12-13 17:00 | 24d |  | 0 | 0 | 54.6 | 10483.1997 | 10483.1997 | 2014-05-15 08:00 | 23d | 10046.3997 | 0 | 0 | 0 | 0 | 10046.3997 | 0 | 1 | Finished | 10483.1997 | 10483.1997 | C2015-09 Railway Station (2).xlsx
360 | 355 | Afsluiting toegang reizigers | 2013-12-03 08:00 | 2013-12-19 17:00 | 13d |  | 0 | 0 | 54.6 | 5678.3998 | 5678.3998 | 2014-05-22 08:00 | 12d | 5241.5999 | 0 | 0 | 0 | 0 | 5241.5999 | 0 | 1 | Finished | 5678.3998 | 5678.3998 | C2015-09 Railway Station (2).xlsx
361 | 356 | Beglaasde portieken GOK - kaders | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-10-22 08:00 | 19d | 1.52 | 0 | 0 | 8299.2002 | 0 | 8300.7202 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
362 | 357 | Beglaasde portieken GOK - integratie elek. | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-10-29 08:00 | 19d | 1.52 | 0 | 0 | 8299.2002 | 0 | 8300.7202 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
363 | 358 | Beglaasde portieken GOK - bekledingen | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-10-29 08:00 | 19d | 1.52 | 0 | 0 | 8299.2002 | 0 | 8300.7202 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
364 | 359 | Beglaasde portieken GOK - beglazing | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-11-13 08:00 | 14d | 1.12 | 0 | 0 | 6115.2002 | 0 | 6116.3202 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
365 | 360 | Afstandbordjes, etc | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-10 08:00 | 11d | 0.88 | 0 | 0 | 4804.7998 | 0 | 4805.6798 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
366 | 361 | Installatie en afwerking technieken perron | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-30 08:00 | 11d | 0.88 | 0 | 0 | 4804.7998 | 0 | 4805.6798 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
367 | 362 | Oplossen opmerkingen ivm indienststelling | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-11-04 08:00 | 25d | 2 | 0 | 0 | 10920 | 0 | 10922 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
368 | 363 | Afwerking spoorbak | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-08-25 08:00 | 12d | 0.96 | 0 | 0 | 5241.6001 | 0 | 5242.5601 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
369 | 364 | Drainageleiding | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-08-25 08:00 | 15d | 1.2 | 0 | 0 | 6552 | 0 | 6553.2 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
370 | 365 | Plaatsing buizen riolering | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-08 09:00 | 6d | 0.48 | 0 | 0 | 2620.8 | 0 | 2621.28 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
371 | 366 | Omkasting brandweerkast | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-08-05 08:00 | 11d | 0.88 | 0 | 0 | 4804.7998 | 0 | 4805.6798 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
372 | 367 | Belettering gevel | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-08 09:00 | 30d | 2.4 | 0 | 0 | 13104 | 0 | 13106.4 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
373 | 368 | Omkasting brandbluskasten | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-09-16 08:00 | 22d | 1.76 | 0 | 0 | 9609.5996 | 0 | 9611.3596 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
374 | 369 | Schermen en ophangingen bovenleiding | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-10-01 08:00 | 26d | 2.08 | 0 | 0 | 11356.7998 | 0 | 11358.8798 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
375 | 370 | Akoestische cassetten | 2012-11-05 08:00 | 2012-11-05 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2014-11-27 08:00 | 7d | 0.56 | 0 | 0 | 3057.6001 | 0 | 3058.1601 | 0 | 1 | Finished | 0.08 | 0.08 | C2015-09 Railway Station (2).xlsx
4 | 0 | Tax Return System (1) | 2014-02-18 08:00 | 2014-06-16 17:00 | 85d |  |  | 0 |  |  | 18990 |  | 85d | [5 empty] | 8010 |  | 1 |  | 18990 | 18990 | C2015-10 Tax Return System (1).xlsx
5 | 21 | supporting tasks | 2014-02-18 08:00 | 2014-02-20 14:00 | 2d 5h |  |  | 0 |  |  | 1890 |  | 2d 3h | [5 empty] | 1710 |  | 1 |  | 1890 | 1890 | C2015-10 Tax Return System (1).xlsx
6 | 1 | project management | 2014-02-18 08:00 | 2014-02-20 14:00 | 2d 5h | Employee A | 1890 | 0 | 0 | 0 | 1890 | 2014-02-18 08:00 | 2d 3h | 1710 | 0 | 0 | 0 | 0 | 1710 | 0 | 1 | Finished | 1890 | 1890 | C2015-10 Tax Return System (1).xlsx
7 | 22 | design | 2014-03-03 08:00 | 2014-04-01 17:00 | 22d |  |  | 0 |  |  | 6150 |  | 31d 7h | [5 empty] | 4050 |  | 1 |  | 6150 | 6150 | C2015-10 Tax Return System (1).xlsx
8 | 2 | design - corp/AIA | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee B | 1125 | 0 | 0 | 0 | 1125 | 2014-03-03 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 1125 | 1125 | C2015-10 Tax Return System (1).xlsx
9 | 3 | design - DWH | 2014-03-24 08:00 | 2014-03-26 12:00 | 2d 4h | Employee C | 1500 | 0 | 0 | 0 | 1500 | 2014-03-31 08:00 | 2d 4h | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 1 | Finished | 1500 | 1500 | C2015-10 Tax Return System (1).xlsx
10 | 4 | design - DWH | 2014-03-24 08:00 | 2014-03-25 17:00 | 2d | Employee D | 1200 | 0 | 0 | 0 | 1200 | 2014-03-31 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 1 | Finished | 1200 | 1200 | C2015-10 Tax Return System (1).xlsx
11 | 5 | design - HP | 2014-03-03 08:00 | 2014-03-05 16:00 | 2d 7h | Employee F | 1725 | 0 | 0 | 0 | 1725 | 2014-03-10 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 1 | Finished | 1725 | 1725 | C2015-10 Tax Return System (1).xlsx
12 | 6 | deisgn - TGL | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2014-02-24 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 600 | 600 | C2015-10 Tax Return System (1).xlsx
13 | 7 | design validated | 2014-04-01 17:00 | 2014-04-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-08 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-10 Tax Return System (1).xlsx
14 | 23 | development | 2014-03-24 08:00 | 2014-04-24 16:00 | 23d 7h |  |  | 0 |  |  | 6450 |  | 21d 1h | [5 empty] | 825 |  | 1 |  | 6450 | 6450 | C2015-10 Tax Return System (1).xlsx
15 | 8 | development - corp/AIA | 2014-03-24 08:00 | 2014-03-25 16:00 | 1d 7h | Employee B | 1125 | 0 | 0 | 0 | 1125 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1125 | 1125 | C2015-10 Tax Return System (1).xlsx
16 | 9 | development - DWH | 2014-04-22 08:00 | 2014-04-24 16:00 | 2d 7h | Employee I | 1725 | 0 | 0 | 0 | 1725 | 2014-04-22 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1725 | 1725 | C2015-10 Tax Return System (1).xlsx
17 | 10 | development - HP | 2014-03-24 08:00 | 2014-03-26 16:00 | 2d 7h | Employee J | 1725 | 0 | 0 | 0 | 1725 | 2014-03-31 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 1725 | 1725 | C2015-10 Tax Return System (1).xlsx
18 | 11 | development - TGL | 2014-04-07 08:00 | 2014-04-10 09:00 | 3d 1h | Employee G | 1875 | 0 | 0 | 0 | 1875 | 2014-04-07 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 1875 | 1875 | C2015-10 Tax Return System (1).xlsx
19 | 12 | development DWH completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-10 Tax Return System (1).xlsx
20 | 24 | test | 2014-05-05 08:00 | 2014-06-13 17:00 | 30d |  |  | 0 |  |  | 3900 |  | 35d 1h | [5 empty] | 825 |  | 1 |  | 3900 | 3900 | C2015-10 Tax Return System (1).xlsx
21 | 13 | test TGL | 2014-05-05 08:00 | 2014-05-05 15:00 | 6h | Employee G | 450 | 0 | 0 | 0 | 450 | 2014-04-14 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 1 | Finished | 450 | 450 | C2015-10 Tax Return System (1).xlsx
22 | 14 | test corp/AIA | 2014-06-02 08:00 | 2014-06-03 16:00 | 1d 7h | Employee B | 1125 | 0 | 0 | 0 | 1125 | 2014-06-02 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1125 | 1125 | C2015-10 Tax Return System (1).xlsx
23 | 15 | test DWH | 2014-05-05 08:00 | 2014-05-05 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 | 2014-05-05 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 600 | 600 | C2015-10 Tax Return System (1).xlsx
24 | 16 | test HP | 2014-05-05 08:00 | 2014-05-07 16:00 | 2d 7h | Employee F | 1725 | 0 | 0 | 0 | 1725 | 2014-04-21 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 1725 | 1725 | C2015-10 Tax Return System (1).xlsx
25 | 17 | test DWH completed | 2014-06-13 17:00 | 2014-06-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-06-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-10 Tax Return System (1).xlsx
26 | 25 | implementation | 2014-06-16 08:00 | 2014-06-16 17:00 | 1d |  |  | 0 |  |  | 600 |  | 1d | [5 empty] | 600 |  | 1 |  | 600 | 600 | C2015-10 Tax Return System (1).xlsx
27 | 18 | execution | 2014-06-16 08:00 | 2014-06-16 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 | 2014-06-16 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 1 | Finished | 600 | 600 | C2015-10 Tax Return System (1).xlsx
28 | 19 | implementation | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-06-16 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-10 Tax Return System (1).xlsx
29 | 20 | go live | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-06-16 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-10 Tax Return System (1).xlsx
4 | 0 | Staff Authorization System | 2014-02-24 08:00 | 2014-05-09 17:00 | 55d |  |  | 0 |  |  | 14400 |  | 54d 7h | [5 empty] | 9105 |  | 1 |  | 14400 | 14400 | C2015-11 Staff Authorization System.xlsx
5 | 14 | supporting tasks | 2014-02-26 08:00 | 2014-04-16 15:00 | 35d 6h |  |  | 0 |  |  | 3525 |  | 35d 1h | [5 empty] | 1950 |  | 1 |  | 3525 | 3525 | C2015-11 Staff Authorization System.xlsx
6 | 1 | project management | 2014-02-26 08:00 | 2014-02-28 12:00 | 2d 4h | Employee A | 1800 | 0 | 0 | 0 | 1800 | 2014-02-24 08:00 | 2d 4h | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 1 | Finished | 1800 | 1800 | C2015-11 Staff Authorization System.xlsx
7 | 2 | validation and support | 2014-04-14 08:00 | 2014-04-14 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 2014-04-14 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 75 | 75 | C2015-11 Staff Authorization System.xlsx
8 | 3 | validation and support | 2014-04-14 08:00 | 2014-04-16 15:00 | 2d 6h | Employee C | 1650 | 0 | 0 | 0 | 1650 | 2014-04-14 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1650 | 1650 | C2015-11 Staff Authorization System.xlsx
9 | 15 | requirements | 2014-02-24 08:00 | 2014-02-28 17:00 | 5d |  |  | 0 |  |  | 1275 |  | 4d 7h | [5 empty] | 1275 |  | 1 |  | 1275 | 1275 | C2015-11 Staff Authorization System.xlsx
10 | 4 | requirements | 2014-02-24 08:00 | 2014-02-26 09:00 | 2d 1h | Employee D | 1275 | 0 | 0 | 0 | 1275 | 2014-02-24 08:00 | 2d 1h | 1275 | 0 | 0 | 0 | 0 | 1275 | 0 | 1 | Finished | 1275 | 1275 | C2015-11 Staff Authorization System.xlsx
11 | 5 | requirements validated | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-28 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-11 Staff Authorization System.xlsx
12 | 16 | analysis | 2014-02-25 08:00 | 2014-03-19 17:00 | 17d |  |  | 0 |  |  | 4500 |  | 41d 7h | [5 empty] | 4680 |  | 1 |  | 4500 | 4500 | C2015-11 Staff Authorization System.xlsx
13 | 6 | analysis - business analysis | 2014-02-25 08:00 | 2014-03-05 10:00 | 6d 2h | Employee A | 4500 | 0 | 0 | 0 | 4500 | 2014-02-24 08:00 | 6d 4h | 4680 | 0 | 0 | 0 | 0 | 4680 | 0 | 1 | Finished | 4500 | 4500 | C2015-11 Staff Authorization System.xlsx
14 | 7 | analysis validated | 2014-03-19 17:00 | 2014-03-19 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-22 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-11 Staff Authorization System.xlsx
15 | 17 | development | 2014-03-03 08:00 | 2014-03-31 17:00 | 21d |  |  | 0 |  |  | 5100 |  | 26d 7h | [5 empty] | 1200 |  | 1 |  | 5100 | 5100 | C2015-11 Staff Authorization System.xlsx
16 | 8 | development - coding | 2014-03-03 08:00 | 2014-03-06 15:00 | 3d 6h | Employee D | 2250 | 0 | 0 | 0 | 2250 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 2250 | 2250 | C2015-11 Staff Authorization System.xlsx
17 | 9 | development - bugfixing and support | 2014-03-17 08:00 | 2014-03-21 15:00 | 4d 6h | Employee D | 2850 | 0 | 0 | 0 | 2850 | 2014-03-31 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 1 | Finished | 2850 | 2850 | C2015-11 Staff Authorization System.xlsx
18 | 10 | development completed | 2014-03-31 17:00 | 2014-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-08 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-11 Staff Authorization System.xlsx
19 | 18 | implementation | 2014-03-21 17:00 | 2014-05-09 17:00 | 35d |  |  | 0 |  |  | 0 |  | 35d | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-11 Staff Authorization System.xlsx
20 | 11 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-11 Staff Authorization System.xlsx
21 | 12 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-11 Staff Authorization System.xlsx
22 | 13 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-11 Staff Authorization System.xlsx
4 | 0 | Premium Payment System | 2014-01-28 08:00 | 2014-10-10 17:00 | 184d |  |  | 0 |  |  | 132570 |  | 183d 7h | [5 empty] | 58410 |  | 1 |  | 132570 | 132570 | C2015-12 Premium Payment System.xlsx
5 | 67 | supporting tasks | 2014-01-28 08:00 | 2014-03-13 16:00 | 32d 7h |  |  | 0 |  |  | 44145 |  | 34d 3h | [5 empty] | 11910 |  | 1 |  | 44145 | 44145 | C2015-12 Premium Payment System.xlsx
6 | 1 | project management | 2014-01-28 08:00 | 2014-03-13 16:00 | 32d 7h | Employee A | 23670 | 0 | 0 | 0 | 23670 | 2014-01-28 08:00 | 6d 6h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 1 | Finished | 23670 | 23670 | C2015-12 Premium Payment System.xlsx
7 | 2 | validation and support | 2014-02-10 08:00 | 2014-02-25 10:00 | 11d 2h | Employee C | 6750 | 0 | 0 | 0 | 6750 | 2014-03-10 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 6750 | 6750 | C2015-12 Premium Payment System.xlsx
8 | 3 | validation and support | 2014-02-10 08:00 | 2014-02-19 12:00 | 7d 4h | Employee G | 4500 | 0 | 0 | 0 | 4500 | 2014-02-10 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 1 | Finished | 4500 | 4500 | C2015-12 Premium Payment System.xlsx
9 | 4 | validation and support | 2014-02-10 08:00 | 2014-02-10 15:00 | 6h | Employee H | 450 | 0 | 0 | 0 | 450 | 2014-02-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 450 | 450 | C2015-12 Premium Payment System.xlsx
10 | 5 | validation and support | 2014-02-10 08:00 | 2014-02-12 16:00 | 2d 7h | Employee I | 1725 | 0 | 0 | 0 | 1725 | 2014-02-24 08:00 | 4d 4h | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 1 | Finished | 1725 | 1725 | C2015-12 Premium Payment System.xlsx
11 | 6 | validation and support | 2014-02-10 08:00 | 2014-02-17 11:00 | 5d 3h | Employee J | 3225 | 0 | 0 | 0 | 3225 | 2014-03-17 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 1 | Finished | 3225 | 3225 | C2015-12 Premium Payment System.xlsx
12 | 7 | validation and support | 2014-02-10 08:00 | 2014-02-18 10:00 | 6d 2h | Employee K | 3750 | 0 | 0 | 0 | 3750 | 2014-02-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 3750 | 3750 | C2015-12 Premium Payment System.xlsx
13 | 8 | validation and support | 2014-02-10 08:00 | 2014-02-10 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 2014-02-10 08:00 | 3d 5h | 2175 | 0 | 0 | 0 | 0 | 2175 | 0 | 1 | Finished | 75 | 75 | C2015-12 Premium Payment System.xlsx
14 | 68 | analysis | 2014-02-11 08:00 | 2014-04-25 17:00 | 54d |  |  | 0 |  |  | 22200 |  | 54d 7h | [5 empty] | 20700 |  | 1 |  | 22200 | 22200 | C2015-12 Premium Payment System.xlsx
15 | 9 | analysis - aanpassing aanbieding | 2014-02-11 08:00 | 2014-02-24 15:00 | 9d 6h | Employee G | 5850 | 0 | 0 | 0 | 5850 | 2014-02-10 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 1 | Finished | 5850 | 5850 | C2015-12 Premium Payment System.xlsx
16 | 10 | analysis - boeking teruggave | 2014-02-17 08:00 | 2014-02-21 09:00 | 4d 1h | Employee C | 2475 | 0 | 0 | 0 | 2475 | 2014-02-17 08:00 | 3d 6h | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 1 | Finished | 2475 | 2475 | C2015-12 Premium Payment System.xlsx
17 | 11 | analysis - convertie teruggaves | 2014-02-17 08:00 | 2014-02-25 14:00 | 6d 5h | Employee K | 3975 | 0 | 0 | 0 | 3975 | 2014-03-17 08:00 | 9d 4h | 5700 | 0 | 0 | 0 | 0 | 5700 | 0 | 1 | Finished | 3975 | 3975 | C2015-12 Premium Payment System.xlsx
18 | 14 | analysis - lay-out brief | 2014-02-17 08:00 | 2014-02-27 17:00 | 9d | Employee K | 5400 | 0 | 0 | 0 | 5400 | 2014-02-17 08:00 | 14d 3h | 8625 | 0 | 0 | 0 | 0 | 8625 | 0 | 1 | Finished | 5400 | 5400 | C2015-12 Premium Payment System.xlsx
19 | 15 | analysis - methode fractioneren | 2014-02-11 08:00 | 2014-02-12 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 | 2014-02-10 08:00 | 3d 2h | 1950 | 0 | 0 | 0 | 0 | 1950 | 0 | 1 | Finished | 1050 | 1050 | C2015-12 Premium Payment System.xlsx
20 | 16 | analysis - proces opzetten | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 1 | Finished | 600 | 600 | C2015-12 Premium Payment System.xlsx
21 | 17 | analysis - stopzetten afbetalingsplan | 2014-03-24 08:00 | 2014-03-28 15:00 | 4d 6h | Employee K | 2850 | 0 | 0 | 0 | 2850 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 2850 | 2850 | C2015-12 Premium Payment System.xlsx
22 | 18 | analysis validated | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-12 Premium Payment System.xlsx
23 | 69 | design | 2014-02-10 08:00 | 2014-05-29 17:00 | 79d |  |  | 0 |  |  | 29175 |  | 78d 7h | [5 empty] | 20700 |  | 1 |  | 29175 | 29175 | C2015-12 Premium Payment System.xlsx
24 | 19 | design - aanleveren input | 2014-03-17 08:00 | 2014-03-26 12:00 | 7d 4h | Employee I | 4500 | 0 | 0 | 0 | 4500 | 2014-03-17 08:00 | 7d 1h | 4275 | 0 | 0 | 0 | 0 | 4275 | 0 | 1 | Finished | 4500 | 4500 | C2015-12 Premium Payment System.xlsx
25 | 20 | design - aanpassingen aanbieding | 2014-03-17 08:00 | 2014-03-25 14:00 | 6d 5h | Employee E | 3975 | 0 | 0 | 0 | 3975 | 2014-03-17 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 1 | Finished | 3975 | 3975 | C2015-12 Premium Payment System.xlsx
26 | 21 | design - boeking teruggave | 2014-03-10 08:00 | 2014-03-14 15:00 | 4d 6h | Employee E | 2850 | 0 | 0 | 0 | 2850 | 2014-03-31 08:00 | 3d 5h | 2175 | 0 | 0 | 0 | 0 | 2175 | 0 | 1 | Finished | 2850 | 2850 | C2015-12 Premium Payment System.xlsx
27 | 22 | design - convertie teruggaves | 2014-05-05 08:00 | 2014-05-08 15:00 | 3d 6h | Employee E | 2250 | 0 | 0 | 0 | 2250 | 2014-05-05 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 2250 | 2250 | C2015-12 Premium Payment System.xlsx
28 | 23 | design - creatie artikels | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee L | 600 | 0 | 0 | 0 | 600 | 2014-03-31 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 600 | 600 | C2015-12 Premium Payment System.xlsx
29 | 24 | design - impact op andere progs | 2014-02-10 08:00 | 2014-02-17 12:00 | 5d 4h | Employee L | 3300 | 0 | 0 | 0 | 3300 | 2014-02-10 08:00 | 5d 5h | 3375 | 0 | 0 | 0 | 0 | 3375 | 0 | 1 | Finished | 3300 | 3300 | C2015-12 Premium Payment System.xlsx
30 | 25 | design - lay-out brief | 2014-03-17 08:00 | 2014-03-21 15:00 | 4d 6h | Employee M | 2850 | 0 | 0 | 0 | 2850 | 2014-03-10 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 2850 | 2850 | C2015-12 Premium Payment System.xlsx
31 | 26 | design - mailoptie | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h | Employee I | 1125 | 0 | 0 | 0 | 1125 | 2014-05-12 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1125 | 1125 | C2015-12 Premium Payment System.xlsx
32 | 27 | design - methode fractioneren | 2014-02-11 08:00 | 2014-02-14 12:00 | 3d 4h | Employee E | 2100 | 0 | 0 | 0 | 2100 | 2014-02-10 08:00 | 7d 7h | 4725 | 0 | 0 | 0 | 0 | 4725 | 0 | 1 | Finished | 2100 | 2100 | C2015-12 Premium Payment System.xlsx
33 | 28 | design - opzet OMS | 2014-04-07 08:00 | 2014-04-08 16:00 | 1d 7h | Employee M | 1125 | 0 | 0 | 0 | 1125 | 2014-03-17 08:00 | 4d 3h | 2625 | 0 | 0 | 0 | 0 | 2625 | 0 | 1 | Finished | 1125 | 1125 | C2015-12 Premium Payment System.xlsx
34 | 29 | design - proces opzetten | 2014-03-06 08:00 | 2014-03-07 10:00 | 1d 2h | Employee I | 750 | 0 | 0 | 0 | 750 | 2014-03-03 08:00 | 2d 2h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 1 | Finished | 750 | 750 | C2015-12 Premium Payment System.xlsx
35 | 30 | design - stopzetting afbetalingsplan | 2014-05-21 08:00 | 2014-05-29 10:00 | 6d 2h | Employee E | 3750 | 0 | 0 | 0 | 3750 | 2014-05-21 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 3750 | 3750 | C2015-12 Premium Payment System.xlsx
36 | 31 | design validated | 2014-05-29 17:00 | 2014-05-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-29 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-12 Premium Payment System.xlsx
37 | 70 | development | 2014-02-11 08:00 | 2014-09-26 17:00 | 164d |  |  | 0 |  |  | 25800 |  | 164d 7h | [5 empty] | 3675 |  | 1 |  | 25800 | 25800 | C2015-12 Premium Payment System.xlsx
38 | 33 | development - boeking teruggave | 2014-04-07 08:00 | 2014-04-15 14:00 | 6d 5h | Employee L | 3975 | 0 | 0 | 0 | 3975 | 2014-04-28 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 3975 | 3975 | C2015-12 Premium Payment System.xlsx
39 | 35 | development - impact op andere progs | 2014-02-11 08:00 | 2014-03-03 11:00 | 14d 3h | Employee N | 8625 | 0 | 0 | 0 | 8625 | 2014-02-10 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 8625 | 8625 | C2015-12 Premium Payment System.xlsx
40 | 36 | development - landscape document voorzien | 2014-02-11 08:00 | 2014-02-17 16:00 | 4d 7h | Employee O | 2925 | 0 | 0 | 0 | 2925 | 2014-02-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 2925 | 2925 | C2015-12 Premium Payment System.xlsx
41 | 37 | development - lay-out brief | 2014-04-28 08:00 | 2014-05-02 15:00 | 4d 6h | Employee M | 2850 | 0 | 0 | 0 | 2850 | 2014-04-28 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 2850 | 2850 | C2015-12 Premium Payment System.xlsx
42 | 38 | development - methode fractioneren | 2014-03-10 08:00 | 2014-03-18 14:00 | 6d 5h | Employee L | 3975 | 0 | 0 | 0 | 3975 | 2014-03-10 08:00 | 4d 7h | 2925 | 0 | 0 | 0 | 0 | 2925 | 0 | 1 | Finished | 3975 | 3975 | C2015-12 Premium Payment System.xlsx
43 | 40 | development - proces opzetten | 2014-03-31 08:00 | 2014-04-02 16:00 | 2d 7h | Employee Q | 1725 | 0 | 0 | 0 | 1725 | 2014-03-31 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1725 | 1725 | C2015-12 Premium Payment System.xlsx
44 | 42 | development - impact op andere progs | 2014-07-07 08:00 | 2014-07-09 16:00 | 2d 7h | Employee M | 1725 | 0 | 0 | 0 | 1725 | 2014-07-07 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1725 | 1725 | C2015-12 Premium Payment System.xlsx
45 | 46 | development completed | 2014-09-26 17:00 | 2014-09-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-09-26 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-12 Premium Payment System.xlsx
46 | 71 | test ict | 2014-06-02 08:00 | 2014-08-29 17:00 | 65d |  |  | 0 |  |  | 11250 |  | 104d 7h | [5 empty] | 1425 |  | 1 |  | 11250 | 11250 | C2015-12 Premium Payment System.xlsx
47 | 49 | test ict - preparation | 2014-06-02 08:00 | 2014-06-26 15:00 | 18d 6h | Employee E | 11250 | 0 | 0 | 0 | 11250 | 2014-04-07 08:00 | 2d 3h | 1425 | 0 | 0 | 0 | 0 | 1425 | 0 | 1 | Finished | 11250 | 11250 | C2015-12 Premium Payment System.xlsx
48 | 50 | ict test completed | 2014-08-29 17:00 | 2014-08-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-08-29 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-12 Premium Payment System.xlsx
49 | 72 | implementation | 2014-07-01 17:00 | 2014-10-10 17:00 | 73d |  |  | 0 |  |  | 0 |  | 73d | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-12 Premium Payment System.xlsx
50 | 51 | uat | 2014-07-01 17:00 | 2014-07-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-07-01 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-12 Premium Payment System.xlsx
51 | 52 | code freeze | 2014-09-26 17:00 | 2014-09-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-09-26 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-12 Premium Payment System.xlsx
52 | 55 | go live | 2014-10-10 17:00 | 2014-10-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-10-10 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-12 Premium Payment System.xlsx
4 | 0 | Broker Account Conversion System | 2013-11-28 08:00 | 2014-05-09 17:00 | 117d |  |  | 0 |  |  | 12735 |  | 116d 7h | [5 empty] | 9990 |  | 1 |  | 12735 | 12735 | C2015-13 Broker Account Conversion System.xlsx
5 | 25 | supporting tasks | 2013-11-28 08:00 | 2013-12-04 10:00 | 4d 2h |  |  | 0 |  |  | 3060 |  | 3d 7h | [5 empty] | 2790 |  | 1 |  | 3060 | 3060 | C2015-13 Broker Account Conversion System.xlsx
6 | 1 | project management | 2013-11-28 08:00 | 2013-12-04 10:00 | 4d 2h | Employee A | 3060 | 0 | 0 | 0 | 3060 | 2013-11-28 08:00 | 3d 7h | 2790 | 0 | 0 | 0 | 0 | 2790 | 0 | 1 | Finished | 3060 | 3060 | C2015-13 Broker Account Conversion System.xlsx
7 | 26 | requirements | 2014-01-10 08:00 | 2014-01-30 17:00 | 15d |  |  | 0 |  |  | 150 |  | 18d 7h | [5 empty] | 150 |  | 1 |  | 150 | 150 | C2015-13 Broker Account Conversion System.xlsx
8 | 2 | requirements | 2014-01-10 08:00 | 2014-01-10 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 | 2014-01-06 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 150 | 150 | C2015-13 Broker Account Conversion System.xlsx
9 | 3 | requirements validated | 2014-01-30 17:00 | 2014-01-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-30 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-13 Broker Account Conversion System.xlsx
10 | 27 | analysis | 2014-01-31 08:00 | 2014-02-18 17:00 | 13d |  |  | 0 |  |  | 150 |  | 16d 7h | [5 empty] | 150 |  | 1 |  | 150 | 150 | C2015-13 Broker Account Conversion System.xlsx
11 | 4 | analysis - solution concept | 2014-01-31 08:00 | 2014-01-31 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 | 2014-01-27 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 150 | 150 | C2015-13 Broker Account Conversion System.xlsx
12 | 5 | analysis validated | 2014-02-18 17:00 | 2014-02-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-13 Broker Account Conversion System.xlsx
13 | 28 | design | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  |  | 0 |  |  | 150 |  | 65d 7h | [5 empty] | 300 |  | 1 |  | 150 | 150 | C2015-13 Broker Account Conversion System.xlsx
14 | 6 | design - data design upload passieve makelaars | 2014-01-24 08:00 | 2014-01-24 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 2014-01-20 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 75 | 75 | C2015-13 Broker Account Conversion System.xlsx
15 | 33 | design - data design upload passieve makelaars | 2014-01-24 08:00 | 2014-01-24 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 2014-04-21 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 1 | Finished | 75 | 75 | C2015-13 Broker Account Conversion System.xlsx
16 | 7 | design validated | 2014-01-29 17:00 | 2014-01-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-13 Broker Account Conversion System.xlsx
17 | 29 | development | 2014-01-24 08:00 | 2014-03-21 17:00 | 41d |  |  | 0 |  |  | 4650 |  | 44d 7h | [5 empty] | 3600 |  | 1 |  | 4650 | 4650 | C2015-13 Broker Account Conversion System.xlsx
18 | 8 | development - TAT testing | 2014-01-24 08:00 | 2014-01-28 12:00 | 2d 4h | Employee D | 1500 | 0 | 0 | 0 | 1500 | 2014-02-03 08:00 | 2d 4h | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 1 | Finished | 1500 | 1500 | C2015-13 Broker Account Conversion System.xlsx
19 | 9 | development - TAT testing | 2014-01-24 08:00 | 2014-01-29 11:00 | 3d 3h | Employee E | 2025 | 0 | 0 | 0 | 2025 | 2014-02-17 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 1 | Finished | 2025 | 2025 | C2015-13 Broker Account Conversion System.xlsx
20 | 10 | development - TAT testing | 2014-01-24 08:00 | 2014-01-27 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2014-01-20 08:00 | 1d 5h | 975 | 0 | 0 | 0 | 0 | 975 | 0 | 1 | Finished | 1125 | 1125 | C2015-13 Broker Account Conversion System.xlsx
21 | 11 | development completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-13 Broker Account Conversion System.xlsx
22 | 30 | test ict | 2014-01-31 08:00 | 2014-04-04 17:00 | 46d |  |  | 0 |  |  | 3600 |  | 60d 7h | [5 empty] | 2550 |  | 1 |  | 3600 | 3600 | C2015-13 Broker Account Conversion System.xlsx
23 | 12 | test ict - build bugfixing | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee D | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 1 | Finished | 600 | 600 | C2015-13 Broker Account Conversion System.xlsx
24 | 13 | test ict - build bugfixing | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 600 | 600 | C2015-13 Broker Account Conversion System.xlsx
25 | 14 | test ict - test coordination | 2014-01-31 08:00 | 2014-02-03 09:00 | 1d 1h | Employee G | 675 | 0 | 0 | 0 | 675 | 2014-01-27 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 1 | Finished | 675 | 675 | C2015-13 Broker Account Conversion System.xlsx
26 | 15 | test ict - test execution | 2014-03-24 08:00 | 2014-03-25 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 | 2014-03-31 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 1125 | 1125 | C2015-13 Broker Account Conversion System.xlsx
27 | 16 | test ict - test preparation | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 1 | Finished | 600 | 600 | C2015-13 Broker Account Conversion System.xlsx
28 | 17 | ict test completed | 2014-04-04 17:00 | 2014-04-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-13 Broker Account Conversion System.xlsx
29 | 31 | implementation | 2014-05-05 08:00 | 2014-05-09 17:00 | 5d |  |  | 0 |  |  | 975 |  | 34d 7h | [5 empty] | 450 |  | 1 |  | 975 | 975 | C2015-13 Broker Account Conversion System.xlsx
30 | 18 | implementation - preparation | 2014-05-05 08:00 | 2014-05-05 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 2014-05-05 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 600 | 600 | C2015-13 Broker Account Conversion System.xlsx
31 | 34 | implementation - preparation | 2014-05-05 08:00 | 2014-05-05 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 | 2014-03-24 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 75 | 75 | C2015-13 Broker Account Conversion System.xlsx
32 | 19 | implementation - preparation | 2014-05-05 08:00 | 2014-05-05 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 | 2014-04-21 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 300 | 300 | C2015-13 Broker Account Conversion System.xlsx
33 | 20 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-13 Broker Account Conversion System.xlsx
4 | 0 | Supplementary Pensions Database | 2013-11-19 08:00 | 2014-05-12 09:00 | 124d 1h |  |  | 0 |  |  | 34260 |  | 123d 7h | [5 empty] | 18285 |  | 1 |  | 34260 | 34185 | C2015-14 Supplementary Pensions Database.xlsx
5 | 25 | supporting tasks | 2013-11-19 08:00 | 2013-11-25 12:00 | 4d 4h |  |  | 0 |  |  | 4320 |  | 76d 2h | [5 empty] | 2820 |  | 1 |  | 4320 | 4320 | C2015-14 Supplementary Pensions Database.xlsx
6 | 1 | project management | 2013-11-19 08:00 | 2013-11-21 10:00 | 2d 2h | Employee F | 1620 | 0 | 0 | 0 | 1620 | 2014-03-03 08:00 | 2d 2h | 1620 | 0 | 0 | 0 | 0 | 1620 | 0 | 1 | Finished | 1620 | 1620 | C2015-14 Supplementary Pensions Database.xlsx
7 | 2 | project management | 2013-11-19 08:00 | 2013-11-25 12:00 | 4d 4h | Employee G | 2700 | 0 | 0 | 0 | 2700 | 2013-11-19 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 1 | Finished | 2700 | 2700 | C2015-14 Supplementary Pensions Database.xlsx
8 | 26 | requirements | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h |  |  | 0 |  |  | 225 |  | 55d 3h | [5 empty] | 300 |  | 1 |  | 225 | 225 | C2015-14 Supplementary Pensions Database.xlsx
9 | 3 | requirements | 2013-12-02 08:00 | 2013-12-02 09:00 | 1h | Employee I | 75 | 0 | 0 | 0 | 75 | 2013-12-02 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 75 | 75 | C2015-14 Supplementary Pensions Database.xlsx
10 | 4 | requirements | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h | Employee G | 150 | 0 | 0 | 0 | 150 | 2014-02-17 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 1 | Finished | 150 | 150 | C2015-14 Supplementary Pensions Database.xlsx
11 | 27 | analysis | 2014-01-31 16:00 | 2014-03-06 17:00 | 24d 1h |  |  | 0 |  |  | 3975 |  | 23d 7h | [5 empty] | 4200 |  | 1 |  | 3975 | 3975 | C2015-14 Supplementary Pensions Database.xlsx
12 | 5 | analysis - functioneel | 2014-02-03 08:00 | 2014-02-10 09:00 | 5d 1h | Employee A | 3075 | 0 | 0 | 0 | 3075 | 2014-02-03 08:00 | 5d 1h | 3075 | 0 | 0 | 0 | 0 | 3075 | 0 | 1 | Finished | 3075 | 3075 | C2015-14 Supplementary Pensions Database.xlsx
13 | 6 | analysis - functioneel | 2014-02-03 08:00 | 2014-02-04 11:00 | 1d 3h | Employee G | 825 | 0 | 0 | 0 | 825 | 2014-03-03 08:00 | 1d 3h | 825 | 0 | 0 | 0 | 0 | 825 | 0 | 1 | Finished | 825 | 825 | C2015-14 Supplementary Pensions Database.xlsx
14 | 7 | analysis - support by code & test | 2014-01-31 16:00 | 2014-01-31 17:00 | 1h | Employee G | 75 | 0 | 0 | 0 | 75 | 2014-02-03 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 75 | 75 | C2015-14 Supplementary Pensions Database.xlsx
15 | 8 | analysis validated | 2014-03-06 17:00 | 2014-03-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-06 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-14 Supplementary Pensions Database.xlsx
16 | 28 | design | 2014-03-10 08:00 | 2014-03-28 17:00 | 15d |  |  | 0 |  |  | 3870 |  | 35d 7h | [5 empty] | 2070 |  | 1 |  | 3870 | 3870 | C2015-14 Supplementary Pensions Database.xlsx
17 | 9 | design - AIA | 2014-03-10 08:00 | 2014-03-17 11:00 | 5d 3h | Employee F | 3870 | 0 | 0 | 0 | 3870 | 2014-03-03 08:00 | 2d 7h | 2070 | 0 | 0 | 0 | 0 | 2070 | 0 | 1 | Finished | 3870 | 3870 | C2015-14 Supplementary Pensions Database.xlsx
18 | 10 | design validated | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-14 Supplementary Pensions Database.xlsx
19 | 29 | development | 2014-03-03 08:00 | 2014-04-04 17:00 | 25d |  |  | 0 |  |  | 9495 |  | 35d 7h | [5 empty] | 1005 |  | 1 |  | 9495 | 9495 | C2015-14 Supplementary Pensions Database.xlsx
20 | 11 | development - AIA | 2014-03-24 08:00 | 2014-04-01 14:00 | 6d 5h | Employee F | 4770 | 0 | 0 | 0 | 4770 | 2014-04-28 08:00 | 2h | 180 | 0 | 0 | 0 | 0 | 180 | 0 | 1 | Finished | 4770 | 4770 | C2015-14 Supplementary Pensions Database.xlsx
21 | 12 | development - progress | 2014-03-03 08:00 | 2014-03-12 16:00 | 7d 7h | Employee D | 4725 | 0 | 0 | 0 | 4725 | 2014-03-10 08:00 | 1d 3h | 825 | 0 | 0 | 0 | 0 | 825 | 0 | 1 | Finished | 4725 | 4725 | C2015-14 Supplementary Pensions Database.xlsx
22 | 13 | development completed | 2014-04-04 17:00 | 2014-04-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-28 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-14 Supplementary Pensions Database.xlsx
23 | 30 | build | 2014-04-14 08:00 | 2014-04-30 17:00 | 13d |  |  | 0 |  |  | 2325 |  | 12d 7h | [5 empty] | 450 |  | 1 |  | 2325 | 2325 | C2015-14 Supplementary Pensions Database.xlsx
24 | 14 | build - bugfixing | 2014-04-14 08:00 | 2014-04-16 11:00 | 2d 3h | Employee J | 1425 | 0 | 0 | 0 | 1425 | 2014-04-14 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1425 | 1425 | C2015-14 Supplementary Pensions Database.xlsx
25 | 15 | build - bugfixing | 2014-04-14 08:00 | 2014-04-15 12:00 | 1d 4h | Employee D | 900 | 0 | 0 | 0 | 900 | 2014-04-21 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 900 | 900 | C2015-14 Supplementary Pensions Database.xlsx
26 | 16 | build completed | 2014-04-30 17:00 | 2014-04-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-30 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-14 Supplementary Pensions Database.xlsx
27 | 31 | ict test | 2014-02-26 08:00 | 2014-04-24 17:00 | 42d |  |  | 0 |  |  | 9975 |  | 43d 7h | [5 empty] | 7365 |  | 1 |  | 9975 | 9975 | C2015-14 Supplementary Pensions Database.xlsx
28 | 17 | test coordination | 2014-03-10 08:00 | 2014-03-11 09:00 | 1d 1h | Employee L | 675 | 0 | 0 | 0 | 675 | 2014-03-03 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 1 | Finished | 675 | 675 | C2015-14 Supplementary Pensions Database.xlsx
29 | 18 | test execution | 2014-03-31 08:00 | 2014-04-03 15:00 | 3d 6h | Employee F | 2700 | 0 | 0 | 0 | 2700 | 2014-03-31 08:00 | 1h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 1 | Finished | 2700 | 2700 | C2015-14 Supplementary Pensions Database.xlsx
30 | 19 | test execution | 2014-03-31 08:00 | 2014-04-07 14:00 | 5d 5h | Employee M | 3375 | 0 | 0 | 0 | 3375 | 2014-04-21 08:00 | 2d 1h | 1275 | 0 | 0 | 0 | 0 | 1275 | 0 | 1 | Finished | 3375 | 3375 | C2015-14 Supplementary Pensions Database.xlsx
31 | 20 | test preparation | 2014-02-26 08:00 | 2014-03-05 11:00 | 5d 3h | Employee M | 3225 | 0 | 0 | 0 | 3225 | 2014-02-24 08:00 | 9d 2h | 5550 | 0 | 0 | 0 | 0 | 5550 | 0 | 1 | Finished | 3225 | 3225 | C2015-14 Supplementary Pensions Database.xlsx
32 | 21 | ict test completed | 2014-04-24 17:00 | 2014-04-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-14 Supplementary Pensions Database.xlsx
33 | 32 | implementation | 2014-04-25 17:00 | 2014-05-09 17:00 | 10d |  |  | 0 |  |  | 0 |  | 10d | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-14 Supplementary Pensions Database.xlsx
34 | 22 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-14 Supplementary Pensions Database.xlsx
35 | 23 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-14 Supplementary Pensions Database.xlsx
36 | 33 | post implementation | 2014-05-12 08:00 | 2014-05-12 09:00 | 1h |  |  | 0 |  |  | 75 |  | 1h | [5 empty] | 75 |  | 1 |  | 75 | 0 | C2015-14 Supplementary Pensions Database.xlsx
37 | 24 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 | 2014-04-21 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 75 | 0 | C2015-14 Supplementary Pensions Database.xlsx
4 | 0 | FACTA System | 2014-02-21 08:00 | 2014-05-12 17:00 | 57d |  |  | 0 |  |  | 11700 |  | 57d | [5 empty] | 7035 |  | 1 |  | 11700 | 10650 | C2015-15 FACTA System.xlsx
5 | 21 | supporting tasks | 2014-02-21 08:00 | 2014-02-24 10:00 | 1d 2h |  |  | 0 |  |  | 900 |  | 2d 3h | [5 empty] | 1710 |  | 1 |  | 900 | 900 | C2015-15 FACTA System.xlsx
6 | 1 | project management | 2014-02-21 08:00 | 2014-02-24 10:00 | 1d 2h | Employee A | 900 | 0 | 0 | 0 | 900 | 2014-02-21 08:00 | 2d 3h | 1710 | 0 | 0 | 0 | 0 | 1710 | 0 | 1 | Finished | 900 | 900 | C2015-15 FACTA System.xlsx
7 | 22 | analysis | 2014-02-28 08:00 | 2014-02-28 17:00 | 1d |  |  | 0 |  |  | 75 |  | 4d 7h | [5 empty] | 75 |  | 1 |  | 75 | 75 | C2015-15 FACTA System.xlsx
8 | 2 | analysis - conceptual design | 2014-02-28 08:00 | 2014-02-28 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 | 2014-02-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 75 | 75 | C2015-15 FACTA System.xlsx
9 | 3 | analysis validated | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-28 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-15 FACTA System.xlsx
10 | 23 | design | 2014-03-03 08:00 | 2014-03-07 17:00 | 5d |  |  | 0 |  |  | 300 |  | 4d 7h | [5 empty] | 75 |  | 1 |  | 300 | 300 | C2015-15 FACTA System.xlsx
11 | 4 | design - technical design | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 300 | 300 | C2015-15 FACTA System.xlsx
12 | 5 | design validated | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-07 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-15 FACTA System.xlsx
13 | 24 | development | 2014-03-03 08:00 | 2014-03-24 17:00 | 16d |  |  | 0 |  |  | 2250 |  | 15d 7h | [5 empty] | 1650 |  | 1 |  | 2250 | 2250 | C2015-15 FACTA System.xlsx
14 | 6 | development - coding | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 300 | 300 | C2015-15 FACTA System.xlsx
15 | 7 | development - coding | 2014-03-03 08:00 | 2014-03-04 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 | 2014-03-03 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 1 | Finished | 1050 | 1050 | C2015-15 FACTA System.xlsx
16 | 8 | development - coding | 2014-03-03 08:00 | 2014-03-04 12:00 | 1d 4h | Employee H | 900 | 0 | 0 | 0 | 900 | 2014-03-10 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 1 | Finished | 900 | 900 | C2015-15 FACTA System.xlsx
17 | 10 | development completed | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-15 FACTA System.xlsx
18 | 25 | ict test | 2014-02-28 08:00 | 2014-03-24 17:00 | 17d |  |  | 0 |  |  | 3525 |  | 20d 7h | [5 empty] | 2175 |  | 1 |  | 3525 | 3525 | C2015-15 FACTA System.xlsx
19 | 11 | test ict - test preparation | 2014-02-28 08:00 | 2014-03-06 10:00 | 4d 2h | Employee K | 2550 | 0 | 0 | 0 | 2550 | 2014-02-24 08:00 | 3d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 1 | Finished | 2550 | 2550 | C2015-15 FACTA System.xlsx
20 | 12 | test ict - test coordination | 2014-03-03 08:00 | 2014-03-04 11:00 | 1d 3h | Employee B | 825 | 0 | 0 | 0 | 825 | 2014-03-17 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 1 | Finished | 825 | 825 | C2015-15 FACTA System.xlsx
21 | 13 | test ict - test execution | 2014-03-24 08:00 | 2014-03-24 10:00 | 2h | Employee K | 150 | 0 | 0 | 0 | 150 | 2014-03-24 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 150 | 150 | C2015-15 FACTA System.xlsx
22 | 14 | ict test completed | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-15 FACTA System.xlsx
23 | 26 | implementation | 2014-03-31 08:00 | 2014-05-09 17:00 | 30d |  |  | 0 |  |  | 3450 |  | 29d 7h | [5 empty] | 150 |  | 1 |  | 3450 | 3450 | C2015-15 FACTA System.xlsx
24 | 15 | uat - test support | 2014-03-31 08:00 | 2014-04-04 15:00 | 4d 6h | Employee K | 2850 | 0 | 0 | 0 | 2850 | 2014-03-31 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 2850 | 2850 | C2015-15 FACTA System.xlsx
25 | 16 | uat completed | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-15 FACTA System.xlsx
26 | 17 | implementation - put in production | 2014-03-31 08:00 | 2014-03-31 17:00 | 1d | Employee L | 600 | 0 | 0 | 0 | 600 | 2014-03-31 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 600 | 600 | C2015-15 FACTA System.xlsx
27 | 18 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-15 FACTA System.xlsx
28 | 27 | post implementation | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d |  |  | 0 |  |  | 1200 |  | 1d | [5 empty] | 1200 |  | 1 |  | 1200 | 150 | C2015-15 FACTA System.xlsx
29 | 19 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 | 2014-05-12 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 1 | Finished | 600 | 75 | C2015-15 FACTA System.xlsx
30 | 20 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 | 2014-05-12 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 1 | Finished | 600 | 75 | C2015-15 FACTA System.xlsx
4 | 0 | Generic Document Output System | 2013-04-29 08:00 | 2014-05-09 17:00 | 270d |  |  | 0 |  |  | 64620 |  | 269d 7h | [5 empty] | 64125 |  | 1 |  | 64620 | 64620 | C2015-16 Generic Document Output System.xlsx
5 | 28 | supporting tasks | 2013-08-19 08:00 | 2014-03-14 10:00 | 149d 2h |  |  | 0 |  |  | 9660 |  | 147d 1h | [5 empty] | 9150 |  | 1 |  | 9660 | 9660 | C2015-16 Generic Document Output System.xlsx
6 | 1 | project management | 2013-08-19 08:00 | 2013-08-26 14:00 | 5d 5h | Employee A | 4050 | 0 | 0 | 0 | 4050 | 2013-08-19 08:00 | 7d 2h | 5220 | 0 | 0 | 0 | 0 | 5220 | 0 | 1 | Finished | 4050 | 4050 | C2015-16 Generic Document Output System.xlsx
7 | 38 | validation and support | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee B | 2550 | 0 | 0 | 0 | 2550 | 2014-02-24 08:00 | 4d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 1 | Finished | 2550 | 2550 | C2015-16 Generic Document Output System.xlsx
8 | 2 | validation and support | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee A | 3060 | 0 | 0 | 0 | 3060 | 2014-03-10 08:00 | 2d 1h | 1530 | 0 | 0 | 0 | 0 | 1530 | 0 | 1 | Finished | 3060 | 3060 | C2015-16 Generic Document Output System.xlsx
9 | 29 | analysis | 2013-04-29 08:00 | 2014-01-27 17:00 | 196d |  |  | 0 |  |  | 6060 |  | 255d 7h | [5 empty] | 10500 |  | 1 |  | 6060 | 6060 | C2015-16 Generic Document Output System.xlsx
10 | 3 | analysis - solution concept | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee A | 450 | 0 | 0 | 0 | 450 | 2013-07-08 08:00 | 5h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 1 | Finished | 450 | 450 | C2015-16 Generic Document Output System.xlsx
11 | 4 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee B | 1800 | 0 | 0 | 0 | 1800 | 2013-04-29 08:00 | 5d 7h | 3525 | 0 | 0 | 0 | 0 | 3525 | 0 | 1 | Finished | 1800 | 1800 | C2015-16 Generic Document Output System.xlsx
12 | 5 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee C | 1800 | 0 | 0 | 0 | 1800 | 2013-09-23 08:00 | 3d 2h | 1950 | 0 | 0 | 0 | 0 | 1950 | 0 | 1 | Finished | 1800 | 1800 | C2015-16 Generic Document Output System.xlsx
13 | 6 | analysis - solution concept | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee D | 375 | 0 | 0 | 0 | 375 | 2013-08-05 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 375 | 375 | C2015-16 Generic Document Output System.xlsx
14 | 7 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 09:00 | 2d 1h | Employee E | 1275 | 0 | 0 | 0 | 1275 | 2013-08-05 08:00 | 6d 2h | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 1 | Finished | 1275 | 1275 | C2015-16 Generic Document Output System.xlsx
15 | 8 | analysis - business analysis | 2013-12-30 08:00 | 2013-12-30 12:00 | 4h | Employee A | 360 | 0 | 0 | 0 | 360 | 2013-12-30 08:00 | 5h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 1 | Finished | 360 | 360 | C2015-16 Generic Document Output System.xlsx
16 | 9 | analysis validated | 2014-01-27 17:00 | 2014-01-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-16 Generic Document Output System.xlsx
17 | 30 | design | 2014-01-21 08:00 | 2014-03-07 17:00 | 34d |  |  | 0 |  |  | 9150 |  | 65d 7h | [5 empty] | 17325 |  | 1 |  | 9150 | 9150 | C2015-16 Generic Document Output System.xlsx
18 | 10 | design - SAD/interface design | 2014-01-21 08:00 | 2014-01-28 09:00 | 5d 1h | Employee H | 3075 | 0 | 0 | 0 | 3075 | 2014-01-20 08:00 | 11d 4h | 6900 | 0 | 0 | 0 | 0 | 6900 | 0 | 1 | Finished | 3075 | 3075 | C2015-16 Generic Document Output System.xlsx
19 | 11 | design - SAD/interface design | 2014-01-21 08:00 | 2014-01-21 10:00 | 2h | Employee I | 150 | 0 | 0 | 0 | 150 | 2014-01-20 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 150 | 150 | C2015-16 Generic Document Output System.xlsx
20 | 12 | design - CDM/process design | 2014-01-21 08:00 | 2014-02-03 11:00 | 9d 3h | Employee F | 5625 | 0 | 0 | 0 | 5625 | 2014-01-20 08:00 | 16d 5h | 9975 | 0 | 0 | 0 | 0 | 9975 | 0 | 1 | Finished | 5625 | 5625 | C2015-16 Generic Document Output System.xlsx
21 | 13 | design - CDM/process design | 2014-01-21 08:00 | 2014-01-21 12:00 | 4h | Employee G | 300 | 0 | 0 | 0 | 300 | 2014-01-20 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 300 | 300 | C2015-16 Generic Document Output System.xlsx
22 | 14 | design validated | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-16 Generic Document Output System.xlsx
23 | 31 | development | 2014-01-06 08:00 | 2014-04-14 17:00 | 71d |  |  | 0 |  |  | 36150 |  | 75d 7h | [5 empty] | 24450 |  | 1 |  | 36150 | 36150 | C2015-16 Generic Document Output System.xlsx
24 | 15 | development - coding DMS | 2014-03-10 08:00 | 2014-03-12 16:00 | 2d 7h | Employee C | 1725 | 0 | 0 | 0 | 1725 | 2014-03-31 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 1 | Finished | 1725 | 1725 | C2015-16 Generic Document Output System.xlsx
25 | 16 | development - coding ESB | 2014-01-28 08:00 | 2014-02-10 11:00 | 9d 3h | Employee J | 5625 | 0 | 0 | 0 | 5625 | 2014-01-28 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 5625 | 5625 | C2015-16 Generic Document Output System.xlsx
26 | 17 | development - coding ESB | 2014-01-28 08:00 | 2014-03-10 17:00 | 30d | Employee E | 18000 | 0 | 0 | 0 | 18000 | 2014-01-27 08:00 | 26d 6h | 16050 | 0 | 0 | 0 | 0 | 16050 | 0 | 1 | Finished | 18000 | 18000 | C2015-16 Generic Document Output System.xlsx
27 | 18 | development - coding OMS | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d | Employee K | 3000 | 0 | 0 | 0 | 3000 | 2014-02-17 08:00 | 4d 4h | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 1 | Finished | 3000 | 3000 | C2015-16 Generic Document Output System.xlsx
28 | 36 | development - bugfixing | 2014-01-06 08:00 | 2014-01-16 15:00 | 8d 6h | Employee C | 5250 | 0 | 0 | 0 | 5250 | 2014-04-07 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 1 | Finished | 5250 | 5250 | C2015-16 Generic Document Output System.xlsx
29 | 37 | development - bugfixing | 2014-01-06 08:00 | 2014-01-09 09:00 | 3d 1h | Employee E | 1875 | 0 | 0 | 0 | 1875 | 2014-04-14 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 1875 | 1875 | C2015-16 Generic Document Output System.xlsx
30 | 19 | development - bugfixing and support | 2014-01-06 08:00 | 2014-01-07 09:00 | 1d 1h | Employee K | 675 | 0 | 0 | 0 | 675 | 2014-01-06 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 1 | Finished | 675 | 675 | C2015-16 Generic Document Output System.xlsx
31 | 20 | development completed | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-16 Generic Document Output System.xlsx
32 | 32 | test ict | 2014-02-20 08:00 | 2014-04-14 17:00 | 38d |  |  | 0 |  |  | 3600 |  | 45d 7h | [5 empty] | 2700 |  | 1 |  | 3600 | 3600 | C2015-16 Generic Document Output System.xlsx
33 | 21 | test ict - test coordination | 2014-02-20 08:00 | 2014-02-21 10:00 | 1d 2h | Employee L | 750 | 0 | 0 | 0 | 750 | 2014-02-17 08:00 | 2d 1h | 1275 | 0 | 0 | 0 | 0 | 1275 | 0 | 1 | Finished | 750 | 750 | C2015-16 Generic Document Output System.xlsx
34 | 22 | test ict - test execution | 2014-03-24 08:00 | 2014-03-28 15:00 | 4d 6h | Employee L | 2850 | 0 | 0 | 0 | 2850 | 2014-04-07 08:00 | 2d 3h | 1425 | 0 | 0 | 0 | 0 | 1425 | 0 | 1 | Finished | 2850 | 2850 | C2015-16 Generic Document Output System.xlsx
35 | 23 | ict test completed | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-16 Generic Document Output System.xlsx
36 | 33 | UAT | 2014-03-14 17:00 | 2014-04-25 17:00 | 30d |  |  | 0 |  |  | 0 |  | 3d | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-16 Generic Document Output System.xlsx
37 | 24 | full handover | 2014-03-14 17:00 | 2014-03-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-22 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-16 Generic Document Output System.xlsx
38 | 25 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-22 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-16 Generic Document Output System.xlsx
39 | 26 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-16 Generic Document Output System.xlsx
40 | 34 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-16 Generic Document Output System.xlsx
41 | 27 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-16 Generic Document Output System.xlsx
4 | 0 | Insurance Bundling System | 2013-04-19 08:00 | 2014-02-05 12:00 | 208d 4h |  |  | 0 |  |  | 281430 |  | 236d 1h | [5 empty] | 281070 |  | 1 |  | 281430 | 281430 | C2015-17 Insurance Bundling System.xlsx
5 | 31 | supporting tasks | 2013-07-16 08:00 | 2013-09-02 17:00 | 35d |  |  | 0 |  |  | 26190 |  | 35d 1h | [5 empty] | 26280 |  | 1 |  | 26190 | 26190 | C2015-17 Insurance Bundling System.xlsx
6 | 1 | project management | 2013-07-16 08:00 | 2013-09-02 17:00 | 35d | Employee A | 25200 | 0 | 0 | 0 | 25200 | 2013-07-15 08:00 | 35d 1h | 25290 | 0 | 0 | 0 | 0 | 25290 | 0 | 1 | Finished | 25200 | 25200 | C2015-17 Insurance Bundling System.xlsx
7 | 2 | project management | 2013-07-16 08:00 | 2013-07-17 11:00 | 1d 3h | Employee B | 990 | 0 | 0 | 0 | 990 | 2013-08-19 08:00 | 1d 3h | 990 | 0 | 0 | 0 | 0 | 990 | 0 | 1 | Finished | 990 | 990 | C2015-17 Insurance Bundling System.xlsx
8 | 30 | analysis | 2013-04-19 08:00 | 2013-09-27 17:00 | 116d |  |  | 0 |  |  | 38340 |  | 142d 7h | [5 empty] | 38490 |  | 1 |  | 38340 | 38340 | C2015-17 Insurance Bundling System.xlsx
9 | 3 | analysis - business analysis | 2013-07-01 08:00 | 2013-08-23 11:00 | 39d 3h | Employee D | 23625 | 0 | 0 | 0 | 23625 | 2013-07-01 08:00 | 39d 5h | 23775 | 0 | 0 | 0 | 0 | 23775 | 0 | 1 | Finished | 23625 | 23625 | C2015-17 Insurance Bundling System.xlsx
10 | 4 | analysis - datamodel | 2013-09-09 08:00 | 2013-09-13 11:00 | 4d 3h | Employee D | 2625 | 0 | 0 | 0 | 2625 | 2013-10-21 08:00 | 4d 3h | 2625 | 0 | 0 | 0 | 0 | 2625 | 0 | 1 | Finished | 2625 | 2625 | C2015-17 Insurance Bundling System.xlsx
11 | 5 | analysis - I/O services | 2013-09-23 08:00 | 2013-09-25 12:00 | 2d 4h | Employee D | 1500 | 0 | 0 | 0 | 1500 | 2013-10-28 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 1 | Finished | 1500 | 1500 | C2015-17 Insurance Bundling System.xlsx
12 | 6 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-22 10:00 | 1d 2h | Employee C | 750 | 0 | 0 | 0 | 750 | 2013-07-01 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 750 | 750 | C2015-17 Insurance Bundling System.xlsx
13 | 7 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-30 10:00 | 7d 2h | Employee E | 4350 | 0 | 0 | 0 | 4350 | 2013-04-22 08:00 | 7d 2h | 4350 | 0 | 0 | 0 | 0 | 4350 | 0 | 1 | Finished | 4350 | 4350 | C2015-17 Insurance Bundling System.xlsx
14 | 8 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-26 12:00 | 5d 4h | Employee F | 3300 | 0 | 0 | 0 | 3300 | 2013-04-19 08:00 | 5d 2h | 3150 | 0 | 0 | 0 | 0 | 3150 | 0 | 1 | Finished | 3300 | 3300 | C2015-17 Insurance Bundling System.xlsx
15 | 9 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 15:00 | 6h | Employee B | 540 | 0 | 0 | 0 | 540 | 2013-07-29 08:00 | 6h | 540 | 0 | 0 | 0 | 0 | 540 | 0 | 1 | Finished | 540 | 540 | C2015-17 Insurance Bundling System.xlsx
16 | 10 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2013-04-19 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 1 | Finished | 600 | 600 | C2015-17 Insurance Bundling System.xlsx
17 | 11 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 16:00 | 7h | Employee H | 525 | 0 | 0 | 0 | 525 | 2013-04-22 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 1 | Finished | 525 | 525 | C2015-17 Insurance Bundling System.xlsx
18 | 12 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 16:00 | 7h | Employee I | 525 | 0 | 0 | 0 | 525 | 2013-07-29 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 1 | Finished | 525 | 525 | C2015-17 Insurance Bundling System.xlsx
19 | 13 | analysis validated | 2013-09-27 17:00 | 2013-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-11-05 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-17 Insurance Bundling System.xlsx
20 | 29 | design | 2013-04-19 08:00 | 2013-11-15 17:00 | 151d |  |  | 0 |  |  | 18600 |  | 68d 7h | [5 empty] | 18900 |  | 1 |  | 18600 | 18600 | C2015-17 Insurance Bundling System.xlsx
21 | 14 | BPA | 2013-09-16 08:00 | 2013-09-17 10:00 | 1d 2h | Employee J | 750 | 0 | 0 | 0 | 750 | 2013-09-16 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 750 | 750 | C2015-17 Insurance Bundling System.xlsx
22 | 15 | CDM | 2013-10-14 08:00 | 2013-10-14 16:00 | 7h | Employee J | 525 | 0 | 0 | 0 | 525 | 2013-10-07 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 1 | Finished | 525 | 525 | C2015-17 Insurance Bundling System.xlsx
23 | 16 | classic | 2013-08-21 08:00 | 2013-08-23 14:00 | 2d 5h | Employee K | 1575 | 0 | 0 | 0 | 1575 | 2013-08-19 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 1 | Finished | 1575 | 1575 | C2015-17 Insurance Bundling System.xlsx
24 | 17 | classic | 2013-08-21 08:00 | 2013-08-26 10:00 | 3d 2h | Employee L | 1950 | 0 | 0 | 0 | 1950 | 2013-10-07 08:00 | 3d 3h | 2025 | 0 | 0 | 0 | 0 | 2025 | 0 | 1 | Finished | 1950 | 1950 | C2015-17 Insurance Bundling System.xlsx
25 | 18 | SAD/interface design | 2013-10-21 08:00 | 2013-10-25 11:00 | 4d 3h | Employee L | 2625 | 0 | 0 | 0 | 2625 | 2013-10-07 08:00 | 4d 4h | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 1 | Finished | 2625 | 2625 | C2015-17 Insurance Bundling System.xlsx
26 | 19 | BPA | 2013-04-19 08:00 | 2013-04-19 09:00 | 1h | Employee J | 75 | 0 | 0 | 0 | 75 | 2013-09-30 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 75 | 75 | C2015-17 Insurance Bundling System.xlsx
27 | 20 | CDM | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Employee J | 225 | 0 | 0 | 0 | 225 | 2013-09-30 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 1 | Finished | 225 | 225 | C2015-17 Insurance Bundling System.xlsx
28 | 21 | get NB | 2013-09-30 08:00 | 2013-10-03 16:00 | 3d 7h | Employee M | 2325 | 0 | 0 | 0 | 2325 | 2013-09-30 08:00 | 3d 7h | 2325 | 0 | 0 | 0 | 0 | 2325 | 0 | 1 | Finished | 2325 | 2325 | C2015-17 Insurance Bundling System.xlsx
29 | 22 | PO - BPA | 2013-09-18 08:00 | 2013-09-18 16:00 | 7h | Employee J | 525 | 0 | 0 | 0 | 525 | 2013-09-16 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 1 | Finished | 525 | 525 | C2015-17 Insurance Bundling System.xlsx
30 | 23 | PO - CDM | 2013-10-01 08:00 | 2013-10-01 14:00 | 5h | Employee J | 375 | 0 | 0 | 0 | 375 | 2013-09-30 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 375 | 375 | C2015-17 Insurance Bundling System.xlsx
31 | 24 | quote - BPA | 2013-10-03 08:00 | 2013-10-04 09:00 | 1d 1h | Employee J | 675 | 0 | 0 | 0 | 675 | 2013-09-30 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 1 | Finished | 675 | 675 | C2015-17 Insurance Bundling System.xlsx
32 | 25 | quote - CDM | 2013-10-14 08:00 | 2013-10-15 11:00 | 1d 3h | Employee J | 825 | 0 | 0 | 0 | 825 | 2013-10-07 08:00 | 1d 3h | 825 | 0 | 0 | 0 | 0 | 825 | 0 | 1 | Finished | 825 | 825 | C2015-17 Insurance Bundling System.xlsx
33 | 26 | quote - NB | 2013-10-07 08:00 | 2013-10-07 16:00 | 7h | Employee M | 525 | 0 | 0 | 0 | 525 | 2013-09-30 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 1 | Finished | 525 | 525 | C2015-17 Insurance Bundling System.xlsx
34 | 27 | web - user interface design | 2013-09-16 08:00 | 2013-09-25 09:00 | 7d 1h | Employee L | 4275 | 0 | 0 | 0 | 4275 | 2013-09-16 08:00 | 7d 1h | 4275 | 0 | 0 | 0 | 0 | 4275 | 0 | 1 | Finished | 4275 | 4275 | C2015-17 Insurance Bundling System.xlsx
35 | 96 | web - user interface integratie | 2013-11-12 08:00 | 2013-11-14 10:00 | 2d 2h | Employee L | 1350 | 0 | 0 | 0 | 1350 | 2013-11-18 08:00 | 2d 2h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 1 | Finished | 1350 | 1350 | C2015-17 Insurance Bundling System.xlsx
36 | 28 | design validated | 2013-11-15 17:00 | 2013-11-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-11-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-17 Insurance Bundling System.xlsx
37 | 66 | build | 2013-09-24 08:00 | 2013-12-16 17:00 | 60d |  |  | 0 |  |  | 81825 |  | 60d 7h | [5 empty] | 87675 |  | 1 |  | 81825 | 81825 | C2015-17 Insurance Bundling System.xlsx
38 | 32 | GP - classic | 2013-10-14 08:00 | 2013-10-29 10:00 | 11d 2h | Employee N | 6750 | 0 | 0 | 0 | 6750 | 2013-10-21 08:00 | 11d 2h | 6750 | 0 | 0 | 0 | 0 | 6750 | 0 | 1 | Finished | 6750 | 6750 | C2015-17 Insurance Bundling System.xlsx
39 | 33 | GP - classic | 2013-10-14 08:00 | 2013-10-14 16:00 | 7h | Employee E | 525 | 0 | 0 | 0 | 525 | 2013-10-21 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 1 | Finished | 525 | 525 | C2015-17 Insurance Bundling System.xlsx
40 | 34 | GP - ESB | 2013-11-04 08:00 | 2013-11-05 17:00 | 2d | Employee O | 1200 | 0 | 0 | 0 | 1200 | 2013-10-21 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 1 | Finished | 1200 | 1200 | C2015-17 Insurance Bundling System.xlsx
41 | 35 | GP - technical assembly test | 2013-11-18 08:00 | 2013-11-18 11:00 | 3h | Employee O | 225 | 0 | 0 | 0 | 225 | 2013-11-04 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 1 | Finished | 225 | 225 | C2015-17 Insurance Bundling System.xlsx
42 | 36 | classic - arbeidsongeval | 2013-09-30 08:00 | 2013-09-30 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2013-10-14 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 300 | 300 | C2015-17 Insurance Bundling System.xlsx
43 | 37 | classic - arbeidsongeval | 2013-09-30 08:00 | 2013-10-10 14:00 | 8d 5h | Employee P | 5175 | 0 | 0 | 0 | 5175 | 2013-09-30 08:00 | 8d 5h | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 1 | Finished | 5175 | 5175 | C2015-17 Insurance Bundling System.xlsx
44 | 38 | classic - auto | 2013-10-07 08:00 | 2013-10-09 10:00 | 2d 2h | Employee E | 1350 | 0 | 0 | 0 | 1350 | 2013-10-07 08:00 | 2d 2h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 1 | Finished | 1350 | 1350 | C2015-17 Insurance Bundling System.xlsx
45 | 39 | classic - auto | 2013-10-07 08:00 | 2013-10-18 10:00 | 9d 2h | Employee P | 5550 | 0 | 0 | 0 | 5550 | 2013-10-07 08:00 | 9d 2h | 5550 | 0 | 0 | 0 | 0 | 5550 | 0 | 1 | Finished | 5550 | 5550 | C2015-17 Insurance Bundling System.xlsx
46 | 40 | classic - brand | 2013-10-28 08:00 | 2013-10-29 10:00 | 1d 2h | Employee E | 750 | 0 | 0 | 0 | 750 | 2013-10-07 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 750 | 750 | C2015-17 Insurance Bundling System.xlsx
47 | 41 | classic - brand | 2013-10-28 08:00 | 2013-10-28 16:00 | 7h | Employee P | 525 | 0 | 0 | 0 | 525 | 2013-10-28 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 1 | Finished | 525 | 525 | C2015-17 Insurance Bundling System.xlsx
48 | 42 | classic - cleansing data | 2013-11-04 08:00 | 2013-11-15 11:00 | 9d 3h | Employee N | 5625 | 0 | 0 | 0 | 5625 | 2013-09-30 08:00 | 3d 6h | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 1 | Finished | 5625 | 5625 | C2015-17 Insurance Bundling System.xlsx
49 | 43 | classic - cleansing | 2013-11-04 08:00 | 2013-11-15 12:00 | 9d 4h | Employee E | 5700 | 0 | 0 | 0 | 5700 | 2013-11-18 08:00 | 9d 4h | 5700 | 0 | 0 | 0 | 0 | 5700 | 0 | 1 | Finished | 5700 | 5700 | C2015-17 Insurance Bundling System.xlsx
50 | 44 | classic - cleansing voorbereiding | 2013-09-30 08:00 | 2013-10-02 16:00 | 2d 7h | Employee N | 1725 | 0 | 0 | 0 | 1725 | 2013-10-07 08:00 | 30d 7h | 18525 | 0 | 0 | 0 | 0 | 18525 | 0 | 1 | Finished | 1725 | 1725 | C2015-17 Insurance Bundling System.xlsx
51 | 45 | classic - cleansing voorbereiding | 2013-09-30 08:00 | 2013-10-04 14:00 | 4d 5h | Employee E | 2775 | 0 | 0 | 0 | 2775 | 2013-10-07 08:00 | 4d 5h | 2775 | 0 | 0 | 0 | 0 | 2775 | 0 | 1 | Finished | 2775 | 2775 | C2015-17 Insurance Bundling System.xlsx
52 | 46 | dashboard - BO | 2013-11-12 08:00 | 2013-11-12 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 | 2013-11-11 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 1 | Finished | 450 | 450 | C2015-17 Insurance Bundling System.xlsx
53 | 47 | dashboard - UI | 2013-11-25 08:00 | 2013-11-25 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2013-11-04 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 300 | 300 | C2015-17 Insurance Bundling System.xlsx
54 | 48 | dashboard - UI | 2013-11-25 08:00 | 2013-12-16 15:00 | 15d 6h | Employee P | 9450 | 0 | 0 | 0 | 9450 | 2013-11-04 08:00 | 15d 7h | 9525 | 0 | 0 | 0 | 0 | 9525 | 0 | 1 | Finished | 9450 | 9450 | C2015-17 Insurance Bundling System.xlsx
55 | 49 | classic - BO leeg gezin | 2013-09-26 08:00 | 2013-09-26 16:00 | 7h | Employee N | 525 | 0 | 0 | 0 | 525 | 2013-09-23 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 1 | Finished | 525 | 525 | C2015-17 Insurance Bundling System.xlsx
56 | 50 | classic - BO leeg gezin | 2013-09-26 08:00 | 2013-09-26 10:00 | 2h | Employee E | 150 | 0 | 0 | 0 | 150 | 2013-10-14 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 150 | 150 | C2015-17 Insurance Bundling System.xlsx
57 | 51 | classic - BO | 2013-10-21 08:00 | 2013-11-04 11:00 | 10d 3h | Employee E | 6225 | 0 | 0 | 0 | 6225 | 2013-11-11 08:00 | 4d 7h | 2925 | 0 | 0 | 0 | 0 | 2925 | 0 | 1 | Finished | 6225 | 6225 | C2015-17 Insurance Bundling System.xlsx
58 | 52 | classic - annuleren | 2013-11-25 08:00 | 2013-11-27 11:00 | 2d 3h | Employee E | 1425 | 0 | 0 | 0 | 1425 | 2013-11-04 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 1425 | 1425 | C2015-17 Insurance Bundling System.xlsx
59 | 53 | classic - voltooien | 2013-11-18 08:00 | 2013-11-20 11:00 | 2d 3h | Employee E | 1425 | 0 | 0 | 0 | 1425 | 2013-11-04 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 1 | Finished | 1425 | 1425 | C2015-17 Insurance Bundling System.xlsx
60 | 54 | classic - UI detail | 2013-09-25 08:00 | 2013-09-25 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 | 2013-09-23 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 1 | Finished | 450 | 450 | C2015-17 Insurance Bundling System.xlsx
61 | 55 | classic - UI | 2013-09-24 08:00 | 2013-09-26 09:00 | 2d 1h | Employee E | 1275 | 0 | 0 | 0 | 1275 | 2013-09-23 08:00 | 2d 1h | 1275 | 0 | 0 | 0 | 0 | 1275 | 0 | 1 | Finished | 1275 | 1275 | C2015-17 Insurance Bundling System.xlsx
62 | 56 | classic - inhoud | 2013-09-30 08:00 | 2013-10-08 15:00 | 6d 6h | Employee E | 4050 | 0 | 0 | 0 | 4050 | 2013-09-30 08:00 | 4d 5h | 2775 | 0 | 0 | 0 | 0 | 2775 | 0 | 1 | Finished | 4050 | 4050 | C2015-17 Insurance Bundling System.xlsx
63 | 57 | classic - leden | 2013-11-12 08:00 | 2013-11-12 17:00 | 1d | Employee P | 600 | 0 | 0 | 0 | 600 | 2013-11-04 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 1 | Finished | 600 | 600 | C2015-17 Insurance Bundling System.xlsx
64 | 58 | classic - varia | 2013-10-22 08:00 | 2013-10-22 14:00 | 5h | Employee E | 375 | 0 | 0 | 0 | 375 | 2013-10-14 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 375 | 375 | C2015-17 Insurance Bundling System.xlsx
65 | 59 | classic - varia | 2013-10-22 08:00 | 2013-10-29 14:00 | 5d 5h | Employee P | 3375 | 0 | 0 | 0 | 3375 | 2013-10-14 08:00 | 2d 3h | 1425 | 0 | 0 | 0 | 0 | 1425 | 0 | 1 | Finished | 3375 | 3375 | C2015-17 Insurance Bundling System.xlsx
66 | 61 | get NB - ESB | 2013-11-18 08:00 | 2013-11-20 17:00 | 3d | Employee V | 1800 | 0 | 0 | 0 | 1800 | 2013-11-18 08:00 | 3d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 1 | Finished | 1800 | 1800 | C2015-17 Insurance Bundling System.xlsx
67 | 62 | PO - classic | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d | Employee E | 3000 | 0 | 0 | 0 | 3000 | 2013-11-18 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 1 | Finished | 3000 | 3000 | C2015-17 Insurance Bundling System.xlsx
68 | 63 | quote - ESB | 2013-11-18 08:00 | 2013-11-19 14:00 | 1d 5h | Employee O | 975 | 0 | 0 | 0 | 975 | 2013-11-04 08:00 | 1d 6h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 1 | Finished | 975 | 975 | C2015-17 Insurance Bundling System.xlsx
69 | 64 | web | 2013-11-18 08:00 | 2013-11-19 17:00 | 2d | Employee H | 1200 | 0 | 0 | 0 | 1200 | 2013-11-18 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 1 | Finished | 1200 | 1200 | C2015-17 Insurance Bundling System.xlsx
70 | 97 | web | 2013-11-18 08:00 | 2013-12-02 17:00 | 11d | Employee Q | 6600 | 0 | 0 | 0 | 6600 | 2013-11-11 08:00 | 11d 3h | 6825 | 0 | 0 | 0 | 0 | 6825 | 0 | 1 | Finished | 6600 | 6600 | C2015-17 Insurance Bundling System.xlsx
71 | 65 | build validated | 2013-12-16 17:00 | 2013-12-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-16 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-17 Insurance Bundling System.xlsx
72 | 93 | test ict | 2013-10-10 08:00 | 2014-01-24 17:00 | 77d |  |  | 0 |  |  | 90675 |  | 115d 1h | [5 empty] | 88050 |  | 1 |  | 90675 | 90675 | C2015-17 Insurance Bundling System.xlsx
73 | 67 | test coordination | 2013-10-14 08:00 | 2013-10-25 09:00 | 9d 1h | Employee R | 5475 | 0 | 0 | 0 | 5475 | 2013-10-14 08:00 | 9d 1h | 5475 | 0 | 0 | 0 | 0 | 5475 | 0 | 1 | Finished | 5475 | 5475 | C2015-17 Insurance Bundling System.xlsx
74 | 68 | test execution | 2013-11-18 08:00 | 2013-12-13 12:00 | 19d 4h | Employee S | 11700 | 0 | 0 | 0 | 11700 | 2013-12-23 08:00 | 4d 4h | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 1 | Finished | 11700 | 11700 | C2015-17 Insurance Bundling System.xlsx
75 | 69 | test execution | 2013-11-18 08:00 | 2013-12-18 16:00 | 22d 7h | Employee R | 13725 | 0 | 0 | 0 | 13725 | 2013-12-02 08:00 | 31d 5h | 18975 | 0 | 0 | 0 | 0 | 18975 | 0 | 1 | Finished | 13725 | 13725 | C2015-17 Insurance Bundling System.xlsx
76 | 70 | test execution | 2013-11-18 08:00 | 2013-12-16 09:00 | 20d 1h | Employee T | 12075 | 0 | 0 | 0 | 12075 | 2013-11-25 08:00 | 30d 7h | 18525 | 0 | 0 | 0 | 0 | 18525 | 0 | 1 | Finished | 12075 | 12075 | C2015-17 Insurance Bundling System.xlsx
77 | 71 | test execution | 2013-11-18 08:00 | 2013-11-18 16:00 | 7h | Employee L | 525 | 0 | 0 | 0 | 525 | 2014-01-13 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 1 | Finished | 525 | 525 | C2015-17 Insurance Bundling System.xlsx
78 | 72 | test preparation | 2013-10-10 08:00 | 2013-10-10 14:00 | 5h | Employee S | 375 | 0 | 0 | 0 | 375 | 2013-11-18 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 375 | 375 | C2015-17 Insurance Bundling System.xlsx
79 | 73 | test preparation | 2013-10-10 08:00 | 2013-10-21 17:00 | 8d | Employee R | 4800 | 0 | 0 | 0 | 4800 | 2013-11-11 08:00 | 9d 7h | 5925 | 0 | 0 | 0 | 0 | 5925 | 0 | 1 | Finished | 4800 | 4800 | C2015-17 Insurance Bundling System.xlsx
80 | 74 | test preparation | 2013-10-10 08:00 | 2013-10-30 10:00 | 14d 2h | Employee T | 8550 | 0 | 0 | 0 | 8550 | 2013-10-07 08:00 | 16d 1h | 9675 | 0 | 0 | 0 | 0 | 9675 | 0 | 1 | Finished | 8550 | 8550 | C2015-17 Insurance Bundling System.xlsx
81 | 75 | test preparation | 2013-10-10 08:00 | 2013-10-14 15:00 | 2d 6h | Employee U | 1650 | 0 | 0 | 0 | 1650 | 2014-01-13 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 1 | Finished | 1650 | 1650 | C2015-17 Insurance Bundling System.xlsx
82 | 76 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee V | 1725 | 0 | 0 | 0 | 1725 | 2013-12-23 08:00 | 3d 2h | 1950 | 0 | 0 | 0 | 0 | 1950 | 0 | 1 | Finished | 1725 | 1725 | C2015-17 Insurance Bundling System.xlsx
83 | 77 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee W | 1725 | 0 | 0 | 0 | 1725 | 2014-01-08 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1725 | 1725 | C2015-17 Insurance Bundling System.xlsx
84 | 78 | bugfixing | 2013-12-02 08:00 | 2013-12-02 15:00 | 6h | Employee Q | 450 | 0 | 0 | 0 | 450 | 2014-01-06 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 1 | Finished | 450 | 450 | C2015-17 Insurance Bundling System.xlsx
85 | 79 | bugfixing | 2013-12-02 08:00 | 2013-12-09 14:00 | 5d 5h | Employee N | 3375 | 0 | 0 | 0 | 3375 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 3375 | 3375 | C2015-17 Insurance Bundling System.xlsx
86 | 80 | bugfixing | 2013-12-02 08:00 | 2014-01-06 12:00 | 25d 4h | Employee E | 15300 | 0 | 0 | 0 | 15300 | 2013-12-02 08:00 | 25d 5h | 15375 | 0 | 0 | 0 | 0 | 15375 | 0 | 1 | Finished | 15300 | 15300 | C2015-17 Insurance Bundling System.xlsx
87 | 81 | bugfixing | 2013-12-02 08:00 | 2013-12-02 12:00 | 4h | Employee X | 300 | 0 | 0 | 0 | 300 | 2013-12-09 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 300 | 300 | C2015-17 Insurance Bundling System.xlsx
88 | 82 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee L | 1725 | 0 | 0 | 0 | 1725 | 2014-01-27 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 1725 | 1725 | C2015-17 Insurance Bundling System.xlsx
89 | 98 | bugfixing | 2013-12-02 08:00 | 2013-12-17 17:00 | 12d | Employee P | 7200 | 0 | 0 | 0 | 7200 | 2013-12-02 08:00 | 9d 4h | 5700 | 0 | 0 | 0 | 0 | 5700 | 0 | 1 | Finished | 7200 | 7200 | C2015-17 Insurance Bundling System.xlsx
90 | 83 | ict test completed | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-17 Insurance Bundling System.xlsx
91 | 94 | ondersteuning | 2013-09-17 08:00 | 2013-10-17 10:00 | 22d 2h |  |  | 0 |  |  | 17400 |  | 57d 2h | [5 empty] | 17700 |  | 1 |  | 17400 | 17400 | C2015-17 Insurance Bundling System.xlsx
92 | 84 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-17 09:00 | 1h | Employee J | 75 | 0 | 0 | 0 | 75 | 2013-09-16 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 75 | 75 | C2015-17 Insurance Bundling System.xlsx
93 | 85 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-17 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 | 2013-11-05 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 1 | Finished | 600 | 600 | C2015-17 Insurance Bundling System.xlsx
94 | 86 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-24 14:00 | 5d 5h | Employee G | 3375 | 0 | 0 | 0 | 3375 | 2013-11-04 08:00 | 5d 5h | 3375 | 0 | 0 | 0 | 0 | 3375 | 0 | 1 | Finished | 3375 | 3375 | C2015-17 Insurance Bundling System.xlsx
95 | 87 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-10-17 10:00 | 22d 2h | Employee D | 13350 | 0 | 0 | 0 | 13350 | 2013-11-04 08:00 | 22d 2h | 13350 | 0 | 0 | 0 | 0 | 13350 | 0 | 1 | Finished | 13350 | 13350 | C2015-17 Insurance Bundling System.xlsx
96 | 100 | implementation | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-17 Insurance Bundling System.xlsx
97 | 95 | go live | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-17 Insurance Bundling System.xlsx
98 | 101 | post implementation | 2014-01-27 08:00 | 2014-02-05 12:00 | 7d 4h |  |  | 0 |  |  | 8400 |  | 12d 3h | [5 empty] | 3975 |  | 1 |  | 8400 | 8400 | C2015-17 Insurance Bundling System.xlsx
99 | 88 | post implementation - post go live support | 2014-01-27 08:00 | 2014-02-05 12:00 | 7d 4h | Employee E | 4500 | 0 | 0 | 0 | 4500 | 2014-01-27 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 4500 | 4500 | C2015-17 Insurance Bundling System.xlsx
100 | 89 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-29 11:00 | 2d 3h | Employee R | 1425 | 0 | 0 | 0 | 1425 | 2014-02-10 08:00 | 2d 3h | 1425 | 0 | 0 | 0 | 0 | 1425 | 0 | 1 | Finished | 1425 | 1425 | C2015-17 Insurance Bundling System.xlsx
101 | 90 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-28 09:00 | 1d 1h | Employee T | 675 | 0 | 0 | 0 | 675 | 2014-02-10 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 1 | Finished | 675 | 675 | C2015-17 Insurance Bundling System.xlsx
102 | 91 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-27 10:00 | 2h | Employee L | 150 | 0 | 0 | 0 | 150 | 2014-02-10 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 150 | 150 | C2015-17 Insurance Bundling System.xlsx
103 | 92 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-29 15:00 | 2d 6h | Employee D | 1650 | 0 | 0 | 0 | 1650 | 2014-02-03 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 1 | Finished | 1650 | 1650 | C2015-17 Insurance Bundling System.xlsx
4 | 0 | Tax Return System (2) | 2014-01-02 08:00 | 2014-06-30 17:00 | 128d |  |  | 0 |  |  | 39450 |  | 127d 7h | [5 empty] | 25380 |  | 1 |  | 39450 | 39450 | C2015-18 Tax Return System (2).xlsx
5 | 23 | supporting tasks | 2014-01-03 08:00 | 2014-01-10 09:00 | 5d 1h |  |  | 0 |  |  | 3690 |  | 3d 1h | [5 empty] | 2250 |  | 1 |  | 3690 | 3690 | C2015-18 Tax Return System (2).xlsx
6 | 1 | project management | 2014-01-03 08:00 | 2014-01-10 09:00 | 5d 1h | Employee A | 3690 | 0 | 0 | 0 | 3690 | 2014-01-02 08:00 | 3d 1h | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 1 | Finished | 3690 | 3690 | C2015-18 Tax Return System (2).xlsx
7 | 24 | analyse | 2014-01-02 08:00 | 2014-03-28 17:00 | 62d |  |  | 0 |  |  | 5010 |  | 67d 7h | [5 empty] | 4455 |  | 1 |  | 5010 | 5010 | C2015-18 Tax Return System (2).xlsx
8 | 2 | analyse | 2014-01-02 08:00 | 2014-01-03 15:00 | 1d 6h | Employee A | 1260 | 0 | 0 | 0 | 1260 | 2014-01-02 08:00 | 7h | 630 | 0 | 0 | 0 | 0 | 630 | 0 | 1 | Finished | 1260 | 1260 | C2015-18 Tax Return System (2).xlsx
9 | 4 | analyse AIA | 2014-01-06 08:00 | 2014-01-14 10:00 | 6d 2h | Employee B | 3750 | 0 | 0 | 0 | 3750 | 2014-01-06 08:00 | 6d 3h | 3825 | 0 | 0 | 0 | 0 | 3825 | 0 | 1 | Finished | 3750 | 3750 | C2015-18 Tax Return System (2).xlsx
10 | 5 | analysis validated | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-07 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-18 Tax Return System (2).xlsx
11 | 25 | design | 2014-01-29 08:00 | 2014-04-11 17:00 | 53d |  |  | 0 |  |  | 6750 |  | 59d 7h | [5 empty] | 6300 |  | 1 |  | 6750 | 6750 | C2015-18 Tax Return System (2).xlsx
12 | 6 | design HP | 2014-01-29 08:00 | 2014-02-10 15:00 | 8d 6h | Employee C | 5250 | 0 | 0 | 0 | 5250 | 2014-02-24 08:00 | 8d 7h | 5325 | 0 | 0 | 0 | 0 | 5325 | 0 | 1 | Finished | 5250 | 5250 | C2015-18 Tax Return System (2).xlsx
13 | 7 | design HP | 2014-01-29 08:00 | 2014-01-30 11:00 | 1d 3h | Employee D | 825 | 0 | 0 | 0 | 825 | 2014-01-27 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 1 | Finished | 825 | 825 | C2015-18 Tax Return System (2).xlsx
14 | 8 | design AIA | 2014-02-12 08:00 | 2014-02-13 09:00 | 1d 1h | Employee B | 675 | 0 | 0 | 0 | 675 | 2014-02-10 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 675 | 675 | C2015-18 Tax Return System (2).xlsx
15 | 9 | design validated | 2014-04-11 17:00 | 2014-04-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-18 Tax Return System (2).xlsx
16 | 26 | development | 2014-01-28 08:00 | 2014-05-23 17:00 | 84d |  |  | 0 |  |  | 15675 |  | 84d 7h | [5 empty] | 9450 |  | 1 |  | 15675 | 15675 | C2015-18 Tax Return System (2).xlsx
17 | 10 | build HP | 2014-01-28 08:00 | 2014-02-07 17:00 | 9d | Employee E | 5400 | 0 | 0 | 0 | 5400 | 2014-01-27 08:00 | 6d 3h | 3825 | 0 | 0 | 0 | 0 | 3825 | 0 | 1 | Finished | 5400 | 5400 | C2015-18 Tax Return System (2).xlsx
18 | 11 | build MF | 2014-01-30 08:00 | 2014-02-07 15:00 | 6d 6h | Employee F | 4050 | 0 | 0 | 0 | 4050 | 2014-01-27 08:00 | 5d 4h | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 1 | Finished | 4050 | 4050 | C2015-18 Tax Return System (2).xlsx
19 | 12 | build AIA | 2014-04-16 08:00 | 2014-04-30 11:00 | 10d 3h | Employee B | 6225 | 0 | 0 | 0 | 6225 | 2014-03-10 08:00 | 3d 7h | 2325 | 0 | 0 | 0 | 0 | 2325 | 0 | 1 | Finished | 6225 | 6225 | C2015-18 Tax Return System (2).xlsx
20 | 13 | development MF completed | 2014-05-23 17:00 | 2014-05-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-23 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-18 Tax Return System (2).xlsx
21 | 27 | test ict & uat | 2014-03-24 08:00 | 2014-06-13 17:00 | 60d |  |  | 0 |  |  | 6000 |  | 39d 7h | [5 empty] | 2250 |  | 1 |  | 6000 | 6000 | C2015-18 Tax Return System (2).xlsx
22 | 14 | testing HP | 2014-05-05 08:00 | 2014-05-06 16:00 | 1d 7h | Employee C | 1125 | 0 | 0 | 0 | 1125 | 2014-05-05 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 1 | Finished | 1125 | 1125 | C2015-18 Tax Return System (2).xlsx
23 | 15 | testing HP | 2014-05-05 08:00 | 2014-05-07 16:00 | 2d 7h | Employee D | 1725 | 0 | 0 | 0 | 1725 | 2014-05-05 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 1 | Finished | 1725 | 1725 | C2015-18 Tax Return System (2).xlsx
24 | 16 | testing MF | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 | 2014-04-21 08:00 | 1d 5h | 975 | 0 | 0 | 0 | 0 | 975 | 0 | 1 | Finished | 300 | 300 | C2015-18 Tax Return System (2).xlsx
25 | 17 | testing AIA | 2014-05-26 08:00 | 2014-05-30 15:00 | 4d 6h | Employee B | 2850 | 0 | 0 | 0 | 2850 | 2014-05-26 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 2850 | 2850 | C2015-18 Tax Return System (2).xlsx
26 | 18 | testing MF completed | 2014-06-13 17:00 | 2014-06-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-06-13 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-18 Tax Return System (2).xlsx
27 | 28 | implementation | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-18 Tax Return System (2).xlsx
28 | 19 | go live MF | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-06-16 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-18 Tax Return System (2).xlsx
29 | 29 | post implementation | 2014-06-16 08:00 | 2014-06-30 17:00 | 11d |  |  | 0 |  |  | 2325 |  | 10d 7h | [5 empty] | 675 |  | 1 |  | 2325 | 2325 | C2015-18 Tax Return System (2).xlsx
30 | 20 | post implementation - post go live support | 2014-06-16 08:00 | 2014-06-16 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 | 2014-06-16 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 1 | Finished | 600 | 600 | C2015-18 Tax Return System (2).xlsx
31 | 21 | post implementation - post go live support | 2014-06-16 08:00 | 2014-06-18 16:00 | 2d 7h | Employee B | 1725 | 0 | 0 | 0 | 1725 | 2014-06-16 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1725 | 1725 | C2015-18 Tax Return System (2).xlsx
32 | 22 | closure project | 2014-06-30 17:00 | 2014-06-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-06-30 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-18 Tax Return System (2).xlsx
4 | 0 | Receipt Numbering System | 2013-09-02 08:00 | 2014-05-13 16:00 | 181d 7h |  |  | 0 |  |  | 43800 |  | 181d 7h | [5 empty] | 37530 |  | 0.96062 |  | 42075 | 43275 | C2015-19 Receipt Numbering System.xlsx
5 | 25 | supporting tasks | 2013-09-02 08:00 | 2013-11-29 17:00 | 65d |  |  | 0 |  |  | 11775 |  | 181d | [5 empty] | 6480 |  | 0.8535 |  | 10050 | 11775 | C2015-19 Receipt Numbering System.xlsx
6 | 1 | project management | 2013-09-02 08:00 | 2013-09-10 16:00 | 6d 7h | Employee I | 4950 | 0 | 0 | 0 | 4950 | 2013-09-02 08:00 | 4d | 2880 | 0 | 0 | 0 | 0 | 2880 | 0 | 1 | Finished | 4950 | 4950 | C2015-19 Receipt Numbering System.xlsx
7 | 2 | validation and support | 2013-11-22 08:00 | 2013-11-25 16:00 | 1d 7h | Employee A | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0 | Not Started | 0 | 1125 | C2015-19 Receipt Numbering System.xlsx
8 | 3 | validation and support | 2013-11-22 08:00 | 2013-11-22 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0 | Not Started | 0 | 600 | C2015-19 Receipt Numbering System.xlsx
9 | 4 | validation and support | 2013-11-22 08:00 | 2013-11-29 17:00 | 6d | Employee D | 3600 | 0 | 0 | 0 | 3600 | 2013-11-18 08:00 | 4d 6h | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 1 | Finished | 3600 | 3600 | C2015-19 Receipt Numbering System.xlsx
10 | 5 | validation and support | 2013-11-22 08:00 | 2013-11-26 12:00 | 2d 4h | Employee L | 1500 | 0 | 0 | 0 | 1500 | 2014-01-20 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 1500 | 1500 | C2015-19 Receipt Numbering System.xlsx
11 | 26 | analysis | 2013-09-06 08:00 | 2013-12-31 17:00 | 83d |  |  | 0 |  |  | 750 |  | 101d 7h | [5 empty] | 750 |  | 1 |  | 750 | 750 | C2015-19 Receipt Numbering System.xlsx
12 | 6 | analysis - conceptual design | 2013-09-06 08:00 | 2013-09-09 09:00 | 1d 1h | Employee A | 675 | 0 | 0 | 0 | 675 | 2013-09-06 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 1 | Finished | 675 | 675 | C2015-19 Receipt Numbering System.xlsx
13 | 7 | analysis - conceptual design | 2013-09-06 08:00 | 2013-09-06 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 2013-12-16 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 75 | 75 | C2015-19 Receipt Numbering System.xlsx
14 | 8 | analysis validated | 2013-12-31 17:00 | 2013-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-27 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-19 Receipt Numbering System.xlsx
15 | 27 | design | 2013-12-02 08:00 | 2014-02-18 17:00 | 57d |  |  | 0 |  |  | 9825 |  | 55d 7h | [5 empty] | 10200 |  | 1 |  | 9825 | 9825 | C2015-19 Receipt Numbering System.xlsx
16 | 9 | design - MF | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h | Employee D | 150 | 0 | 0 | 0 | 150 | 2013-12-30 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 150 | 150 | C2015-19 Receipt Numbering System.xlsx
17 | 10 | design - MF | 2013-12-02 08:00 | 2013-12-03 15:00 | 1d 6h | Employee E | 1050 | 0 | 0 | 0 | 1050 | 2013-12-02 08:00 | 1d 6h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 1 | Finished | 1050 | 1050 | C2015-19 Receipt Numbering System.xlsx
18 | 11 | design - MF | 2013-12-02 08:00 | 2013-12-20 10:00 | 14d 2h | Employee F | 8550 | 0 | 0 | 0 | 8550 | 2014-01-06 08:00 | 14d 7h | 8925 | 0 | 0 | 0 | 0 | 8925 | 0 | 1 | Finished | 8550 | 8550 | C2015-19 Receipt Numbering System.xlsx
19 | 12 | design - DWH | 2013-12-09 08:00 | 2013-12-09 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 2013-12-09 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 75 | 75 | C2015-19 Receipt Numbering System.xlsx
20 | 13 | design validated | 2014-02-18 17:00 | 2014-02-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-17 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-19 Receipt Numbering System.xlsx
21 | 28 | development | 2013-11-19 08:00 | 2014-02-28 17:00 | 74d |  |  | 0 |  |  | 16875 |  | 56d 7h | [5 empty] | 17475 |  | 1 |  | 16875 | 16875 | C2015-19 Receipt Numbering System.xlsx
22 | 14 | development - coding MF | 2013-11-19 08:00 | 2013-12-13 17:00 | 19d | Employee G | 11400 | 0 | 0 | 0 | 11400 | 2014-01-06 08:00 | 20d | 12000 | 0 | 0 | 0 | 0 | 12000 | 0 | 1 | Finished | 11400 | 11400 | C2015-19 Receipt Numbering System.xlsx
23 | 15 | development - coding MF | 2013-11-19 08:00 | 2013-11-28 14:00 | 7d 5h | Employee H | 4575 | 0 | 0 | 0 | 4575 | 2014-01-13 08:00 | 7d 5h | 4575 | 0 | 0 | 0 | 0 | 4575 | 0 | 1 | Finished | 4575 | 4575 | C2015-19 Receipt Numbering System.xlsx
24 | 16 | development - coding MF | 2013-11-19 08:00 | 2013-11-19 14:00 | 5h | Employee E | 375 | 0 | 0 | 0 | 375 | 2013-11-18 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 375 | 375 | C2015-19 Receipt Numbering System.xlsx
25 | 17 | development - coding MF | 2013-11-19 08:00 | 2013-11-19 16:00 | 7h | Employee F | 525 | 0 | 0 | 0 | 525 | 2014-02-03 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 1 | Finished | 525 | 525 | C2015-19 Receipt Numbering System.xlsx
26 | 20 | development completed | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-04 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-19 Receipt Numbering System.xlsx
27 | 33 | development bugfixing | 2014-03-24 08:00 | 2014-03-26 11:00 | 2d 3h |  |  | 0 |  |  | 2250 |  | 6d 2h | [5 empty] | 825 |  | 1 |  | 2250 | 2250 | C2015-19 Receipt Numbering System.xlsx
28 | 32 | development - bugfixing | 2014-03-24 08:00 | 2014-03-26 11:00 | 2d 3h | Employee G | 1425 | 0 | 0 | 0 | 1425 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1425 | 1425 | C2015-19 Receipt Numbering System.xlsx
29 | 31 | development - bugfixing | 2014-03-24 08:00 | 2014-03-25 11:00 | 1d 3h | Employee D | 825 | 0 | 0 | 0 | 825 | 2014-03-31 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 825 | 825 | C2015-19 Receipt Numbering System.xlsx
30 | 29 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-19 Receipt Numbering System.xlsx
31 | 24 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-19 Receipt Numbering System.xlsx
32 | 30 | post implementation | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h |  |  | 0 |  |  | 2325 |  | 1d 7h | [5 empty] | 1800 |  | 1 |  | 2325 | 1800 | C2015-19 Receipt Numbering System.xlsx
33 | 21 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee A | 600 | 0 | 0 | 0 | 600 | 2014-05-12 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 1 | Finished | 600 | 600 | C2015-19 Receipt Numbering System.xlsx
34 | 22 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2014-05-12 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 600 | 600 | C2015-19 Receipt Numbering System.xlsx
35 | 23 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h | Employee D | 1125 | 0 | 0 | 0 | 1125 | 2014-05-12 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 1 | Finished | 1125 | 600 | C2015-19 Receipt Numbering System.xlsx
4 | 0 | Policy Numbering System | 2013-09-09 08:00 | 2014-05-05 17:00 | 171d |  |  | 0 |  |  | 12645 |  | 161d | [5 empty] | 11100 |  | 1 |  | 12645 | 12645 | C2015-20 Policy Numbering System.xlsx
5 | 12 | supporting tasks | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  |  | 0 |  |  | 720 |  | 1d 2h | [5 empty] | 900 |  | 1 |  | 720 | 720 | C2015-20 Policy Numbering System.xlsx
6 | 1 | project management | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d | Employee A | 720 | 0 | 0 | 0 | 720 | 2013-09-16 08:00 | 1d 2h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 1 | Finished | 720 | 720 | C2015-20 Policy Numbering System.xlsx
7 | 13 | analysis | 2013-09-16 08:00 | 2013-11-13 17:00 | 43d |  |  | 0 |  |  | 1050 |  | 42d 7h | [5 empty] | 75 |  | 1 |  | 1050 | 1050 | C2015-20 Policy Numbering System.xlsx
8 | 2 | analysis - business analysis | 2013-09-16 08:00 | 2013-09-17 15:00 | 1d 6h | Employee B | 1050 | 0 | 0 | 0 | 1050 | 2013-09-16 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1050 | 1050 | C2015-20 Policy Numbering System.xlsx
9 | 4 | analysis validated | 2013-11-13 17:00 | 2013-11-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-11-13 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-20 Policy Numbering System.xlsx
10 | 14 | design | 2013-09-10 08:00 | 2013-12-03 17:00 | 61d |  |  | 0 |  |  | 3075 |  | 61d 7h | [5 empty] | 2325 |  | 1 |  | 3075 | 3075 | C2015-20 Policy Numbering System.xlsx
11 | 3 | design - technical design | 2013-09-10 08:00 | 2013-09-17 09:00 | 5d 1h | Employee C | 3075 | 0 | 0 | 0 | 3075 | 2013-09-09 08:00 | 3d 7h | 2325 | 0 | 0 | 0 | 0 | 2325 | 0 | 1 | Finished | 3075 | 3075 | C2015-20 Policy Numbering System.xlsx
12 | 5 | design validated | 2013-12-03 17:00 | 2013-12-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-03 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-20 Policy Numbering System.xlsx
13 | 15 | development | 2013-09-09 08:00 | 2014-03-07 17:00 | 130d |  |  | 0 |  |  | 7800 |  | 161d | [5 empty] | 7800 |  | 1 |  | 7800 | 7800 | C2015-20 Policy Numbering System.xlsx
14 | 6 | development - coding | 2013-09-09 08:00 | 2013-09-17 10:00 | 6d 2h | Employee D | 3750 | 0 | 0 | 0 | 3750 | 2013-09-09 08:00 | 6d 2h | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 1 | Finished | 3750 | 3750 | C2015-20 Policy Numbering System.xlsx
15 | 7 | development - coding | 2013-09-09 08:00 | 2013-09-13 16:00 | 4d 7h | Employee E | 2925 | 0 | 0 | 0 | 2925 | 2013-09-09 08:00 | 4d 7h | 2925 | 0 | 0 | 0 | 0 | 2925 | 0 | 1 | Finished | 2925 | 2925 | C2015-20 Policy Numbering System.xlsx
16 | 8 | development - coding | 2013-09-09 08:00 | 2013-09-10 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2013-09-09 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 1 | Finished | 1125 | 1125 | C2015-20 Policy Numbering System.xlsx
17 | 9 | development completed | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started | 0 | 0 | C2015-20 Policy Numbering System.xlsx
18 | 16 | implementation | 2014-04-25 17:00 | 2014-05-05 17:00 | 6d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-20 Policy Numbering System.xlsx
19 | 10 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started | 0 | 0 | C2015-20 Policy Numbering System.xlsx
20 | 11 | go live | 2014-05-05 17:00 | 2014-05-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started | 0 | 0 | C2015-20 Policy Numbering System.xlsx
4 | 0 | Investment Product (1) | 2014-03-17 08:00 | 2014-05-06 17:00 | 37d |  |  | 0 |  |  | 4020 |  | 36d 7h | [5 empty] | 3240 |  | 1 |  | 4020 | 4020 | C2015-21 Investment Product (1).xlsx
5 | 24 | supporting tasks | 2014-03-17 08:00 | 2014-03-31 10:00 | 10d 2h |  |  | 0 |  |  | 1020 |  | 15d 2h | [5 empty] | 840 |  | 1 |  | 1020 | 1020 | C2015-21 Investment Product (1).xlsx
6 | 1 | project management | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee A | 720 | 0 | 0 | 0 | 720 | 2014-03-17 08:00 | 6h | 540 | 0 | 0 | 0 | 0 | 540 | 0 | 1 | Finished | 720 | 720 | C2015-21 Investment Product (1).xlsx
7 | 2 | validation and support | 2014-03-31 08:00 | 2014-03-31 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 | 2014-04-07 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 150 | 150 | C2015-21 Investment Product (1).xlsx
8 | 3 | validation and support | 2014-03-31 08:00 | 2014-03-31 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 75 | 75 | C2015-21 Investment Product (1).xlsx
9 | 4 | validation and support | 2014-03-31 08:00 | 2014-03-31 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 | 2014-03-31 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 75 | 75 | C2015-21 Investment Product (1).xlsx
10 | 25 | analysis | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d |  |  | 0 |  |  | 300 |  | 7h | [5 empty] | 300 |  | 1 |  | 300 | 300 | C2015-21 Investment Product (1).xlsx
11 | 5 | analysis - business analysis | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | Employee C | 300 | 0 | 0 | 0 | 300 | 2014-03-17 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 300 | 300 | C2015-21 Investment Product (1).xlsx
12 | 6 | analysis validated | 2014-03-17 17:00 | 2014-03-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-17 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-21 Investment Product (1).xlsx
13 | 26 | design | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d |  |  | 0 |  |  | 900 |  | 6d 7h | [5 empty] | 750 |  | 1 |  | 900 | 900 | C2015-21 Investment Product (1).xlsx
14 | 7 | design - integration (mapping) | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2014-03-25 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 300 | 300 | C2015-21 Investment Product (1).xlsx
15 | 8 | design - user interface design | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee D | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 1 | Finished | 600 | 600 | C2015-21 Investment Product (1).xlsx
16 | 9 | design validated | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-21 Investment Product (1).xlsx
17 | 27 | development | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d |  |  | 0 |  |  | 900 |  | 5d 1h | [5 empty] | 300 |  | 1 |  | 900 | 900 | C2015-21 Investment Product (1).xlsx
18 | 10 | development - coding | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 1 | Finished | 600 | 600 | C2015-21 Investment Product (1).xlsx
19 | 12 | development - technical assembly | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee D | 300 | 0 | 0 | 0 | 300 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 300 | 300 | C2015-21 Investment Product (1).xlsx
20 | 28 | test ICT | 2014-03-24 08:00 | 2014-04-07 17:00 | 11d |  |  | 0 |  |  | 900 |  | 15d 7h | [5 empty] | 1050 |  | 1 |  | 900 | 900 | C2015-21 Investment Product (1).xlsx
21 | 13 | test ICT - test coordination | 2014-03-31 08:00 | 2014-03-31 12:00 | 4h | Employee B | 300 | 0 | 0 | 0 | 300 | 2014-03-17 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 300 | 300 | C2015-21 Investment Product (1).xlsx
22 | 16 | test ICT - test preparation | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 2014-03-24 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 300 | 300 | C2015-21 Investment Product (1).xlsx
23 | 19 | test ICT - test execution | 2014-03-31 08:00 | 2014-03-31 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 2014-03-24 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 1 | Finished | 300 | 300 | C2015-21 Investment Product (1).xlsx
24 | 20 | ICT test completed | 2014-04-07 17:00 | 2014-04-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-07 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-21 Investment Product (1).xlsx
25 | 29 | implementation | 2014-04-07 17:00 | 2014-05-06 17:00 | 21d |  |  | 0 |  |  | 0 |  | 21d | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-21 Investment Product (1).xlsx
26 | 21 | full handover | 2014-04-07 17:00 | 2014-04-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-07 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-21 Investment Product (1).xlsx
27 | 22 | go live | 2014-05-06 17:00 | 2014-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-06 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-21 Investment Product (1).xlsx
4 | 0 | Risk Profile Questionnaire | 2013-10-14 08:00 | 2014-05-13 10:00 | 151d 2h |  |  | 0 |  |  | 29880 |  | 151d 2h | [5 empty] | 17400 |  | 1 |  | 29880 | 29430 | C2015-22 Risk Profile Questionnaire.xlsx
5 | 32 | supporting tasks | 2013-10-14 08:00 | 2013-12-17 17:00 | 47d |  |  | 0 |  |  | 8355 |  | 110d 1h | [5 empty] | 5025 |  | 1 |  | 8355 | 8355 | C2015-22 Risk Profile Questionnaire.xlsx
6 | 1 | project management | 2013-10-14 08:00 | 2013-10-22 12:00 | 6d 4h | Employee A | 4680 | 0 | 0 | 0 | 4680 | 2014-02-24 08:00 | 1d 7h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 1 | Finished | 4680 | 4680 | C2015-22 Risk Profile Questionnaire.xlsx
7 | 2 | project management | 2013-10-14 08:00 | 2013-10-15 17:00 | 2d | Employee B | 1200 | 0 | 0 | 0 | 1200 | 2013-10-14 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 1 | Finished | 1200 | 1200 | C2015-22 Risk Profile Questionnaire.xlsx
8 | 3 | validation and support | 2013-12-12 08:00 | 2013-12-12 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 75 | 75 | C2015-22 Risk Profile Questionnaire.xlsx
9 | 4 | validation and support | 2013-12-12 08:00 | 2013-12-17 17:00 | 4d | Employee D | 2400 | 0 | 0 | 0 | 2400 | 2014-03-03 08:00 | 4d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 1 | Finished | 2400 | 2400 | C2015-22 Risk Profile Questionnaire.xlsx
10 | 33 | analysis | 2014-02-07 08:00 | 2014-02-24 17:00 | 12d |  |  | 0 |  |  | 525 |  | 15d 7h | [5 empty] | 525 |  | 1 |  | 525 | 525 | C2015-22 Risk Profile Questionnaire.xlsx
11 | 5 | analysis - conceptual design | 2014-02-07 08:00 | 2014-02-07 16:00 | 7h | Employee C | 525 | 0 | 0 | 0 | 525 | 2014-02-03 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 1 | Finished | 525 | 525 | C2015-22 Risk Profile Questionnaire.xlsx
12 | 6 | analysis validated | 2014-02-24 17:00 | 2014-02-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-22 Risk Profile Questionnaire.xlsx
13 | 34 | design | 2014-01-31 08:00 | 2014-02-06 12:00 | 4d 4h |  |  | 0 |  |  | 2700 |  | 8d 3h | [5 empty] | 2700 |  | 1 |  | 2700 | 2700 | C2015-22 Risk Profile Questionnaire.xlsx
14 | 7 | design - ISP design | 2014-01-31 08:00 | 2014-02-06 12:00 | 4d 4h | Employee D | 2700 | 0 | 0 | 0 | 2700 | 2014-01-27 08:00 | 4d 4h | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 1 | Finished | 2700 | 2700 | C2015-22 Risk Profile Questionnaire.xlsx
15 | 8 | design validated | 2014-02-06 12:00 | 2014-02-06 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-06 11:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-22 Risk Profile Questionnaire.xlsx
16 | 35 | development | 2014-03-10 08:00 | 2014-03-25 17:00 | 12d |  |  | 0 |  |  | 3375 |  | 26d 1h | [5 empty] | 975 |  | 1 |  | 3375 | 3375 | C2015-22 Risk Profile Questionnaire.xlsx
17 | 9 | development - build ISP | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 1 | Finished | 600 | 600 | C2015-22 Risk Profile Questionnaire.xlsx
18 | 10 | development - build ISP | 2014-03-17 08:00 | 2014-03-18 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2014-03-03 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 1125 | 1125 | C2015-22 Risk Profile Questionnaire.xlsx
19 | 11 | development - technical assembly test | 2014-03-10 08:00 | 2014-03-12 10:00 | 2d 2h | Employee D | 1350 | 0 | 0 | 0 | 1350 | 2014-04-08 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1350 | 1350 | C2015-22 Risk Profile Questionnaire.xlsx
20 | 12 | development - bugfixing | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 | 2014-04-08 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 300 | 300 | C2015-22 Risk Profile Questionnaire.xlsx
21 | 13 | development completed | 2014-03-25 17:00 | 2014-03-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-22 Risk Profile Questionnaire.xlsx
22 | 36 | test ict | 2014-02-24 08:00 | 2014-03-28 17:00 | 25d |  |  | 0 |  |  | 6225 |  | 31d 1h | [5 empty] | 5700 |  | 1 |  | 6225 | 6225 | C2015-22 Risk Profile Questionnaire.xlsx
23 | 14 | test ict - regression testing | 2014-03-24 08:00 | 2014-03-25 17:00 | 2d | Employee G | 1200 | 0 | 0 | 0 | 1200 | 2014-04-08 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1200 | 1200 | C2015-22 Risk Profile Questionnaire.xlsx
24 | 15 | test ict - test coordination | 2014-02-27 08:00 | 2014-02-28 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 1 | Finished | 750 | 750 | C2015-22 Risk Profile Questionnaire.xlsx
25 | 16 | test ict - test execution | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2014-03-24 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 1 | Finished | 600 | 600 | C2015-22 Risk Profile Questionnaire.xlsx
26 | 17 | test ict - test execution | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee I | 600 | 0 | 0 | 0 | 600 | 2014-03-10 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 1 | Finished | 600 | 600 | C2015-22 Risk Profile Questionnaire.xlsx
27 | 18 | test ict - test preparation | 2014-02-24 08:00 | 2014-02-25 14:00 | 1d 5h | Employee G | 975 | 0 | 0 | 0 | 975 | 2014-02-24 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 1 | Finished | 975 | 975 | C2015-22 Risk Profile Questionnaire.xlsx
28 | 19 | test ict - test preparation | 2014-02-24 08:00 | 2014-02-27 12:00 | 3d 4h | Employee I | 2100 | 0 | 0 | 0 | 2100 | 2014-03-03 08:00 | 3d 4h | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 1 | Finished | 2100 | 2100 | C2015-22 Risk Profile Questionnaire.xlsx
29 | 20 | ict test completed | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-28 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-22 Risk Profile Questionnaire.xlsx
30 | 37 | uat | 2014-03-21 17:00 | 2014-04-21 17:00 | 21d |  |  | 0 |  |  | 6450 |  | 26d 7h | [5 empty] | 225 |  | 1 |  | 6450 | 6450 | C2015-22 Risk Profile Questionnaire.xlsx
31 | 21 | uat - test execution support | 2014-03-31 08:00 | 2014-04-01 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 | 2014-03-14 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 750 | 750 | C2015-22 Risk Profile Questionnaire.xlsx
32 | 22 | uat - test execution support | 2014-03-31 08:00 | 2014-04-09 12:00 | 7d 4h | Employee G | 4500 | 0 | 0 | 0 | 4500 | 2014-04-09 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 4500 | 4500 | C2015-22 Risk Profile Questionnaire.xlsx
33 | 23 | uat - test execution support | 2014-03-31 08:00 | 2014-04-01 17:00 | 2d | Employee I | 1200 | 0 | 0 | 0 | 1200 | 2014-04-08 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1200 | 1200 | C2015-22 Risk Profile Questionnaire.xlsx
34 | 24 | full handover | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-22 Risk Profile Questionnaire.xlsx
35 | 25 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-22 Risk Profile Questionnaire.xlsx
36 | 26 | uat completed | 2014-04-21 17:00 | 2014-04-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-22 Risk Profile Questionnaire.xlsx
37 | 38 | implementation | 2014-04-28 17:00 | 2014-05-09 17:00 | 9d |  |  | 0 |  |  | 0 |  | 9d | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-22 Risk Profile Questionnaire.xlsx
38 | 27 | code freeze | 2014-04-28 17:00 | 2014-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-28 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-22 Risk Profile Questionnaire.xlsx
39 | 28 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-22 Risk Profile Questionnaire.xlsx
40 | 39 | post implementation | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h |  |  | 0 |  |  | 2250 |  | 1d 2h | [5 empty] | 2250 |  | 1 |  | 2250 | 1800 | C2015-22 Risk Profile Questionnaire.xlsx
41 | 29 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 | 2014-05-12 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 750 | 600 | C2015-22 Risk Profile Questionnaire.xlsx
42 | 30 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee G | 750 | 0 | 0 | 0 | 750 | 2014-05-12 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 750 | 600 | C2015-22 Risk Profile Questionnaire.xlsx
43 | 31 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee I | 750 | 0 | 0 | 0 | 750 | 2014-05-12 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 750 | 600 | C2015-22 Risk Profile Questionnaire.xlsx
4 | 0 | Investment Product (2) | 2013-11-25 08:00 | 2014-05-13 12:00 | 121d 4h |  |  | 0 |  |  | 46920 |  | 119d 7h | [5 empty] | 32805 |  | 1 |  | 46920 | 46020 | C2015-23 Investment Product (2).xlsx
5 | 48 | supporting tasks | 2014-02-24 08:00 | 2014-03-18 10:00 | 16d 2h |  |  | 0 |  |  | 7095 |  | 35d 4h | [5 empty] | 8130 |  | 1 |  | 7095 | 7095 | C2015-23 Investment Product (2).xlsx
6 | 1 | project management | 2014-02-24 08:00 | 2014-03-03 17:00 | 6d | Employee A | 4320 | 0 | 0 | 0 | 4320 | 2014-02-24 08:00 | 7d 6h | 5580 | 0 | 0 | 0 | 0 | 5580 | 0 | 1 | Finished | 4320 | 4320 | C2015-23 Investment Product (2).xlsx
7 | 2 | validation and support | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 600 | 600 | C2015-23 Investment Product (2).xlsx
8 | 3 | validation and support | 2014-03-17 08:00 | 2014-03-18 10:00 | 1d 2h | Employee C | 750 | 0 | 0 | 0 | 750 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 750 | 750 | C2015-23 Investment Product (2).xlsx
9 | 4 | validation and support | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2014-03-17 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 1 | Finished | 300 | 300 | C2015-23 Investment Product (2).xlsx
10 | 5 | validation and support | 2014-03-17 08:00 | 2014-03-18 09:00 | 1d 1h | Employee F | 675 | 0 | 0 | 0 | 675 | 2014-03-24 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 1 | Finished | 675 | 675 | C2015-23 Investment Product (2).xlsx
11 | 32 | validation and support | 2014-03-17 08:00 | 2014-03-17 15:00 | 6h | Employee D | 450 | 0 | 0 | 0 | 450 | 2014-04-14 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 450 | 450 | C2015-23 Investment Product (2).xlsx
12 | 49 | design | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  |  | 0 |  |  | 1125 |  | 9d 7h | [5 empty] | 525 |  | 1 |  | 1125 | 1125 | C2015-23 Investment Product (2).xlsx
13 | 6 | design - OMS | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 | 2014-03-10 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 1 | Finished | 1125 | 1125 | C2015-23 Investment Product (2).xlsx
14 | 7 | design validated | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-23 Investment Product (2).xlsx
15 | 50 | begunstigingsclausules bank | 2013-11-25 08:00 | 2014-03-21 17:00 | 85d |  |  | 0 |  |  | 8100 |  | 24d 7h | [5 empty] | 4500 |  | 1 |  | 8100 | 8100 | C2015-23 Investment Product (2).xlsx
16 | 8 | analyse | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 2014-02-17 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 600 | 600 | C2015-23 Investment Product (2).xlsx
17 | 9 | design front | 2014-02-18 08:00 | 2014-02-24 16:00 | 4d 7h | Employee F | 2925 | 0 | 0 | 0 | 2925 | 2014-02-17 08:00 | 4d 3h | 2625 | 0 | 0 | 0 | 0 | 2625 | 0 | 1 | Finished | 2925 | 2925 | C2015-23 Investment Product (2).xlsx
18 | 10 | design mapping | 2014-02-18 08:00 | 2014-02-21 15:00 | 3d 6h | Employee C | 2250 | 0 | 0 | 0 | 2250 | 2014-02-18 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 2250 | 2250 | C2015-23 Investment Product (2).xlsx
19 | 25 | design extra velden | 2014-03-03 08:00 | 2014-03-03 14:00 | 5h | Employee C | 375 | 0 | 0 | 0 | 375 | 2014-03-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 375 | 375 | C2015-23 Investment Product (2).xlsx
20 | 26 | uitbreiding extra velden | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 300 | 300 | C2015-23 Investment Product (2).xlsx
21 | 27 | uitbreiding service extra velden | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee I | 150 | 0 | 0 | 0 | 150 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 150 | 150 | C2015-23 Investment Product (2).xlsx
22 | 34 | uitbreiding extra velden | 2014-03-03 08:00 | 2014-03-05 12:00 | 2d 4h | Employee K | 1500 | 0 | 0 | 0 | 1500 | 2014-03-17 08:00 | 1d 3h | 825 | 0 | 0 | 0 | 0 | 825 | 0 | 1 | Finished | 1500 | 1500 | C2015-23 Investment Product (2).xlsx
23 | 28 | uitbreiding rapportering completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-23 Investment Product (2).xlsx
24 | 51 | elektronische handtekening | 2014-02-24 08:00 | 2014-04-30 17:00 | 48d |  |  | 0 |  |  | 10200 |  | 47d 7h | [5 empty] | 7650 |  | 1 |  | 10200 | 10200 | C2015-23 Investment Product (2).xlsx
25 | 11 | build OMS | 2014-02-26 08:00 | 2014-02-27 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 | 2014-02-24 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 1 | Finished | 1050 | 1050 | C2015-23 Investment Product (2).xlsx
26 | 12 | build progress | 2014-02-24 08:00 | 2014-02-25 17:00 | 2d | Employee H | 1200 | 0 | 0 | 0 | 1200 | 2014-02-24 08:00 | 2d 2h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 1 | Finished | 1200 | 1200 | C2015-23 Investment Product (2).xlsx
27 | 13 | ICT test | 2014-04-07 08:00 | 2014-04-09 10:00 | 2d 2h | Employee I | 1350 | 0 | 0 | 0 | 1350 | 2014-04-07 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1350 | 1350 | C2015-23 Investment Product (2).xlsx
28 | 14 | iPad: fixing blocking issues | 2014-03-05 08:00 | 2014-03-11 17:00 | 5d | Employee D | 3000 | 0 | 0 | 0 | 3000 | 2014-03-03 08:00 | 6d 1h | 3675 | 0 | 0 | 0 | 0 | 3675 | 0 | 1 | Finished | 3000 | 3000 | C2015-23 Investment Product (2).xlsx
29 | 15 | iPad: test iPad | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee J | 600 | 0 | 0 | 0 | 600 | 2014-03-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 600 | 600 | C2015-23 Investment Product (2).xlsx
30 | 17 | iPad: test ISP | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d | Employee I | 3000 | 0 | 0 | 0 | 3000 | 2014-03-17 08:00 | 3d 6h | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 1 | Finished | 3000 | 3000 | C2015-23 Investment Product (2).xlsx
31 | 18 | Pod iPad completed | 2014-04-30 17:00 | 2014-04-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-30 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-23 Investment Product (2).xlsx
32 | 52 | development | 2014-03-17 08:00 | 2014-03-28 17:00 | 10d |  |  | 0 |  |  | 8100 |  | 25d 7h | [5 empty] | 750 |  | 1 |  | 8100 | 8100 | C2015-23 Investment Product (2).xlsx
33 | 19 | build personal page | 2014-03-17 08:00 | 2014-03-18 11:00 | 1d 3h | Employee B | 825 | 0 | 0 | 0 | 825 | 2014-03-17 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 1 | Finished | 825 | 825 | C2015-23 Investment Product (2).xlsx
34 | 20 | build OMS | 2014-03-17 08:00 | 2014-03-18 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 | 2014-03-31 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 1 | Finished | 1125 | 1125 | C2015-23 Investment Product (2).xlsx
35 | 21 | development - bugfixing | 2014-03-17 08:00 | 2014-03-26 11:00 | 7d 3h | Employee B | 4425 | 0 | 0 | 0 | 4425 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 4425 | 4425 | C2015-23 Investment Product (2).xlsx
36 | 22 | development - bugfixing | 2014-03-17 08:00 | 2014-03-19 14:00 | 2d 5h | Employee C | 1575 | 0 | 0 | 0 | 1575 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1575 | 1575 | C2015-23 Investment Product (2).xlsx
37 | 33 | development - bugfixing | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee E | 150 | 0 | 0 | 0 | 150 | 2014-04-21 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 1 | Finished | 150 | 150 | C2015-23 Investment Product (2).xlsx
38 | 24 | development completed | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-23 Investment Product (2).xlsx
39 | 53 | test ict | 2013-11-25 08:00 | 2014-04-18 17:00 | 105d |  |  | 0 |  |  | 11400 |  | 104d 7h | [5 empty] | 10350 |  | 1 |  | 11400 | 11400 | C2015-23 Investment Product (2).xlsx
40 | 29 | test ict - test coordination | 2014-02-27 08:00 | 2014-03-03 14:00 | 2d 5h | Employee M | 1575 | 0 | 0 | 0 | 1575 | 2014-02-24 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 1 | Finished | 1575 | 1575 | C2015-23 Investment Product (2).xlsx
41 | 30 | test ict - test execution | 2014-03-31 08:00 | 2014-04-07 11:00 | 5d 3h | Employee N | 3225 | 0 | 0 | 0 | 3225 | 2014-03-24 08:00 | 5d 1h | 3075 | 0 | 0 | 0 | 0 | 3075 | 0 | 1 | Finished | 3225 | 3225 | C2015-23 Investment Product (2).xlsx
42 | 35 | test ict - test execution | 2014-03-31 08:00 | 2014-04-01 16:00 | 1d 7h | Employee O | 1125 | 0 | 0 | 0 | 1125 | 2014-03-31 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 1 | Finished | 1125 | 1125 | C2015-23 Investment Product (2).xlsx
43 | 31 | test ict - test preparation | 2014-03-10 08:00 | 2014-03-13 09:00 | 3d 1h | Employee N | 1875 | 0 | 0 | 0 | 1875 | 2014-03-10 08:00 | 4d 3h | 2625 | 0 | 0 | 0 | 0 | 2625 | 0 | 1 | Finished | 1875 | 1875 | C2015-23 Investment Product (2).xlsx
44 | 36 | test ict - test support | 2014-02-21 08:00 | 2014-02-25 09:00 | 2d 1h | Employee F | 1275 | 0 | 0 | 0 | 1275 | 2014-02-21 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 1275 | 1275 | C2015-23 Investment Product (2).xlsx
45 | 37 | test ict - test uitvoering | 2013-11-25 08:00 | 2013-11-27 17:00 | 3d | Employee O | 1800 | 0 | 0 | 0 | 1800 | 2014-01-27 08:00 | 3d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 1 | Finished | 1800 | 1800 | C2015-23 Investment Product (2).xlsx
46 | 38 | test ict - test uitvoering | 2013-11-25 08:00 | 2013-11-25 16:00 | 7h | Employee P | 525 | 0 | 0 | 0 | 525 | 2013-11-25 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 1 | Finished | 525 | 525 | C2015-23 Investment Product (2).xlsx
47 | 39 | test ict completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-23 Investment Product (2).xlsx
48 | 54 | implementation | 2014-04-07 17:00 | 2014-05-09 17:00 | 24d |  |  | 0 |  |  | 0 |  | 24d | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-23 Investment Product (2).xlsx
49 | 40 | full handover | 2014-04-07 17:00 | 2014-04-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-07 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-23 Investment Product (2).xlsx
50 | 41 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-23 Investment Product (2).xlsx
51 | 55 | post implementation | 2014-05-12 08:00 | 2014-05-13 12:00 | 1d 4h |  |  | 0 |  |  | 900 |  | 1d 4h | [5 empty] | 900 |  | 1 |  | 900 | 0 | C2015-23 Investment Product (2).xlsx
52 | 47 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 12:00 | 1d 4h | Employee G | 900 | 0 | 0 | 0 | 900 | 2014-03-10 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 1 | Finished | 900 | 0 | C2015-23 Investment Product (2).xlsx
4 | 0 | CRM System | 2013-06-20 08:00 | 2014-05-12 17:00 | 233d |  |  | 0 |  |  | 44130 |  | 233d | [5 empty] | 36870 |  | 1 |  | 44130 | 43080 | C2015-24 CRM System.xlsx
5 | 28 | supporting tasks | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h |  |  | 0 |  |  | 17730 |  | 14d 1h | [5 empty] | 10170 |  | 1 |  | 17730 | 17730 | C2015-24 CRM System.xlsx
6 | 1 | project management | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h | Employee I | 17730 | 0 | 0 | 0 | 17730 | 2013-06-20 08:00 | 14d 1h | 10170 | 0 | 0 | 0 | 0 | 10170 | 0 | 1 | Finished | 17730 | 17730 | C2015-24 CRM System.xlsx
7 | 29 | requirements | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h |  |  | 0 |  |  | 675 |  | 1d 1h | [5 empty] | 675 |  | 1 |  | 675 | 675 | C2015-24 CRM System.xlsx
8 | 27 | requirements | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h | Employee J | 675 | 0 | 0 | 0 | 675 | 2013-09-23 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 1 | Finished | 675 | 675 | C2015-24 CRM System.xlsx
9 | 30 | analysis | 2013-06-20 08:00 | 2014-02-21 17:00 | 177d |  |  | 0 |  |  | 4200 |  | 187d 7h | [5 empty] | 7725 |  | 1 |  | 4200 | 4200 | C2015-24 CRM System.xlsx
10 | 2 | analysis - solution concept | 2013-06-20 08:00 | 2013-06-21 12:00 | 1d 4h | Employee B | 900 | 0 | 0 | 0 | 900 | 2013-06-20 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 1 | Finished | 900 | 900 | C2015-24 CRM System.xlsx
11 | 3 | analysis - solution concept | 2013-06-20 08:00 | 2013-06-20 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 | 2013-11-04 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 1 | Finished | 600 | 600 | C2015-24 CRM System.xlsx
12 | 4 | analysis - conceptual design | 2013-09-24 08:00 | 2013-09-30 12:00 | 4d 4h | Employee A | 2700 | 0 | 0 | 0 | 2700 | 2013-09-23 08:00 | 10d 3h | 6225 | 0 | 0 | 0 | 0 | 6225 | 0 | 1 | Finished | 2700 | 2700 | C2015-24 CRM System.xlsx
13 | 11 | analysis validated | 2014-02-21 17:00 | 2014-02-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-10 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-24 CRM System.xlsx
14 | 31 | design | 2014-01-06 08:00 | 2014-03-07 17:00 | 45d |  |  | 0 |  |  | 8925 |  | 56d 7h | [5 empty] | 6900 |  | 1 |  | 8925 | 8925 | C2015-24 CRM System.xlsx
15 | 5 | design - data design | 2014-01-06 08:00 | 2014-01-09 16:00 | 3d 7h | Employee G | 2325 | 0 | 0 | 0 | 2325 | 2014-01-06 08:00 | 4d 2h | 2550 | 0 | 0 | 0 | 0 | 2550 | 0 | 1 | Finished | 2325 | 2325 | C2015-24 CRM System.xlsx
16 | 6 | design - data design | 2014-01-06 08:00 | 2014-01-17 15:00 | 9d 6h | Employee A | 5850 | 0 | 0 | 0 | 5850 | 2014-01-27 08:00 | 6d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 1 | Finished | 5850 | 5850 | C2015-24 CRM System.xlsx
17 | 7 | design - distributiekanaal | 2014-01-07 08:00 | 2014-01-07 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 | 2014-01-06 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 1 | Finished | 450 | 450 | C2015-24 CRM System.xlsx
18 | 8 | design - distributiekanaal | 2014-01-07 08:00 | 2014-01-07 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 2014-01-06 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 300 | 300 | C2015-24 CRM System.xlsx
19 | 9 | design completed | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-24 CRM System.xlsx
20 | 32 | build | 2014-01-20 08:00 | 2014-03-11 16:00 | 36d 7h |  |  | 0 |  |  | 6150 |  | 37d 6h | [5 empty] | 5250 |  | 1 |  | 6150 | 6150 | C2015-24 CRM System.xlsx
21 | 10 | build - distributiekanaal | 2014-01-20 08:00 | 2014-01-21 15:00 | 1d 6h | Employee E | 1050 | 0 | 0 | 0 | 1050 | 2014-01-20 08:00 | 1d 6h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 1 | Finished | 1050 | 1050 | C2015-24 CRM System.xlsx
22 | 12 | build - stored procedures A | 2014-01-30 08:00 | 2014-02-06 11:00 | 5d 3h | Employee F | 3225 | 0 | 0 | 0 | 3225 | 2014-01-27 08:00 | 3d 7h | 2325 | 0 | 0 | 0 | 0 | 2325 | 0 | 1 | Finished | 3225 | 3225 | C2015-24 CRM System.xlsx
23 | 13 | build - stored procedures B | 2014-01-30 08:00 | 2014-01-31 10:00 | 1d 2h | Employee F | 750 | 0 | 0 | 0 | 750 | 2014-02-03 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 750 | 750 | C2015-24 CRM System.xlsx
24 | 14 | build - technical assembly test | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2014-03-10 16:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 1 | Finished | 1125 | 1125 | C2015-24 CRM System.xlsx
25 | 33 | development | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  |  | 0 |  |  | 2550 |  | 26d 7h | [5 empty] | 2850 |  | 1 |  | 2550 | 2550 | C2015-24 CRM System.xlsx
26 | 15 | development - bugfixing | 2014-03-10 08:00 | 2014-03-10 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2014-03-31 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 300 | 300 | C2015-24 CRM System.xlsx
27 | 16 | development - bugfixing | 2014-03-10 08:00 | 2014-03-13 15:00 | 3d 6h | Employee F | 2250 | 0 | 0 | 0 | 2250 | 2014-02-24 08:00 | 3d 4h | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 1 | Finished | 2250 | 2250 | C2015-24 CRM System.xlsx
28 | 17 | development completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-01 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-24 CRM System.xlsx
29 | 34 | UAT | 2013-10-21 08:00 | 2014-04-25 17:00 | 135d |  |  | 0 |  |  | 2700 |  | 134d 7h | [5 empty] | 2100 |  | 1 |  | 2700 | 2700 | C2015-24 CRM System.xlsx
30 | 18 | test ict - distributiekanaal - prep | 2014-02-24 08:00 | 2014-02-24 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 | 2014-03-25 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 1 | Finished | 600 | 600 | C2015-24 CRM System.xlsx
31 | 37 | test ict - distributiekanaal - exec | 2014-02-24 08:00 | 2014-02-26 10:00 | 2d 2h | Employee K | 1350 | 0 | 0 | 0 | 1350 | 2014-03-17 08:00 | 2d 2h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 1 | Finished | 1350 | 1350 | C2015-24 CRM System.xlsx
32 | 19 | ict test completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-24 CRM System.xlsx
33 | 20 | uat - test execution support | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee K | 375 | 0 | 0 | 0 | 375 | 2014-03-31 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 1 | Finished | 375 | 375 | C2015-24 CRM System.xlsx
34 | 38 | uat - test execution support | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee L | 375 | 0 | 0 | 0 | 375 | 2013-10-21 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 375 | 375 | C2015-24 CRM System.xlsx
35 | 21 | full handover ict > uat | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-24 CRM System.xlsx
36 | 22 | uat completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-24 CRM System.xlsx
37 | 23 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-24 CRM System.xlsx
38 | 35 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-24 CRM System.xlsx
39 | 24 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-24 CRM System.xlsx
40 | 36 | post implementation | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d |  |  | 0 |  |  | 1200 |  | 1d | [5 empty] | 1200 |  | 1 |  | 1200 | 150 | C2015-24 CRM System.xlsx
41 | 25 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee A | 600 | 0 | 0 | 0 | 600 | 2014-05-12 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 1 | Finished | 600 | 75 | C2015-24 CRM System.xlsx
42 | 26 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 | 2014-05-12 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 1 | Finished | 600 | 75 | C2015-24 CRM System.xlsx
4 | 0 | Beer Tasting | 2014-04-07 08:00 | 2014-04-22 13:00 | 13d 5h |  |  | 200 |  |  | 1210 |  | 13d 5h | [5 empty] | 1780 |  | 1 |  | 1210 | 1210 | C2015-25 Beer Tasting.xlsx
5 | 21 | briefing | 2014-04-07 08:00 | 2014-04-07 10:00 | 2h |  |  | 0 |  |  | 110 |  | 2h | [5 empty] | 110 |  | 1 |  | 110 | 110 | C2015-25 Beer Tasting.xlsx
6 | 1 | briefing NL | 2014-04-07 08:00 | 2014-04-07 09:00 | 1h | HR;Project Manager | 55 | 0 | 0 | 0 | 55 | 2014-04-07 08:00 | 1h | 55 | 0 | 0 | 0 | 0 | 55 | 0 | 1 | Finished | 55 | 55 | C2015-25 Beer Tasting.xlsx
7 | 2 | briefing FR | 2014-04-07 09:00 | 2014-04-07 10:00 | 1h | HR;Project Manager | 55 | 0 | 0 | 0 | 55 | 2014-04-07 09:00 | 1h | 55 | 0 | 0 | 0 | 0 | 55 | 0 | 1 | Finished | 55 | 55 | C2015-25 Beer Tasting.xlsx
8 | 28 | voorbereiding | 2014-04-07 10:00 | 2014-04-09 20:00 | 2d 10h |  |  | 0 |  |  | 180 |  | 2d 10h | [5 empty] | 480 |  | 1 |  | 180 | 180 | C2015-25 Beer Tasting.xlsx
9 | 3 | telechecks winkelpunt 1 | 2014-04-07 10:00 | 2014-04-07 13:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 2014-04-07 10:00 | 8h | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 1 | Finished | 90 | 90 | C2015-25 Beer Tasting.xlsx
10 | 4 | telechecks winkelpunt 2 | 2014-04-07 20:00 | 2014-04-08 10:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 2014-04-07 20:00 | 8h | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 1 | Finished | 90 | 90 | C2015-25 Beer Tasting.xlsx
11 | 7 | levering degustatiemateriaal A | 2014-04-08 20:00 | 2014-04-08 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-08 20:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-25 Beer Tasting.xlsx
12 | 8 | levering degustatiemateriaal B | 2014-04-09 20:00 | 2014-04-09 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-09 20:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-25 Beer Tasting.xlsx
13 | 29 | degustatie vrijdag | 2014-04-11 09:00 | 2014-04-11 18:00 | 9h |  |  | 50 |  |  | 185 |  | 11h | [5 empty] | 155 |  | 1 |  | 185 | 185 | C2015-25 Beer Tasting.xlsx
14 | 5 | VR aankomst + voorbereiding | 2014-04-11 09:00 | 2014-04-11 10:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-11 09:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 1 | Finished | 15 | 15 | C2015-25 Beer Tasting.xlsx
15 | 19 | VR degustatie | 2014-04-11 10:00 | 2014-04-11 17:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 2014-04-11 15:00 | 5h | 125 | 0 | 0 | 0 | 0 | 125 | 0 | 1 | Finished | 155 | 155 | C2015-25 Beer Tasting.xlsx
16 | 6 | VR opkuis + vertrek | 2014-04-11 17:00 | 2014-04-11 18:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-11 17:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 1 | Finished | 15 | 15 | C2015-25 Beer Tasting.xlsx
17 | 30 | degustatie zaterdag | 2014-04-12 08:00 | 2014-04-12 17:00 | 9h |  |  | 50 |  |  | 185 |  | 9h | [5 empty] | 185 |  | 1 |  | 185 | 185 | C2015-25 Beer Tasting.xlsx
18 | 20 | ZA aankomst + voorbereiding | 2014-04-12 08:00 | 2014-04-12 09:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-12 08:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 1 | Finished | 15 | 15 | C2015-25 Beer Tasting.xlsx
19 | 9 | ZA degustatie | 2014-04-12 09:00 | 2014-04-12 16:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 2014-04-12 09:00 | 7h | 155 | 0 | 0 | 0 | 0 | 155 | 0 | 1 | Finished | 155 | 155 | C2015-25 Beer Tasting.xlsx
20 | 10 | ZA opkuis + vertrek | 2014-04-12 16:00 | 2014-04-12 17:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-12 16:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 1 | Finished | 15 | 15 | C2015-25 Beer Tasting.xlsx
21 | 34 | afsluiting | 2014-04-14 13:00 | 2014-04-15 13:00 | 1d |  |  | 0 |  |  | 0 |  | 1d | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-25 Beer Tasting.xlsx
22 | 11 | ophaling degustatiemateriaal A | 2014-04-14 13:00 | 2014-04-14 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-14 13:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-25 Beer Tasting.xlsx
23 | 12 | ophaling degustatiemateriaal B | 2014-04-15 13:00 | 2014-04-15 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-15 13:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-25 Beer Tasting.xlsx
24 | 31 | voorbereiding | 2014-04-12 20:00 | 2014-04-16 20:00 | 3d |  |  | 0 |  |  | 180 |  | 3d | [5 empty] | 480 |  | 1 |  | 180 | 180 | C2015-25 Beer Tasting.xlsx
25 | 13 | telechecks winkelpunt 3 | 2014-04-12 20:00 | 2014-04-14 10:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 2014-04-12 20:00 | 8h | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 1 | Finished | 90 | 90 | C2015-25 Beer Tasting.xlsx
26 | 14 | telechecks winkelpunt 4 | 2014-04-14 20:00 | 2014-04-15 10:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 2014-04-14 10:00 | 8h | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 1 | Finished | 90 | 90 | C2015-25 Beer Tasting.xlsx
27 | 15 | levering degustatiemateriaal C | 2014-04-15 20:00 | 2014-04-15 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-15 20:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-25 Beer Tasting.xlsx
28 | 16 | levering degustatiemateriaal D | 2014-04-16 20:00 | 2014-04-16 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-16 20:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-25 Beer Tasting.xlsx
29 | 32 | degustatie vrijdag | 2014-04-18 09:00 | 2014-04-18 18:00 | 9h |  |  | 50 |  |  | 185 |  | 11h | [5 empty] | 185 |  | 1 |  | 185 | 185 | C2015-25 Beer Tasting.xlsx
30 | 17 | VR aankomst + voorbereiding | 2014-04-18 09:00 | 2014-04-18 10:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-18 09:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 1 | Finished | 15 | 15 | C2015-25 Beer Tasting.xlsx
31 | 18 | VR degustatie | 2014-04-18 10:00 | 2014-04-18 17:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 2014-04-18 13:00 | 7h | 155 | 0 | 0 | 0 | 0 | 155 | 0 | 1 | Finished | 155 | 155 | C2015-25 Beer Tasting.xlsx
32 | 22 | VR opkuis + vertrek | 2014-04-18 17:00 | 2014-04-18 18:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-18 17:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 1 | Finished | 15 | 15 | C2015-25 Beer Tasting.xlsx
33 | 33 | degustatie zaterdag | 2014-04-19 08:00 | 2014-04-19 17:00 | 9h |  |  | 50 |  |  | 185 |  | 9h | [5 empty] | 185 |  | 1 |  | 185 | 185 | C2015-25 Beer Tasting.xlsx
34 | 23 | ZA aankomst + voorbereiding | 2014-04-19 08:00 | 2014-04-19 09:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-19 08:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 1 | Finished | 15 | 15 | C2015-25 Beer Tasting.xlsx
35 | 24 | ZA degustatie | 2014-04-19 09:00 | 2014-04-19 16:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 2014-04-19 09:00 | 7h | 155 | 0 | 0 | 0 | 0 | 155 | 0 | 1 | Finished | 155 | 155 | C2015-25 Beer Tasting.xlsx
36 | 25 | ZA opkuis + vertrek | 2014-04-19 16:00 | 2014-04-19 17:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-19 16:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 1 | Finished | 15 | 15 | C2015-25 Beer Tasting.xlsx
37 | 35 | afsluiting | 2014-04-21 13:00 | 2014-04-22 13:00 | 1d |  |  | 0 |  |  | 0 |  | 1d | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-25 Beer Tasting.xlsx
38 | 26 | ophaling degustatiemateriaal C | 2014-04-21 13:00 | 2014-04-21 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 13:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-25 Beer Tasting.xlsx
39 | 27 | ophaling degustatiemateriaal D | 2014-04-22 13:00 | 2014-04-22 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-22 13:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-25 Beer Tasting.xlsx
4 | 0 | Debt Collection System | 2013-10-24 08:00 | 2014-05-20 12:00 | 148d 4h |  |  | 0 |  |  | 458112.3684 |  | 153d 4h | [5 empty] | 512546.1461 |  | 1 |  | 458112.3684 | 458112.3684 | C2015-26 Debt Collection System.xlsx
5 | 9 | define | 2013-10-24 08:00 | 2013-12-18 17:00 | 40d |  |  | 0 |  |  | 41864.71 |  | 39d 7h | [5 empty] | 41864.71 |  | 1 |  | 41864.71 | 41864.71 | C2015-26 Debt Collection System.xlsx
6 | 1 | kick-off meeting | 2013-10-24 08:00 | 2013-10-24 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2013-10-24 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 1 | Finished | 558.56 | 558.56 | C2015-26 Debt Collection System.xlsx
7 | 266 | project charter set | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d |  |  | 0 |  |  | 37495.44 |  | 24d | [5 empty] | 37495.44 |  | 1 |  | 37495.44 | 37495.44 | C2015-26 Debt Collection System.xlsx
8 | 2 | project charter (scope definition) | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d | Employee A;Employee B | 36531.84 | 0 | 0 | 0 | 36531.84 | 2013-11-04 08:00 | 24d | 36531.84 | 0 | 0 | 0 | 0 | 36531.84 | 0 | 1 | Finished | 36531.84 | 36531.84 | C2015-26 Debt Collection System.xlsx
9 | 3 | project security risks | 2013-11-13 08:00 | 2013-11-13 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2013-11-13 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 1 | Finished | 963.6 | 963.6 | C2015-26 Debt Collection System.xlsx
10 | 267 | project charter - communication and validation | 2013-11-25 08:00 | 2013-12-18 17:00 | 18d |  |  | 0 |  |  | 3810.71 |  | 17d 7h | [5 empty] | 3810.71 |  | 1 |  | 3810.71 | 3810.71 | C2015-26 Debt Collection System.xlsx
11 | 4 | inform IT governance | 2013-11-25 08:00 | 2013-11-25 09:00 | 1h | Employee B;Employee C | 240.9 | 0 | 0 | 0 | 240.9 | 2013-11-25 08:00 | 1h | 240.9 | 0 | 0 | 0 | 0 | 240.9 | 0 | 1 | Finished | 240.9 | 240.9 | C2015-26 Debt Collection System.xlsx
12 | 5 | send info | 2013-11-28 08:00 | 2013-11-28 17:00 | 1d | Employee B;Employee D | 1927.2 | 0 | 0 | 0 | 1927.2 | 2013-11-28 08:00 | 1d | 1927.2 | 0 | 0 | 0 | 0 | 1927.2 | 0 | 1 | Finished | 1927.2 | 1927.2 | C2015-26 Debt Collection System.xlsx
13 | 6 | send project charter for validation + delivery board validation | 2013-12-13 08:00 | 2013-12-16 09:00 | 1d 1h | Employee B | 1084.05 | 0 | 0 | 0 | 1084.05 | 2013-12-13 08:00 | 1d 1h | 1084.05 | 0 | 0 | 0 | 0 | 1084.05 | 0 | 1 | Finished | 1084.05 | 1084.05 | C2015-26 Debt Collection System.xlsx
14 | 7 | business validation | 2013-12-17 08:00 | 2013-12-17 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2013-12-17 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 1 | Finished | 558.56 | 558.56 | C2015-26 Debt Collection System.xlsx
15 | 8 | end of define | 2013-12-18 17:00 | 2013-12-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-26 Debt Collection System.xlsx
16 | 22 | design | 2013-11-25 08:00 | 2014-02-10 17:00 | 56d |  |  | 0 |  |  | 107215.84 |  | 55d 7h | [5 empty] | 100711.54 |  | 1 |  | 107215.84 | 107215.84 | C2015-26 Debt Collection System.xlsx
17 | 15 | blueprint set | 2013-11-25 08:00 | 2014-01-23 17:00 | 44d |  |  | 0 |  |  | 103826.72 |  | 51d | [5 empty] | 98045.12 |  | 1 |  | 103826.72 | 103826.72 | C2015-26 Debt Collection System.xlsx
18 | 10 | functional analysis List/file creation | 2013-12-02 08:00 | 2014-01-03 17:00 | 25d | Employee G | 15056 | 0 | 0 | 0 | 15056 | 2013-12-02 08:00 | 25d | 15056 | 0 | 0 | 0 | 0 | 15056 | 0 | 1 | Finished | 15056 | 15056 | C2015-26 Debt Collection System.xlsx
19 | 11 | functional analysis Monitoring | 2013-11-25 08:00 | 2014-01-08 17:00 | 33d | Employee H | 19873.92 | 0 | 0 | 0 | 19873.92 | 2013-11-25 08:00 | 33d | 19873.92 | 0 | 0 | -3.638e-12 | 0 | 19873.92 | 0 | 1 | Finished | 19873.92 | 19873.92 | C2015-26 Debt Collection System.xlsx
20 | 12 | functional analysis Interfacing | 2013-11-25 08:00 | 2014-01-03 17:00 | 30d | Employee F;Employee I | 36134.4 | 0 | 0 | 0 | 36134.4 | 2013-11-25 08:00 | 30d | 36134.4 | 0 | 0 | 0 | 0 | 36134.4 | 0 | 1 | Finished | 36134.4 | 36134.4 | C2015-26 Debt Collection System.xlsx
21 | 13 | architecture analysis | 2013-11-25 08:00 | 2013-12-27 17:00 | 25d | Employee E | 24090 | 0 | 0 | 0 | 24090 | 2013-11-25 08:00 | 25d | 24090 | 0 | 0 | 0 | 0 | 24090 | 0 | 1 | Finished | 24090 | 24090 | C2015-26 Debt Collection System.xlsx
22 | 14 | budget &amp; planning for development + master test chapter | 2014-01-13 08:00 | 2014-01-23 17:00 | 9d | Employee B | 8672.4 | 0 | 0 | 0 | 8672.4 | 2014-01-30 08:00 | 3d | 2890.8 | 0 | 0 | 0 | 0 | 2890.8 | 0 | 1 | Finished | 8672.4 | 8672.4 | C2015-26 Debt Collection System.xlsx
23 | 21 | design phase - validations | 2014-01-21 08:00 | 2014-02-10 17:00 | 15d |  |  | 0 |  |  | 3389.12 |  | 14d 7h | [5 empty] | 2666.42 |  | 1 |  | 3389.12 | 3389.12 | C2015-26 Debt Collection System.xlsx
24 | 16 | presentation to Business part 1 | 2014-01-21 08:00 | 2014-01-21 12:00 | 4h | Employee G;Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-01-21 08:00 | 4h | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
25 | 17 | presentation to Business part 2 | 2014-01-31 08:00 | 2014-01-31 12:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-01-31 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 1 | Finished | 301.12 | 301.12 | C2015-26 Debt Collection System.xlsx
26 | 18 | send to delivery board + IT governance validation | 2014-02-07 08:00 | 2014-02-10 17:00 | 2d | Employee B | 1927.2 | 0 | 0 | 0 | 1927.2 | 2014-02-07 08:00 | 1d 2h | 1204.5 | 0 | 0 | 0 | 0 | 1204.5 | 0 | 1 | Finished | 1927.2 | 1927.2 | C2015-26 Debt Collection System.xlsx
27 | 19 | business validation | 2014-02-07 08:00 | 2014-02-07 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2014-02-07 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 1 | Finished | 558.56 | 558.56 | C2015-26 Debt Collection System.xlsx
28 | 20 | end of design | 2014-02-10 17:00 | 2014-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-10 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-26 Debt Collection System.xlsx
29 | 184 | build | 2013-12-27 15:00 | 2014-05-14 17:00 | 98d 2h |  |  | 0 |  |  | 178453.6384 |  | 79d | [5 empty] | 177190.4961 |  | 1 |  | 178453.6384 | 178453.6384 | C2015-26 Debt Collection System.xlsx
30 | 32 | weekly file | 2014-01-02 15:00 | 2014-03-11 17:00 | 48d 2h |  |  | 0 |  |  | 19499.28 |  | 29d | [5 empty] | 18611.852 |  | 1 |  | 19499.28 | 19499.28 | C2015-26 Debt Collection System.xlsx
31 | 23 | build/technical design | 2014-01-02 15:00 | 2014-01-09 15:00 | 5d | Employee G[0.60 #1] | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-01-30 08:00 | 5d 4h | 1987.392 | 0 | 0 | 0 | 0 | 1987.392 | 0 | 1 | Finished | 1806.72 | 1806.72 | C2015-26 Debt Collection System.xlsx
32 | 24 | ABAP | 2014-01-09 15:00 | 2014-01-22 15:00 | 9d | ABAP | 6750 | 0 | 0 | 0 | 6750 | 2014-02-06 08:00 | 9d | 6750 | 0 | 0 | 0 | 0 | 6750 | 0 | 1 | Finished | 6750 | 6750 | C2015-26 Debt Collection System.xlsx
33 | 25 | UT program in general | 2014-01-23 15:00 | 2014-01-27 10:00 | 1d 4h | Employee G | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 903.36 | 903.36 | C2015-26 Debt Collection System.xlsx
34 | 26 | UT submission file | 2014-01-31 15:00 | 2014-02-06 10:00 | 3d 4h | Employee G | 2107.84 | 0 | 0 | 0 | 2107.84 | 2014-02-20 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 1 | Finished | 2107.84 | 2107.84 | C2015-26 Debt Collection System.xlsx
35 | 27 | UT clearing file | 2014-01-27 10:00 | 2014-01-31 10:00 | 4d | Employee H | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-02-20 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 1 | Finished | 2408.96 | 2408.96 | C2015-26 Debt Collection System.xlsx
36 | 28 | UT other treatment file | 2014-01-31 10:00 | 2014-02-06 10:00 | 4d | Employee G | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-02-26 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 1 | Finished | 2408.96 | 2408.96 | C2015-26 Debt Collection System.xlsx
37 | 29 | business UT submission | 2014-03-05 13:00 | 2014-03-10 12:00 | 3d | Employee M | 1908.96 | 0 | 0 | 0 | 1908.96 | 2014-02-25 08:00 | 3h | 238.62 | 0 | 0 | 0 | 0 | 238.62 | 0 | 1 | Finished | 1908.96 | 1908.96 | C2015-26 Debt Collection System.xlsx
38 | 30 | UT sending via e-mail | 2014-03-11 08:00 | 2014-03-11 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-11 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
39 | 31 | build/technical design | 2014-01-22 15:00 | 2014-01-23 15:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
40 | 82 | monthly file | 2013-12-27 15:00 | 2014-02-14 17:00 | 35d 2h |  |  | 0 |  |  | 6713.344 |  | 33d | [5 empty] | 6277.012 |  | 1 |  | 6713.344 | 6713.344 | C2015-26 Debt Collection System.xlsx
41 | 33 | build/technical design | 2013-12-27 15:00 | 2014-01-02 15:00 | 4d | Employee G | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-01-24 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 1 | Finished | 2408.96 | 2408.96 | C2015-26 Debt Collection System.xlsx
42 | 34 | ABAP | 2014-01-30 08:00 | 2014-02-03 12:00 | 2d 4h | ABAP[0.80 #1] | 1500 | 0 | 0 | 0 | 1500 | 2014-01-30 08:00 | 2d 4h | 1500 | 0 | 0 | 2.2352e-05 | 0 | 1500 | 0 | 1 | Finished | 1500 | 1500 | C2015-26 Debt Collection System.xlsx
43 | 35 | UT | 2014-02-03 13:00 | 2014-02-11 17:00 | 6d 4h | Employee G[0.40 #1] | 1565.824 | 0 | 0 | 0 | 1565.824 | 2014-02-03 08:00 | 7d | 1686.272 | 0 | 0 | 2.5127e-05 | 0 | 1686.272 | 0 | 1 | Finished | 1565.824 | 1565.824 | C2015-26 Debt Collection System.xlsx
44 | 36 | business UT | 2014-02-13 08:00 | 2014-02-13 17:00 | 1d | Employee M | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-18 08:00 | 1h | 79.54 | 0 | 0 | 0 | 0 | 79.54 | 0 | 1 | Finished | 636.32 | 636.32 | C2015-26 Debt Collection System.xlsx
45 | 37 | UT sending via e-mail | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-11 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
46 | 83 | authorization check | 2014-01-24 08:00 | 2014-03-24 12:00 | 41d 4h |  |  | 0 |  |  | 15386.2 |  | 38d | [5 empty] | 15386.2 |  | 1 |  | 15386.2 | 15386.2 | C2015-26 Debt Collection System.xlsx
47 | 38 | IRIS-SC | 2014-03-13 08:00 | 2014-03-18 17:00 | 4d | Java | 3000 | 0 | 0 | 0 | 3000 | 2014-03-13 08:00 | 4d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 1 | Finished | 3000 | 3000 | C2015-26 Debt Collection System.xlsx
48 | 39 | build/technical design | 2014-01-24 08:00 | 2014-01-24 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-01-24 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
49 | 40 | ABAP | 2014-01-27 08:00 | 2014-02-10 17:00 | 11d | ABAP | 8250 | 0 | 0 | 0 | 8250 | 2014-01-27 08:00 | 11d | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 1 | Finished | 8250 | 8250 | C2015-26 Debt Collection System.xlsx
50 | 41 | UT | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
51 | 42 | build/technical design | 2014-02-13 08:00 | 2014-02-13 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
52 | 43 | ABAP | 2014-03-19 13:00 | 2014-03-20 12:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-17 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 750 | 750 | C2015-26 Debt Collection System.xlsx
53 | 44 | UT | 2014-03-20 13:00 | 2014-03-21 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
54 | 45 | import WSDL | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | Java | 375 | 0 | 0 | 0 | 375 | 2014-02-13 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 375 | 375 | C2015-26 Debt Collection System.xlsx
55 | 46 | ESB (pass BP to basic) | 2014-03-21 13:00 | 2014-03-24 12:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
56 | 84 | send DMS file via e-mail | 2014-02-05 15:00 | 2014-03-10 17:00 | 23d 2h |  |  | 0 |  |  | 13548.8944 |  | 16d | [5 empty] | 13580.512 |  | 1 |  | 13548.8944 | 13548.8944 | C2015-26 Debt Collection System.xlsx
57 | 47 | build/technical design | 2014-02-17 08:00 | 2014-03-07 10:00 | 14d 2h | Employee I[0.07 #1] | 600.7344 | 0 | 0 | 0 | 600.7344 | 2014-02-17 08:00 | 15d | 632.352 | 0 | 0 | 2.6922e-06 | 0 | 632.352 | 0 | 1 | Finished | 600.7344 | 600.7344 | C2015-26 Debt Collection System.xlsx
58 | 48 | import WSDL | 2014-02-05 15:00 | 2014-02-06 10:00 | 4h | EAI | 301.12 | 0 | 0 | 0 | 301.12 | 2014-02-17 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 1 | Finished | 301.12 | 301.12 | C2015-26 Debt Collection System.xlsx
59 | 49 | build/technical design | 2014-02-07 08:00 | 2014-02-07 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
60 | 50 | EAI | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
61 | 51 | UT | 2014-02-11 08:00 | 2014-02-12 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
62 | 52 | build/technical design | 2014-02-18 08:00 | 2014-02-18 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
63 | 53 | EAI | 2014-02-19 08:00 | 2014-02-19 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
64 | 54 | UT | 2014-02-20 08:00 | 2014-02-20 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-20 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
65 | 55 | design | 2014-02-19 08:00 | 2014-02-20 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
66 | 56 | build | 2014-02-21 08:00 | 2014-02-25 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-21 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 1 | Finished | 1806.72 | 1806.72 | C2015-26 Debt Collection System.xlsx
67 | 57 | queue handling | 2014-02-26 08:00 | 2014-02-28 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-26 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 1 | Finished | 1806.72 | 1806.72 | C2015-26 Debt Collection System.xlsx
68 | 58 | UT | 2014-03-03 08:00 | 2014-03-06 17:00 | 4d | EAI | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-03-03 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 1 | Finished | 2408.96 | 2408.96 | C2015-26 Debt Collection System.xlsx
69 | 59 | deployment | 2014-03-07 08:00 | 2014-03-10 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-07 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
70 | 85 | duplicates | 2014-02-12 13:00 | 2014-03-26 17:00 | 30d 4h |  |  | 0 |  |  | 5261.2 |  | 11d | [5 empty] | 5261.2 |  | 1 |  | 5261.2 | 5261.2 | C2015-26 Debt Collection System.xlsx
71 | 60 | build/technical design | 2014-02-12 13:00 | 2014-02-14 12:00 | 2d | Employee I | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-12 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
72 | 61 | java | 2014-03-19 08:00 | 2014-03-21 17:00 | 3d | Java | 2250 | 0 | 0 | 0 | 2250 | 2014-02-19 08:00 | 3d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 1 | Finished | 2250 | 2250 | C2015-26 Debt Collection System.xlsx
73 | 62 | UT | 2014-03-24 08:00 | 2014-03-26 17:00 | 3d | Employee I | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-24 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 1 | Finished | 1806.72 | 1806.72 | C2015-26 Debt Collection System.xlsx
74 | 86 | current saldo | 2014-02-11 08:00 | 2014-02-20 17:00 | 8d |  |  | 0 |  |  | 3943.04 |  | 7d 4h | [5 empty] | 3386.26 |  | 1 |  | 3943.04 | 3943.04 | C2015-26 Debt Collection System.xlsx
75 | 63 | build/technical design | 2014-02-11 08:00 | 2014-02-12 12:00 | 1d 4h | Employee I | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-11 08:00 | 1d 4h | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 1 | Finished | 903.36 | 903.36 | C2015-26 Debt Collection System.xlsx
76 | 64 | java | 2014-02-14 13:00 | 2014-02-18 12:00 | 2d | Java | 1500 | 0 | 0 | 0 | 1500 | 2014-02-17 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 1 | Finished | 1500 | 1500 | C2015-26 Debt Collection System.xlsx
77 | 65 | UT | 2014-02-18 13:00 | 2014-02-19 17:00 | 1d 4h | Employee I | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-19 08:00 | 1d 4h | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 1 | Finished | 903.36 | 903.36 | C2015-26 Debt Collection System.xlsx
78 | 66 | business UT | 2014-02-20 08:00 | 2014-02-20 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-20 08:00 | 1h | 79.54 | 0 | 0 | 0 | 0 | 79.54 | 0 | 1 | Finished | 636.32 | 636.32 | C2015-26 Debt Collection System.xlsx
79 | 88 | BRM | 2014-03-07 10:00 | 2014-03-17 10:00 | 6d |  |  | 0 |  |  | 3613.44 |  | 6d | [5 empty] | 3613.44 |  | 1 |  | 3613.44 | 3613.44 | C2015-26 Debt Collection System.xlsx
80 | 67 | BRM | 2014-03-07 10:00 | 2014-03-17 10:00 | 6d | Employee I | 3613.44 | 0 | 0 | 0 | 3613.44 | 2014-03-07 10:00 | 6d | 3613.44 | 0 | 0 | 0 | 0 | 3613.44 | 0 | 1 | Finished | 3613.44 | 3613.44 | C2015-26 Debt Collection System.xlsx
81 | 87 | account statement | 2014-01-24 15:00 | 2014-03-31 12:00 | 45d 6h |  |  | 0 |  |  | 15044.8 |  | 41d | [5 empty] | 15044.8 |  | 1 |  | 15044.8 | 15044.8 | C2015-26 Debt Collection System.xlsx
82 | 68 | build/technical design | 2014-01-24 15:00 | 2014-02-07 15:00 | 10d | Employee F[0.50 #1];Employee L[0.50 #1] | 6022.4 | 0 | 0 | 0 | 6022.4 | 2014-02-10 08:00 | 10d | 6022.4 | 0 | 0 | 0 | 0 | 6022.4 | 0 | 1 | Finished | 6022.4 | 6022.4 | C2015-26 Debt Collection System.xlsx
83 | 69 | ABAP | 2014-02-11 08:00 | 2014-02-12 17:00 | 2d | ABAP | 1500 | 0 | 0 | 0 | 1500 | 2014-02-20 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 1 | Finished | 1500 | 1500 | C2015-26 Debt Collection System.xlsx
84 | 70 | UT | 2014-02-13 08:00 | 2014-02-14 17:00 | 2d | Employee F;Employee L | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-04-02 08:00 | 2d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 1 | Finished | 2408.96 | 2408.96 | C2015-26 Debt Collection System.xlsx
85 | 71 | spec proxy | 2014-03-21 13:00 | 2014-03-24 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
86 | 72 | ABAP proxy | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 750 | 750 | C2015-26 Debt Collection System.xlsx
87 | 73 | UT proxy | 2014-02-17 08:00 | 2014-02-17 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-04 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
88 | 74 | spec wrapper core | 2014-03-24 13:00 | 2014-03-26 12:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-20 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
89 | 75 | ABAP wrapper core | 2014-03-26 13:00 | 2014-03-27 12:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 750 | 750 | C2015-26 Debt Collection System.xlsx
90 | 76 | UT wrapper core | 2014-03-27 13:00 | 2014-03-28 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-07 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
91 | 77 | email functionality | 2014-03-28 13:00 | 2014-03-31 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-28 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
92 | 173 | monitoring and reporting | 2014-01-29 08:00 | 2014-03-05 15:00 | 25d 6h |  |  | 0 |  |  | 31228.56 |  | 25d 6h | [5 empty] | 31228.56 |  | 1 |  | 31228.56 | 31228.56 | C2015-26 Debt Collection System.xlsx
93 | 78 | build/technical design | 2014-01-29 08:00 | 2014-02-03 17:00 | 4d | Employee H | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-01-29 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 1 | Finished | 2408.96 | 2408.96 | C2015-26 Debt Collection System.xlsx
94 | 79 | ABAP | 2014-02-06 08:00 | 2014-02-12 17:00 | 5d | ABAP | 3750 | 0 | 0 | 0 | 3750 | 2014-02-06 08:00 | 5d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 1 | Finished | 3750 | 3750 | C2015-26 Debt Collection System.xlsx
95 | 80 | UT | 2014-02-13 08:00 | 2014-02-19 17:00 | 5d | Employee H;ABAP | 6761.2 | 0 | 0 | 0 | 6761.2 | 2014-02-13 08:00 | 5d | 6761.2 | 0 | 0 | 0 | 0 | 6761.2 | 0 | 1 | Finished | 6761.2 | 6761.2 | C2015-26 Debt Collection System.xlsx
96 | 81 | BI reports | 2014-02-06 15:00 | 2014-03-05 15:00 | 19d | Employee K | 18308.4 | 0 | 0 | 0 | 18308.4 | 2014-02-06 15:00 | 19d | 18308.4 | 0 | 0 | 0 | 0 | 18308.4 | 0 | 1 | Finished | 18308.4 | 18308.4 | C2015-26 Debt Collection System.xlsx
97 | 174 | weekly file | 2014-03-21 08:00 | 2014-04-01 15:00 | 7d 6h |  |  | 0 |  |  | 3219.2 |  | 7d 6h | [5 empty] | 3219.2 |  | 1 |  | 3219.2 | 3219.2 | C2015-26 Debt Collection System.xlsx
98 | 89 | build/technical design | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-21 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
99 | 90 | ABAP | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 750 | 750 | C2015-26 Debt Collection System.xlsx
100 | 91 | UT | 2014-03-25 08:00 | 2014-03-25 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-25 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
101 | 92 | build/technical design | 2014-03-28 15:00 | 2014-03-31 10:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-31 15:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 1 | Finished | 301.12 | 301.12 | C2015-26 Debt Collection System.xlsx
102 | 93 | setup autosys | 2014-03-31 15:00 | 2014-04-01 15:00 | 1d | Employee D | 963.6 | 0 | 0 | 0 | 963.6 | 2014-03-31 15:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 1 | Finished | 963.6 | 963.6 | C2015-26 Debt Collection System.xlsx
103 | 175 | monthly file | 2014-03-31 10:00 | 2014-04-01 17:00 | 1d 6h |  |  | 0 |  |  | 1505.62 |  | 1d 6h | [5 empty] | 1264.72 |  | 1 |  | 1505.62 | 1505.62 | C2015-26 Debt Collection System.xlsx
104 | 94 | build/technical design | 2014-03-31 10:00 | 2014-03-31 15:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-31 10:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 1 | Finished | 301.12 | 301.12 | C2015-26 Debt Collection System.xlsx
105 | 95 | setup autosys | 2014-03-31 15:00 | 2014-04-01 17:00 | 1d 2h | Employee D | 1204.5 | 0 | 0 | 0 | 1204.5 | 2014-04-01 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 1 | Finished | 1204.5 | 1204.5 | C2015-26 Debt Collection System.xlsx
106 | 176 | list | 2014-03-26 08:00 | 2014-03-28 15:00 | 2d 6h |  |  | 0 |  |  | 1579.48 |  | 3d | [5 empty] | 1579.48 |  | 1 |  | 1579.48 | 1579.48 | C2015-26 Debt Collection System.xlsx
107 | 96 | build/technical design | 2014-03-26 08:00 | 2014-03-26 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-26 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
108 | 97 | ABAP | 2014-03-27 08:00 | 2014-03-27 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-27 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 375 | 375 | C2015-26 Debt Collection System.xlsx
109 | 98 | UT | 2014-03-27 15:00 | 2014-03-28 15:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-28 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
110 | 177 | migration program | 2014-03-21 08:00 | 2014-04-07 17:00 | 12d |  |  | 0 |  |  | 7522.4 |  | 12d | [5 empty] | 7522.4 |  | 1 |  | 7522.4 | 7522.4 | C2015-26 Debt Collection System.xlsx
111 | 99 | build/technical design | 2014-03-21 08:00 | 2014-04-01 17:00 | 8d | Employee H | 4817.92 | 0 | 0 | 0 | 4817.92 | 2014-03-24 08:00 | 8d | 4817.92 | 0 | 0 | 0 | 0 | 4817.92 | 0 | 1 | Finished | 4817.92 | 4817.92 | C2015-26 Debt Collection System.xlsx
112 | 100 | ABAP | 2014-04-02 08:00 | 2014-04-03 17:00 | 2d | ABAP | 1500 | 0 | 0 | 0 | 1500 | 2014-04-03 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 1 | Finished | 1500 | 1500 | C2015-26 Debt Collection System.xlsx
113 | 101 | UT | 2014-04-04 08:00 | 2014-04-07 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-07 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
114 | 178 | send DMS file via e-mail | 2014-03-14 08:00 | 2014-03-27 15:00 | 9d 6h |  |  | 0 |  |  | 7463.06 |  | 9d 4h | [5 empty] | 7463.06 |  | 1 |  | 7463.06 | 7463.06 | C2015-26 Debt Collection System.xlsx
115 | 102 | WSDL update | 2014-03-14 08:00 | 2014-03-14 10:00 | 2h | Java;Employee I | 338.06 | 0 | 0 | 0 | 338.06 | 2014-04-17 08:00 | 2h | 338.06 | 0 | 0 | 0 | 0 | 338.06 | 0 | 1 | Finished | 338.06 | 338.06 | C2015-26 Debt Collection System.xlsx
116 | 103 | get cert / encrypt | 2014-03-14 10:00 | 2014-03-21 10:00 | 5d | Java | 3750 | 0 | 0 | 0 | 3750 | 2014-04-17 08:00 | 5d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 1 | Finished | 3750 | 3750 | C2015-26 Debt Collection System.xlsx
117 | 104 | error handling | 2014-03-21 10:00 | 2014-03-25 10:00 | 2d | Java | 1500 | 0 | 0 | 0 | 1500 | 2014-04-24 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 1 | Finished | 1500 | 1500 | C2015-26 Debt Collection System.xlsx
118 | 105 | UT java team | 2014-03-25 10:00 | 2014-03-27 15:00 | 2d 4h | Java | 1875 | 0 | 0 | 0 | 1875 | 2014-04-28 08:00 | 2d 4h | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 1 | Finished | 1875 | 1875 | C2015-26 Debt Collection System.xlsx
119 | 179 | feedback | 2014-03-11 15:00 | 2014-04-04 10:00 | 17d 4h |  |  | 0 |  |  | 29314.4 |  | 40d | [5 empty] | 30141.08 |  | 1 |  | 29314.4 | 29314.4 | C2015-26 Debt Collection System.xlsx
120 | 106 | build/technical design | 2014-03-13 08:00 | 2014-03-13 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
121 | 107 | ABAP | 2014-03-14 08:00 | 2014-03-14 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-14 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 750 | 750 | C2015-26 Debt Collection System.xlsx
122 | 108 | UT | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
123 | 109 | build/technical design | 2014-03-11 15:00 | 2014-03-12 10:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-12 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 1 | Finished | 301.12 | 301.12 | C2015-26 Debt Collection System.xlsx
124 | 110 | ABAP | 2014-03-21 15:00 | 2014-03-24 10:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-13 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 375 | 375 | C2015-26 Debt Collection System.xlsx
125 | 111 | UT | 2014-03-24 10:00 | 2014-03-24 12:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 150.56 | 150.56 | C2015-26 Debt Collection System.xlsx
126 | 112 | build/technical design | 2014-03-14 08:00 | 2014-03-14 12:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-14 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 1 | Finished | 301.12 | 301.12 | C2015-26 Debt Collection System.xlsx
127 | 113 | ABAP | 2014-03-14 13:00 | 2014-03-14 17:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-14 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 375 | 375 | C2015-26 Debt Collection System.xlsx
128 | 114 | UT | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-17 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 1 | Finished | 150.56 | 150.56 | C2015-26 Debt Collection System.xlsx
129 | 115 | build/technical design | 2014-03-12 10:00 | 2014-03-13 10:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
130 | 116 | ABAP | 2014-03-13 10:00 | 2014-03-14 10:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-14 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 750 | 750 | C2015-26 Debt Collection System.xlsx
131 | 117 | UT | 2014-03-14 10:00 | 2014-03-17 10:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
132 | 118 | build/technical design | 2014-03-14 13:00 | 2014-03-14 17:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-14 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 1 | Finished | 301.12 | 301.12 | C2015-26 Debt Collection System.xlsx
133 | 119 | ABAP | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-17 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 375 | 375 | C2015-26 Debt Collection System.xlsx
134 | 120 | UT | 2014-03-17 13:00 | 2014-03-17 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-17 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 1 | Finished | 150.56 | 150.56 | C2015-26 Debt Collection System.xlsx
135 | 121 | build/technical design | 2014-03-17 10:00 | 2014-03-17 15:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-18 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 1 | Finished | 301.12 | 301.12 | C2015-26 Debt Collection System.xlsx
136 | 122 | ABAP | 2014-03-17 15:00 | 2014-03-18 10:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-18 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 375 | 375 | C2015-26 Debt Collection System.xlsx
137 | 123 | UT | 2014-03-18 10:00 | 2014-03-18 12:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-19 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 1 | Finished | 150.56 | 150.56 | C2015-26 Debt Collection System.xlsx
138 | 124 | build/technical design | 2014-03-18 08:00 | 2014-03-18 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
139 | 125 | ABAP | 2014-03-19 08:00 | 2014-03-19 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-19 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 750 | 750 | C2015-26 Debt Collection System.xlsx
140 | 126 | UT | 2014-03-20 08:00 | 2014-03-20 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-20 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
141 | 127 | build/technical design | 2014-03-18 13:00 | 2014-03-18 17:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-19 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 1 | Finished | 301.12 | 301.12 | C2015-26 Debt Collection System.xlsx
142 | 128 | ABAP | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-19 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 375 | 375 | C2015-26 Debt Collection System.xlsx
143 | 129 | UT | 2014-03-19 13:00 | 2014-03-19 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 1 | Finished | 150.56 | 150.56 | C2015-26 Debt Collection System.xlsx
144 | 130 | build/technical design | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-19 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 1 | Finished | 301.12 | 301.12 | C2015-26 Debt Collection System.xlsx
145 | 131 | ABAP | 2014-03-19 13:00 | 2014-03-19 17:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-19 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 375 | 375 | C2015-26 Debt Collection System.xlsx
146 | 132 | UT | 2014-03-20 08:00 | 2014-03-20 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 1 | Finished | 150.56 | 150.56 | C2015-26 Debt Collection System.xlsx
147 | 133 | build/technical design | 2014-03-19 15:00 | 2014-03-20 10:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-20 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 1 | Finished | 301.12 | 301.12 | C2015-26 Debt Collection System.xlsx
148 | 134 | ABAP | 2014-03-20 10:00 | 2014-03-20 15:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-21 10:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 375 | 375 | C2015-26 Debt Collection System.xlsx
149 | 135 | UT | 2014-03-20 15:00 | 2014-03-20 17:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-24 15:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 1 | Finished | 150.56 | 150.56 | C2015-26 Debt Collection System.xlsx
150 | 136 | import WSDL | 2014-03-17 10:00 | 2014-03-17 15:00 | 4h | Java | 375 | 0 | 0 | 0 | 375 | 2014-03-17 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 1 | Finished | 375 | 375 | C2015-26 Debt Collection System.xlsx
151 | 137 | spec proxy | 2014-03-14 08:00 | 2014-03-17 17:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-17 08:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
152 | 138 | ABAP proxy | 2014-03-18 08:00 | 2014-03-18 15:00 | 6h | ABAP | 562.5 | 0 | 0 | 0 | 562.5 | 2014-04-21 08:00 | 6h | 562.5 | 0 | 0 | 0 | 0 | 562.5 | 0 | 1 | Finished | 562.5 | 562.5 | C2015-26 Debt Collection System.xlsx
153 | 139 | UT proxy | 2014-03-18 15:00 | 2014-03-20 10:00 | 1d 4h | Employee F[0.50 #1] | 451.68 | 0 | 0 | 0 | 451.68 | 2014-04-21 15:00 | 1d 4h | 451.68 | 0 | 0 | 0 | 0 | 451.68 | 0 | 1 | Finished | 451.68 | 451.68 | C2015-26 Debt Collection System.xlsx
154 | 140 | spec wrapper core | 2014-03-18 08:00 | 2014-03-19 17:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-21 08:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
155 | 141 | ABAP wrapper core | 2014-03-20 08:00 | 2014-03-20 15:00 | 6h | ABAP | 562.5 | 0 | 0 | 0 | 562.5 | 2014-04-23 08:00 | 6h | 562.5 | 0 | 0 | 0 | 0 | 562.5 | 0 | 1 | Finished | 562.5 | 562.5 | C2015-26 Debt Collection System.xlsx
156 | 142 | UT wrapper core | 2014-03-20 15:00 | 2014-03-24 10:00 | 1d 4h | Employee F[0.50 #1] | 451.68 | 0 | 0 | 0 | 451.68 | 2014-04-23 15:00 | 1d 4h | 451.68 | 0 | 0 | 0 | 0 | 451.68 | 0 | 1 | Finished | 451.68 | 451.68 | C2015-26 Debt Collection System.xlsx
157 | 143 | spec proxy | 2014-03-18 08:00 | 2014-03-20 17:00 | 3d | Employee F[0.50 #1] | 903.36 | 0 | 0 | 0 | 903.36 | 2014-04-21 08:00 | 3d | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 1 | Finished | 903.36 | 903.36 | C2015-26 Debt Collection System.xlsx
158 | 144 | ABAP proxy | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-04-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 750 | 750 | C2015-26 Debt Collection System.xlsx
159 | 145 | UT proxy | 2014-03-24 10:00 | 2014-03-26 10:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-25 10:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
160 | 146 | spec wrapper core | 2014-03-21 08:00 | 2014-03-26 17:00 | 4d | Employee F[0.50 #1] | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-24 08:00 | 4d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
161 | 147 | ABAP wrapper core | 2014-03-27 08:00 | 2014-03-28 12:00 | 1d 4h | ABAP | 1125 | 0 | 0 | 0 | 1125 | 2014-04-30 08:00 | 1d 4h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 1 | Finished | 1125 | 1125 | C2015-26 Debt Collection System.xlsx
162 | 148 | UT wrapper core | 2014-03-28 13:00 | 2014-04-03 12:00 | 4d | Employee F[0.50 #1] | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-01 08:00 | 4d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
163 | 149 | content | 2014-03-20 10:00 | 2014-03-20 12:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 1 | Finished | 150.56 | 150.56 | C2015-26 Debt Collection System.xlsx
164 | 150 | UT | 2014-03-20 13:00 | 2014-03-20 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 1 | Finished | 150.56 | 150.56 | C2015-26 Debt Collection System.xlsx
165 | 151 | content | 2014-03-20 15:00 | 2014-03-20 17:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 1 | Finished | 150.56 | 150.56 | C2015-26 Debt Collection System.xlsx
166 | 152 | UT | 2014-03-21 08:00 | 2014-03-21 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-21 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 1 | Finished | 150.56 | 150.56 | C2015-26 Debt Collection System.xlsx
167 | 153 | content | 2014-03-21 10:00 | 2014-03-21 12:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-21 10:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 1 | Finished | 150.56 | 150.56 | C2015-26 Debt Collection System.xlsx
168 | 154 | UT | 2014-03-21 13:00 | 2014-03-21 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-21 13:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 1 | Finished | 150.56 | 150.56 | C2015-26 Debt Collection System.xlsx
169 | 155 | build/technical design | 2014-03-17 10:00 | 2014-03-20 10:00 | 3d | Employee I | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-17 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 1 | Finished | 1806.72 | 1806.72 | C2015-26 Debt Collection System.xlsx
170 | 156 | java | 2014-03-20 10:00 | 2014-03-27 10:00 | 5d | Java | 3750 | 0 | 0 | 0 | 3750 | 2014-03-20 08:00 | 5d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 1 | Finished | 3750 | 3750 | C2015-26 Debt Collection System.xlsx
171 | 157 | UT | 2014-03-27 10:00 | 2014-04-04 10:00 | 6d | Employee F[0.50 #1] | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-27 10:00 | 6d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 1 | Finished | 1806.72 | 1806.72 | C2015-26 Debt Collection System.xlsx
172 | 180 | performance report | 2014-05-05 08:00 | 2014-05-14 17:00 | 8d |  |  | 0 |  |  | 4817.92 |  | 8d | [5 empty] | 4817.92 |  | 1 |  | 4817.92 | 4817.92 | C2015-26 Debt Collection System.xlsx
173 | 158 | build/technical design | 2014-05-05 08:00 | 2014-05-06 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-05 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
174 | 159 | EAI | 2014-05-07 08:00 | 2014-05-09 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-05-07 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 1 | Finished | 1806.72 | 1806.72 | C2015-26 Debt Collection System.xlsx
175 | 160 | UT | 2014-05-12 08:00 | 2014-05-14 17:00 | 3d | Employee H | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-05-12 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 1 | Finished | 1806.72 | 1806.72 | C2015-26 Debt Collection System.xlsx
176 | 181 | preparation IT test strategy | 2014-02-04 08:00 | 2014-02-17 17:00 | 10d |  |  | 0 |  |  | 3011.2 |  | 10d | [5 empty] | 3011.2 |  | 1 |  | 3011.2 | 3011.2 | C2015-26 Debt Collection System.xlsx
177 | 161 | preparation core | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-04 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
178 | 162 | preparation migration | 2014-02-17 08:00 | 2014-02-17 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
179 | 163 | preparation interfacing | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
180 | 164 | preparation reporting | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-04 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
181 | 165 | preparation interfacing | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
182 | 182 | service preparation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d |  |  | 0 |  |  | 2890.8 |  | 1d | [5 empty] | 2890.8 |  | 1 |  | 2890.8 | 2890.8 | C2015-26 Debt Collection System.xlsx
183 | 166 | service manual draft | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-04-30 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 1 | Finished | 963.6 | 963.6 | C2015-26 Debt Collection System.xlsx
184 | 167 | SDM validation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-04-30 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 1 | Finished | 963.6 | 963.6 | C2015-26 Debt Collection System.xlsx
185 | 168 | TCS validation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-04-30 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 1 | Finished | 963.6 | 963.6 | C2015-26 Debt Collection System.xlsx
186 | 183 | build phase - validation | 2014-04-08 08:00 | 2014-04-09 17:00 | 2d |  |  | 0 |  |  | 2890.8 |  | 1d | [5 empty] | 2890.8 |  | 1 |  | 2890.8 | 2890.8 | C2015-26 Debt Collection System.xlsx
187 | 169 | program manager validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-07 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 1 | Finished | 963.6 | 963.6 | C2015-26 Debt Collection System.xlsx
188 | 170 | SCM validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-07 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 1 | Finished | 963.6 | 963.6 | C2015-26 Debt Collection System.xlsx
189 | 171 | information security validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-07 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 1 | Finished | 963.6 | 963.6 | C2015-26 Debt Collection System.xlsx
190 | 172 | end of build | 2014-04-09 17:00 | 2014-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-26 Debt Collection System.xlsx
191 | 260 | implement | 2013-10-25 08:00 | 2014-05-19 17:00 | 147d |  |  | 0 |  |  | 120846.38 |  | 152d | [5 empty] | 183047.6 |  | 1 |  | 120846.38 | 120846.38 | C2015-26 Debt Collection System.xlsx
192 | 250 | certificates | 2014-04-02 10:00 | 2014-05-08 17:00 | 26d 6h |  |  | 0 |  |  | 17344.8 |  | 10d | [5 empty] | 5781.6 |  | 1 |  | 17344.8 | 17344.8 | C2015-26 Debt Collection System.xlsx
193 | 185 | certificates on acceptance | 2014-04-02 10:00 | 2014-04-15 10:00 | 9d | Employee D | 8672.4 | 0 | 0 | 0 | 8672.4 | 2014-04-25 08:00 | 3d | 2890.8 | 0 | 0 | 0 | 0 | 2890.8 | 0 | 1 | Finished | 8672.4 | 8672.4 | C2015-26 Debt Collection System.xlsx
194 | 186 | certificates on production | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d | Employee D | 8672.4 | 0 | 0 | 0 | 8672.4 | 2014-05-06 08:00 | 3d | 2890.8 | 0 | 0 | 0 | 0 | 2890.8 | 0 | 1 | Finished | 8672.4 | 8672.4 | C2015-26 Debt Collection System.xlsx
195 | 251 | integration testing release 1 | 2014-02-06 10:00 | 2014-03-20 17:00 | 30d 6h |  |  | 0 |  |  | 26287.92 |  | 39d | [5 empty] | 26890.16 |  | 1 |  | 26287.92 | 26287.92 | C2015-26 Debt Collection System.xlsx
196 | 187 | backend | 2014-03-03 15:00 | 2014-03-05 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-04 15:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
197 | 188 | backend and extract | 2014-03-05 15:00 | 2014-03-07 15:00 | 2d | Employee H;Employee K | 3131.68 | 0 | 0 | 0 | 3131.68 | 2014-03-06 15:00 | 2d | 3131.68 | 0 | 0 | -4.5475e-13 | 0 | 3131.68 | 0 | 1 | Finished | 3131.68 | 3131.68 | C2015-26 Debt Collection System.xlsx
198 | 189 | performance testing monitoring backend | 2014-03-05 15:00 | 2014-03-07 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-06 15:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
199 | 190 | monitoring BI | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d | Employee K | 4818 | 0 | 0 | 0 | 4818 | 2014-03-12 08:00 | 5d | 4818 | 0 | 0 | 0 | 0 | 4818 | 0 | 1 | Finished | 4818 | 4818 | C2015-26 Debt Collection System.xlsx
200 | 191 | weekly files | 2014-02-06 10:00 | 2014-02-11 17:00 | 3d 6h | Employee G | 2258.4 | 0 | 0 | 0 | 2258.4 | 2014-03-04 08:00 | 3d 6h | 2258.4 | 0 | 0 | 0 | 0 | 2258.4 | 0 | 1 | Finished | 2258.4 | 2258.4 | C2015-26 Debt Collection System.xlsx
201 | 192 | monthly files | 2014-02-21 08:00 | 2014-02-25 12:00 | 2d 4h | Employee G | 1505.6 | 0 | 0 | 0 | 1505.6 | 2014-02-21 08:00 | 2d 4h | 1505.6 | 0 | 0 | 0 | 0 | 1505.6 | 0 | 1 | Finished | 1505.6 | 1505.6 | C2015-26 Debt Collection System.xlsx
202 | 193 | duplicate documents | 2014-03-05 08:00 | 2014-03-06 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-08 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
203 | 194 | current saldo | 2014-03-03 08:00 | 2014-03-04 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-04 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
204 | 195 | account statement | 2014-03-07 08:00 | 2014-03-11 17:00 | 3d | Employee F | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-04-10 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 1 | Finished | 1806.72 | 1806.72 | C2015-26 Debt Collection System.xlsx
205 | 196 | defect core weekly | 2014-02-12 08:00 | 2014-02-14 17:00 | 3d | Employee G | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-10 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 1 | Finished | 1806.72 | 1806.72 | C2015-26 Debt Collection System.xlsx
206 | 197 | defect core monthly | 2014-02-26 08:00 | 2014-02-28 17:00 | 3d | Employee G | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-26 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 1 | Finished | 1806.72 | 1806.72 | C2015-26 Debt Collection System.xlsx
207 | 198 | defect interfacing | 2014-03-12 08:00 | 2014-03-13 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-15 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
208 | 199 | defect monitoring | 2014-03-07 15:00 | 2014-03-11 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-10 15:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
209 | 200 | defect BI reporting | 2014-03-19 08:00 | 2014-03-20 17:00 | 2d | Employee K | 1927.2 | 0 | 0 | 0 | 1927.2 | 2014-03-19 08:00 | 2d | 1927.2 | 0 | 0 | 0 | 0 | 1927.2 | 0 | 1 | Finished | 1927.2 | 1927.2 | C2015-26 Debt Collection System.xlsx
210 | 252 | integration testing release 2 | 2014-04-01 08:00 | 2014-04-23 17:00 | 17d |  |  | 0 |  |  | 15056 |  | 37d | [5 empty] | 15056 |  | 1 |  | 15056 | 15056 | C2015-26 Debt Collection System.xlsx
211 | 201 | feedback | 2014-04-04 08:00 | 2014-04-17 17:00 | 10d | Employee F[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 2014-05-07 08:00 | 10d | 3011.2 | 0 | 0 | 0 | 0 | 3011.2 | 0 | 1 | Finished | 3011.2 | 3011.2 | C2015-26 Debt Collection System.xlsx
212 | 202 | migration | 2014-04-08 08:00 | 2014-04-21 17:00 | 10d | Employee H[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 2014-04-09 08:00 | 10d | 3011.2 | 0 | 0 | 0 | 0 | 3011.2 | 0 | 1 | Finished | 3011.2 | 3011.2 | C2015-26 Debt Collection System.xlsx
213 | 203 | list batch testing | 2014-04-02 08:00 | 2014-04-03 17:00 | 2d | Employee G[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-02 08:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
214 | 204 | core | 2014-04-04 08:00 | 2014-04-17 17:00 | 10d | Employee G[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 2014-04-04 08:00 | 10d | 3011.2 | 0 | 0 | 0 | 0 | 3011.2 | 0 | 1 | Finished | 3011.2 | 3011.2 | C2015-26 Debt Collection System.xlsx
215 | 205 | mail encryption | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee I | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-30 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
216 | 206 | defect core | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee G | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-18 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
217 | 207 | defect interfacing | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-21 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
218 | 208 | defect migration | 2014-04-22 08:00 | 2014-04-23 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-23 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
219 | 209 | defect mail encryption | 2014-04-02 10:00 | 2014-04-04 10:00 | 2d | Employee I | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-01 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
220 | 253 | p2p testing | 2014-04-15 08:00 | 2014-04-22 17:00 | 6d |  |  | 0 |  |  | 6022.4 |  | 14d 4h | [5 empty] | 5721.28 |  | 1 |  | 6022.4 | 6022.4 | C2015-26 Debt Collection System.xlsx
221 | 210 | p2p weekly files | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-22 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
222 | 211 | p2p monthly files | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-05-05 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 1 | Finished | 602.24 | 602.24 | C2015-26 Debt Collection System.xlsx
223 | 212 | p2p current saldo | 2014-04-15 08:00 | 2014-04-15 17:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-15 08:00 | 1d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
224 | 213 | p2p duplicate documents | 2014-04-16 10:00 | 2014-04-17 10:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-16 08:00 | 1d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
225 | 214 | p2p account statement | 2014-04-17 13:00 | 2014-04-18 12:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-17 13:00 | 1d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
226 | 215 | p2p feedback | 2014-04-18 15:00 | 2014-04-21 15:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-18 15:00 | 1d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 1 | Finished | 1204.48 | 1204.48 | C2015-26 Debt Collection System.xlsx
227 | 254 | business acceptance testing release 1 | 2013-10-25 08:00 | 2014-04-04 12:00 | 115d 4h |  |  | 0 |  |  | 45815.04 |  | 115d 4h | [5 empty] | 78585.52 |  | 1 |  | 45815.04 | 45815.04 | C2015-26 Debt Collection System.xlsx
228 | 216 | part 1 - information lists | 2014-02-17 08:00 | 2014-03-28 12:00 | 29d 4h | Employee M | 18771.44 | 0 | 0 | 0 | 18771.44 | 2014-02-17 08:00 | 30d | 19089.6 | 0 | 0 | -3.638e-12 | 0 | 19089.6 | 0 | 1 | Finished | 18771.44 | 18771.44 | C2015-26 Debt Collection System.xlsx
229 | 217 | part 2 - interface | 2013-10-25 08:00 | 2013-10-29 17:00 | 3d | Employee N | 1908.96 | 0 | 0 | 0 | 1908.96 | 2013-10-25 08:00 | 54d | 34361.28 | 0 | 0 | -7.276e-12 | 0 | 34361.28 | 0 | 1 | Finished | 1908.96 | 1908.96 | C2015-26 Debt Collection System.xlsx
230 | 218 | part 3 - reporting | 2014-02-10 08:00 | 2014-04-04 12:00 | 39d 4h | Employee P | 25134.64 | 0 | 0 | 0 | 25134.64 | 2014-02-10 08:00 | 39d 4h | 25134.64 | 0 | 0 | -3.638e-12 | 0 | 25134.64 | 0 | 1 | Finished | 25134.64 | 25134.64 | C2015-26 Debt Collection System.xlsx
231 | 255 | business acceptance testing release 2 | 2014-04-21 08:00 | 2014-04-22 17:00 | 2d |  |  | 0 |  |  | 2545.28 |  | 57d | [5 empty] | 38179.2 |  | 1 |  | 2545.28 | 2545.28 | C2015-26 Debt Collection System.xlsx
232 | 219 | test definition | 2014-04-21 08:00 | 2014-04-21 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-17 08:00 | 19d | 12090.08 | 0 | 0 | -1.819e-12 | 0 | 12090.08 | 0 | 1 | Finished | 636.32 | 636.32 | C2015-26 Debt Collection System.xlsx
233 | 220 | test data | 2014-04-21 08:00 | 2014-04-21 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-17 08:00 | 19d | 12090.08 | 0 | 0 | -1.819e-12 | 0 | 12090.08 | 0 | 1 | Finished | 636.32 | 636.32 | C2015-26 Debt Collection System.xlsx
234 | 221 | test execution | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee N;Employee O | 1272.64 | 0 | 0 | 0 | 1272.64 | 2014-04-22 08:00 | 11d | 13999.04 | 0 | 0 | 0 | 0 | 13999.04 | 0 | 1 | Finished | 1272.64 | 1272.64 | C2015-26 Debt Collection System.xlsx
235 | 256 | service preparation | 2014-03-24 08:00 | 2014-04-23 17:00 | 23d |  |  | 0 |  |  | 3208.46 |  | 1d | [5 empty] | 8267.36 |  | 1 |  | 3208.46 | 3208.46 | C2015-26 Debt Collection System.xlsx
236 | 227 | SLA review | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 | 2014-05-08 08:00 | 1d | 1927.2 | 0 | 0 | 0 | 0 | 1927.2 | 0 | 1 | Finished | 481.8 | 481.8 | C2015-26 Debt Collection System.xlsx
237 | 228 | service budget agreement | 2014-03-24 08:00 | 2014-03-24 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 | 2014-05-08 08:00 | 1d | 1927.2 | 0 | 0 | 0 | 0 | 1927.2 | 0 | 1 | Finished | 481.8 | 481.8 | C2015-26 Debt Collection System.xlsx
238 | 229 | production handbook | 2014-04-23 08:00 | 2014-04-23 17:00 | 1d | Employee D | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-08 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 1 | Finished | 963.6 | 963.6 | C2015-26 Debt Collection System.xlsx
239 | 230 | service manual | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 | 2014-05-08 08:00 | 1d | 1927.2 | 0 | 0 | 0 | 0 | 1927.2 | 0 | 1 | Finished | 481.8 | 481.8 | C2015-26 Debt Collection System.xlsx
240 | 231 | SCM validation | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 2014-05-08 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 1 | Finished | 240.9 | 240.9 | C2015-26 Debt Collection System.xlsx
241 | 232 | CIO validation | 2014-04-23 08:00 | 2014-04-23 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2014-05-08 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 1 | Finished | 558.56 | 558.56 | C2015-26 Debt Collection System.xlsx
242 | 257 | go-no go meeting | 2014-05-14 08:00 | 2014-05-14 17:00 | 1d |  |  | 0 |  |  | 1522.16 |  | 1d | [5 empty] | 1522.16 |  | 1 |  | 1522.16 | 1522.16 | C2015-26 Debt Collection System.xlsx
243 | 233 | formal validation | 2014-05-14 08:00 | 2014-05-14 17:00 | 1d | Employee A;Employee B | 1522.16 | 0 | 0 | 0 | 1522.16 | 2014-05-22 08:00 | 1d | 1522.16 | 0 | 0 | 2.2737e-13 | 0 | 1522.16 | 0 | 1 | Finished | 1522.16 | 1522.16 | C2015-26 Debt Collection System.xlsx
244 | 258 | deploy on production | 2013-10-25 08:00 | 2014-05-16 17:00 | 146d |  |  | 0 |  |  | 1522.16 |  | 1d | [5 empty] | 1522.16 |  | 1 |  | 1522.16 | 1522.16 | C2015-26 Debt Collection System.xlsx
245 | 234 | go live | 2014-05-16 17:00 | 2014-05-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-26 Debt Collection System.xlsx
246 | 235 | PIN testing IT | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-23 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 1 | Finished | 963.6 | 963.6 | C2015-26 Debt Collection System.xlsx
247 | 236 | PIN testing business | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2014-05-23 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 1 | Finished | 558.56 | 558.56 | C2015-26 Debt Collection System.xlsx
248 | 259 | validation | 2014-05-16 17:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 1522.16 |  | 1d 1h | [5 empty] | 1522.16 |  | 1 |  | 1522.16 | 1522.16 | C2015-26 Debt Collection System.xlsx
249 | 237 | steerco validation | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee A;Employee B | 1522.16 | 0 | 0 | 0 | 1522.16 | 2014-05-26 08:00 | 1d | 1522.16 | 0 | 0 | 2.2737e-13 | 0 | 1522.16 | 0 | 1 | Finished | 1522.16 | 1522.16 | C2015-26 Debt Collection System.xlsx
250 | 238 | end of implement | 2014-05-16 17:00 | 2014-05-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-23 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-26 Debt Collection System.xlsx
251 | 265 | close | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h |  |  | 0 |  |  | 9731.8 |  | 1d 4h | [5 empty] | 9731.8 |  | 1 |  | 9731.8 | 9731.8 | C2015-26 Debt Collection System.xlsx
252 | 261 | hand-over preparation | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h |  |  | 0 |  |  | 6841 |  | 1d 4h | [5 empty] | 6841 |  | 1 |  | 6841 | 6841 | C2015-26 Debt Collection System.xlsx
253 | 239 | project charter as built | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h | Employee A;Employee B | 2283.24 | 0 | 0 | 0 | 2283.24 | 2014-05-26 08:00 | 1d 4h | 2283.24 | 0 | 0 | 0 | 0 | 2283.24 | 0 | 1 | Finished | 2283.24 | 2283.24 | C2015-26 Debt Collection System.xlsx
254 | 240 | blueprint as built | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee A;Employee J;Employee M;Employee N | 2751.04 | 0 | 0 | 0 | 2751.04 | 2014-05-26 08:00 | 1d | 2751.04 | 0 | 0 | -4.5475e-13 | 0 | 2751.04 | 0 | 1 | Finished | 2751.04 | 2751.04 | C2015-26 Debt Collection System.xlsx
255 | 241 | technical design as built | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee F;Employee G;Employee H | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-05-26 08:00 | 1d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 1 | Finished | 1806.72 | 1806.72 | C2015-26 Debt Collection System.xlsx
256 | 262 | hand-over | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 1927.2 |  | 1d | [5 empty] | 1927.2 |  | 1 |  | 1927.2 | 1927.2 | C2015-26 Debt Collection System.xlsx
257 | 242 | service manual | 2014-05-19 08:00 | 2014-05-19 12:00 | 4h | Employee B | 481.8 | 0 | 0 | 0 | 481.8 | 2014-05-26 08:00 | 4h | 481.8 | 0 | 0 | 0 | 0 | 481.8 | 0 | 1 | Finished | 481.8 | 481.8 | C2015-26 Debt Collection System.xlsx
258 | 243 | CMDB check | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee C | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-26 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 1 | Finished | 963.6 | 963.6 | C2015-26 Debt Collection System.xlsx
259 | 244 | SCM validation | 2014-05-19 08:00 | 2014-05-19 12:00 | 4h | Employee B | 481.8 | 0 | 0 | 0 | 481.8 | 2014-05-26 08:00 | 4h | 481.8 | 0 | 0 | 0 | 0 | 481.8 | 0 | 1 | Finished | 481.8 | 481.8 | C2015-26 Debt Collection System.xlsx
260 | 263 | project evaluation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h |  |  | 0 |  |  | 722.7 |  | 2h | [5 empty] | 722.7 |  | 1 |  | 722.7 | 722.7 | C2015-26 Debt Collection System.xlsx
261 | 245 | customer satisfaction survey | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 2014-05-26 08:00 | 2h | 240.9 | 0 | 0 | 0 | 0 | 240.9 | 0 | 1 | Finished | 240.9 | 240.9 | C2015-26 Debt Collection System.xlsx
262 | 246 | project team briefing | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 2014-05-26 08:00 | 2h | 240.9 | 0 | 0 | 0 | 0 | 240.9 | 0 | 1 | Finished | 240.9 | 240.9 | C2015-26 Debt Collection System.xlsx
263 | 247 | suppliers evaluation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 2014-05-26 08:00 | 2h | 240.9 | 0 | 0 | 0 | 0 | 240.9 | 0 | 1 | Finished | 240.9 | 240.9 | C2015-26 Debt Collection System.xlsx
264 | 264 | close phase | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 240.9 |  | 7h | [5 empty] | 240.9 |  | 1 |  | 240.9 | 240.9 | C2015-26 Debt Collection System.xlsx
265 | 248 | program manager validation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 2014-05-26 08:00 | 2h | 240.9 | 0 | 0 | 0 | 0 | 240.9 | 0 | 1 | Finished | 240.9 | 240.9 | C2015-26 Debt Collection System.xlsx
266 | 249 | end of project | 2014-05-19 17:00 | 2014-05-19 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-26 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-26 Debt Collection System.xlsx
4 | 0 | Railway Station Antwerp | 2014-01-27 08:00 | 2014-04-30 17:00 | 68d |  |  | 0 |  |  | 22703.5193 |  | 81d | [5 empty] | 25313.1192 |  | 1 |  | 22703.5193 | 22703.5193 | C2015-27 Railway Station Antwerp.xlsx
5 | 3 | zaal Andries | 2014-01-27 08:00 | 2014-03-19 17:00 | 38d |  |  | 0 |  |  | 4958.2398 |  | 34d | [5 empty] | 6263.0398 |  | 1 |  | 4958.2398 | 4958.2398 | C2015-27 Railway Station Antwerp.xlsx
6 | 1 | schilderen traphal zaal Andries | 2014-01-27 08:00 | 2014-02-13 17:00 | 14d | Employee B;Employee C;Employee A | 0 | 0 | 32.62 | 3653.4399 | 3653.4399 | 2014-01-27 08:00 | 23d | 6002.0798 | 0 | 0 | 0 | 0 | 6002.0798 | 0 | 1 | Finished | 3653.4399 | 3653.4399 | C2015-27 Railway Station Antwerp.xlsx
7 | 2 | trapje naar beneden schilderen | 2014-03-13 08:00 | 2014-03-19 17:00 | 5d | Employee B | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-03-13 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 1 | Finished | 1304.8 | 1304.8 | C2015-27 Railway Station Antwerp.xlsx
8 | 10 | aanpassing magazijn B-MO niv. +0 | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 3131.5199 |  | 26d | [5 empty] | 5741.1198 |  | 1 |  | 3131.5199 | 3131.5199 | C2015-27 Railway Station Antwerp.xlsx
9 | 6 | schilderwerken | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 2609.5999 |  | 13d 4h | [5 empty] | 3131.5199 |  | 1 |  | 2609.5999 | 2609.5999 | C2015-27 Railway Station Antwerp.xlsx
10 | 4 | schilderwerken - deel 1 | 2014-02-03 08:00 | 2014-02-07 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-01-30 08:00 | 7d | 1826.7199 | 0 | 0 | 0 | 0 | 1826.7199 | 0 | 1 | Finished | 1304.8 | 1304.8 | C2015-27 Railway Station Antwerp.xlsx
11 | 5 | schilderwerken - deel 2 | 2014-02-10 08:00 | 2014-02-14 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-02-11 13:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 1 | Finished | 1304.8 | 1304.8 | C2015-27 Railway Station Antwerp.xlsx
12 | 9 | overige werken | 2014-02-12 08:00 | 2014-02-14 17:00 | 3d |  |  | 0 |  |  | 521.92 |  | 15d | [5 empty] | 2609.5999 |  | 1 |  | 521.92 | 521.92 | C2015-27 Railway Station Antwerp.xlsx
13 | 7 | plaatsing boiler | 2014-02-12 08:00 | 2014-02-12 17:00 | 1d | Employee E;Employee F | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-02-24 08:00 | 9d | 2348.6399 | 0 | 0 | 0 | 0 | 2348.6399 | 0 | 1 | Finished | 260.96 | 260.96 | C2015-27 Railway Station Antwerp.xlsx
14 | 8 | verplaatsen deurstop | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | Employee G | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-02-14 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 1 | Finished | 260.96 | 260.96 | C2015-27 Railway Station Antwerp.xlsx
15 | 12 | travel center | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d |  |  | 0 |  |  | 2870.5599 |  | 10d | [5 empty] | 2609.5999 |  | 1 |  | 2870.5599 | 2870.5599 | C2015-27 Railway Station Antwerp.xlsx
16 | 11 | travel center - vernieuwen urinoirs | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d | Employee E;Employee F | 0 | 0 | 32.62 | 2870.5599 | 2870.5599 | 2014-03-10 08:00 | 10d | 2609.5999 | 0 | 0 | 0 | 0 | 2609.5999 | 0 | 1 | Finished | 2870.5599 | 2870.5599 | C2015-27 Railway Station Antwerp.xlsx
17 | 14 | herstellingswerken restaurant | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d |  |  | 0 |  |  | 782.88 |  | 3d | [5 empty] | 782.88 |  | 1 |  | 782.88 | 782.88 | C2015-27 Railway Station Antwerp.xlsx
18 | 13 | schilderen radiatoren | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d | Employee B | 0 | 0 | 32.62 | 782.88 | 782.88 | 2014-03-10 08:00 | 3d | 782.88 | 0 | 0 | 0 | 0 | 782.88 | 0 | 1 | Finished | 782.88 | 782.88 | C2015-27 Railway Station Antwerp.xlsx
19 | 16 | portiersloge | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d |  |  | 0 |  |  | 1043.84 |  | 5d | [5 empty] | 1304.8 |  | 1 |  | 1043.84 | 1043.84 | C2015-27 Railway Station Antwerp.xlsx
20 | 15 | schilderwerken portiersloge | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d | Employee D | 0 | 0 | 32.62 | 1043.84 | 1043.84 | 2014-03-11 08:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 1 | Finished | 1043.84 | 1043.84 | C2015-27 Railway Station Antwerp.xlsx
21 | 22 | lok. 211 | 2014-03-17 08:00 | 2014-03-31 17:00 | 11d |  |  | 0 |  |  | 6002.0798 |  | 8d | [5 empty] | 5219.1998 |  | 1 |  | 6002.0798 | 6002.0798 | C2015-27 Railway Station Antwerp.xlsx
22 | 21 | schilderen lok. 211 | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-03-17 08:00 | 7d | 1826.7199 | 0 | 0 | 0 | 0 | 1826.7199 | 0 | 1 | Finished | 1304.8 | 1304.8 | C2015-27 Railway Station Antwerp.xlsx
23 | 19 | herstelling schilderwerk | 2014-03-17 08:00 | 2014-03-26 17:00 | 8d | Employee B | 0 | 0 | 32.62 | 2087.6799 | 2087.6799 | 2014-03-17 08:00 | 8d | 2087.6799 | 0 | 0 | 0 | 0 | 2087.6799 | 0 | 1 | Finished | 2087.6799 | 2087.6799 | C2015-27 Railway Station Antwerp.xlsx
24 | 20 | schilderen automatische deuren | 2014-03-18 08:00 | 2014-03-31 17:00 | 10d | Employee D | 0 | 0 | 32.62 | 2609.5999 | 2609.5999 | 2014-03-18 08:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 1 | Finished | 2609.5999 | 2609.5999 | C2015-27 Railway Station Antwerp.xlsx
25 | 29 | renovatie toiletten VOO +1 | 2014-04-14 08:00 | 2014-04-30 17:00 | 13d |  |  | 0 |  |  | 3914.3999 |  | 10d | [5 empty] | 3392.4799 |  | 1 |  | 3914.3999 | 3914.3999 | C2015-27 Railway Station Antwerp.xlsx
26 | 23 | aanpassing verlichting | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-05-19 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 1 | Finished | 260.96 | 260.96 | C2015-27 Railway Station Antwerp.xlsx
27 | 24 | afbraak bestaande plafonds | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H;Employee I | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-05-06 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 1 | Finished | 260.96 | 260.96 | C2015-27 Railway Station Antwerp.xlsx
28 | 25 | demontage elec uit bestaande plafonds | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee K;Employee J | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-05-06 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 1 | Finished | 260.96 | 260.96 | C2015-27 Railway Station Antwerp.xlsx
29 | 26 | opbouw nieuw vals plafond | 2014-04-15 08:00 | 2014-04-17 17:00 | 3d | Employee I;Employee H | 0 | 0 | 32.62 | 782.88 | 782.88 | 2014-05-07 08:00 | 3d | 782.88 | 0 | 0 | 0 | 0 | 782.88 | 0 | 1 | Finished | 782.88 | 782.88 | C2015-27 Railway Station Antwerp.xlsx
30 | 27 | schilderwerken | 2014-04-22 08:00 | 2014-04-30 17:00 | 7d | Employee B | 0 | 0 | 32.62 | 1826.7199 | 1826.7199 | 2014-05-09 08:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 1 | Finished | 1826.7199 | 1826.7199 | C2015-27 Railway Station Antwerp.xlsx
31 | 28 | herstelling bestaand vals plafond in toiletten | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee I;Employee H | 0 | 0 | 32.62 | 521.92 | 521.92 | 2014-05-13 08:00 | 2d | 521.92 | 0 | 0 | 0 | 0 | 521.92 | 0 | 1 | Finished | 521.92 | 521.92 | C2015-27 Railway Station Antwerp.xlsx
4 | 0 | Website Tennis Vlaanderen | 2013-05-24 08:00 | 2014-02-28 17:00 | 201d |  |  | 0 |  |  | 219275 |  | 212d | [5 empty] | 382475 |  | 1 |  | 219275 | 219275 | C2015-28 Website Tennis Vlaanderen.xlsx
5 | 28 | aanvang | 2013-05-24 13:00 | 2013-07-11 17:00 | 34d 4h |  |  | 0 |  |  | 32100 |  | 108d | [5 empty] | 98250 |  | 1 |  | 32100 | 32100 | C2015-28 Website Tennis Vlaanderen.xlsx
6 | 1 | start implementatie project | 2013-06-11 08:00 | 2013-06-12 12:00 | 1d 4h | developer | 1050 | 0 | 0 | 0 | 1050 | 2013-06-11 08:00 | 1d 4h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 1 | Finished | 1050 | 1050 | C2015-28 Website Tennis Vlaanderen.xlsx
7 | 2 | project management plan inclusief acceptatiecriteria | 2013-05-24 13:00 | 2013-07-11 17:00 | 34d 4h | project manager | 31050 | 0 | 0 | 0 | 31050 | 2013-05-24 13:00 | 108d | 97200 | 0 | 0 | 0 | 0 | 97200 | 0 | 1 | Finished | 31050 | 31050 | C2015-28 Website Tennis Vlaanderen.xlsx
8 | 29 | detaillering | 2013-05-24 08:00 | 2013-09-17 17:00 | 83d |  |  | 0 |  |  | 42800 |  | 137d | [5 empty] | 92400 |  | 1 |  | 42800 | 42800 | C2015-28 Website Tennis Vlaanderen.xlsx
9 | 3 | start functionele analyse/wireframes | 2013-05-24 08:00 | 2013-06-12 17:00 | 14d | senior consultant | 11200 | 0 | 0 | 0 | 11200 | 2013-05-24 08:00 | 14d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 1 | Finished | 11200 | 11200 | C2015-28 Website Tennis Vlaanderen.xlsx
10 | 4 | deliverable wireframes Amplexor | 2013-07-16 08:00 | 2013-08-19 17:00 | 25d | senior consultant | 20000 | 0 | 0 | 0 | 20000 | 2013-07-16 08:00 | 21d | 16800 | 0 | 0 | 0 | 0 | 16800 | 0 | 1 | Finished | 20000 | 20000 | C2015-28 Website Tennis Vlaanderen.xlsx
11 | 5 | functioneel & technisch ontwerp | 2013-08-12 13:00 | 2013-08-30 17:00 | 14d 4h | senior consultant | 11600 | 0 | 0 | 0 | 11600 | 2013-08-12 13:00 | 80d 4h | 64400 | 0 | 0 | 0 | 0 | 64400 | 0 | 1 | Finished | 11600 | 11600 | C2015-28 Website Tennis Vlaanderen.xlsx
12 | 6 | volledige oplevering HIG | 2013-09-17 17:00 | 2013-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-09-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-28 Website Tennis Vlaanderen.xlsx
13 | 35 | bouw | 2013-08-07 08:00 | 2014-02-28 17:00 | 148d |  |  | 0 |  |  | 144375 |  | 159d | [5 empty] | 191825 |  | 1 |  | 144375 | 144375 | C2015-28 Website Tennis Vlaanderen.xlsx
14 | 7 | installatie en algemene opzet | 2013-08-07 08:00 | 2013-08-23 17:00 | 13d | senior developer | 9750 | 0 | 0 | 0 | 9750 | 2013-08-07 08:00 | 13d | 9750 | 0 | 0 | 0 | 0 | 9750 | 0 | 1 | Finished | 9750 | 9750 | C2015-28 Website Tennis Vlaanderen.xlsx
15 | 30 | sprints naar release 1 | 2013-08-29 08:00 | 2013-10-30 17:00 | 45d |  |  | 0 |  |  | 63000 |  | 45d | [5 empty] | 63000 |  | 1 |  | 63000 | 63000 | C2015-28 Website Tennis Vlaanderen.xlsx
16 | 8 | WCM-luik: search, inloggen, infotheek, basisrechten, ... | 2013-08-29 08:00 | 2013-10-30 17:00 | 45d | developer;extra developer | 63000 | 0 | 0 | 0 | 63000 | 2013-08-29 08:00 | 45d | 63000 | 0 | 0 | 0 | 0 | 63000 | 0 | 1 | Finished | 63000 | 63000 | C2015-28 Website Tennis Vlaanderen.xlsx
17 | 31 | transitie (tussentijds) | 2013-10-31 08:00 | 2014-01-17 17:00 | 57d |  |  | 0 |  |  | 8625 |  | 57d | [5 empty] | 8625 |  | 1 |  | 8625 | 8625 | C2015-28 Website Tennis Vlaanderen.xlsx
18 | 9 | deploy 1 naar ACC-omgeving | 2013-10-31 08:00 | 2013-10-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2013-10-31 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 1 | Finished | 700 | 700 | C2015-28 Website Tennis Vlaanderen.xlsx
19 | 10 | deploy 2 naar ACC-omgeving | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2013-11-25 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 1 | Finished | 700 | 700 | C2015-28 Website Tennis Vlaanderen.xlsx
20 | 11 | rework | 2013-12-06 08:00 | 2013-12-12 12:00 | 4d 4h | developer | 3150 | 0 | 0 | 0 | 3150 | 2013-12-06 08:00 | 4d 4h | 3150 | 0 | 0 | 0 | 0 | 3150 | 0 | 1 | Finished | 3150 | 3150 | C2015-28 Website Tennis Vlaanderen.xlsx
21 | 12 | deploy 3 naar ACC-omgeving | 2013-12-17 08:00 | 2013-12-17 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2013-12-17 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 1 | Finished | 700 | 700 | C2015-28 Website Tennis Vlaanderen.xlsx
22 | 13 | acceptatie release 1 - einde testfase | 2014-01-16 17:00 | 2014-01-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-28 Website Tennis Vlaanderen.xlsx
23 | 14 | deploy 4 naar ACC-omgeving | 2014-01-13 08:00 | 2014-01-17 12:00 | 4d 4h | senior developer | 3375 | 0 | 0 | 0 | 3375 | 2014-01-13 08:00 | 4d 4h | 3375 | 0 | 0 | 0 | 0 | 3375 | 0 | 1 | Finished | 3375 | 3375 | C2015-28 Website Tennis Vlaanderen.xlsx
24 | 15 | installatie PROD-server | 2014-01-16 17:00 | 2014-01-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-28 Website Tennis Vlaanderen.xlsx
25 | 16 | start authoring door klant (alleen site) | 2014-01-17 17:00 | 2014-01-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-28 Website Tennis Vlaanderen.xlsx
26 | 32 | vervollediging naar release voor go live | 2014-01-17 08:00 | 2014-01-31 17:00 | 11d |  |  | 0 |  |  | 2150 |  | 12d | [5 empty] | 4400 |  | 1 |  | 2150 | 2150 | C2015-28 Website Tennis Vlaanderen.xlsx
27 | 17 | productie installed, deploy 4 ook naar PROD-omgeving | 2014-01-17 08:00 | 2014-01-17 17:00 | 1d | senior developer | 750 | 0 | 0 | 0 | 750 | 2014-01-16 08:00 | 4d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 1 | Finished | 750 | 750 | C2015-28 Website Tennis Vlaanderen.xlsx
28 | 18 | bugfixing + 'profielbeheer aanmaken' | 2014-01-31 08:00 | 2014-01-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2014-01-06 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 1 | Finished | 700 | 700 | C2015-28 Website Tennis Vlaanderen.xlsx
29 | 19 | deploy 5 naar ACC | 2014-01-31 08:00 | 2014-01-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2014-01-06 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 1 | Finished | 700 | 700 | C2015-28 Website Tennis Vlaanderen.xlsx
30 | 20 | release januari | 2014-01-30 17:00 | 2014-01-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-28 Website Tennis Vlaanderen.xlsx
31 | 33 | sprints naar release after go live | 2013-12-16 08:00 | 2014-02-28 17:00 | 55d |  |  | 0 |  |  | 60850 |  | 65d | [5 empty] | 106050 |  | 1 |  | 60850 | 60850 | C2015-28 Website Tennis Vlaanderen.xlsx
32 | 21 | ontwikkeling release 2 | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d | developer | 18900 | 0 | 0 | 0 | 18900 | 2014-01-22 08:00 | 23d | 16100 | 0 | 0 | 0 | 0 | 16100 | 0 | 1 | Finished | 18900 | 18900 | C2015-28 Website Tennis Vlaanderen.xlsx
33 | 22 | extra deploy (CR1) | 2014-02-27 08:00 | 2014-02-27 17:00 | 1d | senior developer | 750 | 0 | 0 | 0 | 750 | 2014-02-27 08:00 | 6d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 1 | Finished | 750 | 750 | C2015-28 Website Tennis Vlaanderen.xlsx
34 | 23 | release februari | 2014-02-27 17:00 | 2014-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-28 Website Tennis Vlaanderen.xlsx
35 | 24 | testfase | 2013-12-16 08:00 | 2014-01-17 17:00 | 25d | senior developer | 18750 | 0 | 0 | 0 | 18750 | 2013-12-30 08:00 | 51d | 38250 | 0 | 0 | 0 | 0 | 38250 | 0 | 1 | Finished | 18750 | 18750 | C2015-28 Website Tennis Vlaanderen.xlsx
36 | 25 | rework | 2013-12-17 08:00 | 2014-01-24 17:00 | 29d | senior developer | 21750 | 0 | 0 | 0 | 21750 | 2013-12-17 08:00 | 62d | 46500 | 0 | 0 | 0 | 0 | 46500 | 0 | 1 | Finished | 21750 | 21750 | C2015-28 Website Tennis Vlaanderen.xlsx
37 | 26 | deploy 6 naar PROD-omgeving | 2014-02-28 08:00 | 2014-02-28 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2014-03-17 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 1 | Finished | 700 | 700 | C2015-28 Website Tennis Vlaanderen.xlsx
38 | 37 | productie | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2015-28 Website Tennis Vlaanderen.xlsx
39 | 36 | uiterste deadline - officiële voorstelling | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-28 Website Tennis Vlaanderen.xlsx
4 | 0 | Fire Station | 2010-06-01 08:00 | 2011-08-29 10:00 | 284d 2h |  |  | 1576017.5957 |  |  | 1874496.8225 |  | 298d 1h | [5 empty] | 1887087.2528 |  | 1 |  | 1874496.8225 | 1874496.8225 | C2015-29 Fire Station.xlsx
5 | 1 | Opruiming beplanting + massieven (OA) | 2010-06-01 08:00 | 2010-06-01 17:00 | 1d |  | 0 | 204.05 | 0 | 0 | 204.05 | 2010-06-01 08:00 | 1d | 204.05 | 0 | 0 | 0 | 0 | 204.05 | 0 | 1 | Finished | 204.05 | 204.05 | C2015-29 Fire Station.xlsx
6 | 2 | Afgraven teelaarde + bergen (OA) | 2010-06-02 10:00 | 2010-06-07 10:00 | 3d |  | 0 | 2019.0601 | 0 | 0 | 2019.0601 | 2010-06-02 08:00 | 3d 2h | 2019.0601 | 0 | 0 | 25.34 | 0 | 2044.4001 | 0 | 1 | Finished | 2019.0601 | 2019.0601 | C2015-29 Fire Station.xlsx
7 | 3 | Aanleg werfpiste + werkvloer voor paalfundering (OA) | 2010-06-07 10:00 | 2010-06-10 10:00 | 3d |  | 0 | 14045 | 0 | 0 | 14045 | 2010-06-07 10:00 | 3d | 14045 | 0 | 0 | 0 | 0 | 14045 | 0 | 1 | Finished | 14045 | 14045 | C2015-29 Fire Station.xlsx
8 | 4 | Inplanting van de hoofdassen (OA) | 2010-06-10 10:00 | 2010-06-14 10:00 | 2d |  | 0 | 2650 | 0 | 0 | 2650 | 2010-06-10 10:00 | 2d 4h | 2650 | 0 | 0 | 130.9 | 0 | 2780.9 | 0 | 1 | Finished | 2650 | 2650 | C2015-29 Fire Station.xlsx
9 | 5 | Plaatsen werfinrichting | 2010-06-14 10:00 | 2010-06-14 16:00 | 5h |  | 0 | 122707 | 94.48 | 472.4 | 123179.4 | 2010-06-14 15:00 | 5h | 123179.4 | 0 | 0 | 0 | 0 | 123179.4 | 0 | 1 | Finished | 123179.4 | 123179.4 | C2015-29 Fire Station.xlsx
10 | 6 | Funderingspalen + palen torenkraan (OA) | 2010-06-15 13:00 | 2010-06-25 12:00 | 8d |  | 0 | 95929.3672 | 0 | 0 | 95929.3672 | 2010-06-15 11:00 | 8d | 95929.3672 | 0 | 0 | 0 | 0 | 95929.3672 | 0 | 1 | Finished | 95929.3672 | 95929.3672 | C2015-29 Fire Station.xlsx
11 | 7 | Uitgraven funderingsplaat torenkraan | 2010-06-25 13:00 | 2010-06-25 14:00 | 1h |  | 0 | 0 | 35.52 | 35.52 | 35.52 | 2010-06-25 11:00 | 1h | 35.52 | 0 | 0 | 0 | 0 | 35.52 | 0 | 1 | Finished | 35.52 | 35.52 | C2015-29 Fire Station.xlsx
12 | 8 | Afschieten paalkoppen torenkraan | 2010-06-25 13:00 | 2010-06-25 15:00 | 2h |  | 0 | 1 | 29.52 | 59.04 | 60.04 | 2010-06-25 11:00 | 3h | 89.56 | 0 | 0 | 0 | 0 | 89.56 | 0 | 1 | Finished | 60.04 | 60.04 | C2015-29 Fire Station.xlsx
13 | 9 | Plaatsen bekisting funderingsplaat torenkraan | 2010-06-25 13:00 | 2010-06-25 14:00 | 1h |  | 0 | 24 | 115.91 | 115.91 | 139.91 | 2010-06-25 11:00 | 2h | 255.82 | 0 | 0 | 0 | 0 | 255.82 | 0 | 1 | Finished | 139.91 | 139.91 | C2015-29 Fire Station.xlsx
14 | 10 | Plaatsen wapening funderingsplaat torenkraan | 2010-06-25 13:00 | 2010-06-25 14:00 | 1h |  | 0 | 107.25 | 115.91 | 115.91 | 223.16 | 2010-06-25 11:00 | 1h | 223.16 | 0 | 0 | 0 | 0 | 223.16 | 0 | 1 | Finished | 223.16 | 223.16 | C2015-29 Fire Station.xlsx
15 | 11 | Storten funderingsplaat torenkraan | 2010-06-25 13:00 | 2010-06-25 14:00 | 1h |  | 0 | 145.5 | 94.47 | 94.47 | 239.97 | 2010-06-25 11:00 | 1h | 239.97 | 0 | 0 | 0 | 0 | 239.97 | 0 | 1 | Finished | 239.97 | 239.97 | C2015-29 Fire Station.xlsx
16 | 12 | Plaatsen torenkraan (OA) | 2010-06-28 15:00 | 2010-06-29 15:00 | 1d |  | 0 | 6678 | 0 | 0 | 6678 | 2010-06-28 08:00 | 1d | 6678 | 0 | 0 | 0 | 0 | 6678 | 0 | 1 | Finished | 6678 | 6678 | C2015-29 Fire Station.xlsx
17 | 13 | Uitgraven paalkoppen en funderingsbalken + bergen grond | 2010-06-25 13:00 | 2010-08-05 12:00 | 9d |  | 0 | 1049.58 | 59.04 | 4250.8801 | 5300.46 | 2010-06-25 11:00 | 8d 5h | 5123.34 | 0 | 0 | 200.4 | 0 | 5323.74 | 0 | 1 | Finished | 5300.46 | 5300.46 | C2015-29 Fire Station.xlsx
18 | 14 | Afschieten paalkoppen + afvoeren grond | 2010-08-05 13:00 | 2010-08-17 12:00 | 8d |  | 0 | 14921.6797 | 29.52 | 1889.28 | 16810.9597 | 2010-08-09 08:00 | 8d | 16810.9597 | 0 | 0 | 0 | 0 | 16810.9597 | 0 | 1 | Finished | 16810.9597 | 16810.9597 | C2015-29 Fire Station.xlsx
19 | 15 | Plaatsen aardingslus | 2010-08-17 13:00 | 2010-08-17 16:00 | 3h |  | 0 | 371.9 | 29.52 | 88.56 | 460.46 | 2010-08-18 08:00 | 3h | 460.46 | 0 | 0 | 0 | 0 | 460.46 | 0 | 1 | Finished | 460.46 | 460.46 | C2015-29 Fire Station.xlsx
20 | 16 | Uitgraven riolering onderbouw | 2010-08-05 13:00 | 2010-08-09 12:00 | 2d |  | 0 | 96 | 64 | 1024 | 1120 | 2010-08-09 08:00 | 2d | 1120 | 0 | 0 | 0 | 0 | 1120 | 0 | 1 | Finished | 1120 | 1120 | C2015-29 Fire Station.xlsx
21 | 17 | Plaatsen riolering onderbouw | 2010-08-09 13:00 | 2010-08-18 12:00 | 7d |  | 0 | 4228.9102 | 94.47 | 5290.3201 | 9519.2302 | 2010-08-11 08:00 | 7d | 9519.2302 | 0 | 0 | 50 | 0 | 9569.2302 | 0 | 1 | Finished | 9519.2302 | 9519.2302 | C2015-29 Fire Station.xlsx
22 | 18 | Plaatsen verloren bekisting paalkoppen en funderingsbalken | 2010-08-18 13:00 | 2010-09-17 12:00 | 22d |  | 0 | 33319.6016 | 115.91 | 20400.1606 | 53719.7622 | 2010-08-20 08:00 | 24d | 55574.3223 | 0 | 0 | 0 | 0 | 55574.3223 | 0 | 1 | Finished | 53719.7622 | 53719.7622 | C2015-29 Fire Station.xlsx
23 | 19 | Aanvullen fundering + riolering | 2010-09-17 13:00 | 2010-10-14 12:00 | 19d |  | 0 | 7317.3398 | 94.47 | 14359.4402 | 21676.78 | 2010-09-23 08:00 | 19d | 21676.78 | 0 | 0 | 60 | 0 | 21736.78 | 0 | 1 | Finished | 21676.78 | 21676.78 | C2015-29 Fire Station.xlsx
24 | 20 | Plaatsing wapening paalkoppen + funderingsbalken | 2010-09-17 13:00 | 2010-11-05 12:00 | 35d |  | 0 | 24149.7793 | 115.91 | 32454.801 | 56604.5803 | 2010-09-23 08:00 | 35d | 56604.5803 | 0 | 0 | 0 | 0 | 56604.5803 | 0 | 1 | Finished | 56604.5803 | 56604.5803 | C2015-29 Fire Station.xlsx
25 | 21 | Storten paalkoppen + funderingsbalken | 2010-11-05 13:00 | 2010-11-12 12:00 | 5d |  | 0 | 26195.7891 | 94.47 | 3778.8 | 29974.5891 | 2010-11-11 08:00 | 6d | 30730.3491 | 0 | 0 | 0 | 0 | 30730.3491 | 0 | 1 | Finished | 29974.5891 | 29974.5891 | C2015-29 Fire Station.xlsx
26 | 22 | Plaatsen randbekisting vloerplaat | 2010-11-12 13:00 | 2010-11-12 16:00 | 3h |  | 0 | 1121.2 | 115.91 | 347.73 | 1468.93 | 2010-11-22 08:00 | 3h | 1468.93 | 0 | 0 | 0 | 0 | 1468.93 | 0 | 1 | Finished | 1468.93 | 1468.93 | C2015-29 Fire Station.xlsx
27 | 23 | Wapenen vloerplaat | 2010-11-12 16:00 | 2010-12-02 16:00 | 14d |  | 0 | 13088.3604 | 115.91 | 12981.9204 | 26070.2808 | 2010-11-22 11:00 | 14d | 26070.2808 | 0 | 0 | 70.5 | 0 | 26140.7808 | 0 | 1 | Finished | 26070.2808 | 26070.2808 | C2015-29 Fire Station.xlsx
28 | 24 | Storten en verdichten vloerplaat | 2010-12-02 16:00 | 2010-12-06 16:00 | 2d |  | 0 | 14777.1201 | 94.47 | 1511.52 | 16288.6401 | 2010-12-10 13:00 | 2d | 16288.6401 | 0 | 0 | 0 | 0 | 16288.6401 | 0 | 1 | Finished | 16288.6401 | 16288.6401 | C2015-29 Fire Station.xlsx
29 | 25 | Ontkisten vloerplaat | 2010-12-06 16:00 | 2010-12-06 17:00 | 1h |  | 0 | 0 | 94.47 | 94.47 | 94.47 | 2010-12-14 13:00 | 2h | 188.94 | 0 | 0 | 0 | 0 | 188.94 | 0 | 1 | Finished | 94.47 | 94.47 | C2015-29 Fire Station.xlsx
30 | 26 | Plaatsen holle wanden | 2010-12-07 08:00 | 2010-12-07 17:00 | 1d |  | 0 | 16351.4805 | 115.91 | 927.28 | 17278.7605 | 2010-12-14 15:00 | 1d | 17278.7605 | 0 | 0 | 27.49 | 0 | 17306.2505 | 0 | 1 | Finished | 17278.7605 | 17278.7605 | C2015-29 Fire Station.xlsx
31 | 27 | Plaatsen verbindingswapening holle wanden | 2010-12-08 08:00 | 2010-12-08 09:00 | 1h |  | 0 | 232.12 | 115.91 | 115.91 | 348.03 | 2010-12-15 15:00 | 1h | 348.03 | 0 | 0 | 0 | 0 | 348.03 | 0 | 1 | Finished | 348.03 | 348.03 | C2015-29 Fire Station.xlsx
32 | 28 | Plaatsen prefabkolommen | 2010-12-08 09:00 | 2010-12-08 14:00 | 4h |  | 0 | 1592.5 | 115.91 | 463.64 | 2056.14 | 2010-12-15 16:00 | 5h | 2172.05 | 0 | 0 | 0 | 0 | 2172.05 | 0 | 1 | Finished | 2056.14 | 2056.14 | C2015-29 Fire Station.xlsx
33 | 29 | Plaatsen mortelsilo (OA) | 2010-12-08 09:00 | 2010-12-08 11:00 | 2h |  | 0 | 132.5 | 0 | 0 | 132.5 | 2010-12-15 16:00 | 2h | 132.5 | 0 | 0 | 0 | 0 | 132.5 | 0 | 1 | Finished | 132.5 | 132.5 | C2015-29 Fire Station.xlsx
34 | 30 | Storten en trillen holle wanden | 2010-12-08 14:00 | 2010-12-09 14:00 | 1d |  | 0 | 1073.08 | 115.91 | 927.28 | 2000.36 | 2010-12-16 13:00 | 1d | 2000.36 | 0 | 0 | 0 | 0 | 2000.36 | 0 | 1 | Finished | 2000.36 | 2000.36 | C2015-29 Fire Station.xlsx
35 | 31 | Metsen binnenmetselwerk | 2010-12-08 11:00 | 2010-12-08 15:00 | 3h |  | 0 | 3460.05 | 143.72 | 431.16 | 3891.2101 | 2010-12-16 09:00 | 3h | 3891.2101 | 0 | 0 | 0 | 0 | 3891.2101 | 0 | 1 | Finished | 3891.2101 | 3891.2101 | C2015-29 Fire Station.xlsx
36 | 32 | Plaatsen prefabbalken | 2010-12-09 14:00 | 2010-12-15 14:00 | 4d |  | 0 | 4054.27 | 115.91 | 3709.1201 | 7763.3901 | 2010-12-17 13:00 | 4d | 7763.3901 | 0 | 0 | 54.7 | 0 | 7818.0901 | 0 | 1 | Finished | 7763.3901 | 7763.3901 | C2015-29 Fire Station.xlsx
37 | 33 | Plaatsen voorgespannen welfsels | 2010-12-15 14:00 | 2010-12-15 15:00 | 1h |  | 0 | 10923.9297 | 115.91 | 115.91 | 11039.8397 | 2010-12-23 13:00 | 1h | 11039.8397 | 0 | 0 | 0 | 0 | 11039.8397 | 0 | 1 | Finished | 11039.8397 | 11039.8397 | C2015-29 Fire Station.xlsx
38 | 34 | Plaatsen wapening op voorgespannen welfsel | 2010-12-15 15:00 | 2010-12-16 14:00 | 7h |  | 0 | 1090.34 | 115.91 | 811.37 | 1901.71 | 2010-12-23 14:00 | 7h | 1901.71 | 0 | 0 | 0 | 0 | 1901.71 | 0 | 1 | Finished | 1901.71 | 1901.71 | C2015-29 Fire Station.xlsx
39 | 35 | Storten, trillen en afreien druklaag | 2010-12-16 14:00 | 2010-12-17 12:00 | 7h |  | 0 | 995.74 | 115.91 | 811.37 | 1807.11 | 2010-12-24 13:00 | 7h | 1807.11 | 0 | 0 | 0 | 0 | 1807.11 | 0 | 1 | Finished | 1807.11 | 1807.11 | C2015-29 Fire Station.xlsx
40 | 36 | Plaatsen waterdichting ondergrondse holle wanden | 2010-12-09 14:00 | 2010-12-10 10:00 | 5h |  | 0 | 277.77 | 115.91 | 579.55 | 857.32 | 2010-12-17 13:00 | 4h | 741.41 | 0 | 0 | 30 | 0 | 771.41 | 0 | 1 | Finished | 857.32 | 857.32 | C2015-29 Fire Station.xlsx
41 | 37 | Plaatsen stelling voor gevelmetselwerk (0A) | 2010-12-10 10:00 | 2010-12-10 14:00 | 3h |  | 0 | 0 | 40 | 120 | 120 | 2010-12-20 08:00 | 3h | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 1 | Finished | 120 | 120 | C2015-29 Fire Station.xlsx
42 | 38 | Metsen gevelmetselwerk (inclusief plaatsen spouwisolatie) | 2010-12-10 14:00 | 2010-12-15 14:00 | 3d |  | 0 | 10913.1504 | 143.72 | 3449.28 | 14362.4304 | 2010-12-20 11:00 | 3d 1h | 14506.1504 | 0 | 0 | 0 | 0 | 14506.1504 | 0 | 1 | Finished | 14362.4304 | 14362.4304 | C2015-29 Fire Station.xlsx
43 | 39 | Wegnemen stelling | 2010-12-15 14:00 | 2010-12-17 14:00 | 2d |  | 0 | 0 | 40 | 640 | 640 | 2010-12-23 13:00 | 2d | 640 | 0 | 0 | 0 | 0 | 640 | 0 | 1 | Finished | 640 | 640 | C2015-29 Fire Station.xlsx
44 | 40 | Plaatsen schuimbeton (OA) | 2010-12-17 13:00 | 2010-12-21 12:00 | 2d |  | 0 | 7935.6899 | 0 | 0 | 7935.6899 | 2011-01-03 11:00 | 2d 1h | 7935.6899 | 0 | 0 | 115.3 | 0 | 8050.9899 | 0 | 1 | Finished | 7935.6899 | 7935.6899 | C2015-29 Fire Station.xlsx
45 | 41 | Dakopbouw fase 1 (OA) | 2010-12-21 13:00 | 2011-01-03 12:00 | 4d |  | 0 | 15961.3496 | 0 | 0 | 15961.3496 | 2011-01-05 13:00 | 4d | 15961.3496 | 0 | 0 | 0 | 0 | 15961.3496 | 0 | 1 | Finished | 15961.3496 | 15961.3496 | C2015-29 Fire Station.xlsx
46 | 42 | Dakopbouw fase 2 (OA) | 2011-01-03 13:00 | 2011-01-07 12:00 | 4d |  | 0 | 9694.5596 | 0 | 0 | 9694.5596 | 2011-01-11 13:00 | 4d | 9694.5596 | 0 | 0 | 0 | 0 | 9694.5596 | 0 | 1 | Finished | 9694.5596 | 9694.5596 | C2015-29 Fire Station.xlsx
47 | 43 | Plaatsen prefabkolommen (OA) | 2010-12-07 08:00 | 2010-12-15 17:00 | 7d |  | 0 | 23185.1895 | 0 | 0 | 23185.1895 | 2010-12-14 15:00 | 7d | 23185.1895 | 0 | 0 | 105 | 0 | 23290.1895 | 0 | 1 | Finished | 23185.1895 | 23185.1895 | C2015-29 Fire Station.xlsx
48 | 44 | Plaatsen prefab balken (OA) | 2010-12-16 08:00 | 2010-12-20 17:00 | 3d |  | 0 | 5118.7402 | 0 | 0 | 5118.7402 | 2010-12-24 08:00 | 3d | 5118.7402 | 0 | 0 | 0 | 0 | 5118.7402 | 0 | 1 | Finished | 5118.7402 | 5118.7402 | C2015-29 Fire Station.xlsx
49 | 45 | Plaasten I liggers (OA) | 2010-12-21 08:00 | 2011-01-05 17:00 | 7d |  | 0 | 34952 | 0 | 0 | 34952 | 2011-01-05 08:00 | 7d | 34952 | 0 | 0 | 270 | 0 | 35222 | 0 | 1 | Finished | 34952 | 34952 | C2015-29 Fire Station.xlsx
50 | 46 | Plaatsen staalstructuur (OA) | 2011-01-06 08:00 | 2011-01-19 17:00 | 10d |  | 0 | 64952 | 0 | 0 | 64952 | 2011-01-14 08:00 | 10d | 64952 | 0 | 0 | 0 | 0 | 64952 | 0 | 1 | Finished | 64952 | 64952 | C2015-29 Fire Station.xlsx
51 | 47 | Metsen binnenmetselwerk | 2010-12-21 08:00 | 2011-01-04 12:00 | 5d 4h |  | 0 | 4065.6101 | 143.72 | 6323.6801 | 10389.2902 | 2011-01-05 08:00 | 6d | 10964.1702 | 0 | 0 | 0 | 0 | 10964.1702 | 0 | 1 | Finished | 10389.2902 | 10389.2902 | C2015-29 Fire Station.xlsx
52 | 48 | Plaatsen veiligheidsnetten | 2011-01-20 08:00 | 2011-01-20 17:00 | 1d |  | 0 | 1110.78 | 0 | 0 | 1110.78 | 2011-02-03 08:00 | 1d 4h | 1110.78 | 0 | 0 | 35 | 0 | 1145.78 | 0 | 1 | Finished | 1110.78 | 1110.78 | C2015-29 Fire Station.xlsx
53 | 49 | Plaatsen steeldeck (OA) | 2011-01-21 08:00 | 2011-02-03 17:00 | 10d |  | 0 | 20437.0508 | 0 | 0 | 20437.0508 | 2011-02-04 13:00 | 10d 4h | 20437.0508 | 0 | 0 | 0 | 0 | 20437.0508 | 0 | 1 | Finished | 20437.0508 | 20437.0508 | C2015-29 Fire Station.xlsx
54 | 50 | Plaatsen bekisting plinten | 2011-01-21 08:00 | 2011-01-24 16:00 | 1d 7h |  | 0 | 89.78 | 94.47 | 1417.05 | 1506.83 | 2011-02-04 13:00 | 2d | 1601.3 | 0 | 0 | 0 | 0 | 1601.3 | 0 | 1 | Finished | 1506.83 | 1506.83 | C2015-29 Fire Station.xlsx
55 | 51 | Plaatsen wapening plinten | 2011-01-24 16:00 | 2011-01-25 16:00 | 1d |  | 0 | 354.94 | 94.47 | 755.76 | 1110.7 | 2011-02-08 13:00 | 1d | 1110.7 | 0 | 0 | 0 | 0 | 1110.7 | 0 | 1 | Finished | 1110.7 | 1110.7 | C2015-29 Fire Station.xlsx
56 | 52 | Storten en trillen plinten | 2011-01-25 16:00 | 2011-01-25 17:00 | 1h |  | 0 | 454.38 | 94.4 | 94.4 | 548.78 | 2011-02-09 13:00 | 2h | 643.18 | 0 | 0 | 0 | 0 | 643.18 | 0 | 1 | Finished | 548.78 | 548.78 | C2015-29 Fire Station.xlsx
57 | 53 | Ontkisten plinten | 2011-01-26 08:00 | 2011-01-26 17:00 | 1d |  | 0 | 0 | 94.47 | 755.76 | 755.76 | 2011-02-09 15:00 | 1d | 755.76 | 0 | 0 | 0 | 0 | 755.76 | 0 | 1 | Finished | 755.76 | 755.76 | C2015-29 Fire Station.xlsx
58 | 54 | Plaatsen binnendozen (OA) | 2011-02-04 08:00 | 2011-02-10 17:00 | 5d |  | 0 | 22454.1094 | 0 | 0 | 22454.1094 | 2011-02-21 08:00 | 5d | 22454.1094 | 0 | 0 | 0 | 0 | 22454.1094 | 0 | 1 | Finished | 22454.1094 | 22454.1094 | C2015-29 Fire Station.xlsx
59 | 55 | Isoleren loods (OA) | 2011-02-11 08:00 | 2011-02-24 17:00 | 10d |  | 0 | 17305.3008 | 0 | 0 | 17305.3008 | 2011-02-28 08:00 | 10d 2h | 17305.3008 | 0 | 0 | 0 | 0 | 17305.3008 | 0 | 1 | Finished | 17305.3008 | 17305.3008 | C2015-29 Fire Station.xlsx
60 | 56 | Plaatsen beplating (OA) | 2011-02-25 08:00 | 2011-02-25 17:00 | 1d |  | 0 | 36382.5117 | 0 | 0 | 36382.5117 | 2011-03-11 10:00 | 1d 2h | 36382.5117 | 0 | 0 | 0 | 0 | 36382.5117 | 0 | 1 | Finished | 36382.5117 | 36382.5117 | C2015-29 Fire Station.xlsx
61 | 57 | Plaatsen regenwaterafvoersysteem (OA) | 2011-02-04 08:00 | 2011-02-15 17:00 | 8d |  | 0 | 12978.9697 | 0 | 0 | 12978.9697 | 2011-02-21 08:00 | 8d | 12978.9697 | 0 | 0 | 0 | 0 | 12978.9697 | 0 | 1 | Finished | 12978.9697 | 12978.9697 | C2015-29 Fire Station.xlsx
62 | 58 | Dakdichting fase 1 (OA) | 2011-02-28 08:00 | 2011-03-08 17:00 | 7d |  | 0 | 53118.7188 | 0 | 0 | 53118.7188 | 2011-03-14 13:00 | 7d | 53118.7188 | 0 | 0 | 0 | 0 | 53118.7188 | 0 | 1 | Finished | 53118.7188 | 53118.7188 | C2015-29 Fire Station.xlsx
63 | 59 | Dakdichting fase 2 (OA) | 2011-03-09 08:00 | 2011-03-09 17:00 | 1d |  | 0 | 17560.9492 | 0 | 0 | 17560.9492 | 2011-03-23 13:00 | 1d | 17560.9492 | 0 | 0 | 0 | 0 | 17560.9492 | 0 | 1 | Finished | 17560.9492 | 17560.9492 | C2015-29 Fire Station.xlsx
64 | 60 | Plaatsen prefbabkolommen verdiep -1 fase 1 | 2010-12-16 14:00 | 2010-12-17 09:00 | 4h |  | 0 | 8373.9004 | 115.91 | 463.64 | 8837.5404 | 2010-12-24 13:00 | 4h | 8837.5404 | 0 | 0 | 0 | 0 | 8837.5404 | 0 | 1 | Finished | 8837.5404 | 8837.5404 | C2015-29 Fire Station.xlsx
65 | 61 | Plaatsen verloren bekisting ter plaatse gestorte kolommen | 2010-12-16 14:00 | 2010-12-17 09:00 | 4h |  | 0 | 124.74 | 94.47 | 377.88 | 502.62 | 2010-12-24 13:00 | 4h | 502.62 | 0 | 0 | 30.6 | 0 | 533.22 | 0 | 1 | Finished | 502.62 | 502.62 | C2015-29 Fire Station.xlsx
66 | 62 | Plaatsen wapening ter plaatse gestorte kolommen verdiep -1 | 2010-12-17 09:00 | 2010-12-17 10:00 | 1h |  | 0 | 53.58 | 94.47 | 94.47 | 148.05 | 2011-01-03 08:00 | 2h | 242.52 | 0 | 0 | 0 | 0 | 242.52 | 0 | 1 | Finished | 148.05 | 148.05 | C2015-29 Fire Station.xlsx
67 | 63 | Storten en trillen ter plaatse gestorte kolommen verdiep -1 | 2010-12-17 10:00 | 2010-12-17 11:00 | 1h |  | 0 | 53 | 115.91 | 115.91 | 168.91 | 2011-01-03 10:00 | 1h | 168.91 | 0 | 0 | 0 | 0 | 168.91 | 0 | 1 | Finished | 168.91 | 168.91 | C2015-29 Fire Station.xlsx
68 | 64 | Plaatsen prefbabalken verdiep -1 fase 1 | 2010-12-17 09:00 | 2010-12-17 10:00 | 1h |  | 0 | 13089.1104 | 115.91 | 115.91 | 13205.0204 | 2011-01-03 08:00 | 1h | 13205.0204 | 0 | 0 | 0 | 0 | 13205.0204 | 0 | 1 | Finished | 13205.0204 | 13205.0204 | C2015-29 Fire Station.xlsx
69 | 65 | Plaatsen stempels + bekisting ter plaatse gestorte balken verdiep -1 | 2010-12-17 11:00 | 2010-12-17 16:00 | 4h |  | 0 | 1314.04 | 115.91 | 463.64 | 1777.6801 | 2011-01-03 13:00 | 4h | 1777.6801 | 0 | 0 | 137 | 0 | 1914.6801 | 0 | 1 | Finished | 1777.6801 | 1777.6801 | C2015-29 Fire Station.xlsx
70 | 66 | Plaatsen wapening/HEB ter plaatse gestorte balken verdiep -1 | 2010-12-17 16:00 | 2010-12-21 12:00 | 1d 5h |  | 0 | 15156.1602 | 115.91 | 1506.83 | 16662.9902 | 2011-01-04 08:00 | 2d | 17010.7202 | 0 | 0 | 0 | 0 | 17010.7202 | 0 | 1 | Finished | 16662.9902 | 16662.9902 | C2015-29 Fire Station.xlsx
71 | 67 | Storten en trillen ter plaatse gestorte balken verdiep -1 | 2010-12-21 13:00 | 2010-12-21 16:00 | 3h |  | 0 | 1155.04 | 115.91 | 347.73 | 1502.7701 | 2011-01-06 08:00 | 4h | 1618.6801 | 0 | 0 | 0 | 0 | 1618.6801 | 0 | 1 | Finished | 1502.7701 | 1502.7701 | C2015-29 Fire Station.xlsx
72 | 68 | Ontkisten ter plaatse gestorte balken verdiep -1 | 2010-12-21 16:00 | 2010-12-22 09:00 | 2h |  | 0 | 0 | 115.91 | 231.82 | 231.82 | 2011-01-06 13:00 | 2h | 231.82 | 0 | 0 | 0 | 0 | 231.82 | 0 | 1 | Finished | 231.82 | 231.82 | C2015-29 Fire Station.xlsx
73 | 69 | Metsen binnenmetselwerk (niet dragend) verdiep -1 | 2011-01-04 13:00 | 2011-01-05 10:00 | 6h |  | 0 | 15951.5098 | 143.72 | 862.32 | 16813.8298 | 2011-01-13 08:00 | 1d | 17101.2698 | 0 | 0 | 0 | 0 | 17101.2698 | 0 | 1 | Finished | 16813.8298 | 16813.8298 | C2015-29 Fire Station.xlsx
74 | 70 | Plaatsen binnenbekisting wanden verdiep -1 fase 1 | 2010-12-21 13:00 | 2011-01-25 12:00 | 20d |  | 0 | 123.99 | 115.91 | 18545.6006 | 18669.5906 | 2011-01-06 08:00 | 20d | 18669.5906 | 0 | 0 | 0 | 0 | 18669.5906 | 0 | 1 | Finished | 18669.5906 | 18669.5906 | C2015-29 Fire Station.xlsx
75 | 71 | Plaatsen wapening wanden verdiep -1 fase 1 | 2011-01-25 13:00 | 2011-01-27 12:00 | 2d |  | 0 | 1557.91 | 115.91 | 1854.5601 | 3412.4701 | 2011-02-03 08:00 | 2d | 3412.4701 | 0 | 0 | 0 | 0 | 3412.4701 | 0 | 1 | Finished | 3412.4701 | 3412.4701 | C2015-29 Fire Station.xlsx
76 | 72 | Plaatsen buitenbekisting wanden verdiep -1 fase 1 | 2011-01-27 13:00 | 2011-01-31 10:00 | 1d 6h |  | 0 | 123.99 | 115.91 | 1622.7401 | 1746.73 | 2011-02-07 08:00 | 2d | 1978.5501 | 0 | 0 | 0 | 0 | 1978.5501 | 0 | 1 | Finished | 1746.73 | 1746.73 | C2015-29 Fire Station.xlsx
77 | 73 | Storten en trillen wanden verdiep -1 fase 1 | 2011-01-31 10:00 | 2011-02-02 15:00 | 2d 4h |  | 0 | 1761.62 | 115.91 | 2318.2001 | 4079.8201 | 2011-02-09 08:00 | 2d 4h | 4079.8201 | 0 | 0 | 320 | 0 | 4399.8201 | 0 | 1 | Finished | 4079.8201 | 4079.8201 | C2015-29 Fire Station.xlsx
78 | 74 | Ontkisten wanden verdiep -1 fase 1 | 2011-02-02 15:00 | 2011-02-03 11:00 | 5h |  | 0 | 0 | 115.91 | 579.55 | 579.55 | 2011-02-11 13:00 | 4h | 463.64 | 0 | 0 | 0 | 0 | 463.64 | 0 | 1 | Finished | 579.55 | 579.55 | C2015-29 Fire Station.xlsx
79 | 75 | Plaatsen voorgespannen welfsels verdiep -1 fase 1 | 2011-02-03 11:00 | 2011-02-08 14:00 | 3d 2h |  | 0 | 20158.7695 | 115.91 | 3013.6601 | 23172.4296 | 2011-02-14 08:00 | 3d 4h | 23404.2496 | 0 | 0 | 0 | 0 | 23404.2496 | 0 | 1 | Finished | 23172.4296 | 23172.4296 | C2015-29 Fire Station.xlsx
80 | 76 | Plaatsen wapening verdiepingsvloer verdiep -1 fase 1 | 2011-02-08 14:00 | 2011-02-11 14:00 | 3d |  | 0 | 2012.09 | 115.91 | 2781.8401 | 4793.9301 | 2011-02-17 13:00 | 3d | 4793.9301 | 0 | 0 | 0 | 0 | 4793.9301 | 0 | 1 | Finished | 4793.9301 | 4793.9301 | C2015-29 Fire Station.xlsx
81 | 77 | Plaatsen bekisting bordes buitenzijde verdiep -1 | 2011-02-11 14:00 | 2011-02-15 10:00 | 1d 5h |  | 0 | 120.93 | 115.91 | 1506.83 | 1627.76 | 2011-02-22 13:00 | 1d 4h | 1511.85 | 0 | 0 | 200 | 0 | 1711.85 | 0 | 1 | Finished | 1627.76 | 1627.76 | C2015-29 Fire Station.xlsx
82 | 78 | Plaatsen wapening bordes buitenzijde verdiep -1 | 2011-02-15 10:00 | 2011-02-16 16:00 | 1d 5h |  | 0 | 22.68 | 115.91 | 1506.83 | 1529.51 | 2011-02-25 08:00 | 1d 5h | 1529.51 | 0 | 0 | 0 | 0 | 1529.51 | 0 | 1 | Finished | 1529.51 | 1529.51 | C2015-29 Fire Station.xlsx
83 | 79 | Storten en trillen druklaag + bordes verdiep -1 fase 1 | 2011-02-16 16:00 | 2011-02-16 17:00 | 1h |  | 0 | 1859.8101 | 115.91 | 115.91 | 1975.7201 | 2011-02-28 14:00 | 1h | 1975.7201 | 0 | 0 | 0 | 0 | 1975.7201 | 0 | 1 | Finished | 1975.7201 | 1975.7201 | C2015-29 Fire Station.xlsx
84 | 80 | Plaatsen prefbabkolommen verdiep -1 fase 2 | 2011-01-25 13:00 | 2011-01-25 14:00 | 1h |  | 0 | 4204.1699 | 115.91 | 115.91 | 4320.0799 | 2011-02-03 08:00 | 1h | 4320.0799 | 0 | 0 | 0 | 0 | 4320.0799 | 0 | 1 | Finished | 4320.0799 | 4320.0799 | C2015-29 Fire Station.xlsx
85 | 81 | Plaatsen prefbabalken verdiep -1 fase 2 | 2011-01-25 14:00 | 2011-01-26 16:00 | 1d 2h |  | 0 | 7243.8599 | 115.91 | 1159.1 | 8402.9599 | 2011-02-03 09:00 | 1d 3h | 8518.8699 | 0 | 0 | 0 | 0 | 8518.8699 | 0 | 1 | Finished | 8402.9599 | 8402.9599 | C2015-29 Fire Station.xlsx
86 | 82 | Plaatsen binnenbekisting wanden verdiep -1 fase 2 | 2011-02-03 11:00 | 2011-02-03 14:00 | 2h |  | 0 | 920.95 | 115.91 | 231.82 | 1152.77 | 2011-02-14 08:00 | 2h | 1152.77 | 0 | 0 | 0 | 0 | 1152.77 | 0 | 1 | Finished | 1152.77 | 1152.77 | C2015-29 Fire Station.xlsx
87 | 83 | Plaatsen wapening wanden verdiep -1 fase 2 | 2011-02-03 14:00 | 2011-02-03 16:00 | 2h |  | 0 | 617.76 | 115.91 | 231.82 | 849.58 | 2011-02-14 10:00 | 2h | 849.58 | 0 | 0 | 0 | 0 | 849.58 | 0 | 1 | Finished | 849.58 | 849.58 | C2015-29 Fire Station.xlsx
88 | 84 | Plaatsen buitenbekisting wanden verdiep -1 fase 2 | 2011-02-03 16:00 | 2011-02-07 12:00 | 1d 5h |  | 0 | 78.13 | 115.91 | 1506.83 | 1584.96 | 2011-02-14 13:00 | 1d 4h | 1469.05 | 0 | 0 | 0 | 0 | 1469.05 | 0 | 1 | Finished | 1584.96 | 1584.96 | C2015-29 Fire Station.xlsx
89 | 85 | Storten en trillen wanden verdiep -1 fase 2 | 2011-02-07 13:00 | 2011-02-07 17:00 | 4h |  | 0 | 1309.78 | 115.91 | 463.64 | 1773.42 | 2011-02-16 08:00 | 4h | 1773.42 | 0 | 0 | 78.65 | 0 | 1852.07 | 0 | 1 | Finished | 1773.42 | 1773.42 | C2015-29 Fire Station.xlsx
90 | 86 | Ontkisten wanden verdiep -1 fase 2 | 2011-02-08 08:00 | 2011-02-09 17:00 | 2d |  | 0 | 0 | 115.91 | 1854.5601 | 1854.5601 | 2011-02-16 13:00 | 2d | 1854.5601 | 0 | 0 | 0 | 0 | 1854.5601 | 0 | 1 | Finished | 1854.5601 | 1854.5601 | C2015-29 Fire Station.xlsx
91 | 87 | Plaatsen voorgespannen welfsels verdiep -1 fase 2 | 2011-02-17 08:00 | 2011-02-17 15:00 | 6h |  | 0 | 10079.3896 | 115.91 | 695.46 | 10774.8497 | 2011-02-28 15:00 | 6h | 10774.8497 | 0 | 0 | 0 | 0 | 10774.8497 | 0 | 1 | Finished | 10774.8497 | 10774.8497 | C2015-29 Fire Station.xlsx
92 | 88 | Plaatsen wapening verdiepingsvloer verdiep -1 fase 2 | 2011-02-17 15:00 | 2011-02-18 14:00 | 7h |  | 0 | 1006.05 | 115.91 | 811.37 | 1817.42 | 2011-03-01 13:00 | 7h | 1817.42 | 0 | 0 | 0 | 0 | 1817.42 | 0 | 1 | Finished | 1817.42 | 1817.42 | C2015-29 Fire Station.xlsx
93 | 89 | Storten en trillen druklaag verdiep -1 fase 2 | 2011-02-18 14:00 | 2011-02-21 10:00 | 5h |  | 0 | 919.36 | 115.91 | 579.55 | 1498.91 | 2011-03-02 11:00 | 5h | 1498.91 | 0 | 0 | 40.29 | 0 | 1539.2 | 0 | 1 | Finished | 1498.91 | 1498.91 | C2015-29 Fire Station.xlsx
94 | 90 | Plaatsen stempels + bekisting bordessen traphal verdiep -1 | 2011-02-10 08:00 | 2011-02-10 09:00 | 1h |  | 0 | 273.86 | 115.91 | 115.91 | 389.77 | 2011-02-18 13:00 | 1h | 389.77 | 0 | 0 | 0 | 0 | 389.77 | 0 | 1 | Finished | 389.77 | 389.77 | C2015-29 Fire Station.xlsx
95 | 91 | Plaatsen wapening bordessen traphal verdiep -1 | 2011-02-10 09:00 | 2011-02-10 16:00 | 6h |  | 0 | 393.12 | 115.91 | 695.46 | 1088.58 | 2011-02-18 14:00 | 1d | 1320.4 | 0 | 0 | 0 | 0 | 1320.4 | 0 | 1 | Finished | 1088.58 | 1088.58 | C2015-29 Fire Station.xlsx
96 | 92 | Storten en trillen bordessen traphal verdiep -1 | 2011-02-21 10:00 | 2011-02-21 11:00 | 1h |  | 0 | 378.55 | 115.91 | 115.91 | 494.46 | 2011-03-03 08:00 | 1h | 494.46 | 0 | 0 | 0 | 0 | 494.46 | 0 | 1 | Finished | 494.46 | 494.46 | C2015-29 Fire Station.xlsx
97 | 93 | Ontkisten bordessen traphal verdiep -1 | 2011-02-21 11:00 | 2011-02-21 14:00 | 2h |  | 0 | 0 | 115.91 | 231.82 | 231.82 | 2011-03-03 09:00 | 3h | 347.73 | 0 | 0 | 0 | 0 | 347.73 | 0 | 1 | Finished | 231.82 | 231.82 | C2015-29 Fire Station.xlsx
98 | 94 | Plaatsen prefabtrappen verdiep -1 | 2011-02-21 14:00 | 2011-02-21 15:00 | 1h |  | 0 | 1558.25 | 115.91 | 115.91 | 1674.16 | 2011-03-03 13:00 | 1h | 1674.16 | 0 | 0 | 0 | 0 | 1674.16 | 0 | 1 | Finished | 1674.16 | 1674.16 | C2015-29 Fire Station.xlsx
99 | 95 | Plaatsen prefbabkolommen verdiep 0 fase 1 | 2011-02-17 08:00 | 2011-02-17 10:00 | 2h |  | 0 | 446.94 | 115.91 | 231.82 | 678.76 | 2011-02-28 15:00 | 2h | 678.76 | 0 | 0 | 0 | 0 | 678.76 | 0 | 1 | Finished | 678.76 | 678.76 | C2015-29 Fire Station.xlsx
100 | 96 | Plaatsen verloren bekisting ter plaatste gestorte kolommen verdiep 0 | 2011-02-17 08:00 | 2011-02-17 10:00 | 2h |  | 0 | 968.94 | 94.74 | 189.48 | 1158.42 | 2011-02-28 15:00 | 2h | 1158.42 | 0 | 0 | 0 | 0 | 1158.42 | 0 | 1 | Finished | 1158.42 | 1158.42 | C2015-29 Fire Station.xlsx
101 | 97 | Plaatsen wapening ter plaatste gestorte kolommen verdiep 0 | 2011-02-17 10:00 | 2011-02-18 11:00 | 1d 1h |  | 0 | 415.89 | 94.74 | 852.66 | 1268.55 | 2011-03-01 08:00 | 1d 4h | 1552.77 | 0 | 0 | 0 | 0 | 1552.77 | 0 | 1 | Finished | 1268.55 | 1268.55 | C2015-29 Fire Station.xlsx
102 | 98 | Storten en trillen ter plaatste gestorte kolommen verdiep 0 | 2011-02-18 11:00 | 2011-02-18 12:00 | 1h |  | 0 | 411.83 | 115.91 | 115.91 | 527.74 | 2011-03-02 13:00 | 1h | 527.74 | 0 | 0 | 0 | 0 | 527.74 | 0 | 1 | Finished | 527.74 | 527.74 | C2015-29 Fire Station.xlsx
103 | 99 | Plaatsen prefbabalken verdiep 0 fase 1 | 2011-02-18 13:00 | 2011-02-18 15:00 | 2h |  | 0 | 11013.1699 | 115.91 | 231.82 | 11244.9899 | 2011-03-02 14:00 | 2h | 11244.9899 | 0 | 0 | 0 | 0 | 11244.9899 | 0 | 1 | Finished | 11244.9899 | 11244.9899 | C2015-29 Fire Station.xlsx
104 | 100 | Plaatsen stempels + bekisting ter plaatse gestorte balken verdiep 0 | 2011-02-18 15:00 | 2011-02-21 12:00 | 6h |  | 0 | 736.2 | 115.91 | 695.46 | 1431.66 | 2011-03-02 16:00 | 1d | 1663.48 | 0 | 0 | 0 | 0 | 1663.48 | 0 | 1 | Finished | 1431.66 | 1431.66 | C2015-29 Fire Station.xlsx
105 | 101 | Plaatsen wapening/HEB ter plaatse gestorte balken verdiep 0 | 2011-02-21 13:00 | 2011-02-21 14:00 | 1h |  | 0 | 7449.0698 | 115.91 | 115.91 | 7564.9798 | 2011-03-03 13:00 | 1h | 7564.9798 | 0 | 0 | 0 | 0 | 7564.9798 | 0 | 1 | Finished | 7564.9798 | 7564.9798 | C2015-29 Fire Station.xlsx
106 | 102 | Storten en trillen ter plaatse gestorte balken verdiep 0 | 2011-02-21 14:00 | 2011-02-21 15:00 | 1h |  | 0 | 655 | 115.91 | 115.91 | 770.91 | 2011-03-03 14:00 | 2h | 886.82 | 0 | 0 | 0 | 0 | 886.82 | 0 | 1 | Finished | 770.91 | 770.91 | C2015-29 Fire Station.xlsx
107 | 103 | Ontkisten ter plaatse gestorte balken verdiep 0 | 2011-02-21 15:00 | 2011-02-22 09:00 | 3h |  | 0 | 0 | 115.91 | 347.73 | 347.73 | 2011-03-03 16:00 | 3h | 347.73 | 0 | 0 | 0 | 0 | 347.73 | 0 | 1 | Finished | 347.73 | 347.73 | C2015-29 Fire Station.xlsx
108 | 104 | Metsen binnenmetselwerk (niet dragend) verdiep 0 | 2011-02-18 13:00 | 2011-02-25 14:00 | 5d 1h |  | 0 | 4294.8501 | 115.91 | 4752.3102 | 9047.1602 | 2011-03-02 14:00 | 5d 3h | 9278.9803 | 0 | 0 | 0 | 0 | 9278.9803 | 0 | 1 | Finished | 9047.1602 | 9047.1602 | C2015-29 Fire Station.xlsx
109 | 105 | Plaatsen binnenbekisting wanden verdiep 0 fase 1 | 2011-02-21 14:00 | 2011-02-24 09:00 | 2d 4h |  | 0 | 130.48 | 115.91 | 2318.2001 | 2448.6801 | 2011-03-03 14:00 | 2d 3h | 2332.7701 | 0 | 0 | 0 | 0 | 2332.7701 | 0 | 1 | Finished | 2448.6801 | 2448.6801 | C2015-29 Fire Station.xlsx
110 | 106 | Plaatsen wapening wanden verdiep 0 fase 1 | 2011-02-24 09:00 | 2011-02-25 15:00 | 1d 5h |  | 0 | 1639.64 | 115.91 | 1506.83 | 3146.4701 | 2011-03-08 08:00 | 1d 5h | 3146.4701 | 0 | 0 | 0 | 0 | 3146.4701 | 0 | 1 | Finished | 3146.4701 | 3146.4701 | C2015-29 Fire Station.xlsx
111 | 107 | Plaatsen buitenbekisting wanden verdiep 0 fase 1 | 2011-02-25 15:00 | 2011-03-02 11:00 | 2d 5h |  | 0 | 130.48 | 115.91 | 2434.1101 | 2564.5901 | 2011-03-09 14:00 | 2d 3h | 2332.7701 | 0 | 0 | 0 | 0 | 2332.7701 | 0 | 1 | Finished | 2564.5901 | 2564.5901 | C2015-29 Fire Station.xlsx
112 | 108 | Storten en trillen wanden verdiep 0 fase 1 | 2011-03-02 11:00 | 2011-03-02 17:00 | 5h |  | 0 | 1639.64 | 115.91 | 579.55 | 2219.19 | 2011-03-14 08:00 | 5h | 2219.19 | 0 | 0 | 67.8 | 0 | 2286.99 | 0 | 1 | Finished | 2219.19 | 2219.19 | C2015-29 Fire Station.xlsx
113 | 109 | Ontkisten wanden verdiep 0 fase 1 | 2011-03-03 08:00 | 2011-03-08 11:00 | 3d 3h |  | 0 | 130.48 | 115.91 | 3129.5701 | 3260.0501 | 2011-03-14 14:00 | 3d 3h | 3260.0501 | 0 | 0 | 0 | 0 | 3260.0501 | 0 | 1 | Finished | 3260.0501 | 3260.0501 | C2015-29 Fire Station.xlsx
114 | 110 | Plaatsen voorgespannen welfsels verdiep 0 fase 1 | 2011-03-07 11:00 | 2011-03-08 11:00 | 1d |  | 0 | 1842.92 | 115.91 | 927.28 | 2770.2001 | 2011-03-17 08:00 | 1d | 2770.2001 | 0 | 0 | 0 | 0 | 2770.2001 | 0 | 1 | Finished | 2770.2001 | 2770.2001 | C2015-29 Fire Station.xlsx
115 | 111 | Plaatsen wapening verdiepingsvloer verdiep 0 fase 1 | 2011-03-08 11:00 | 2011-03-09 11:00 | 1d |  | 0 | 0 | 115.91 | 927.28 | 927.28 | 2011-03-18 08:00 | 1d | 927.28 | 0 | 0 | 0 | 0 | 927.28 | 0 | 1 | Finished | 927.28 | 927.28 | C2015-29 Fire Station.xlsx
116 | 112 | Storten en trillen druklaag verdiep 0 fase 1 | 2011-03-09 11:00 | 2011-03-10 09:00 | 6h |  | 0 | 12325.3701 | 115.91 | 695.46 | 13020.8301 | 2011-03-21 08:00 | 6h | 13020.8301 | 0 | 0 | 0 | 0 | 13020.8301 | 0 | 1 | Finished | 13020.8301 | 13020.8301 | C2015-29 Fire Station.xlsx
117 | 113 | Plaatsen prefbabkolommen verdiep 0 fase 2 | 2011-02-24 09:00 | 2011-02-24 10:00 | 1h |  | 0 | 1230.22 | 115.91 | 115.91 | 1346.13 | 2011-03-08 08:00 | 1h | 1346.13 | 0 | 0 | 0 | 0 | 1346.13 | 0 | 1 | Finished | 1346.13 | 1346.13 | C2015-29 Fire Station.xlsx
118 | 114 | Plaatsen prefbabalken verdiep 0 fase 2 | 2011-02-24 10:00 | 2011-02-24 12:00 | 2h |  | 0 | 1124.03 | 115.91 | 231.82 | 1355.85 | 2011-03-08 09:00 | 2h | 1355.85 | 0 | 0 | 0 | 0 | 1355.85 | 0 | 1 | Finished | 1355.85 | 1355.85 | C2015-29 Fire Station.xlsx
119 | 115 | Plaatsen binnenbekisting wanden verdiep 0 fase 2 | 2011-03-08 11:00 | 2011-03-08 12:00 | 1h |  | 0 | 2217.5 | 115.91 | 115.91 | 2333.41 | 2011-03-18 08:00 | 2h | 2449.32 | 0 | 0 | 0 | 0 | 2449.32 | 0 | 1 | Finished | 2333.41 | 2333.41 | C2015-29 Fire Station.xlsx
120 | 116 | Plaatsen wapening wanden verdiep 0 fase 2 | 2011-03-08 13:00 | 2011-03-08 15:00 | 2h |  | 0 | 6343.6401 | 115.91 | 231.82 | 6575.4601 | 2011-03-18 10:00 | 2h | 6575.4601 | 0 | 0 | 0 | 0 | 6575.4601 | 0 | 1 | Finished | 6575.4601 | 6575.4601 | C2015-29 Fire Station.xlsx
121 | 117 | Plaatsen buitenbekisting wanden verdiep 0 fase 2 | 2011-03-08 15:00 | 2011-03-09 15:00 | 1d |  | 0 | 38.7 | 115.91 | 927.28 | 965.98 | 2011-03-18 13:00 | 1d | 965.98 | 0 | 0 | 0 | 0 | 965.98 | 0 | 1 | Finished | 965.98 | 965.98 | C2015-29 Fire Station.xlsx
122 | 118 | Storten en trillen wanden verdiep 0 fase 2 | 2011-03-09 15:00 | 2011-03-10 11:00 | 5h |  | 0 | 525.74 | 115.91 | 579.55 | 1105.29 | 2011-03-21 13:00 | 4h | 989.38 | 0 | 0 | 70.9 | 0 | 1060.28 | 0 | 1 | Finished | 1105.29 | 1105.29 | C2015-29 Fire Station.xlsx
123 | 119 | Ontkisten wanden verdiep 0 fase 2 | 2011-03-10 11:00 | 2011-03-11 11:00 | 1d |  | 0 | 38.7 | 115.91 | 927.28 | 965.98 | 2011-03-22 08:00 | 1d | 965.98 | 0 | 0 | 0 | 0 | 965.98 | 0 | 1 | Finished | 965.98 | 965.98 | C2015-29 Fire Station.xlsx
124 | 120 | Plaatsen voorgespannen welfsels verdiep 0 fase 2 | 2011-03-11 11:00 | 2011-03-11 14:00 | 2h |  | 0 | 594.87 | 115.91 | 231.82 | 826.69 | 2011-03-23 08:00 | 2h | 826.69 | 0 | 0 | 0 | 0 | 826.69 | 0 | 1 | Finished | 826.69 | 826.69 | C2015-29 Fire Station.xlsx
125 | 121 | Plaatsen wapening verdiepingsvloer verdiep 0 fase 2 | 2011-03-11 14:00 | 2011-03-14 14:00 | 1d |  | 0 | 0 | 115.91 | 927.28 | 927.28 | 2011-03-23 10:00 | 1d | 927.28 | 0 | 0 | 0 | 0 | 927.28 | 0 | 1 | Finished | 927.28 | 927.28 | C2015-29 Fire Station.xlsx
126 | 122 | Storten en trillen druklaag verdiep 0 fase 2 | 2011-03-14 14:00 | 2011-03-15 09:00 | 4h |  | 0 | 6162.6899 | 115.91 | 463.64 | 6626.33 | 2011-03-24 10:00 | 6h | 6858.15 | 0 | 0 | 0 | 0 | 6858.15 | 0 | 1 | Finished | 6626.33 | 6626.33 | C2015-29 Fire Station.xlsx
127 | 123 | Plaatsen stempels + bekisting bordessen traphal verdiep 0 | 2011-03-11 11:00 | 2011-03-11 16:00 | 4h |  | 0 | 615.11 | 115.91 | 463.64 | 1078.75 | 2011-03-23 08:00 | 4h | 1078.75 | 0 | 0 | 0 | 0 | 1078.75 | 0 | 1 | Finished | 1078.75 | 1078.75 | C2015-29 Fire Station.xlsx
128 | 124 | Plaatsen wapening bordessen traphal verdiep 0 | 2011-03-11 16:00 | 2011-03-14 10:00 | 3h |  | 0 | 561.65 | 115.91 | 347.73 | 909.38 | 2011-03-23 13:00 | 4h | 1025.29 | 0 | 0 | 0 | 0 | 1025.29 | 0 | 1 | Finished | 909.38 | 909.38 | C2015-29 Fire Station.xlsx
129 | 125 | Storten en trillen bordessen traphal verdiep 0 | 2011-03-15 09:00 | 2011-03-16 09:00 | 1d |  | 0 | 369.54 | 115.91 | 927.28 | 1296.82 | 2011-03-25 08:00 | 1d | 1296.82 | 0 | 0 | 115.8 | 0 | 1412.62 | 0 | 1 | Finished | 1296.82 | 1296.82 | C2015-29 Fire Station.xlsx
130 | 126 | Ontkisten bordessen traphal verdiep 0 | 2011-03-16 09:00 | 2011-03-17 09:00 | 1d |  | 0 | 532.98 | 115.91 | 927.28 | 1460.26 | 2011-03-28 08:00 | 1d | 1460.26 | 0 | 0 | 0 | 0 | 1460.26 | 0 | 1 | Finished | 1460.26 | 1460.26 | C2015-29 Fire Station.xlsx
131 | 127 | Plaatsen prefabtrappen verdiep 0 | 2011-03-17 09:00 | 2011-03-17 10:00 | 1h |  | 0 | 513.14 | 115.91 | 115.91 | 629.05 | 2011-03-29 08:00 | 1h | 629.05 | 0 | 0 | 0 | 0 | 629.05 | 0 | 1 | Finished | 629.05 | 629.05 | C2015-29 Fire Station.xlsx
132 | 128 | Plaatsen prefbabkolommen verdiep 1 fase 1 | 2011-03-15 09:00 | 2011-03-15 12:00 | 3h |  | 0 | 0 | 115.91 | 347.73 | 347.73 | 2011-03-25 08:00 | 4h | 463.64 | 0 | 0 | 0 | 0 | 463.64 | 0 | 1 | Finished | 347.73 | 347.73 | C2015-29 Fire Station.xlsx
133 | 129 | Plaatsen prefbabalken verdiep 1 fase 1 | 2011-03-15 13:00 | 2011-03-15 14:00 | 1h |  | 0 | 1604.87 | 115.91 | 115.91 | 1720.78 | 2011-03-25 13:00 | 1h | 1720.78 | 0 | 0 | 0 | 0 | 1720.78 | 0 | 1 | Finished | 1720.78 | 1720.78 | C2015-29 Fire Station.xlsx
134 | 130 | Plaatsen stempels + bekisting ter plaatse gestorte balken verdiep 1 | 2011-03-15 14:00 | 2011-03-15 16:00 | 2h |  | 0 | 3037.3 | 115.91 | 231.82 | 3269.1201 | 2011-03-25 14:00 | 2h | 3269.1201 | 0 | 0 | 0 | 0 | 3269.1201 | 0 | 1 | Finished | 3269.1201 | 3269.1201 | C2015-29 Fire Station.xlsx
135 | 131 | Plaatsen wapening/HEB ter plaatse gestorte balken verdiep 1 | 2011-03-15 16:00 | 2011-03-16 09:00 | 2h |  | 0 | 8774.75 | 115.91 | 231.82 | 9006.57 | 2011-03-25 16:00 | 1h | 8890.66 | 0 | 0 | 0 | 0 | 8890.66 | 0 | 1 | Finished | 9006.57 | 9006.57 | C2015-29 Fire Station.xlsx
136 | 132 | Storten en trillen ter plaatse gestorte balken verdiep 1 | 2011-03-16 09:00 | 2011-03-16 14:00 | 4h |  | 0 | 564.68 | 115.91 | 463.64 | 1028.32 | 2011-03-28 08:00 | 4h | 1028.32 | 0 | 0 | 0 | 0 | 1028.32 | 0 | 1 | Finished | 1028.32 | 1028.32 | C2015-29 Fire Station.xlsx
137 | 133 | Ontkisten ter plaatse gestorte balken verdiep 1 | 2011-03-16 14:00 | 2011-03-16 15:00 | 1h |  | 0 | 7638.25 | 115.91 | 115.91 | 7754.16 | 2011-03-28 13:00 | 1h | 7754.16 | 0 | 0 | 0 | 0 | 7754.16 | 0 | 1 | Finished | 7754.16 | 7754.16 | C2015-29 Fire Station.xlsx
138 | 134 | Metsen binnenmetselwerk (niet dragend) verdiep 1 | 2011-03-15 09:00 | 2011-03-15 10:00 | 1h |  | 0 | 518.96 | 115.91 | 115.91 | 634.87 | 2011-03-25 08:00 | 1h | 634.87 | 0 | 0 | 0 | 0 | 634.87 | 0 | 1 | Finished | 634.87 | 634.87 | C2015-29 Fire Station.xlsx
139 | 135 | Plaatsen binnenbekisting wanden verdiep 1 fase 1 | 2011-03-16 09:00 | 2011-03-16 11:00 | 2h |  | 0 | 0 | 115.91 | 231.82 | 231.82 | 2011-03-28 08:00 | 4h | 463.64 | 0 | 0 | 0 | 0 | 463.64 | 0 | 1 | Finished | 231.82 | 231.82 | C2015-29 Fire Station.xlsx
140 | 136 | Plaatsen wapening wanden verdiep 1 fase 1 | 2011-03-16 11:00 | 2011-03-30 11:00 | 10d |  | 0 | 8326.2402 | 143.72 | 11497.6001 | 19823.8403 | 2011-03-28 13:00 | 10d | 19823.8403 | 0 | 0 | 0 | 0 | 19823.8403 | 0 | 1 | Finished | 19823.8403 | 19823.8403 | C2015-29 Fire Station.xlsx
141 | 137 | Plaatsen buitenbekisting wanden verdiep 1 fase 1 | 2011-03-30 11:00 | 2011-04-01 15:00 | 2d 3h |  | 0 | 81.82 | 115.91 | 2202.2901 | 2284.1101 | 2011-04-11 13:00 | 2d 4h | 2400.0201 | 0 | 0 | 0 | 0 | 2400.0201 | 0 | 1 | Finished | 2284.1101 | 2284.1101 | C2015-29 Fire Station.xlsx
142 | 138 | Storten en trillen wanden verdiep 1 fase 1 | 2011-04-01 15:00 | 2011-04-04 11:00 | 5h |  | 0 | 1681.78 | 115.91 | 579.55 | 2261.33 | 2011-04-14 08:00 | 5h | 2261.33 | 0 | 0 | 0 | 0 | 2261.33 | 0 | 1 | Finished | 2261.33 | 2261.33 | C2015-29 Fire Station.xlsx
143 | 139 | Ontkisten wanden verdiep 1 fase 1 | 2011-04-04 11:00 | 2011-04-07 11:00 | 3d |  | 0 | 0 | 115.91 | 2781.8401 | 2781.8401 | 2011-04-14 14:00 | 3d 3h | 3129.5701 | 0 | 0 | 0 | 0 | 3129.5701 | 0 | 1 | Finished | 2781.8401 | 2781.8401 | C2015-29 Fire Station.xlsx
144 | 140 | Plaatsen voorgespannen welfsels verdiep 1 fase 1 | 2011-04-06 11:00 | 2011-04-07 11:00 | 1d |  | 0 | 12956.5801 | 115.91 | 927.28 | 13883.8601 | 2011-04-19 08:00 | 1d | 13883.8601 | 0 | 0 | 0 | 0 | 13883.8601 | 0 | 1 | Finished | 13883.8601 | 13883.8601 | C2015-29 Fire Station.xlsx
145 | 141 | Plaatsen wapening verdiepingsvloer verdiep 1 fase 1 | 2011-04-07 11:00 | 2011-04-08 11:00 | 1d |  | 0 | 1422.95 | 115.91 | 927.28 | 2350.23 | 2011-04-20 08:00 | 1d | 2350.23 | 0 | 0 | 0 | 0 | 2350.23 | 0 | 1 | Finished | 2350.23 | 2350.23 | C2015-29 Fire Station.xlsx
146 | 142 | Storten en trillen druklaag verdiep 1 fase 1 | 2011-04-08 11:00 | 2011-04-11 09:00 | 6h |  | 0 | 1181.51 | 115.91 | 695.46 | 1876.97 | 2011-04-21 08:00 | 1d | 2108.79 | 0 | 0 | 0 | 0 | 2108.79 | 0 | 1 | Finished | 1876.97 | 1876.97 | C2015-29 Fire Station.xlsx
147 | 143 | Plaatsen prefbabkolommen verdiep 1 fase 2 | 2011-03-16 11:00 | 2011-03-16 12:00 | 1h |  | 0 | 4870.1201 | 115.91 | 115.91 | 4986.0301 | 2011-03-28 13:00 | 1h | 4986.0301 | 0 | 0 | 0 | 0 | 4986.0301 | 0 | 1 | Finished | 4986.0301 | 4986.0301 | C2015-29 Fire Station.xlsx
148 | 144 | Plaatsen prefbabalken verdiep 1 fase 2 | 2011-03-16 13:00 | 2011-03-16 15:00 | 2h |  | 0 | 5918.3901 | 115.91 | 231.82 | 6150.2101 | 2011-03-28 14:00 | 2h | 6150.2101 | 0 | 0 | 0 | 0 | 6150.2101 | 0 | 1 | Finished | 6150.2101 | 6150.2101 | C2015-29 Fire Station.xlsx
149 | 145 | Plaatsen binnenbekisting wanden verdiep 1 fase 2 | 2011-04-07 11:00 | 2011-04-08 09:00 | 6h |  | 0 | 35.05 | 115.91 | 695.46 | 730.51 | 2011-04-20 08:00 | 1d | 962.33 | 0 | 0 | 0 | 0 | 962.33 | 0 | 1 | Finished | 730.51 | 730.51 | C2015-29 Fire Station.xlsx
150 | 146 | Plaatsen wapening wanden verdiep 1 fase 2 | 2011-04-08 09:00 | 2011-04-08 14:00 | 4h |  | 0 | 476.19 | 115.91 | 463.64 | 939.83 | 2011-04-21 08:00 | 4h | 939.83 | 0 | 0 | 0 | 0 | 939.83 | 0 | 1 | Finished | 939.83 | 939.83 | C2015-29 Fire Station.xlsx
151 | 147 | Plaatsen buitenbekisting wanden verdiep 1 fase 2 | 2011-04-08 14:00 | 2011-04-11 11:00 | 6h |  | 0 | 35.05 | 115.91 | 695.46 | 730.51 | 2011-04-21 13:00 | 1d | 962.33 | 0 | 0 | 0 | 0 | 962.33 | 0 | 1 | Finished | 730.51 | 730.51 | C2015-29 Fire Station.xlsx
152 | 148 | Storten en trillen wanden verdiep 1 fase 2 | 2011-04-11 11:00 | 2011-04-11 12:00 | 1h |  | 0 | 538.6 | 115.91 | 115.91 | 654.51 | 2011-04-22 13:00 | 1h | 654.51 | 0 | 0 | 0 | 0 | 654.51 | 0 | 1 | Finished | 654.51 | 654.51 | C2015-29 Fire Station.xlsx
153 | 149 | Ontkisten wanden verdiep 1 fase 2 | 2011-04-11 13:00 | 2011-04-12 12:00 | 1d |  | 0 | 0 | 115.91 | 927.28 | 927.28 | 2011-04-22 14:00 | 1d 3h | 1275.01 | 0 | 0 | 0 | 0 | 1275.01 | 0 | 1 | Finished | 927.28 | 927.28 | C2015-29 Fire Station.xlsx
154 | 150 | Plaatsen voorgespannen welfsels verdiep 1 fase 2 | 2011-04-12 13:00 | 2011-04-12 17:00 | 4h |  | 0 | 6478 | 115.91 | 463.64 | 6941.64 | 2011-04-26 08:00 | 4h | 6941.64 | 0 | 0 | 0 | 0 | 6941.64 | 0 | 1 | Finished | 6941.64 | 6941.64 | C2015-29 Fire Station.xlsx
155 | 151 | Plaatsen wapening verdiepingsvloer verdiep 1 fase 2 | 2011-04-13 08:00 | 2011-04-13 12:00 | 4h |  | 0 | 646.61 | 115.91 | 463.64 | 1110.25 | 2011-04-26 13:00 | 4h | 1110.25 | 0 | 0 | 86.78 | 0 | 1197.03 | 0 | 1 | Finished | 1110.25 | 1110.25 | C2015-29 Fire Station.xlsx
156 | 152 | Storten en trillen druklaag verdiep 1 fase 2 | 2011-04-13 13:00 | 2011-04-18 12:00 | 3d |  | 0 | 514.11 | 115.91 | 2781.8401 | 3295.9501 | 2011-04-27 08:00 | 3d | 3295.9501 | 0 | 0 | 0 | 0 | 3295.9501 | 0 | 1 | Finished | 3295.9501 | 3295.9501 | C2015-29 Fire Station.xlsx
157 | 153 | Plaatsen stempels + bekisting bordessen traphal verdiep 1 | 2011-04-12 13:00 | 2011-04-13 12:00 | 1d |  | 0 | 413.57 | 115.91 | 927.28 | 1340.85 | 2011-04-26 08:00 | 1d | 1340.85 | 0 | 0 | 0 | 0 | 1340.85 | 0 | 1 | Finished | 1340.85 | 1340.85 | C2015-29 Fire Station.xlsx
158 | 154 | Plaatsen wapening bordessen traphal verdiep 1 | 2011-04-13 13:00 | 2011-04-14 12:00 | 1d |  | 0 | 597.24 | 115.91 | 927.28 | 1524.52 | 2011-04-27 08:00 | 1d | 1524.52 | 0 | 0 | 0 | 0 | 1524.52 | 0 | 1 | Finished | 1524.52 | 1524.52 | C2015-29 Fire Station.xlsx
159 | 155 | Storten en trillen bordessen traphal verdiep 1 | 2011-04-14 13:00 | 2011-04-14 14:00 | 1h |  | 0 | 574.98 | 115.91 | 115.91 | 690.89 | 2011-04-28 08:00 | 1h | 690.89 | 0 | 0 | 25 | 0 | 715.89 | 0 | 1 | Finished | 690.89 | 690.89 | C2015-29 Fire Station.xlsx
160 | 156 | Ontkisten bordessen traphal verdiep 1 | 2011-04-14 14:00 | 2011-04-14 17:00 | 3h |  | 0 | 0 | 115.91 | 347.73 | 347.73 | 2011-04-28 09:00 | 3h | 347.73 | 0 | 0 | 0 | 0 | 347.73 | 0 | 1 | Finished | 347.73 | 347.73 | C2015-29 Fire Station.xlsx
161 | 157 | Plaatsen prefabtrappen verdiep 1 | 2011-04-15 08:00 | 2011-04-15 09:00 | 1h |  | 0 | 1431.73 | 115.91 | 115.91 | 1547.64 | 2011-04-28 13:00 | 2h | 1663.55 | 0 | 0 | 0 | 0 | 1663.55 | 0 | 1 | Finished | 1547.64 | 1547.64 | C2015-29 Fire Station.xlsx
162 | 158 | Plaatsen prefbabkolommen verdiep 2 fase 1 | 2011-04-11 09:00 | 2011-04-11 11:00 | 2h |  | 0 | 5187.1802 | 115.91 | 231.82 | 5419.0002 | 2011-04-22 08:00 | 4h | 5650.8202 | 0 | 0 | 0 | 0 | 5650.8202 | 0 | 1 | Finished | 5419.0002 | 5419.0002 | C2015-29 Fire Station.xlsx
163 | 159 | Plaatsen prefbabalken verdiep 2 fase 1 | 2011-04-11 11:00 | 2011-04-11 12:00 | 1h |  | 0 | 7046.4302 | 115.91 | 115.91 | 7162.3402 | 2011-04-22 13:00 | 1h | 7162.3402 | 0 | 0 | 0 | 0 | 7162.3402 | 0 | 1 | Finished | 7162.3402 | 7162.3402 | C2015-29 Fire Station.xlsx
164 | 160 | Plaatsen stempels + bekisting ter plaatse gestorte balken verdiep 2 | 2011-04-11 13:00 | 2011-04-11 17:00 | 4h |  | 0 | 465.49 | 115.91 | 463.64 | 929.13 | 2011-04-22 14:00 | 5h | 1045.04 | 0 | 0 | 0 | 0 | 1045.04 | 0 | 1 | Finished | 929.13 | 929.13 | C2015-29 Fire Station.xlsx
165 | 161 | Plaatsen wapening/HEB ter plaatse gestorte balken verdiep 2 | 2011-04-12 08:00 | 2011-04-12 10:00 | 2h |  | 0 | 6365.2798 | 115.91 | 231.82 | 6597.0998 | 2011-04-25 10:00 | 2h | 6597.0998 | 0 | 0 | 0 | 0 | 6597.0998 | 0 | 1 | Finished | 6597.0998 | 6597.0998 | C2015-29 Fire Station.xlsx
166 | 162 | Storten en trillen ter plaatse gestorte balken verdiep 2 | 2011-04-12 10:00 | 2011-04-12 11:00 | 1h |  | 0 | 311.62 | 115.91 | 115.91 | 427.53 | 2011-04-25 13:00 | 2h | 543.44 | 0 | 0 | 0 | 0 | 543.44 | 0 | 1 | Finished | 427.53 | 427.53 | C2015-29 Fire Station.xlsx
167 | 163 | Ontkisten ter plaatse gestorte balken verdiep 2 | 2011-04-12 11:00 | 2011-04-12 14:00 | 2h |  | 0 | 0 | 115.91 | 231.82 | 231.82 | 2011-04-25 14:00 | 2h | 231.82 | 0 | 0 | 0 | 0 | 231.82 | 0 | 1 | Finished | 231.82 | 231.82 | C2015-29 Fire Station.xlsx
168 | 164 | Metsen binnenmetselwerk (niet dragend) verdiep 2 | 2011-04-11 11:00 | 2011-05-02 11:00 | 15d |  | 0 | 11025 | 143.72 | 17246.4001 | 28271.4001 | 2011-04-22 13:00 | 15d | 28271.4001 | 0 | 0 | 0 | 0 | 28271.4001 | 0 | 1 | Finished | 28271.4001 | 28271.4001 | C2015-29 Fire Station.xlsx
169 | 165 | Plaatsen binnenbekisting wanden verdiep 2 fase 1 | 2011-04-12 10:00 | 2011-04-14 12:00 | 2d 2h |  | 0 | 116.39 | 115.91 | 2086.3801 | 2202.7701 | 2011-04-25 13:00 | 2d 4h | 2434.5901 | 0 | 0 | 0 | 0 | 2434.5901 | 0 | 1 | Finished | 2202.7701 | 2202.7701 | C2015-29 Fire Station.xlsx
170 | 166 | Plaatsen wapening wanden verdiep 2 fase 1 | 2011-04-14 13:00 | 2011-04-18 09:00 | 1d 5h |  | 0 | 1462.6801 | 115.91 | 1506.83 | 2969.5101 | 2011-04-28 08:00 | 1d 6h | 3085.4201 | 0 | 0 | 0 | 0 | 3085.4201 | 0 | 1 | Finished | 2969.5101 | 2969.5101 | C2015-29 Fire Station.xlsx
171 | 167 | Plaatsen buitenbekisting wanden verdiep 2 fase 1 | 2011-04-18 09:00 | 2011-04-20 09:00 | 2d |  | 0 | 116.39 | 115.91 | 1854.5601 | 1970.9501 | 2011-04-29 15:00 | 2d | 1970.9501 | 0 | 0 | 0 | 0 | 1970.9501 | 0 | 1 | Finished | 1970.9501 | 1970.9501 | C2015-29 Fire Station.xlsx
172 | 168 | Storten en trillen wanden verdiep 2 fase 1 | 2011-04-20 09:00 | 2011-04-20 17:00 | 7h |  | 0 | 1654.86 | 115.91 | 811.37 | 2466.23 | 2011-05-03 15:00 | 7h | 2466.23 | 0 | 0 | 0 | 0 | 2466.23 | 0 | 1 | Finished | 2466.23 | 2466.23 | C2015-29 Fire Station.xlsx
173 | 169 | Ontkisten wanden verdiep 2 fase 1 | 2011-04-21 08:00 | 2011-04-25 17:00 | 3d |  | 0 | 0 | 115.91 | 2781.8401 | 2781.8401 | 2011-05-04 14:00 | 3d 3h | 3129.5701 | 0 | 0 | 0 | 0 | 3129.5701 | 0 | 1 | Finished | 2781.8401 | 2781.8401 | C2015-29 Fire Station.xlsx
174 | 170 | Plaatsen voorgespannen welfsels verdiep 2 fase 1 | 2011-04-25 08:00 | 2011-04-25 17:00 | 1d |  | 0 | 14608.9199 | 115.91 | 927.28 | 15536.2 | 2011-05-09 08:00 | 1d | 15536.2 | 0 | 0 | 0 | 0 | 15536.2 | 0 | 1 | Finished | 15536.2 | 15536.2 | C2015-29 Fire Station.xlsx
175 | 171 | Plaatsen wapening verdiepingsvloer verdiep 2 fase 1 | 2011-04-26 08:00 | 2011-04-26 17:00 | 1d |  | 0 | 1458.15 | 115.91 | 927.28 | 2385.4301 | 2011-05-10 08:00 | 1d | 2385.4301 | 0 | 0 | 0 | 0 | 2385.4301 | 0 | 1 | Finished | 2385.4301 | 2385.4301 | C2015-29 Fire Station.xlsx
176 | 172 | Storten en trillen druklaag verdiep 2 fase 1 | 2011-04-27 08:00 | 2011-04-27 15:00 | 6h |  | 0 | 1331.62 | 115.91 | 695.46 | 2027.08 | 2011-05-11 08:00 | 1d | 2258.9 | 0 | 0 | 0 | 0 | 2258.9 | 0 | 1 | Finished | 2027.08 | 2027.08 | C2015-29 Fire Station.xlsx
177 | 173 | Plaatsen prefbabkolommen verdiep 2 fase 2 | 2011-04-14 13:00 | 2011-04-14 14:00 | 1h |  | 0 | 2578.02 | 115.91 | 115.91 | 2693.93 | 2011-04-28 08:00 | 1h | 2693.93 | 0 | 0 | 0 | 0 | 2693.93 | 0 | 1 | Finished | 2693.93 | 2693.93 | C2015-29 Fire Station.xlsx
178 | 174 | Plaatsen prefbabalken verdiep 2 fase 2 | 2011-04-14 14:00 | 2011-04-14 15:00 | 1h |  | 0 | 5315 | 115.91 | 115.91 | 5430.91 | 2011-04-28 09:00 | 2h | 5546.82 | 0 | 0 | 0 | 0 | 5546.82 | 0 | 1 | Finished | 5430.91 | 5430.91 | C2015-29 Fire Station.xlsx
179 | 175 | Plaatsen binnenbekisting wanden verdiep 2 fase 2 | 2011-04-26 08:00 | 2011-04-26 12:00 | 4h |  | 0 | 23.21 | 115.91 | 463.64 | 486.85 | 2011-05-10 08:00 | 4h | 486.85 | 0 | 0 | 0 | 0 | 486.85 | 0 | 1 | Finished | 486.85 | 486.85 | C2015-29 Fire Station.xlsx
180 | 176 | Plaatsen wapening wanden verdiep 2 fase 2 | 2011-04-26 13:00 | 2011-04-26 16:00 | 3h |  | 0 | 315.32 | 115.91 | 347.73 | 663.05 | 2011-05-10 13:00 | 4h | 778.96 | 0 | 0 | 0 | 0 | 778.96 | 0 | 1 | Finished | 663.05 | 663.05 | C2015-29 Fire Station.xlsx
181 | 177 | Plaatsen buitenbekisting wanden verdiep 2 fase 2 | 2011-04-26 16:00 | 2011-04-27 11:00 | 4h |  | 0 | 23.21 | 115.91 | 463.64 | 486.85 | 2011-05-11 08:00 | 4h | 486.85 | 0 | 0 | 0 | 0 | 486.85 | 0 | 1 | Finished | 486.85 | 486.85 | C2015-29 Fire Station.xlsx
182 | 178 | Storten en trillen wanden verdiep 2 fase 2 | 2011-04-27 11:00 | 2011-04-27 12:00 | 1h |  | 0 | 356.73 | 115.91 | 115.91 | 472.64 | 2011-05-11 13:00 | 1h | 472.64 | 0 | 0 | 0 | 0 | 472.64 | 0 | 1 | Finished | 472.64 | 472.64 | C2015-29 Fire Station.xlsx
183 | 179 | Ontkisten wanden verdiep 2 fase 2 | 2011-04-27 13:00 | 2011-04-28 09:00 | 5h |  | 0 | 0 | 115.91 | 579.55 | 579.55 | 2011-05-11 13:00 | 4h | 463.64 | 0 | 0 | 0 | 0 | 463.64 | 0 | 1 | Finished | 579.55 | 579.55 | C2015-29 Fire Station.xlsx
184 | 180 | Plaatsen voorgespannen welfsels verdiep 2 fase 2 | 2011-04-28 09:00 | 2011-04-28 15:00 | 5h |  | 0 | 7304.46 | 115.91 | 579.55 | 7884.01 | 2011-05-12 08:00 | 5h | 7884.01 | 0 | 0 | 0 | 0 | 7884.01 | 0 | 1 | Finished | 7884.01 | 7884.01 | C2015-29 Fire Station.xlsx
185 | 181 | Plaatsen wapening verdiepingsvloer verdiep 2 fase 2 | 2011-04-28 15:00 | 2011-04-29 11:00 | 5h |  | 0 | 729.08 | 115.91 | 579.55 | 1308.63 | 2011-05-12 14:00 | 5h | 1308.63 | 0 | 0 | 0 | 0 | 1308.63 | 0 | 1 | Finished | 1308.63 | 1308.63 | C2015-29 Fire Station.xlsx
186 | 182 | Storten en trillen druklaag verdiep 2 fase 2 | 2011-04-29 11:00 | 2011-04-29 16:00 | 4h |  | 0 | 665.93 | 115.91 | 463.64 | 1129.57 | 2011-05-13 10:00 | 6h | 1361.39 | 0 | 0 | 0 | 0 | 1361.39 | 0 | 1 | Finished | 1129.57 | 1129.57 | C2015-29 Fire Station.xlsx
187 | 183 | Plaatsen stempels + bekisting bordessen traphal verdiep 2 | 2011-04-28 09:00 | 2011-04-29 09:00 | 1d |  | 0 | 357.16 | 115.91 | 927.28 | 1284.44 | 2011-05-13 08:00 | 1d | 1284.44 | 0 | 0 | 0 | 0 | 1284.44 | 0 | 1 | Finished | 1284.44 | 1284.44 | C2015-29 Fire Station.xlsx
188 | 184 | Plaatsen wapening bordessen traphal verdiep 2 | 2011-04-29 09:00 | 2011-05-02 09:00 | 1d |  | 0 | 518.84 | 115.91 | 927.28 | 1446.1201 | 2011-05-13 08:00 | 1d | 1446.1201 | 0 | 0 | 0 | 0 | 1446.1201 | 0 | 1 | Finished | 1446.1201 | 1446.1201 | C2015-29 Fire Station.xlsx
189 | 185 | Storten en trillen bordessen traphal verdiep 2 | 2011-05-02 09:00 | 2011-05-02 10:00 | 1h |  | 0 | 495.67 | 115.91 | 115.91 | 611.58 | 2011-05-16 08:00 | 2h | 727.49 | 0 | 0 | 0 | 0 | 727.49 | 0 | 1 | Finished | 611.58 | 611.58 | C2015-29 Fire Station.xlsx
190 | 186 | Ontkisten bordessen traphal verdiep 2 | 2011-05-02 10:00 | 2011-05-02 14:00 | 3h |  | 0 | 0 | 115.91 | 347.73 | 347.73 | 2011-05-16 10:00 | 5h | 579.55 | 0 | 0 | 0 | 0 | 579.55 | 0 | 1 | Finished | 347.73 | 347.73 | C2015-29 Fire Station.xlsx
191 | 187 | Metsen opstand dak | 2011-05-02 14:00 | 2011-05-09 09:00 | 4d 4h |  | 0 | 4035.7 | 115.91 | 4172.7601 | 8208.4601 | 2011-05-16 16:00 | 4d 4h | 8208.4601 | 0 | 0 | 0 | 0 | 8208.4601 | 0 | 1 | Finished | 8208.4601 | 8208.4601 | C2015-29 Fire Station.xlsx
192 | 188 | Wegnemen mortelsilo (OA) | 2011-05-09 09:00 | 2011-05-10 09:00 | 1d |  | 0 | 132.5 | 0 | 0 | 132.5 | 2011-05-23 11:00 | 1d | 132.5 | 0 | 0 | 0 | 0 | 132.5 | 0 | 1 | Finished | 132.5 | 132.5 | C2015-29 Fire Station.xlsx
193 | 189 | Plaatsen stelling voor gevelmetselwerk (0A) | 2011-03-16 13:00 | 2011-03-24 12:00 | 6d |  | 0 | 0 | 40 | 1920 | 1920 | 2011-03-28 14:00 | 1d 4h | 480 | 0 | 0 | 1150 | 0 | 1630 | 0 | 1 | Finished | 1920 | 1920 | C2015-29 Fire Station.xlsx
194 | 190 | Metsen gevelmetselwerk (inclusief plaatsen isolatie) | 2011-03-24 13:00 | 2011-04-21 15:00 | 20d 2h |  | 0 | 55687.7695 | 143.72 | 23282.6402 | 78970.4097 | 2011-03-30 09:00 | 20d 2h | 78970.4097 | 0 | 0 | 0 | 0 | 78970.4097 | 0 | 1 | Finished | 78970.4097 | 78970.4097 | C2015-29 Fire Station.xlsx
195 | 191 | Wegnemen stelling (0A) | 2011-04-21 15:00 | 2011-04-27 15:00 | 4d |  | 0 | 0 | 40 | 1280 | 1280 | 2011-05-03 16:00 | 4d | 1280 | 0 | 0 | 0 | 0 | 1280 | 0 | 1 | Finished | 1280 | 1280 | C2015-29 Fire Station.xlsx
196 | 192 | Plaatsen blauwe hardsteen + isolatieblokken | 2011-04-21 15:00 | 2011-05-02 15:00 | 7d |  | 0 | 9004.1904 | 64.95 | 3637.1998 | 12641.3903 | 2011-05-03 16:00 | 8d | 13160.9902 | 0 | 0 | 0 | 0 | 13160.9902 | 0 | 1 | Finished | 12641.3903 | 12641.3903 | C2015-29 Fire Station.xlsx
197 | 193 | Voegen binnenmetselwerk zichtbaar | 2011-03-24 13:00 | 2011-04-21 12:00 | 20d |  | 0 | 25706 | 0 | 0 | 25706 | 2011-03-30 09:00 | 21d | 25706 | 0 | 0 | 0 | 0 | 25706 | 0 | 1 | Finished | 25706 | 25706 | C2015-29 Fire Station.xlsx
198 | 194 | Plaatsen onderstructuur voor vezelcementplaten (OA) | 2011-05-09 09:00 | 2011-05-25 09:00 | 12d |  | 0 | 46588.7812 | 0 | 0 | 46588.7812 | 2011-05-23 11:00 | 12d | 46588.7812 | 0 | 0 | 0 | 0 | 46588.7812 | 0 | 1 | Finished | 46588.7812 | 46588.7812 | C2015-29 Fire Station.xlsx
199 | 195 | Plaatsen spouwisolatie voor vezelcementplaten (OA) | 2011-05-25 09:00 | 2011-06-06 09:00 | 8d |  | 0 | 31644.5703 | 0 | 0 | 31644.5703 | 2011-06-08 11:00 | 10d | 31644.5703 | 0 | 0 | 0 | 0 | 31644.5703 | 0 | 1 | Finished | 31644.5703 | 31644.5703 | C2015-29 Fire Station.xlsx
200 | 196 | Plaatsen vezelcementplaten (OA) + sandwichpanelen (OA) | 2011-06-06 09:00 | 2011-08-01 09:00 | 25d |  | 0 | 106333 | 0 | 0 | 106333 | 2011-06-22 11:00 | 24d 5h | 106333 | 0 | 0 | 0 | 0 | 106333 | 0 | 1 | Finished | 106333 | 106333 | C2015-29 Fire Station.xlsx
201 | 197 | Plaatsen schuimbeton (OA) + dakisolatiesysteem (OA) | 2011-08-01 09:00 | 2011-08-08 09:00 | 5d |  | 0 | 30847.7793 | 0 | 0 | 30847.7793 | 2011-08-17 08:00 | 5d | 30847.7793 | 0 | 0 | 0 | 0 | 30847.7793 | 0 | 1 | Finished | 30847.7793 | 30847.7793 | C2015-29 Fire Station.xlsx
202 | 198 | Plaatsen staalstructuur bovendaks (OA) | 2011-08-08 09:00 | 2011-08-15 09:00 | 5d |  | 0 | 44261.0195 | 0 | 0 | 44261.0195 | 2011-08-24 08:00 | 5d | 44261.0195 | 0 | 0 | 203 | 0 | 44464.0195 | 0 | 1 | Finished | 44261.0195 | 44261.0195 | C2015-29 Fire Station.xlsx
203 | 199 | Ontkisten verloren bekisting ronde kolommen | 2011-08-15 09:00 | 2011-08-15 10:00 | 1h |  | 0 | 0 | 94.47 | 94.47 | 94.47 | 2011-09-02 08:00 | 1h | 94.47 | 0 | 0 | 0 | 0 | 94.47 | 0 | 1 | Finished | 94.47 | 94.47 | C2015-29 Fire Station.xlsx
204 | 200 | Dakopbouw fase 1 (OA) | 2011-08-15 10:00 | 2011-08-19 10:00 | 4d |  | 0 | 42261.0195 | 0 | 0 | 42261.0195 | 2011-09-02 09:00 | 3d | 42261.0195 | 0 | 0 | 0 | 0 | 42261.0195 | 0 | 1 | Finished | 42261.0195 | 42261.0195 | C2015-29 Fire Station.xlsx
205 | 201 | Dakopbouw fase 2 (OA) | 2011-08-19 10:00 | 2011-08-25 10:00 | 4d |  | 0 | 16364.4102 | 0 | 0 | 16364.4102 | 2011-09-08 08:00 | 3d | 16364.4102 | 0 | 0 | 0 | 0 | 16364.4102 | 0 | 1 | Finished | 16364.4102 | 16364.4102 | C2015-29 Fire Station.xlsx
206 | 202 | Wegnemen torenkraan | 2011-08-25 10:00 | 2011-08-26 10:00 | 1d |  | 0 | 5543.7998 | 0 | 0 | 5543.7998 | 2011-08-15 08:00 | 1d | 5543.7998 | 0 | 0 | 0 | 0 | 5543.7998 | 0 | 1 | Finished | 5543.7998 | 5543.7998 | C2015-29 Fire Station.xlsx
207 | 203 | Plaatsen groen dak | 2011-08-15 10:00 | 2011-08-22 10:00 | 5d |  | 0 | 10763.2002 | 0 | 0 | 10763.2002 | 2011-09-02 09:00 | 5d | 10763.2002 | 0 | 0 | 0 | 0 | 10763.2002 | 0 | 1 | Finished | 10763.2002 | 10763.2002 | C2015-29 Fire Station.xlsx
208 | 204 | Plaatsen buitentrap | 2011-08-15 10:00 | 2011-08-29 10:00 | 10d |  | 0 | 45239.3281 | 0 | 0 | 45239.3281 | 2011-09-02 09:00 | 10d | 45239.3281 | 0 | 0 | 0 | 0 | 45239.3281 | 0 | 1 | Finished | 45239.3281 | 45239.3281 | C2015-29 Fire Station.xlsx
4 | 0 | Social Apartments Ypres (1) | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 |  | 254d | [5 empty] | 440940.8905 |  | 1 |  | 440940.8905 | 440940.8905 | C2015-30 Social Apartments Ypres (1).xlsx
5 | 1 | grondwerken | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 2012-05-14 08:00 | 8d | 7881.5601 | 0 | 0 | 0 | 0 | 7881.5601 | 0 | 1 | Finished | 7881.5601 | 7881.5601 | C2015-30 Social Apartments Ypres (1).xlsx
6 | 2 | fundering | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 2012-05-24 08:00 | 8d | 34900.1281 | 0 | 0 | -13087.548 | 0 | 21812.5801 | 0 | 1 | Finished | 21812.5801 | 21812.5801 | C2015-30 Social Apartments Ypres (1).xlsx
7 | 3 | rioleringswerken | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 2012-05-21 08:00 | 7d | 10531.4199 | 0 | 0 | 0 | 0 | 10531.4199 | 0 | 1 | Finished | 10531.4199 | 10531.4199 | C2015-30 Social Apartments Ypres (1).xlsx
8 | 4 | regenputten | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 | 2012-06-04 08:00 | 2d | 2029.04 | 0 | 0 | 0 | 0 | 2029.04 | 0 | 1 | Finished | 2029.04 | 2029.04 | C2015-30 Social Apartments Ypres (1).xlsx
9 | 5 | wanden gelijkvloers | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-04 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 1 | Finished | 21831.3809 | 21831.3809 | C2015-30 Social Apartments Ypres (1).xlsx
10 | 6 | predallen + vloerplaat | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 | 2012-06-11 08:00 | 5d | 8663.8096 | 0 | 0 | 0 | 0 | 8663.8096 | 0 | 1 | Finished | 8663.8096 | 8663.8096 | C2015-30 Social Apartments Ypres (1).xlsx
11 | 7 | wanden 1e verdiep | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-18 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 1 | Finished | 21831.3809 | 21831.3809 | C2015-30 Social Apartments Ypres (1).xlsx
12 | 8 | predallen + vloerplaat | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 | 2012-08-06 08:00 | 5d | 17906.6992 | 0 | 0 | 0 | 0 | 17906.6992 | 0 | 1 | Finished | 17906.6992 | 17906.6992 | C2015-30 Social Apartments Ypres (1).xlsx
13 | 9 | wanden 2e verdiep | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-08-13 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 1 | Finished | 21831.3809 | 21831.3809 | C2015-30 Social Apartments Ypres (1).xlsx
14 | 11 | gevel | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 | 2012-07-02 08:00 | 57d | 35895.0486 | 0 | 0 | 1889.2131 | 0 | 37784.2617 | 0 | 1 | Finished | 37784.2617 | 37784.2617 | C2015-30 Social Apartments Ypres (1).xlsx
15 | 12 | plaatsen blauwe hardsteen | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 | 2012-10-08 08:00 | 5d | 2059.53 | 0 | 0 | 0 | 0 | 2059.53 | 0 | 1 | Finished | 2059.53 | 2059.53 | C2015-30 Social Apartments Ypres (1).xlsx
16 | 13 | schoorsteen | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 | 2012-09-10 08:00 | 12d | 15447.1922 | 0 | 0 | -2574.532 | 0 | 12872.6602 | 0 | 1 | Finished | 12872.6602 | 12872.6602 | C2015-30 Social Apartments Ypres (1).xlsx
17 | 14 | plaatsen betonnen trappen | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 | 2012-09-06 08:00 | 2d | 3656.3799 | 0 | 0 | 0 | 0 | 3656.3799 | 0 | 1 | Finished | 3656.3799 | 3656.3799 | C2015-30 Social Apartments Ypres (1).xlsx
18 | 15 | houten dakstructuur | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 | 2012-11-05 08:00 | 5d | 3148.28 | 0 | 0 | 0 | 0 | 3148.28 | 0 | 1 | Finished | 3148.28 | 3148.28 | C2015-30 Social Apartments Ypres (1).xlsx
19 | 16 | hellingsbeton | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 | 2012-11-13 08:00 | 5d | 2339.1299 | 0 | 0 | 0 | 0 | 2339.1299 | 0 | 1 | Finished | 2339.1299 | 2339.1299 | C2015-30 Social Apartments Ypres (1).xlsx
20 | 17 | dakisolatie | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 | 2012-11-28 08:00 | 8d | 8238.4156 | 0 | 0 | -3089.4059 | 0 | 5149.0098 | 0 | 1 | Finished | 5149.0098 | 5149.0098 | C2015-30 Social Apartments Ypres (1).xlsx
21 | 18 | membranen + koepels plaatsen | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 | 2012-12-03 08:00 | 5d | 21134.7998 | 0 | 0 | -12680.8799 | 0 | 8453.9199 | 0 | 1 | Finished | 8453.9199 | 8453.9199 | C2015-30 Social Apartments Ypres (1).xlsx
22 | 19 | dakrandprofielen | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 | 2013-01-14 08:00 | 8d | 8754.0797 | 0 | 0 | -3282.7799 | 0 | 5471.2998 | 0 | 1 | Finished | 5471.2998 | 5471.2998 | C2015-30 Social Apartments Ypres (1).xlsx
23 | 20 | kroonlijsten | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 | 2013-04-08 08:00 | 5d | 4534.79 | 0 | 0 | 0 | 0 | 4534.79 | 0 | 1 | Finished | 4534.79 | 4534.79 | C2015-30 Social Apartments Ypres (1).xlsx
24 | 21 | afwerking dakverdichting | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 | 2013-02-04 08:00 | 4d | 914.392 | 0 | 0 | 228.598 | 0 | 1142.99 | 0 | 1 | Finished | 1142.99 | 1142.99 | C2015-30 Social Apartments Ypres (1).xlsx
25 | 41 | opmeten buitenschrijnwerk | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 | 2012-11-13 08:00 | 1d | 8 | 0 | 0 | 2 | 0 | 10 | 0 | 1 | Finished | 10 | 10 | C2015-30 Social Apartments Ypres (1).xlsx
26 | 22 | plaatsen buitendeuren en ramen | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 | 2013-01-21 08:00 | 12d | 48187.8234 | 0 | 0 | -8031.3039 | 0 | 40156.5195 | 0 | 1 | Finished | 40156.5195 | 40156.5195 | C2015-30 Social Apartments Ypres (1).xlsx
27 | 23 | buitentrapleuningen | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 | 2013-06-10 08:00 | 2d | 2099.71 | 0 | 0 | 0 | 0 | 2099.71 | 0 | 1 | Finished | 2099.71 | 2099.71 | C2015-30 Social Apartments Ypres (1).xlsx
28 | 24 | andere afwerkingen | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 | 2013-06-10 08:00 | 5d | 13254.2402 | 0 | 0 | 0 | 0 | 13254.2402 | 0 | 1 | Finished | 13254.2402 | 13254.2402 | C2015-30 Social Apartments Ypres (1).xlsx
29 | 25 | pleisterwerken | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 | 2013-02-04 08:00 | 15d | 11790.1729 | 0 | 0 | 3930.0576 | 0 | 15720.2305 | 0 | 1 | Finished | 15720.2305 | 15720.2305 | C2015-30 Social Apartments Ypres (1).xlsx
30 | 42 | PUR + chape | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 | 2013-03-04 08:00 | 8d | 4166.9922 | 0 | 0 | 1041.748 | 0 | 5208.7402 | 0 | 1 | Finished | 5208.7402 | 5208.7402 | C2015-30 Social Apartments Ypres (1).xlsx
31 | 26 | binnenvloeren | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 | 2013-03-25 08:00 | 10d | 15135.6699 | 0 | 0 | 0 | 0 | 15135.6699 | 0 | 1 | Finished | 15135.6699 | 15135.6699 | C2015-30 Social Apartments Ypres (1).xlsx
32 | 27 | plaatsen plinten | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 | 2013-04-22 08:00 | 10d | 10833.8604 | 0 | 0 | -5416.9302 | 0 | 5416.9302 | 0 | 1 | Finished | 5416.9302 | 5416.9302 | C2015-30 Social Apartments Ypres (1).xlsx
33 | 28 | plaatsen binnendeuren | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 | 2013-06-10 08:00 | 10d | 4277.3532 | 0 | 0 | 2138.6766 | 0 | 6416.0298 | 0 | 1 | Finished | 6416.0298 | 6416.0298 | C2015-30 Social Apartments Ypres (1).xlsx
34 | 29 | keukens | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 | 2013-05-13 08:00 | 15d | 18357.8496 | 0 | 0 | 0 | 0 | 18357.8496 | 0 | 1 | Finished | 18357.8496 | 18357.8496 | C2015-30 Social Apartments Ypres (1).xlsx
35 | 30 | venstertabletten + faience | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 | 2013-04-26 08:00 | 8d | 11430.9117 | 0 | 0 | -4286.5919 | 0 | 7144.3198 | 0 | 1 | Finished | 7144.3198 | 7144.3198 | C2015-30 Social Apartments Ypres (1).xlsx
36 | 31 | sanitair | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 | 2012-11-19 08:00 | 25d | 21297.4365 | 0 | 0 | -4259.4873 | 0 | 17037.9492 | 0 | 1 | Finished | 17037.9492 | 17037.9492 | C2015-30 Social Apartments Ypres (1).xlsx
37 | 33 | CLV | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 | 2012-11-19 08:00 | 18d | 25361.6572 | 0 | 0 | 2817.9619 | 0 | 28179.6191 | 0 | 1 | Finished | 28179.6191 | 28179.6191 | C2015-30 Social Apartments Ypres (1).xlsx
38 | 34 | ventilatie | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 | 2012-11-19 08:00 | 18d | 11273.0133 | 0 | 0 | 1252.557 | 0 | 12525.5703 | 0 | 1 | Finished | 12525.5703 | 12525.5703 | C2015-30 Social Apartments Ypres (1).xlsx
39 | 35 | electriciteitsnet + toebehoren | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 | 2012-11-19 08:00 | 37d | 11461.0704 | 0 | 0 | 7124.4492 | 0 | 18585.5195 | 0 | 1 | Finished | 18585.5195 | 18585.5195 | C2015-30 Social Apartments Ypres (1).xlsx
40 | 36 | tegels buiten | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 | 2013-05-21 08:00 | 5d | 5298.2998 | 0 | 0 | 0 | 0 | 5298.2998 | 0 | 1 | Finished | 5298.2998 | 5298.2998 | C2015-30 Social Apartments Ypres (1).xlsx
41 | 37 | plaatsen brievenbussen | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 | 2013-03-19 08:00 | 2d | 688.18 | 0 | 0 | 0 | 0 | 688.18 | 0 | 1 | Finished | 688.18 | 688.18 | C2015-30 Social Apartments Ypres (1).xlsx
42 | 38 | plaatsen afsluiting | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 | 2013-06-10 08:00 | 3d | 2495.03 | 0 | 0 | 0 | 0 | 2495.03 | 0 | 1 | Finished | 2495.03 | 2495.03 | C2015-30 Social Apartments Ypres (1).xlsx
43 | 39 | fietsrekken | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 | 2013-06-10 08:00 | 1d | 367.44 | 0 | 0 | 0 | 0 | 367.44 | 0 | 1 | Finished | 367.44 | 367.44 | C2015-30 Social Apartments Ypres (1).xlsx
44 | 40 | afwerking omgevingswerken | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 | 2013-06-10 08:00 | 5d | 5911.54 | 0 | 0 | 0 | 0 | 5911.54 | 0 | 1 | Finished | 5911.54 | 5911.54 | C2015-30 Social Apartments Ypres (1).xlsx
4 | 0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 364d | [5 empty] | 1282185.9797 |  | 1 |  | 1310723.4601 | 1310723.4601 | C2015-31 Social Apartments Ypres (2).xlsx
5 | 1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 1 | Finished | 19800 | 19800 | C2015-31 Social Apartments Ypres (2).xlsx
6 | 2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 137.72 | 0 | 250.8 | 0 | 1 | Finished | 113.08 | 113.08 | C2015-31 Social Apartments Ypres (2).xlsx
7 | 3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 1 | Finished | 100.8 | 100.8 | C2015-31 Social Apartments Ypres (2).xlsx
8 | 4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 10d | 18801.6094 | 0 | 0 | -2450 | 0 | 16351.6094 | 0 | 1 | Finished | 18801.6094 | 18801.6094 | C2015-31 Social Apartments Ypres (2).xlsx
9 | 5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 1 | Finished | 56390.1289 | 56390.1289 | C2015-31 Social Apartments Ypres (2).xlsx
10 | 6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 14d | 34167.2042 | 0 | 0 | -1682.4854 | 0 | 32484.7188 | 0 | 1 | Finished | 36607.7188 | 36607.7188 | C2015-31 Social Apartments Ypres (2).xlsx
11 | 7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 125d | 267780.25 | 0 | 0 | -766.88 | 0 | 267013.37 | 0 | 1 | Finished | 267780.25 | 267780.25 | C2015-31 Social Apartments Ypres (2).xlsx
12 | 8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 23d | 18990.5843 | 0 | 0 | 352.6552 | 0 | 19343.2395 | 0 | 1 | Finished | 20641.9395 | 20641.9395 | C2015-31 Social Apartments Ypres (2).xlsx
13 | 9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 2012-11-21 08:00 | 89d | 75883.1924 | 0 | 0 | -313.5299 | 0 | 75569.6625 | 0 | 1 | Finished | 76735.8125 | 76735.8125 | C2015-31 Social Apartments Ypres (2).xlsx
14 | 10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 | 2013-04-18 08:00 | 19d | 82333.2789 | 0 | 0 | 973.3305 | 0 | 83306.6094 | 0 | 1 | Finished | 86666.6094 | 86666.6094 | C2015-31 Social Apartments Ypres (2).xlsx
15 | 11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 | 2013-09-23 08:00 | 30d | 100799.9531 | 0 | 0 | 0 | 0 | 100799.9531 | 0 | 1 | Finished | 100799.9531 | 100799.9531 | C2015-31 Social Apartments Ypres (2).xlsx
16 | 12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 | 2013-10-14 08:00 | 2d | 14942.6732 | 0 | 0 | -5297.6038 | 0 | 9645.0693 | 0 | 1 | Finished | 22414.0098 | 22414.0098 | C2015-31 Social Apartments Ypres (2).xlsx
17 | 13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 | 2013-06-03 08:00 | 57d | 47679.7393 | 0 | 0 | -189.54 | 0 | 47490.1992 | 0 | 1 | Finished | 50189.1992 | 50189.1992 | C2015-31 Social Apartments Ypres (2).xlsx
18 | 14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 | 2013-04-29 08:00 | 25d | 93184.9062 | 0 | 0 | 0 | 0 | 93184.9062 | 0 | 1 | Finished | 93184.9062 | 93184.9062 | C2015-31 Social Apartments Ypres (2).xlsx
19 | 15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 | 2013-04-19 08:00 | 45d | 50489.0357 | 0 | 0 | 27265.4643 | 0 | 77754.5 | 0 | 1 | Finished | 78538.5 | 78538.5 | C2015-31 Social Apartments Ypres (2).xlsx
20 | 16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 | 2013-05-20 08:00 | 26d | 38562.16 | 0 | 0 | -256.16 | 0 | 38306 | 0 | 1 | Finished | 37079 | 37079 | C2015-31 Social Apartments Ypres (2).xlsx
21 | 17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 | 2013-04-22 08:00 | 10d | 51566 | 0 | 0 | -1127 | 0 | 50439 | 0 | 1 | Finished | 51566 | 51566 | C2015-31 Social Apartments Ypres (2).xlsx
22 | 18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 | 2013-06-24 08:00 | 25d | 11998.533 | 0 | 0 | 9598.8264 | 0 | 21597.3594 | 0 | 1 | Finished | 21597.3594 | 21597.3594 | C2015-31 Social Apartments Ypres (2).xlsx
23 | 19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 | 2013-06-10 08:00 | 30d | 16105.9902 | 0 | 0 | -0.04 | 0 | 16105.9502 | 0 | 1 | Finished | 16105.9902 | 16105.9902 | C2015-31 Social Apartments Ypres (2).xlsx
24 | 20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 | 2013-06-24 08:00 | 25d | 63303.9414 | 0 | 0 | 0 | 0 | 63303.9414 | 0 | 1 | Finished | 63303.9414 | 63303.9414 | C2015-31 Social Apartments Ypres (2).xlsx
25 | 21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 | 2013-10-01 08:00 | 20d | 21388 | 0 | 0 | 0 | 0 | 21388 | 0 | 1 | Finished | 21388 | 21388 | C2015-31 Social Apartments Ypres (2).xlsx
26 | 22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 | 2013-12-02 08:00 | 10d | 2936 | 0 | 0 | 0 | 0 | 2936 | 0 | 1 | Finished | 2936 | 2936 | C2015-31 Social Apartments Ypres (2).xlsx
27 | 23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 | 2013-10-01 08:00 | 19d 1h | 48009.4875 | 0 | 0 | 2196.5125 | 0 | 50206 | 0 | 1 | Finished | 50206 | 50206 | C2015-31 Social Apartments Ypres (2).xlsx
28 | 24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 | 2013-10-18 08:00 | 10d | 8126.7402 | 0 | 0 | 0 | 0 | 8126.7402 | 0 | 1 | Finished | 8126.7402 | 8126.7402 | C2015-31 Social Apartments Ypres (2).xlsx
29 | 25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 15d | 54529.5312 | 0 | 0 | -0.6 | 0 | 54528.9312 | 0 | 1 | Finished | 54529.5312 | 54529.5312 | C2015-31 Social Apartments Ypres (2).xlsx
30 | 26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 2012-11-21 08:00 | 21d | 46845.8977 | 0 | 0 | -354.447 | 0 | 46491.4507 | 0 | 1 | Finished | 44615.1406 | 44615.1406 | C2015-31 Social Apartments Ypres (2).xlsx
31 | 27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 | 2013-12-02 08:00 | 2d | 2140 | 0 | 0 | 0 | 0 | 2140 | 0 | 1 | Finished | 2140 | 2140 | C2015-31 Social Apartments Ypres (2).xlsx
32 | 28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 | 2013-12-02 08:00 | 2d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 1 | Finished | 700 | 700 | C2015-31 Social Apartments Ypres (2).xlsx
33 | 29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 25d | 6387.7002 | 0 | 0 | 43.54 | 0 | 6431.2402 | 0 | 1 | Finished | 7665.2402 | 7665.2402 | C2015-31 Social Apartments Ypres (2).xlsx
4 | 0 | Social Apartments Ypres (3) | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 |  | 265d | [5 empty] | 2509031.4207 |  | 1 |  | 2509031.4221 | 2101911.2693 | C2015-32 Social Apartments Ypres (3).xlsx
5 | 1 | werfinrichting | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 2012-11-13 08:00 | 10d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 1 | Finished | 100 | 100 | C2015-32 Social Apartments Ypres (3).xlsx
6 | 2 | aanvraag verslag Bom.be | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 2012-11-29 08:00 | 22d | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 1 | Finished | 10 | 10 | C2015-32 Social Apartments Ypres (3).xlsx
7 | 3 | grondwerken + bom detectie | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 | 2013-01-11 08:00 | 14d 7h | 64710.2897 | 0 | 0 | 26645.4134 | 0 | 91355.7031 | 0 | 1 | Finished | 91355.7031 | 91355.7031 | C2015-32 Social Apartments Ypres (3).xlsx
8 | 4 | paalfundering | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 | 2013-02-15 08:00 | 8d | 34864.2 | 0 | 0 | 8716.05 | 0 | 43580.25 | 0 | 1 | Finished | 43580.25 | 43580.25 | C2015-32 Social Apartments Ypres (3).xlsx
9 | 5 | afkappen palen | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 2013-03-01 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2015-32 Social Apartments Ypres (3).xlsx
10 | 6 | rioleringwerken onder fundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 | 2013-03-04 08:00 | 5d | 15568.9102 | 0 | 0 | 0 | 0 | 15568.9102 | 0 | 1 | Finished | 15568.9102 | 15568.9102 | C2015-32 Social Apartments Ypres (3).xlsx
11 | 7 | funderingsplaat (bekisten, ijzer, beton) | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 | 2013-03-04 08:00 | 18d | 96816.4312 | 0 | 0 | 10757.3813 | 0 | 107573.8125 | 0 | 1 | Finished | 107573.8125 | 107573.8125 | C2015-32 Social Apartments Ypres (3).xlsx
12 | 8 | montage kraan | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-02-27 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2015-32 Social Apartments Ypres (3).xlsx
13 | 9 | kelderwanden | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 | 2013-03-25 08:00 | 15d | 112336.2891 | 0 | 0 | 0 | 0 | 112336.2891 | 0 | 1 | Finished | 112336.2891 | 112336.2891 | C2015-32 Social Apartments Ypres (3).xlsx
14 | 10 | kolommen + balken + metalen profielen kelder | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 | 2013-03-25 08:00 | 5d | 11543.9502 | 0 | 0 | 11543.9502 | 0 | 23087.9004 | 0 | 1 | Finished | 23087.9004 | 23087.9004 | C2015-32 Social Apartments Ypres (3).xlsx
15 | 11 | metselwerk kelderverdieping | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 | 2013-04-08 08:00 | 10d | 26678.2207 | 0 | 0 | 0 | 0 | 26678.2207 | 0 | 1 | Finished | 26678.2207 | 26678.2207 | C2015-32 Social Apartments Ypres (3).xlsx
16 | 12 | afdek kelder + balken | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-04-15 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2015-32 Social Apartments Ypres (3).xlsx
17 | 13 | wanden gelijkvloers | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-06 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 1 | Finished | 49470.1211 | 49470.1211 | C2015-32 Social Apartments Ypres (3).xlsx
18 | 14 | binnenzetten bouwmaterialen | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-05-13 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2015-32 Social Apartments Ypres (3).xlsx
19 | 15 | verwarming helling | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 | 2013-05-16 08:00 | 1d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 1 | Finished | 100 | 100 | C2015-32 Social Apartments Ypres (3).xlsx
20 | 16 | helling - vloer en wanden | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 | 2013-05-13 08:00 | 10d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2015-32 Social Apartments Ypres (3).xlsx
21 | 17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-21 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2015-32 Social Apartments Ypres (3).xlsx
22 | 18 | wanden 1ste verdiep | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-27 08:00 | 4d | 16490.0404 | 0 | 0 | 32980.0807 | 0 | 49470.1211 | 0 | 1 | Finished | 49470.1211 | 49470.1211 | C2015-32 Social Apartments Ypres (3).xlsx
23 | 19 | binnenzetten bouwmaterialen | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-03 08:00 | 3d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2015-32 Social Apartments Ypres (3).xlsx
24 | 20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-06-03 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2015-32 Social Apartments Ypres (3).xlsx
25 | 21 | stelling plaatsen | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-24 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2015-32 Social Apartments Ypres (3).xlsx
26 | 22 | gevelmetselwerk + blauwe hardsteen | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 | 2013-06-19 08:00 | 41d | 64053.6167 | 0 | 0 | 53117.6333 | 0 | 117171.25 | 0 | 1 | Finished | 117171.25 | 117171.25 | C2015-32 Social Apartments Ypres (3).xlsx
27 | 23 | wanden 2de verdiep | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-06-24 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 1 | Finished | 49470.1211 | 49470.1211 | C2015-32 Social Apartments Ypres (3).xlsx
28 | 24 | binnenzetten bouwmaterialen | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-24 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2015-32 Social Apartments Ypres (3).xlsx
29 | 25 | prefabmontage | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 | 2013-07-01 08:00 | 42d | 325007.0625 | 0 | 0 | 216671.375 | 0 | 541678.4375 | 0 | 1 | Finished | 541678.4375 | 541678.4375 | C2015-32 Social Apartments Ypres (3).xlsx
30 | 26 | afdek 2de verdiep (dakplaat) + balken | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-07-01 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2015-32 Social Apartments Ypres (3).xlsx
31 | 27 | dakranden Ytong | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 | 2013-07-01 08:00 | 5d | 14570.25 | 0 | 0 | 0 | 0 | 14570.25 | 0 | 1 | Finished | 14570.25 | 14570.25 | C2015-32 Social Apartments Ypres (3).xlsx
32 | 28 | Hellingsbeton + dakverdichting | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 | 2013-07-08 08:00 | 7d | 25071.0387 | 0 | 0 | 10744.7309 | 0 | 35815.7695 | 0 | 1 | Finished | 35815.7695 | 35815.7695 | C2015-32 Social Apartments Ypres (3).xlsx
33 | 29 | dakverdicting-eindlaag | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 | 2013-07-11 08:00 | 7d | 104335.6016 | 0 | 0 | -29810.1719 | 0 | 74525.4297 | 0 | 1 | Finished | 74525.4297 | 74525.4297 | C2015-32 Social Apartments Ypres (3).xlsx
34 | 30 | binnenwanden niv 0/1/2 | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 | 2013-08-05 08:00 | 18d | 57024.0375 | 0 | 0 | 38016.025 | 0 | 95040.0625 | 0 | 1 | Finished | 95040.0625 | 95040.0625 | C2015-32 Social Apartments Ypres (3).xlsx
35 | 53 | leiding technieken - sanitair | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 | 2013-07-01 08:00 | 33d | 291266.4562 | 0 | 0 | -26478.7687 | 0 | 264787.6875 | 0 | 1 | Finished | 264787.6875 | 264787.6875 | C2015-32 Social Apartments Ypres (3).xlsx
36 | 31 | leidingen technieken - electriciteit | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 | 2013-07-01 08:00 | 30d | 97978.7969 | 0 | 0 | 0 | 0 | 97978.7969 | 0 | 1 | Finished | 97978.7969 | 97978.7969 | C2015-32 Social Apartments Ypres (3).xlsx
37 | 32 | chape | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 | 2013-08-05 08:00 | 18d | 37480.7039 | 0 | 0 | 24987.1359 | 0 | 62467.8398 | 0 | 1 | Finished | 62467.8398 | 62467.8398 | C2015-32 Social Apartments Ypres (3).xlsx
38 | 33 | pleisterwerken | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 | 2013-08-26 08:00 | 20d | 44570.7656 | 0 | 0 | 22285.3828 | 0 | 66856.1484 | 0 | 1 | Finished | 66856.1484 | 50977.8132 | C2015-32 Social Apartments Ypres (3).xlsx
39 | 34 | leuningen | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 | 2013-09-16 08:00 | 10d | 116780.3203 | 0 | 0 | 0 | 0 | 116780.3203 | 0 | 1 | Finished | 116780.3203 | 116780.3203 | C2015-32 Social Apartments Ypres (3).xlsx
40 | 35 | voegwerken | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 | 2013-10-07 08:00 | 15d | 2696.4675 | 0 | 0 | 898.8225 | 0 | 3595.29 | 0 | 1 | Finished | 3595.29 | 1595.41 | C2015-32 Social Apartments Ypres (3).xlsx
41 | 36 | dakverdichting boven trapzalen | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 2013-10-21 08:00 | 3d | 0.6 | 0 | 0 | 0.4 | 0 | 1 | 0 | 1 | Finished | 1 | 0.575 | C2015-32 Social Apartments Ypres (3).xlsx
42 | 37 | stelling afbreken | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 | 2013-11-04 08:00 | 2d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2015-32 Social Apartments Ypres (3).xlsx
43 | 38 | afbreken torenkraan | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-10-04 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2015-32 Social Apartments Ypres (3).xlsx
44 | 39 | buitenaanleg - ABM | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 | 2013-12-02 08:00 | 20d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 0.04375 | C2015-32 Social Apartments Ypres (3).xlsx
45 | 40 | tegelwerken | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 | 2013-11-04 08:00 | 19d | 57078.5185 | 0 | 0 | 33045.4581 | 0 | 90123.9766 | 0 | 1 | Finished | 90123.9766 | 59707.1345 | C2015-32 Social Apartments Ypres (3).xlsx
46 | 41 | buitenschrijnwerk | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 | 2013-08-21 08:00 | 8d | 3116.84 | 0 | 0 | 779.21 | 0 | 3896.05 | 0 | 1 | Finished | 3896.05 | 0 | C2015-32 Social Apartments Ypres (3).xlsx
47 | 42 | binnenschrijnwerk | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 | 2013-11-12 08:00 | 30d | 52241.3672 | 0 | 0 | 8706.8945 | 0 | 60948.2617 | 0 | 1 | Finished | 60948.2617 | 0 | C2015-32 Social Apartments Ypres (3).xlsx
48 | 43 | schilderwerk | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 | 2013-11-25 08:00 | 25d | 29193.7134 | 0 | 0 | 17516.2266 | 0 | 46709.94 | 0 | 1 | Finished | 46709.9414 | 0 | C2015-32 Social Apartments Ypres (3).xlsx
49 | 44 | keukens | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 | 2013-11-20 08:00 | 15d | 39683.3408 | 0 | 0 | 13227.7803 | 0 | 52911.1211 | 0 | 1 | Finished | 52911.1211 | 0 | C2015-32 Social Apartments Ypres (3).xlsx
50 | 45 | lift | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 | 2013-12-02 08:00 | 15d | 38883 | 0 | 0 | 0 | 0 | 38883 | 0 | 1 | Finished | 38883 | 0 | C2015-32 Social Apartments Ypres (3).xlsx
51 | 46 | afwerken technieken - sanitair | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 | 2013-11-25 08:00 | 15d | 85110.3223 | 0 | 0 | 28370.1074 | 0 | 113480.4297 | 0 | 1 | Finished | 113480.4297 | 0 | C2015-32 Social Apartments Ypres (3).xlsx
52 | 54 | afwerken technieken - electriciteit | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 | 2013-11-15 08:00 | 20d | 41990.9102 | 0 | 0 | 0 | 0 | 41990.9102 | 0 | 1 | Finished | 41990.9102 | 0 | C2015-32 Social Apartments Ypres (3).xlsx
53 | 47 | algemene opkuis | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 | 2013-12-02 08:00 | 11d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 0 | C2015-32 Social Apartments Ypres (3).xlsx
54 | 48 | datum contract zonder VAA | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2015-32 Social Apartments Ypres (3).xlsx
55 | 49 | in orde brengen punten voor voorlopige oplevering | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 | 2013-12-02 08:00 | 32d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 0 | C2015-32 Social Apartments Ypres (3).xlsx
56 | 50 | oplevering contract + VAA-1-43 KD | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-12-02 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 0 | C2015-32 Social Apartments Ypres (3).xlsx
57 | 51 | buitenaanleg - bouwheer | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-12-02 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 0 | C2015-32 Social Apartments Ypres (3).xlsx
4 | 0 | IJzertoren Memorial Square | 2013-10-14 08:00 | 2013-12-20 17:00 | 50d |  |  | 0 |  |  | 214417.7109 |  | 94d | [5 empty] | 224789.6707 |  | 1 |  | 214417.7109 | 214417.7109 | C2015-33 IJzertoren Memorial Square.xlsx
5 | 1 | opbraak &amp;amp;amp; riolering | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 615.3959 | 49231.6719 | 49231.6719 | 2013-10-21 08:00 | 13d | 64001.1734 | 0 | 0 | -22405.4918 | 0 | 41595.6816 | 0 | 1 | Finished | 49231.6719 | 49231.6719 | C2015-33 IJzertoren Memorial Square.xlsx
6 | 2 | grondwerken &amp;amp;amp; onderfundering | 2013-10-28 08:00 | 2013-11-08 17:00 | 10d |  | 0 | 0 | 374.8181 | 29985.4492 | 29985.4492 | 2013-10-31 08:00 | 19d | 56972.3535 | 0 | 0 | 2114.1758 | 0 | 59086.5293 | 0 | 1 | Finished | 29985.4492 | 29985.4492 | C2015-33 IJzertoren Memorial Square.xlsx
7 | 3 | fundering | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 208.5481 | 16683.8496 | 16683.8496 | 2014-01-06 08:00 | 2d | 3336.7699 | 0 | 0 | -1544.5805 | 0 | 1792.1895 | 0 | 1 | Finished | 16683.8496 | 16683.8496 | C2015-33 IJzertoren Memorial Square.xlsx
8 | 4 | boordstenen | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 26.563 | 1062.52 | 1062.52 | 2013-12-04 08:00 | 1d | 212.504 | 0 | 0 | 1371.806 | 0 | 1584.31 | 0 | 1 | Finished | 1062.52 | 1062.52 | C2015-33 IJzertoren Memorial Square.xlsx
9 | 5 | verharding | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 86.0285 | 3441.1399 | 3441.1399 | 2013-11-13 08:00 | 3d | 2064.6839 | 0 | 0 | 5165.706 | 0 | 7230.3899 | 0 | 1 | Finished | 3441.1399 | 3441.1399 | C2015-33 IJzertoren Memorial Square.xlsx
10 | 6 | bekisting: voorbereding + beton gieten | 2013-12-02 08:00 | 2013-12-13 17:00 | 10d |  | 0 | 0 | 784.5386 | 62763.0898 | 62763.0898 | 2013-11-19 08:00 | 7d | 43934.1629 | 0 | 0 | 14036.2868 | 0 | 57970.4497 | 0 | 1 | Finished | 62763.0898 | 62763.0898 | C2015-33 IJzertoren Memorial Square.xlsx
11 | 7 | afwerking: straatmeubilair, signalisatie, ... | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 426.514 | 17060.5605 | 17060.5605 | 2013-11-29 08:00 | 3d | 10236.3363 | 0 | 0 | 5795.6242 | 0 | 16031.9606 | 0 | 1 | Finished | 17060.5605 | 17060.5605 | C2015-33 IJzertoren Memorial Square.xlsx
12 | 8 | grondwerken &amp;amp;amp; onderfundering | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 242.015 | 9680.5996 | 9680.5996 | 2013-12-09 08:00 | 7d | 13552.8395 | 0 | 0 | 3496.0302 | 0 | 17048.8696 | 0 | 1 | Finished | 9680.5996 | 9680.5996 | C2015-33 IJzertoren Memorial Square.xlsx
13 | 9 | fundering | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 41.894 | 1675.76 | 1675.76 | 2013-12-18 08:00 | 3d | 1005.456 | 0 | 0 | 1934.3541 | 0 | 2939.8101 | 0 | 1 | Finished | 1675.76 | 1675.76 | C2015-33 IJzertoren Memorial Square.xlsx
14 | 10 | boordstenen | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 86.625 | 3465 | 3465 | 2014-02-26 08:00 | 1d | 693 | 0 | 0 | 325.3701 | 0 | 1018.3701 | 0 | 1 | Finished | 3465 | 3465 | C2015-33 IJzertoren Memorial Square.xlsx
15 | 11 | bekisting: voorbereding + beton gieten | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 190.6238 | 7624.9502 | 7624.9502 | 2013-12-09 08:00 | 8d | 12199.9203 | 0 | 0 | -4456.4901 | 0 | 7743.4302 | 0 | 1 | Finished | 7624.9502 | 7624.9502 | C2015-33 IJzertoren Memorial Square.xlsx
16 | 12 | afwerking: straatmeubilair, signalisatie, ... | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 293.578 | 11743.1201 | 11743.1201 | 2014-02-21 08:00 | 5d | 11743.1201 | 0 | 0 | -995.44 | 0 | 10747.6801 | 0 | 1 | Finished | 11743.1201 | 11743.1201 | C2015-33 IJzertoren Memorial Square.xlsx
4 | 0 | Roadworks Poperinge | 2013-04-08 08:00 | 2013-10-25 17:00 | 120d |  |  | 0 |  |  | 511325.8597 |  | 193d | [5 empty] | 440394.1596 |  | 1 |  | 511325.8597 | 511325.8597 | C2015-34 Roadworks Poperinge.xlsx
5 | 1 | opbraak &amp;amp;amp; grondwerken | 2013-04-08 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 375.3961 | 75079.2266 | 75079.2266 | 2013-06-17 08:00 | 15d | 45047.5359 | 0 | 0 | -4565.6102 | 0 | 40481.9258 | 0 | 1 | Finished | 75079.2266 | 75079.2266 | C2015-34 Roadworks Poperinge.xlsx
6 | 2 | riolering | 2013-04-15 08:00 | 2013-05-24 17:00 | 25d |  | 0 | 0 | 613.1923 | 122638.4609 | 122638.4609 | 2013-07-01 08:00 | 18d | 88299.6919 | 0 | 0 | 26789.3491 | 0 | 115089.041 | 0 | 1 | Finished | 122638.4609 | 122638.4609 | C2015-34 Roadworks Poperinge.xlsx
7 | 3 | huisaansluiting | 2013-04-29 08:00 | 2013-05-31 17:00 | 20d |  | 0 | 0 | 449.8004 | 71968.0703 | 71968.0703 | 2013-07-01 08:00 | 27d | 97156.8949 | 0 | 0 | -17026.3446 | 0 | 80130.5503 | 0 | 1 | Finished | 71968.0703 | 71968.0703 | C2015-34 Roadworks Poperinge.xlsx
8 | 4 | koffer | 2013-05-13 08:00 | 2013-06-07 17:00 | 20d |  | 0 | 0 | 64.3906 | 10302.5 | 10302.5 | 2013-07-05 08:00 | 21d | 10817.625 | 0 | 0 | -515.125 | 0 | 10302.5 | 0 | 1 | Finished | 10302.5 | 10302.5 | C2015-34 Roadworks Poperinge.xlsx
9 | 5 | opbraak oude rioleringsbuizen | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 88.7186 | 7097.4902 | 7097.4902 | 2013-06-20 08:00 | 2d | 1419.498 | 0 | 0 | 3408.4021 | 0 | 4827.9001 | 0 | 1 | Finished | 7097.4902 | 7097.4902 | C2015-34 Roadworks Poperinge.xlsx
10 | 6 | boorstenen/greppel prefab | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 127.5467 | 15305.5996 | 15305.5996 | 2013-10-16 08:00 | 7d | 7142.6132 | 0 | 0 | 1344.4664 | 0 | 8487.0796 | 0 | 1 | Finished | 15305.5996 | 15305.5996 | C2015-34 Roadworks Poperinge.xlsx
11 | 7 | boorstenen/greppel ter plaatse | 2013-06-17 08:00 | 2013-07-19 17:00 | 25d |  | 0 | 0 | 94.85 | 18970 | 18970 | 2013-10-21 08:00 | 10d | 7588 | 0 | 0 | 10855.58 | 0 | 18443.58 | 0 | 1 | Finished | 18970 | 18970 | C2015-34 Roadworks Poperinge.xlsx
12 | 8 | fundering | 2013-08-19 08:00 | 2013-09-06 17:00 | 15d |  | 0 | 0 | 591.8188 | 71018.25 | 71018.25 | 2013-10-24 08:00 | 18d | 85221.9 | 0 | 0 | -22181.4 | 0 | 63040.5 | 0 | 1 | Finished | 71018.25 | 71018.25 | C2015-34 Roadworks Poperinge.xlsx
13 | 9 | betonstraatstenen | 2013-09-02 08:00 | 2013-10-18 17:00 | 35d |  | 0 | 0 | 164.6099 | 46090.7617 | 46090.7617 | 2013-11-08 08:00 | 8d | 10535.0312 | 0 | 0 | 27066.1709 | 0 | 37601.2021 | 0 | 1 | Finished | 46090.7617 | 46090.7617 | C2015-34 Roadworks Poperinge.xlsx
14 | 10 | plaatsen aanrijelement | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 234.9788 | 9399.1504 | 9399.1504 | 2013-11-22 08:00 | 5d | 9399.1504 | 0 | 0 | -626.61 | 0 | 8772.5404 | 0 | 1 | Finished | 9399.1504 | 9399.1504 | C2015-34 Roadworks Poperinge.xlsx
15 | 11 | KWS onderlaag | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 741.8625 | 29674.5 | 29674.5 | 2013-11-06 08:00 | 3d | 17804.7 | 0 | 0 | 7025.8 | 0 | 24830.5 | 0 | 1 | Finished | 29674.5 | 29674.5 | C2015-34 Roadworks Poperinge.xlsx
16 | 12 | KWS bovenlaag | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 817.8813 | 32715.25 | 32715.25 | 2014-04-03 08:00 | 2d | 13086.1 | 0 | 0 | 14234.1402 | 0 | 27320.2402 | 0 | 1 | Finished | 32715.25 | 32715.25 | C2015-34 Roadworks Poperinge.xlsx
17 | 13 | opkuis &amp;amp;amp; afwerken | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 26.665 | 1066.6 | 1066.6 | 2014-04-28 08:00 | 3d | 639.96 | 0 | 0 | 426.64 | 0 | 1066.6 | 0 | 1 | Finished | 1066.6 | 1066.6 | C2015-34 Roadworks Poperinge.xlsx
4 | 0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 951d | [5 empty] | 16068878.2993 |  | 1 |  | 14956314.25 | 14956314.25 | C2015-35 Retirement Apartments.xlsx
5 | 1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 1 | Finished | 185018.6094 | 185018.6094 | C2015-35 Retirement Apartments.xlsx
6 | 2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 669d | 8415935.5093 | 0 | 0 | -1618988.0093 | 0 | 6796947.5 | 0 | 1 | Finished | 6076079 | 6076079 | C2015-35 Retirement Apartments.xlsx
7 | 3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 329d | 3859742.6507 | 0 | 0 | 489549.3493 | 0 | 4349292 | 0 | 1 | Finished | 4047450.5 | 4047450.5 | C2015-35 Retirement Apartments.xlsx
8 | 11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 475d | [5 empty] | 3526000.4902 |  | 1 |  | 3470216 | 3470216 | C2015-35 Retirement Apartments.xlsx
9 | 4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 409d | 1089603.2667 | 0 | 0 | -105574.626 | 0 | 984028.6406 | 0 | 1 | Finished | 919103 | 919103 | C2015-35 Retirement Apartments.xlsx
10 | 5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 325d | 1564183.5559 | 0 | 0 | -380687.1214 | 0 | 1183496.4346 | 0 | 1 | Finished | 1193592.375 | 1193592.375 | C2015-35 Retirement Apartments.xlsx
11 | 6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 389d | 1286701.0786 | 0 | 0 | -148372.1636 | 0 | 1138328.915 | 0 | 1 | Finished | 1141161.625 | 1141161.625 | C2015-35 Retirement Apartments.xlsx
12 | 7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 | 2011-03-01 08:00 | 244d | 212869.3387 | 0 | 0 | 7277.1613 | 0 | 220146.5 | 0 | 1 | Finished | 216359 | 216359 | C2015-35 Retirement Apartments.xlsx
13 | 12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 231d | [5 empty] | 946589.2441 |  | 1 |  | 958011.375 | 958011.375 | C2015-35 Retirement Apartments.xlsx
14 | 8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 | 2011-10-03 08:00 | 74d | 129415.5565 | 0 | 0 | 269195.4435 | 0 | 398611 | 0 | 1 | Finished | 433717 | 433717 | C2015-35 Retirement Apartments.xlsx
15 | 9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 | 2011-06-06 08:00 | 231d | 946187.5049 | 0 | 0 | -398209.2607 | 0 | 547978.2441 | 0 | 1 | Finished | 524294.375 | 524294.375 | C2015-35 Retirement Apartments.xlsx
16 | 10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 | 2011-06-21 08:00 | 35d | 192096.4199 | 0 | 0 | 29157.0356 | 0 | 221253.4556 | 0 | 1 | Finished | 219538.7656 | 219538.7656 | C2015-35 Retirement Apartments.xlsx
4 | 0 | Railway Bridge (1) | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 |  | 274d | [5 empty] | 703703.4988 |  | 1 |  | 671383.4988 | 671383.4988 | C2016-01 Railway Bridge (1).xlsx
5 | 1 | Voorbereidende studie | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 2012-10-25 07:00 | 16d | 24125.54 | 0 | 0 | 0 | 0 | 24125.54 | 0 | 1 | Finished | 24125.54 | 24125.54 | C2016-01 Railway Bridge (1).xlsx
6 | 2 | Goedkeuring controlebureau | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-01 Railway Bridge (1).xlsx
7 | 3 | Goedkeuring bedrijf | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-01 Railway Bridge (1).xlsx
8 | 4 | Werfinrichting | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 | 2012-11-12 07:00 | 5d | 24173.9004 | 0 | 0 | 0 | 0 | 24173.9004 | 0 | 1 | Finished | 24173.9004 | 24173.9004 | C2016-01 Railway Bridge (1).xlsx
9 | 7 | Voorbereiding afbraak | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 | 2012-11-15 07:00 | 2d | 4724.28 | 0 | 0 | 0 | 0 | 4724.28 | 0 | 1 | Finished | 4724.28 | 4724.28 | C2016-01 Railway Bridge (1).xlsx
10 | 8 | Afbraak brug | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 | 2012-11-19 07:00 | 1d | 42159.0195 | 0 | 0 | 0 | 0 | 42159.0195 | 0 | 1 | Finished | 42159.0195 | 42159.0195 | C2016-01 Railway Bridge (1).xlsx
11 | 9 | Uitgraving bouwputten | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 | 2012-11-19 07:00 | 10d | 23378.1602 | 0 | 0 | 0 | 0 | 23378.1602 | 0 | 1 | Finished | 23378.1602 | 23378.1602 | C2016-01 Railway Bridge (1).xlsx
12 | 10 | Uitvoering paalfunderingen zijde A | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 | 2012-12-10 07:00 | 40d | 44330.29 | 0 | 0 | 0 | 0 | 44330.29 | 0 | 1 | Finished | 15530.29 | 15530.29 | C2016-01 Railway Bridge (1).xlsx
13 | 11 | Uitvoering paalfunderingen zijde B | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 | 2013-02-21 07:00 | 15d | 18484.03 | 0 | 0 | 0 | 0 | 18484.03 | 0 | 1 | Finished | 13684.03 | 13684.03 | C2016-01 Railway Bridge (1).xlsx
14 | 12 | Uitvoeren van funderingsbalken zijde A | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 | 2013-03-20 07:00 | 10d | 53267.0508 | 0 | 0 | 0 | 0 | 53267.0508 | 0 | 1 | Finished | 53267.0508 | 53267.0508 | C2016-01 Railway Bridge (1).xlsx
15 | 13 | Uitvoering van funderingsbalken zijde B | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 | 2013-04-08 07:00 | 10d | 49507.8203 | 0 | 0 | 0 | 0 | 49507.8203 | 0 | 1 | Finished | 49507.8203 | 49507.8203 | C2016-01 Railway Bridge (1).xlsx
16 | 31 | 1e fase brug | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 |  | 15d | [5 empty] | 61673.7598 |  | 1 |  | 61673.7598 | 61673.7598 | C2016-01 Railway Bridge (1).xlsx
17 | 14 | Plaatsen bekisting | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 | 2013-04-25 07:00 | 2d | 15810.8799 | 0 | 0 | 0 | 0 | 15810.8799 | 0 | 1 | Finished | 15810.8799 | 15810.8799 | C2016-01 Railway Bridge (1).xlsx
18 | 15 | Wapening | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 | 2013-04-26 07:00 | 5d | 21662.75 | 0 | 0 | 0 | 0 | 21662.75 | 0 | 1 | Finished | 21662.75 | 21662.75 | C2016-01 Railway Bridge (1).xlsx
19 | 16 | Bekisting + beton | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 | 2013-04-26 07:00 | 8d | 24199.1299 | 0 | 0 | 0 | 0 | 24199.1299 | 0 | 1 | Finished | 24199.1299 | 24199.1299 | C2016-01 Railway Bridge (1).xlsx
20 | 17 | Uitharden | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2013-05-08 07:00 | 6d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2016-01 Railway Bridge (1).xlsx
21 | 32 | 2e fase brug | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 |  | 19d | [5 empty] | 46921.3115 |  | 1 |  | 48201.3115 | 48201.3115 | C2016-01 Railway Bridge (1).xlsx
22 | 18 | Plaatsen bekisting | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 | 2013-05-21 07:00 | 2d | 5625.3701 | 0 | 0 | 0 | 0 | 5625.3701 | 0 | 1 | Finished | 5625.3701 | 5625.3701 | C2016-01 Railway Bridge (1).xlsx
23 | 19 | Wapening | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 | 2013-05-23 07:00 | 5d | 23526.2109 | 0 | 0 | 0 | 0 | 23526.2109 | 0 | 1 | Finished | 23526.2109 | 23526.2109 | C2016-01 Railway Bridge (1).xlsx
24 | 20 | Bekisting + beton | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 | 2013-05-23 07:00 | 7d | 17768.7305 | 0 | 0 | 0 | 0 | 17768.7305 | 0 | 1 | Finished | 19048.7305 | 19048.7305 | C2016-01 Railway Bridge (1).xlsx
25 | 21 | Uitharden | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2013-06-03 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2016-01 Railway Bridge (1).xlsx
26 | 33 | 3e fase brug | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 |  | 17d | [5 empty] | 37238.2502 |  | 1 |  | 37238.2502 | 37238.2502 | C2016-01 Railway Bridge (1).xlsx
27 | 22 | Plaatsen bekisting | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 | 2013-06-10 07:00 | 2d | 4936.26 | 0 | 0 | 0 | 0 | 4936.26 | 0 | 1 | Finished | 4936.26 | 4936.26 | C2016-01 Railway Bridge (1).xlsx
28 | 23 | Wapening | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 | 2013-06-12 07:00 | 5d | 21119.2402 | 0 | 0 | 0 | 0 | 21119.2402 | 0 | 1 | Finished | 21119.2402 | 21119.2402 | C2016-01 Railway Bridge (1).xlsx
29 | 24 | Bekisting + beton | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 | 2013-06-12 07:00 | 8d | 8802.22 | 0 | 0 | 0 | 0 | 8802.22 | 0 | 1 | Finished | 8802.22 | 8802.22 | C2016-01 Railway Bridge (1).xlsx
30 | 25 | Uitharden | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2013-06-24 07:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2016-01 Railway Bridge (1).xlsx
31 | 26 | Ontkisten | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 | 2013-07-01 07:00 | 2d | 2379.53 | 0 | 0 | 0 | 0 | 2379.53 | 0 | 1 | Finished | 2379.53 | 2379.53 | C2016-01 Railway Bridge (1).xlsx
32 | 27 | Verbindingsbalken brug | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 | 2013-07-03 07:00 | 5d | 30930.5508 | 0 | 0 | 0 | 0 | 30930.5508 | 0 | 1 | Finished | 30930.5508 | 30930.5508 | C2016-01 Railway Bridge (1).xlsx
33 | 28 | Aanbrengen waterdichte rok | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 | 2013-07-10 07:00 | 5d | 45342.1289 | 0 | 0 | 0 | 0 | 45342.1289 | 0 | 1 | Finished | 45342.1289 | 45342.1289 | C2016-01 Railway Bridge (1).xlsx
34 | 29 | Aanvullingen en wegeniswerken | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 | 2013-07-17 07:00 | 25d | 97785.5469 | 0 | 0 | 0 | 0 | 97785.5469 | 0 | 1 | Finished | 97785.5469 | 97785.5469 | C2016-01 Railway Bridge (1).xlsx
35 | 30 | Afwerkingen | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 | 2013-09-18 07:00 | 40d | 99661.8594 | 0 | 0 | 0 | 0 | 99661.8594 | 0 | 1 | Finished | 99661.8594 | 99661.8594 | C2016-01 Railway Bridge (1).xlsx
4 | 0 | Railway Bridge (2) | 2013-01-25 07:00 | 2013-12-30 16:00 | 229d |  |  | 788781.5584 |  |  | 962181.5584 |  | 239d | [5 empty] | 972341.5584 |  | 1 |  | 962181.5584 | 962181.5584 | C2016-02 Railway Bridge (2).xlsx
5 | 1 | Voorbereidende studie | 2013-01-25 07:00 | 2013-03-07 16:00 | 30d |  | 0 | 7575.7402 | 60 | 14400 | 21975.7402 | 2013-01-25 07:00 | 30d | 21975.7402 | 0 | 0 | 0 | 0 | 21975.7402 | 0 | 1 | Finished | 21975.7402 | 21975.7402 | C2016-02 Railway Bridge (2).xlsx
6 | 2 | Werfinrichting | 2013-03-01 07:00 | 2013-03-07 16:00 | 5d |  | 0 | 23303.5801 | 140 | 5600 | 28903.5801 | 2013-03-01 07:00 | 5d | 28903.5801 | 0 | 0 | 0 | 0 | 28903.5801 | 0 | 1 | Finished | 28903.5801 | 28903.5801 | C2016-02 Railway Bridge (2).xlsx
7 | 3 | Afbraak brug | 2013-03-09 07:00 | 2013-03-10 16:00 | 2d |  | 0 | 51669.3711 | 250 | 4000 | 55669.3711 | 2013-03-09 07:00 | 2d | 55669.3711 | 0 | 0 | 0 | 0 | 55669.3711 | 0 | 1 | Finished | 55669.3711 | 55669.3711 | C2016-02 Railway Bridge (2).xlsx
8 | 4 | Uitgraving bouwputten | 2013-03-11 07:00 | 2013-03-22 16:00 | 10d |  | 0 | 64593.9688 | 120 | 9600 | 74193.9688 | 2013-03-11 07:00 | 10d | 74193.9688 | 0 | 0 | 0 | 0 | 74193.9688 | 0 | 1 | Finished | 74193.9688 | 74193.9688 | C2016-02 Railway Bridge (2).xlsx
9 | 5 | Uitvoering paalfunderingen | 2013-03-25 07:00 | 2013-04-05 16:00 | 10d |  | 0 | 234823.1875 | 130 | 10400 | 245223.1875 | 2013-03-25 07:00 | 25d | 260823.1875 | 0 | 0 | 0 | 0 | 260823.1875 | 0 | 1 | Finished | 245223.1875 | 245223.1875 | C2016-02 Railway Bridge (2).xlsx
10 | 24 | Uitvoeren van funderingsbalken | 2013-04-29 07:00 | 2013-05-24 16:00 | 20d |  |  | 86325.3379 |  |  | 105525.3379 |  | 47d | [5 empty] | 98805.3379 |  | 1 |  | 105525.3379 | 105525.3379 | C2016-02 Railway Bridge (2).xlsx
11 | 6 | LH spoor B | 2013-04-29 07:00 | 2013-05-10 16:00 | 10d |  | 0 | 61602.2188 | 120 | 9600 | 71202.2188 | 2013-05-07 07:00 | 1d | 62562.2188 | 0 | 0 | 0 | 0 | 62562.2188 | 0 | 1 | Finished | 71202.2188 | 71202.2188 | C2016-02 Railway Bridge (2).xlsx
12 | 7 | LH spoor A | 2013-05-13 07:00 | 2013-05-24 16:00 | 10d |  | 0 | 24723.1191 | 120 | 9600 | 34323.1191 | 2013-06-25 07:00 | 12d | 36243.1191 | 0 | 0 | 0 | 0 | 36243.1191 | 0 | 1 | Finished | 34323.1191 | 34323.1191 | C2016-02 Railway Bridge (2).xlsx
13 | 25 | Brug fase 1 | 2013-06-10 07:00 | 2013-07-05 16:00 | 20d |  |  | 52066.4302 |  |  | 66146.4302 |  | 18d | [5 empty] | 64226.4302 |  | 1 |  | 66146.4302 | 66146.4302 | C2016-02 Railway Bridge (2).xlsx
14 | 8 | Plaatsen bekisting (incl. reiniging) | 2013-06-10 07:00 | 2013-06-11 16:00 | 2d |  | 0 | 9076.6904 | 140 | 2240 | 11316.6904 | 2013-08-22 07:00 | 2d | 11316.6904 | 0 | 0 | 0 | 0 | 11316.6904 | 0 | 1 | Finished | 11316.6904 | 11316.6904 | C2016-02 Railway Bridge (2).xlsx
15 | 9 | Wapenen + randkist | 2013-06-12 07:00 | 2013-06-25 16:00 | 10d |  | 0 | 9460.2002 | 120 | 9600 | 19060.2002 | 2013-08-27 07:00 | 8d | 17140.2002 | 0 | 0 | 0 | 0 | 17140.2002 | 0 | 1 | Finished | 19060.2002 | 19060.2002 | C2016-02 Railway Bridge (2).xlsx
16 | 10 | Betonneren | 2013-06-26 07:00 | 2013-06-26 16:00 | 1d |  | 0 | 29587.9395 | 160 | 1280 | 30867.9395 | 2013-09-06 07:00 | 1d | 30867.9395 | 0 | 0 | 0 | 0 | 30867.9395 | 0 | 1 | Finished | 30867.9395 | 30867.9395 | C2016-02 Railway Bridge (2).xlsx
17 | 11 | Ontkisten | 2013-07-05 07:00 | 2013-07-05 16:00 | 1d |  | 0 | 3941.6001 | 120 | 960 | 4901.6001 | 2013-09-16 07:00 | 1d | 4901.6001 | 0 | 0 | 0 | 0 | 4901.6001 | 0 | 1 | Finished | 4901.6001 | 4901.6001 | C2016-02 Railway Bridge (2).xlsx
18 | 26 | Brug fase 2 | 2013-07-08 07:00 | 2013-08-27 16:00 | 22d |  |  | 26282.1102 |  |  | 41322.1102 |  | 15d | [5 empty] | 37962.1102 |  | 1 |  | 41322.1102 | 41322.1102 | C2016-02 Railway Bridge (2).xlsx
19 | 12 | Reinigen | 2013-07-08 07:00 | 2013-07-09 16:00 | 2d |  | 0 | 2598.0601 | 120 | 1920 | 4518.0601 | 2013-09-17 07:00 | 2d | 4518.0601 | 0 | 0 | 0 | 0 | 4518.0601 | 0 | 1 | Finished | 4518.0601 | 4518.0601 | C2016-02 Railway Bridge (2).xlsx
20 | 13 | Wapenen + randkist | 2013-07-10 07:00 | 2013-08-13 16:00 | 10d |  | 0 | 3760.46 | 140 | 11200 | 14960.46 | 2013-09-18 07:00 | 7d | 11600.46 | 0 | 0 | 0 | 0 | 11600.46 | 0 | 1 | Finished | 14960.46 | 14960.46 | C2016-02 Railway Bridge (2).xlsx
21 | 14 | Betonneren | 2013-08-16 07:00 | 2013-08-16 16:00 | 1d |  | 0 | 19107.1602 | 120 | 960 | 20067.1602 | 2013-09-27 07:00 | 1d | 20067.1602 | 0 | 0 | 0 | 0 | 20067.1602 | 0 | 1 | Finished | 20067.1602 | 20067.1602 | C2016-02 Railway Bridge (2).xlsx
22 | 15 | Ontkisten | 2013-08-27 07:00 | 2013-08-27 16:00 | 1d |  | 0 | 816.43 | 120 | 960 | 1776.43 | 2013-10-07 07:00 | 1d | 1776.43 | 0 | 0 | 0 | 0 | 1776.43 | 0 | 1 | Finished | 1776.43 | 1776.43 | C2016-02 Railway Bridge (2).xlsx
23 | 27 | Brug fase 3 | 2013-09-02 07:00 | 2013-09-20 16:00 | 15d |  |  | 30825.9009 |  |  | 40505.9009 |  | 15d | [5 empty] | 40505.9009 |  | 1 |  | 40505.9009 | 40505.9009 | C2016-02 Railway Bridge (2).xlsx
24 | 16 | Reinigen | 2013-09-02 07:00 | 2013-09-02 16:00 | 1d |  | 0 | 3473.1499 | 130 | 1040 | 4513.1499 | 2013-10-08 07:00 | 1d | 4513.1499 | 0 | 0 | 0 | 0 | 4513.1499 | 0 | 1 | Finished | 4513.1499 | 4513.1499 | C2016-02 Railway Bridge (2).xlsx
25 | 17 | Wapenen + randkist | 2013-09-03 07:00 | 2013-09-10 16:00 | 6d |  | 0 | 5938.8501 | 140 | 6720 | 12658.8501 | 2013-10-09 07:00 | 6d | 12658.8501 | 0 | 0 | 0 | 0 | 12658.8501 | 0 | 1 | Finished | 12658.8501 | 12658.8501 | C2016-02 Railway Bridge (2).xlsx
26 | 18 | Betonneren | 2013-09-11 07:00 | 2013-09-11 16:00 | 1d |  | 0 | 19538.7109 | 120 | 960 | 20498.7109 | 2013-10-18 07:00 | 1d | 20498.7109 | 0 | 0 | 0 | 0 | 20498.7109 | 0 | 1 | Finished | 20498.7109 | 20498.7109 | C2016-02 Railway Bridge (2).xlsx
27 | 19 | Ontkisten | 2013-09-20 07:00 | 2013-09-20 16:00 | 1d |  | 0 | 1875.1899 | 120 | 960 | 2835.1899 | 2013-10-28 07:00 | 1d | 2835.1899 | 0 | 0 | 0 | 0 | 2835.1899 | 0 | 1 | Finished | 2835.1899 | 2835.1899 | C2016-02 Railway Bridge (2).xlsx
28 | 20 | Verbindingsbalken brug | 2013-09-23 07:00 | 2013-09-27 16:00 | 5d |  | 0 | 20816.3496 | 130 | 5200 | 26016.3496 | 2013-10-29 07:00 | 4d | 24976.3496 | 0 | 0 | 0 | 0 | 24976.3496 | 0 | 1 | Finished | 26016.3496 | 26016.3496 | C2016-02 Railway Bridge (2).xlsx
29 | 21 | Aanbrengen waterdichte rok | 2013-09-30 07:00 | 2013-10-04 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 | 2013-11-05 07:00 | 5d | 45342.1289 | 0 | 0 | 0 | 0 | 45342.1289 | 0 | 1 | Finished | 45342.1289 | 45342.1289 | C2016-02 Railway Bridge (2).xlsx
30 | 22 | Aanvullingen en wegeniswerken | 2013-10-07 07:00 | 2013-11-06 16:00 | 23d |  | 0 | 99584.3438 | 125 | 23000 | 122584.3438 | 2013-11-12 07:00 | 21d | 120584.3438 | 0 | 0 | 0 | 0 | 120584.3438 | 0 | 1 | Finished | 122584.3438 | 122584.3438 | C2016-02 Railway Bridge (2).xlsx
31 | 23 | Afwerkingen | 2013-11-05 07:00 | 2013-12-30 16:00 | 40d |  | 0 | 50373.1094 | 120 | 38400 | 88773.1094 | 2013-11-05 07:00 | 50d | 98373.1094 | 0 | 0 | 0 | 0 | 98373.1094 | 0 | 1 | Finished | 88773.1094 | 88773.1094 | C2016-02 Railway Bridge (2).xlsx
4 | 0 | Railway Bridge (3) | 2013-08-19 07:00 | 2014-05-28 16:00 | 203d |  |  | 753448.0109 |  |  | 926888.0109 |  | 220d | [5 empty] | 910728.0109 |  | 1 |  | 926888.0109 | 926888.0109 | C2016-03 Railway Bridge (3).xlsx
5 | 1 | Werfinrichting | 2013-08-19 07:00 | 2013-08-23 16:00 | 5d |  | 0 | 27564.4199 | 140 | 5600 | 33164.4199 | 2013-08-19 07:00 | 5d | 33164.4199 | 0 | 0 | 0 | 0 | 33164.4199 | 0 | 1 | Finished | 33164.4199 | 33164.4199 | C2016-03 Railway Bridge (3).xlsx
6 | 2 | Uitgraving bouwputten + aanvullingen | 2013-08-19 07:00 | 2013-09-24 16:00 | 27d |  | 0 | 134694.3594 | 120 | 25920 | 160614.3594 | 2013-08-19 07:00 | 27d | 160614.3594 | 0 | 0 | 0 | 0 | 160614.3594 | 0 | 1 | Finished | 160614.3594 | 160614.3594 | C2016-03 Railway Bridge (3).xlsx
7 | 3 | Paalfundering kant spoor B | 2013-09-18 07:00 | 2013-10-01 16:00 | 10d |  | 0 | 105788.6172 | 130 | 10400 | 116188.6172 | 2013-09-18 07:00 | 10d | 116188.6172 | 0 | 0 | 0 | 0 | 116188.6172 | 0 | 1 | Finished | 116188.6172 | 116188.6172 | C2016-03 Railway Bridge (3).xlsx
8 | 4 | Paalfundering kant spoor A | 2013-10-02 07:00 | 2013-10-15 16:00 | 10d |  | 0 | 113762.3516 | 130 | 10400 | 124162.3516 | 2013-10-02 07:00 | 10d | 124162.3516 | 0 | 0 | 0 | 0 | 124162.3516 | 0 | 1 | Finished | 124162.3516 | 124162.3516 | C2016-03 Railway Bridge (3).xlsx
9 | 5 | Plaatsen grachtelementen B | 2013-10-02 07:00 | 2013-10-10 16:00 | 7d |  | 0 | 1249.91 | 70 | 3920 | 5169.91 | 2013-10-02 07:00 | 7d | 5169.91 | 0 | 0 | 0 | 0 | 5169.91 | 0 | 1 | Finished | 5169.91 | 5169.91 | C2016-03 Railway Bridge (3).xlsx
10 | 6 | Plaatsen schanskorven B | 2013-10-11 07:00 | 2013-10-17 16:00 | 5d |  | 0 | 31464.6992 | 110 | 4400 | 35864.6992 | 2013-10-11 07:00 | 5d | 35864.6992 | 0 | 0 | 0 | 0 | 35864.6992 | 0 | 1 | Finished | 35864.6992 | 35864.6992 | C2016-03 Railway Bridge (3).xlsx
11 | 7 | Funderingszool B | 2013-10-08 07:00 | 2013-10-17 16:00 | 8d |  | 0 | 22808.5703 | 115 | 7360 | 30168.5703 | 2013-11-20 07:00 | 5d | 27408.5703 | 0 | 0 | 0 | 0 | 27408.5703 | 0 | 1 | Finished | 30168.5703 | 30168.5703 | C2016-03 Railway Bridge (3).xlsx
12 | 8 | Grachtelementen A | 2013-10-18 07:00 | 2013-10-28 16:00 | 7d |  | 0 | 817.85 | 75 | 4200 | 5017.85 | 2013-10-18 07:00 | 7d | 5017.85 | 0 | 0 | 0 | 0 | 5017.85 | 0 | 1 | Finished | 5017.85 | 5017.85 | C2016-03 Railway Bridge (3).xlsx
13 | 9 | Schanskorven A | 2013-10-29 07:00 | 2013-11-04 16:00 | 5d |  | 0 | 30220.0996 | 115 | 4600 | 34820.0996 | 2013-10-29 07:00 | 5d | 34820.0996 | 0 | 0 | 0 | 0 | 34820.0996 | 0 | 1 | Finished | 34820.0996 | 34820.0996 | C2016-03 Railway Bridge (3).xlsx
14 | 10 | Funderingszool A | 2013-11-07 07:00 | 2013-11-18 16:00 | 8d |  | 0 | 17917.6309 | 110 | 7040 | 24957.6309 | 2013-11-27 07:00 | 5d | 22317.6309 | 0 | 0 | 0 | 0 | 22317.6309 | 0 | 1 | Finished | 24957.6309 | 24957.6309 | C2016-03 Railway Bridge (3).xlsx
15 | 11 | Aanvoer en monteren boogbrug | 2013-11-20 07:00 | 2013-11-26 16:00 | 5d |  | 0 | 101037.5234 | 140 | 5600 | 106637.5234 | 2013-12-04 07:00 | 5d | 106637.5234 | 0 | 0 | 0 | 0 | 106637.5234 | 0 | 1 | Finished | 106637.5234 | 106637.5234 | C2016-03 Railway Bridge (3).xlsx
16 | 26 | 1e fase brug | 2013-11-27 07:00 | 2013-12-20 16:00 | 18d |  |  | 16483.7797 |  |  | 21843.7797 |  | 17d | [5 empty] | 20523.7797 |  | 1 |  | 21843.7797 | 21843.7797 | C2016-03 Railway Bridge (3).xlsx
17 | 12 | Wapenen | 2013-11-27 07:00 | 2013-12-06 16:00 | 8d |  | 0 | 974.6 | 55 | 3520 | 4494.6 | 2014-01-16 07:00 | 5d | 3174.6 | 0 | 0 | 0 | 0 | 3174.6 | 0 | 1 | Finished | 4494.6 | 4494.6 | C2016-03 Railway Bridge (3).xlsx
18 | 13 | Betonneren | 2013-12-09 07:00 | 2013-12-09 16:00 | 1d |  | 0 | 5563.0498 | 120 | 960 | 6523.0498 | 2014-01-23 07:00 | 1d | 6523.0498 | 0 | 0 | 0 | 0 | 6523.0498 | 0 | 1 | Finished | 6523.0498 | 6523.0498 | C2016-03 Railway Bridge (3).xlsx
19 | 14 | Plaatsen metalen uitkraging | 2013-12-12 07:00 | 2013-12-12 16:00 | 1d |  | 0 | 9945.1299 | 110 | 880 | 10825.1299 | 2014-01-29 07:00 | 1d | 10825.1299 | 0 | 0 | 0 | 0 | 10825.1299 | 0 | 1 | Finished | 10825.1299 | 10825.1299 | C2016-03 Railway Bridge (3).xlsx
20 | 15 | Uitharden | 2013-12-11 07:00 | 2013-12-20 16:00 | 8d |  | 0 | 1 | 0 | 0 | 1 | 2014-01-27 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2016-03 Railway Bridge (3).xlsx
21 | 27 | 2e fase brug | 2013-12-17 07:00 | 2014-01-29 09:00 | 31d 2h |  |  | 41465.4304 |  |  | 52105.4304 |  | 19d | [5 empty] | 51665.4304 |  | 1 |  | 52105.4304 | 52105.4304 | C2016-03 Railway Bridge (3).xlsx
22 | 16 | Verplaatsen bekisting + opkuis | 2014-01-08 07:00 | 2014-01-09 16:00 | 2d |  | 0 | 23882.3008 | 320 | 5120 | 29002.3008 | 2014-02-10 07:00 | 2d | 29002.3008 | 0 | 0 | 0 | 0 | 29002.3008 | 0 | 1 | Finished | 29002.3008 | 29002.3008 | C2016-03 Railway Bridge (3).xlsx
23 | 17 | Wapenen | 2013-12-17 07:00 | 2013-12-24 16:00 | 6d |  | 0 | 2327.72 | 55 | 2640 | 4967.72 | 2014-02-10 07:00 | 5d | 4527.72 | 0 | 0 | 0 | 0 | 4527.72 | 0 | 1 | Finished | 4967.72 | 4967.72 | C2016-03 Railway Bridge (3).xlsx
24 | 18 | Betonneren | 2014-01-13 07:00 | 2014-01-13 16:00 | 1d |  | 0 | 5635.5298 | 120 | 960 | 6595.5298 | 2014-02-17 07:00 | 1d | 6595.5298 | 0 | 0 | 0 | 0 | 6595.5298 | 0 | 1 | Finished | 6595.5298 | 6595.5298 | C2016-03 Railway Bridge (3).xlsx
25 | 19 | Plaatsen metalen uitkraging | 2014-01-14 09:00 | 2014-01-15 09:00 | 1d |  | 0 | 9618.8799 | 240 | 1920 | 11538.8799 | 2014-02-20 07:00 | 1d | 11538.8799 | 0 | 0 | 0 | 0 | 11538.8799 | 0 | 1 | Finished | 11538.8799 | 11538.8799 | C2016-03 Railway Bridge (3).xlsx
26 | 20 | Uitharden | 2014-01-15 09:00 | 2014-01-29 09:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-02-21 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2016-03 Railway Bridge (3).xlsx
27 | 21 | Verbindingsbalken brug | 2014-01-29 07:00 | 2014-02-04 16:00 | 5d |  | 0 | 4491.5698 | 80 | 3200 | 7691.5698 | 2014-02-17 07:00 | 5d | 7691.5698 | 0 | 0 | 0 | 0 | 7691.5698 | 0 | 1 | Finished | 7691.5698 | 7691.5698 | C2016-03 Railway Bridge (3).xlsx
28 | 22 | Aanbrengen waterdichte rok | 2014-02-12 07:00 | 2014-02-18 16:00 | 5d |  | 0 | 45579.3594 | 120 | 4800 | 50379.3594 | 2014-03-03 07:00 | 5d | 50379.3594 | 0 | 0 | 0 | 0 | 50379.3594 | 0 | 1 | Finished | 50379.3594 | 50379.3594 | C2016-03 Railway Bridge (3).xlsx
29 | 23 | Aanvullingen en wegeniswerken | 2014-02-19 07:00 | 2014-03-19 16:00 | 21d |  | 0 | 47251.2305 | 125 | 21000 | 68251.2305 | 2014-03-10 07:00 | 30d | 77251.2305 | 0 | 0 | 0 | 0 | 77251.2305 | 0 | 1 | Finished | 68251.2305 | 68251.2305 | C2016-03 Railway Bridge (3).xlsx
30 | 24 | Plaatsen leuningen | 2014-03-27 07:00 | 2014-04-30 16:00 | 25d |  | 0 | 9990.5996 | 85 | 17000 | 26990.5996 | 2014-04-21 07:00 | 5d | 13390.5996 | 0 | 0 | 0 | 0 | 13390.5996 | 0 | 1 | Finished | 26990.5996 | 26990.5996 | C2016-03 Railway Bridge (3).xlsx
31 | 25 | Afwerkingen | 2014-03-20 07:00 | 2014-05-28 16:00 | 50d |  | 0 | 860.01 | 55 | 22000 | 22860.01 | 2014-04-28 07:00 | 40d | 18460.01 | 0 | 0 | 0 | 0 | 18460.01 | 0 | 1 | Finished | 22860.01 | 22860.01 | C2016-03 Railway Bridge (3).xlsx
4 | 0 | Railway Bridge (4) | 2014-01-24 07:00 | 2014-12-29 16:00 | 248d |  |  | 674453.8672 |  |  | 906253.8672 |  | 242d | [5 empty] | 906253.8672 |  | 1 |  | 906253.8672 | 906253.8672 | C2016-04 Railway Bridge (4).xlsx
5 | 1 | Voorbereidende studie | 2014-01-24 07:00 | 2014-03-06 16:00 | 30d |  | 0 | 9475.3398 | 70 | 16800 | 26275.3398 | 2014-01-24 07:00 | 30d | 26275.3398 | 0 | 0 | 0 | 0 | 26275.3398 | 0 | 1 | Finished | 26275.3398 | 26275.3398 | C2016-04 Railway Bridge (4).xlsx
6 | 2 | Werfinrichting | 2014-02-28 07:00 | 2014-03-06 16:00 | 5d |  | 0 | 19624.9395 | 140 | 5600 | 25224.9395 | 2014-02-28 07:00 | 5d | 25224.9395 | 0 | 0 | 0 | 0 | 25224.9395 | 0 | 1 | Finished | 25224.9395 | 25224.9395 | C2016-04 Railway Bridge (4).xlsx
7 | 3 | Afbraak brug | 2014-03-08 07:00 | 2014-03-09 16:00 | 2d |  | 0 | 62658.8984 | 400 | 6400 | 69058.8984 | 2014-03-08 07:00 | 2d | 69058.8984 | 0 | 0 | 0 | 0 | 69058.8984 | 0 | 1 | Finished | 69058.8984 | 69058.8984 | C2016-04 Railway Bridge (4).xlsx
8 | 4 | Uitgraving bouwputten | 2014-03-10 07:00 | 2014-03-21 16:00 | 10d |  | 0 | 2127.0901 | 80 | 6400 | 8527.0901 | 2014-03-10 07:00 | 10d | 8527.0901 | 0 | 0 | 0 | 0 | 8527.0901 | 0 | 1 | Finished | 8527.0901 | 8527.0901 | C2016-04 Railway Bridge (4).xlsx
9 | 5 | Uitvoering paalfunderingen | 2014-03-24 07:00 | 2014-04-18 16:00 | 20d |  | 0 | 205488.3125 | 200 | 32000 | 237488.3125 | 2014-03-24 07:00 | 20d | 237488.3125 | 0 | 0 | 0 | 0 | 237488.3125 | 0 | 1 | Finished | 237488.3125 | 237488.3125 | C2016-04 Railway Bridge (4).xlsx
10 | 6 | Uitvoeren van funderingsbalken | 2014-04-28 07:00 | 2014-05-23 16:00 | 20d |  | 0 | 75153.4062 | 130 | 20800 | 95953.4062 | 2014-04-28 07:00 | 20d | 95953.4062 | 0 | 0 | 0 | 0 | 95953.4062 | 0 | 1 | Finished | 95953.4062 | 95953.4062 | C2016-04 Railway Bridge (4).xlsx
11 | 7 | Montage boogkist | 2014-05-27 07:00 | 2014-05-28 16:00 | 2d |  | 0 | 1810.99 | 115 | 1840 | 3650.99 | 2014-05-27 07:00 | 2d | 3650.99 | 0 | 0 | 0 | 0 | 3650.99 | 0 | 1 | Finished | 3650.99 | 3650.99 | C2016-04 Railway Bridge (4).xlsx
12 | 8 | Plaatsen boogkist | 2014-06-02 07:00 | 2014-06-03 16:00 | 2d |  | 0 | 5811.3198 | 135 | 2160 | 7971.3198 | 2014-06-02 07:00 | 2d | 7971.3198 | 0 | 0 | 0 | 0 | 7971.3198 | 0 | 1 | Finished | 7971.3198 | 7971.3198 | C2016-04 Railway Bridge (4).xlsx
13 | 27 | 1e fase brug | 2014-06-02 07:00 | 2014-07-04 16:00 | 25d |  |  | 45189.1116 |  |  | 56829.1116 |  | 21d | [5 empty] | 56829.1116 |  | 1 |  | 56829.1116 | 56829.1116 | C2016-04 Railway Bridge (4).xlsx
14 | 9 | Opkuisen bekisting + plaatsen randkist | 2014-06-02 07:00 | 2014-06-04 16:00 | 3d |  | 0 | 3060.8401 | 125 | 3000 | 6060.8401 | 2014-06-04 07:00 | 3d | 6060.8401 | 0 | 0 | 0 | 0 | 6060.8401 | 0 | 1 | Finished | 6060.8401 | 6060.8401 | C2016-04 Railway Bridge (4).xlsx
15 | 10 | Wapenen | 2014-06-05 07:00 | 2014-06-12 16:00 | 6d |  | 0 | 24447.6309 | 140 | 6720 | 31167.6309 | 2014-06-10 07:00 | 6d | 31167.6309 | 0 | 0 | 0 | 0 | 31167.6309 | 0 | 1 | Finished | 31167.6309 | 31167.6309 | C2016-04 Railway Bridge (4).xlsx
16 | 11 | Betonneren | 2014-06-13 07:00 | 2014-06-13 16:00 | 1d |  | 0 | 17679.6406 | 240 | 1920 | 19599.6406 | 2014-06-18 07:00 | 1d | 19599.6406 | 0 | 0 | 0 | 0 | 19599.6406 | 0 | 1 | Finished | 19599.6406 | 19599.6406 | C2016-04 Railway Bridge (4).xlsx
17 | 12 | Uitharden | 2014-06-23 07:00 | 2014-07-04 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-06-19 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2016-04 Railway Bridge (4).xlsx
18 | 28 | 2e fase brug | 2014-07-07 07:00 | 2014-08-01 16:00 | 20d |  |  | 32321.73 |  |  | 45121.73 |  | 22d | [5 empty] | 45121.73 |  | 1 |  | 45121.73 | 45121.73 | C2016-04 Railway Bridge (4).xlsx
19 | 13 | Zakken bekisting + verschuiven en opkuisen | 2014-07-07 07:00 | 2014-07-09 16:00 | 3d |  | 0 | 2081.4399 | 160 | 3840 | 5921.4399 | 2014-07-02 07:00 | 3d | 5921.4399 | 0 | 0 | 0 | 0 | 5921.4399 | 0 | 1 | Finished | 5921.4399 | 5921.4399 | C2016-04 Railway Bridge (4).xlsx
20 | 14 | Wapenen | 2014-07-10 07:00 | 2014-07-17 16:00 | 6d |  | 0 | 13226.29 | 160 | 7680 | 20906.29 | 2014-07-08 07:00 | 6d | 20906.29 | 0 | 0 | 0 | 0 | 20906.29 | 0 | 1 | Finished | 20906.29 | 20906.29 | C2016-04 Railway Bridge (4).xlsx
21 | 15 | Betonneren | 2014-07-18 07:00 | 2014-07-18 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 | 2014-07-15 07:00 | 1d | 18293 | 0 | 0 | 0 | 0 | 18293 | 0 | 1 | Finished | 18293 | 18293 | C2016-04 Railway Bridge (4).xlsx
22 | 16 | Uitharden | 2014-07-21 07:00 | 2014-08-01 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-07-16 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2016-04 Railway Bridge (4).xlsx
23 | 29 | 3e fase brug | 2014-09-01 07:00 | 2014-09-26 16:00 | 20d |  |  | 31904.6599 |  |  | 43664.6599 |  | 17d | [5 empty] | 43664.6599 |  | 1 |  | 43664.6599 | 43664.6599 | C2016-04 Railway Bridge (4).xlsx
24 | 17 | Zakken bekisting + verschuiven en opkuisen | 2014-09-01 07:00 | 2014-09-02 16:00 | 2d |  | 0 | 1475.8 | 160 | 2560 | 4035.8 | 2014-08-18 07:00 | 2d | 4035.8 | 0 | 0 | 0 | 0 | 4035.8 | 0 | 1 | Finished | 4035.8 | 4035.8 | C2016-04 Railway Bridge (4).xlsx
25 | 18 | Plaatsen randbekisting | 2014-09-03 07:00 | 2014-09-04 16:00 | 2d |  | 0 | 1401.98 | 95 | 1520 | 2921.98 | 2014-08-21 07:00 | 2d | 2921.98 | 0 | 0 | 0 | 0 | 2921.98 | 0 | 1 | Finished | 2921.98 | 2921.98 | C2016-04 Railway Bridge (4).xlsx
26 | 19 | Wapenen | 2014-09-05 07:00 | 2014-09-11 16:00 | 5d |  | 0 | 12012.8799 | 160 | 6400 | 18412.8799 | 2014-08-25 07:00 | 5d | 18412.8799 | 0 | 0 | 0 | 0 | 18412.8799 | 0 | 1 | Finished | 18412.8799 | 18412.8799 | C2016-04 Railway Bridge (4).xlsx
27 | 20 | Betonneren | 2014-09-12 07:00 | 2014-09-12 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 | 2014-09-02 07:00 | 1d | 18293 | 0 | 0 | 0 | 0 | 18293 | 0 | 1 | Finished | 18293 | 18293 | C2016-04 Railway Bridge (4).xlsx
28 | 21 | Uitharden | 2014-09-22 07:00 | 2014-09-26 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2014-09-03 07:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2016-04 Railway Bridge (4).xlsx
29 | 22 | Wapenen en betonneren voeg | 2014-09-18 07:00 | 2014-09-24 16:00 | 5d |  | 0 | 15864.21 | 185 | 7400 | 23264.21 | 2014-09-03 07:00 | 5d | 23264.21 | 0 | 0 | 0 | 0 | 23264.21 | 0 | 1 | Finished | 23264.21 | 23264.21 | C2016-04 Railway Bridge (4).xlsx
30 | 23 | Plaatsen dakdichting | 2014-09-25 07:00 | 2014-10-01 16:00 | 5d |  | 0 | 39542.1289 | 145 | 5800 | 45342.1289 | 2014-09-15 07:00 | 5d | 45342.1289 | 0 | 0 | 0 | 0 | 45342.1289 | 0 | 1 | Finished | 45342.1289 | 45342.1289 | C2016-04 Railway Bridge (4).xlsx
31 | 24 | Aanvullen boogbrug | 2014-10-02 07:00 | 2014-10-08 16:00 | 5d |  | 0 | 34719.3984 | 160 | 6400 | 41119.3984 | 2014-09-22 07:00 | 5d | 41119.3984 | 0 | 0 | 0 | 0 | 41119.3984 | 0 | 1 | Finished | 41119.3984 | 41119.3984 | C2016-04 Railway Bridge (4).xlsx
32 | 25 | Wegeniswerken | 2014-10-09 07:00 | 2014-11-05 16:00 | 20d |  | 0 | 27239.8906 | 135 | 21600 | 48839.8906 | 2014-10-01 07:00 | 20d | 48839.8906 | 0 | 0 | 0 | 0 | 48839.8906 | 0 | 1 | Finished | 48839.8906 | 48839.8906 | C2016-04 Railway Bridge (4).xlsx
33 | 26 | Afwerkingen | 2014-11-06 07:00 | 2014-12-29 16:00 | 40d |  | 0 | 65522.4414 | 195 | 62400 | 127922.4414 | 2014-10-29 07:00 | 40d | 127922.4414 | 0 | 0 | 0 | 0 | 127922.4414 | 0 | 1 | Finished | 127922.4414 | 127922.4414 | C2016-04 Railway Bridge (4).xlsx
4 | 0 | Railway Bridge (5) | 2014-11-03 07:00 | 2015-08-12 16:00 | 195d |  |  | 579697.4604 |  |  | 832497.4604 |  | 197d | [5 empty] | 832497.4604 |  | 1 |  | 832497.4604 | 832497.4604 | C2016-05 Railway Bridge (5).xlsx
5 | 1 | Voorbereidende werken afbraak | 2014-11-03 07:00 | 2014-11-07 16:00 | 5d |  | 0 | 22673.4492 | 130 | 5200 | 27873.4492 | 2014-11-03 07:00 | 5d | 27873.4492 | 0 | 0 | 0 | 0 | 27873.4492 | 0 | 1 | Finished | 27873.4492 | 27873.4492 | C2016-05 Railway Bridge (5).xlsx
6 | 2 | Afbraak | 2014-11-08 07:00 | 2014-11-09 16:00 | 2d |  | 0 | 59376.7305 | 350 | 5600 | 64976.7305 | 2014-11-08 07:00 | 2d | 64976.7305 | 0 | 0 | 0 | 0 | 64976.7305 | 0 | 1 | Finished | 64976.7305 | 64976.7305 | C2016-05 Railway Bridge (5).xlsx
7 | 3 | Voorbereiding werkplatform spoor A | 2014-11-10 07:00 | 2014-11-14 16:00 | 5d |  | 0 | 5143 | 165 | 6600 | 11743 | 2014-11-10 07:00 | 5d | 11743 | 0 | 0 | 0 | 0 | 11743 | 0 | 1 | Finished | 11743 | 11743 | C2016-05 Railway Bridge (5).xlsx
8 | 4 | Installatie paalfunderingen | 2014-11-17 07:00 | 2014-11-18 16:00 | 2d |  | 0 | 24394.2891 | 185 | 2960 | 27354.2891 | 2014-11-17 07:00 | 2d | 27354.2891 | 0 | 0 | 0 | 0 | 27354.2891 | 0 | 1 | Finished | 27354.2891 | 27354.2891 | C2016-05 Railway Bridge (5).xlsx
9 | 5 | Boren paalfundering spoor A | 2014-11-19 07:00 | 2014-12-02 16:00 | 10d |  | 0 | 37034.6406 | 190 | 15200 | 52234.6406 | 2014-11-19 07:00 | 10d | 52234.6406 | 0 | 0 | 0 | 0 | 52234.6406 | 0 | 1 | Finished | 52234.6406 | 52234.6406 | C2016-05 Railway Bridge (5).xlsx
10 | 6 | Voorbereiding werkplatform spoor B | 2014-11-17 07:00 | 2014-11-26 16:00 | 8d |  | 0 | 6576.8799 | 110 | 7040 | 13616.8799 | 2014-11-17 07:00 | 8d | 13616.8799 | 0 | 0 | 0 | 0 | 13616.8799 | 0 | 1 | Finished | 13616.8799 | 13616.8799 | C2016-05 Railway Bridge (5).xlsx
11 | 7 | Boren paalfundering spoor B | 2014-12-03 07:00 | 2014-12-16 16:00 | 10d |  | 0 | 34742.1289 | 185 | 14800 | 49542.1289 | 2014-12-03 07:00 | 10d | 49542.1289 | 0 | 0 | 0 | 0 | 49542.1289 | 0 | 1 | Finished | 49542.1289 | 49542.1289 | C2016-05 Railway Bridge (5).xlsx
12 | 8 | Grachtelementen A | 2014-12-03 07:00 | 2014-12-05 16:00 | 3d |  | 0 | 3158.28 | 115 | 2760 | 5918.28 | 2014-12-03 07:00 | 3d | 5918.28 | 0 | 0 | 0 | 0 | 5918.28 | 0 | 1 | Finished | 5918.28 | 5918.28 | C2016-05 Railway Bridge (5).xlsx
13 | 9 | Plaatsen schanskorven A | 2014-12-08 07:00 | 2014-12-16 16:00 | 7d |  | 0 | 3124.6299 | 105 | 5880 | 9004.6299 | 2014-12-08 07:00 | 7d | 9004.6299 | 0 | 0 | 0 | 0 | 9004.6299 | 0 | 1 | Finished | 9004.6299 | 9004.6299 | C2016-05 Railway Bridge (5).xlsx
14 | 10 | Zuiveringsbeton spoor A | 2014-12-17 07:00 | 2014-12-17 16:00 | 1d |  | 0 | 1740.75 | 180 | 1440 | 3180.75 | 2014-12-17 07:00 | 1d | 3180.75 | 0 | 0 | 0 | 0 | 3180.75 | 0 | 1 | Finished | 3180.75 | 3180.75 | C2016-05 Railway Bridge (5).xlsx
15 | 11 | Grachtelementen B | 2014-12-18 07:00 | 2015-01-05 16:00 | 3d |  | 0 | 2478.3701 | 130 | 3120 | 5598.3701 | 2014-12-18 07:00 | 3d | 5598.3701 | 0 | 0 | 0 | 0 | 5598.3701 | 0 | 1 | Finished | 5598.3701 | 5598.3701 | C2016-05 Railway Bridge (5).xlsx
16 | 12 | Schanskorven B | 2015-01-06 07:00 | 2015-01-14 16:00 | 7d |  | 0 | 3813.29 | 75 | 4200 | 8013.29 | 2015-01-06 07:00 | 7d | 8013.29 | 0 | 0 | 0 | 0 | 8013.29 | 0 | 1 | Finished | 8013.29 | 8013.29 | C2016-05 Railway Bridge (5).xlsx
17 | 13 | Zuiveringsbeton B | 2015-01-15 07:00 | 2015-01-15 16:00 | 1d |  | 0 | 1165.85 | 150 | 1200 | 2365.85 | 2015-01-15 07:00 | 1d | 2365.85 | 0 | 0 | 0 | 0 | 2365.85 | 0 | 1 | Finished | 2365.85 | 2365.85 | C2016-05 Railway Bridge (5).xlsx
18 | 14 | Betonneren palen A | 2014-12-18 07:00 | 2014-12-19 16:00 | 2d |  | 0 | 56952.1602 | 210 | 3360 | 60312.1602 | 2014-12-18 07:00 | 2d | 60312.1602 | 0 | 0 | 0 | 0 | 60312.1602 | 0 | 1 | Finished | 60312.1602 | 60312.1602 | C2016-05 Railway Bridge (5).xlsx
19 | 15 | Funderingszool A | 2015-01-05 07:00 | 2015-01-09 16:00 | 5d |  | 0 | 7605.8101 | 155 | 6200 | 13805.8101 | 2015-01-05 07:00 | 5d | 13805.8101 | 0 | 0 | 0 | 0 | 13805.8101 | 0 | 1 | Finished | 13805.8101 | 13805.8101 | C2016-05 Railway Bridge (5).xlsx
20 | 16 | Betonneren palen B | 2015-01-16 07:00 | 2015-01-19 16:00 | 2d |  | 0 | 48416.1406 | 205 | 3280 | 51696.1406 | 2015-01-16 07:00 | 2d | 51696.1406 | 0 | 0 | 0 | 0 | 51696.1406 | 0 | 1 | Finished | 51696.1406 | 51696.1406 | C2016-05 Railway Bridge (5).xlsx
21 | 17 | Funderingszool B | 2015-01-20 07:00 | 2015-01-26 16:00 | 5d |  | 0 | 9827.4404 | 155 | 6200 | 16027.4404 | 2015-01-20 07:00 | 5d | 16027.4404 | 0 | 0 | 0 | 0 | 16027.4404 | 0 | 1 | Finished | 16027.4404 | 16027.4404 | C2016-05 Railway Bridge (5).xlsx
22 | 33 | Boog fase 1 | 2015-02-03 07:00 | 2015-02-18 16:00 | 12d |  |  | 49789.54 |  |  | 66669.54 |  | 12d | [5 empty] | 66669.54 |  | 1 |  | 66669.54 | 66669.54 | C2016-05 Railway Bridge (5).xlsx
23 | 18 | Plaatsen bekisting | 2015-02-03 07:00 | 2015-02-05 16:00 | 3d |  | 0 | 11142.7197 | 195 | 4680 | 15822.7197 | 2015-02-05 07:00 | 3d | 15822.7197 | 0 | 0 | 0 | 0 | 15822.7197 | 0 | 1 | Finished | 15822.7197 | 15822.7197 | C2016-05 Railway Bridge (5).xlsx
24 | 19 | Wapenen | 2015-02-06 07:00 | 2015-02-17 16:00 | 8d |  | 0 | 17346.2402 | 160 | 10240 | 27586.2402 | 2015-02-10 07:00 | 8d | 27586.2402 | 0 | 0 | 0 | 0 | 27586.2402 | 0 | 1 | Finished | 27586.2402 | 27586.2402 | C2016-05 Railway Bridge (5).xlsx
25 | 20 | Betonneren | 2015-02-18 07:00 | 2015-02-18 16:00 | 1d |  | 0 | 21300.5801 | 245 | 1960 | 23260.5801 | 2015-02-20 07:00 | 1d | 23260.5801 | 0 | 0 | 0 | 0 | 23260.5801 | 0 | 1 | Finished | 23260.5801 | 23260.5801 | C2016-05 Railway Bridge (5).xlsx
26 | 34 | Boog fase 2 | 2015-03-05 07:00 | 2015-04-08 16:00 | 25d |  |  | 44511.1687 |  |  | 61991.1687 |  | 25d | [5 empty] | 61991.1687 |  | 1 |  | 61991.1687 | 61991.1687 | C2016-05 Railway Bridge (5).xlsx
27 | 21 | Verplaatsen bekisting | 2015-03-05 07:00 | 2015-03-11 16:00 | 5d |  | 0 | 2372.8 | 105 | 4200 | 6572.8 | 2015-03-09 07:00 | 5d | 6572.8 | 0 | 0 | 0 | 0 | 6572.8 | 0 | 1 | Finished | 6572.8 | 6572.8 | C2016-05 Railway Bridge (5).xlsx
28 | 22 | Wapenen | 2015-03-12 07:00 | 2015-03-23 16:00 | 8d |  | 0 | 11752.8096 | 150 | 9600 | 21352.8096 | 2015-03-16 07:00 | 8d | 21352.8096 | 0 | 0 | 0 | 0 | 21352.8096 | 0 | 1 | Finished | 21352.8096 | 21352.8096 | C2016-05 Railway Bridge (5).xlsx
29 | 23 | Betonneren | 2015-03-24 07:00 | 2015-03-24 16:00 | 1d |  | 0 | 23932.6992 | 245 | 1960 | 25892.6992 | 2015-03-26 07:00 | 1d | 25892.6992 | 0 | 0 | 0 | 0 | 25892.6992 | 0 | 1 | Finished | 25892.6992 | 25892.6992 | C2016-05 Railway Bridge (5).xlsx
30 | 24 | Ontkisten | 2015-04-08 07:00 | 2015-04-08 16:00 | 1d |  | 0 | 6452.8599 | 215 | 1720 | 8172.8599 | 2015-04-10 07:00 | 1d | 8172.8599 | 0 | 0 | 0 | 0 | 8172.8599 | 0 | 1 | Finished | 8172.8599 | 8172.8599 | C2016-05 Railway Bridge (5).xlsx
31 | 25 | Wanden fase 1 | 2015-03-12 07:00 | 2015-04-15 16:00 | 25d |  | 0 | 17149.0195 | 65 | 13000 | 30149.0195 | 2015-03-16 07:00 | 25d | 30149.0195 | 0 | 0 | 0 | 0 | 30149.0195 | 0 | 1 | Finished | 30149.0195 | 30149.0195 | C2016-05 Railway Bridge (5).xlsx
32 | 26 | Wanden fase 2 | 2015-04-09 07:00 | 2015-05-13 16:00 | 25d |  | 0 | 15290.0596 | 60 | 12000 | 27290.0596 | 2015-04-13 07:00 | 25d | 27290.0596 | 0 | 0 | 0 | 0 | 27290.0596 | 0 | 1 | Finished | 27290.0596 | 27290.0596 | C2016-05 Railway Bridge (5).xlsx
33 | 27 | Waterdichting | 2015-05-14 07:00 | 2015-05-27 16:00 | 10d |  | 0 | 30552.9609 | 195 | 15600 | 46152.9609 | 2015-05-18 07:00 | 10d | 46152.9609 | 0 | 0 | 0 | 0 | 46152.9609 | 0 | 1 | Finished | 46152.9609 | 46152.9609 | C2016-05 Railway Bridge (5).xlsx
34 | 28 | Aanvullen | 2015-05-28 07:00 | 2015-06-03 16:00 | 5d |  | 0 | 29016.3203 | 180 | 7200 | 36216.3203 | 2015-06-01 07:00 | 5d | 36216.3203 | 0 | 0 | 0 | 0 | 36216.3203 | 0 | 1 | Finished | 36216.3203 | 36216.3203 | C2016-05 Railway Bridge (5).xlsx
35 | 29 | Wegenis | 2015-06-04 07:00 | 2015-07-15 16:00 | 30d |  | 0 | 20580.4004 | 135 | 32400 | 52980.4004 | 2015-06-08 07:00 | 30d | 52980.4004 | 0 | 0 | 0 | 0 | 52980.4004 | 0 | 1 | Finished | 52980.4004 | 52980.4004 | C2016-05 Railway Bridge (5).xlsx
36 | 30 | Metselwerk fase 1 | 2015-04-16 07:00 | 2015-05-06 16:00 | 15d |  | 0 | 1160.59 | 50 | 6000 | 7160.59 | 2015-04-20 07:00 | 15d | 7160.59 | 0 | 0 | 0 | 0 | 7160.59 | 0 | 1 | Finished | 7160.59 | 7160.59 | C2016-05 Railway Bridge (5).xlsx
37 | 31 | Metselwerk fase 2 | 2015-05-07 07:00 | 2015-05-27 16:00 | 15d |  | 0 | 2281.21 | 50 | 6000 | 8281.21 | 2015-05-11 07:00 | 15d | 8281.21 | 0 | 0 | 0 | 0 | 8281.21 | 0 | 1 | Finished | 8281.21 | 8281.21 | C2016-05 Railway Bridge (5).xlsx
38 | 32 | Afwerkingen | 2015-07-16 07:00 | 2015-08-12 16:00 | 20d |  | 0 | 41142.3516 | 195 | 31200 | 72342.3516 | 2015-07-20 07:00 | 20d | 72342.3516 | 0 | 0 | 0 | 0 | 72342.3516 | 0 | 1 | Finished | 72342.3516 | 72342.3516 | C2016-05 Railway Bridge (5).xlsx
4 | 0 | Defense Building | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 |  | 232d | [5 empty] | 4331260.4859 |  | 1 |  | 4331260.4859 | 4331260.4859 | C2016-06 Defense Building.xlsx
5 | 1 | Plaatsbeschrijving | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 | 2014-02-17 08:00 | 1d | 935 | 0 | 0 | 0 | 0 | 935 | 0 | 1 | Finished | 935 | 935 | C2016-06 Defense Building.xlsx
6 | 2 | Opstellen URS | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 | 2014-02-17 08:00 | 5d | 2937 | 0 | 0 | 0 | 0 | 2937 | 0 | 1 | Finished | 2937 | 2937 | C2016-06 Defense Building.xlsx
7 | 3 | Werfinrichting / stofwanden | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 | 2014-02-18 08:00 | 10d | 2435.05 | 0 | 0 | 0 | 0 | 2435.05 | 0 | 1 | Finished | 2435.05 | 2435.05 | C2016-06 Defense Building.xlsx
8 | 4 | Risk Assessment | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 | 2014-02-24 08:00 | 5d | 4928 | 0 | 0 | 0 | 0 | 4928 | 0 | 1 | Finished | 4928 | 4928 | C2016-06 Defense Building.xlsx
9 | 5 | Uitzetten van de werf | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 | 2014-02-24 08:00 | 6d | 8937 | 0 | 0 | 0 | 0 | 8937 | 0 | 1 | Finished | 8937 | 8937 | C2016-06 Defense Building.xlsx
10 | 6 | Validation Master Plan | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 | 2014-03-03 08:00 | 80d | 199353.2734 | 0 | 0 | 0 | 0 | 199353.2734 | 0 | 1 | Finished | 199353.2734 | 199353.2734 | C2016-06 Defense Building.xlsx
11 | 7 | Metselwerken / Betonwerken | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 | 2014-03-04 08:00 | 19d | 51444.7695 | 0 | 0 | 0 | 0 | 51444.7695 | 0 | 1 | Finished | 51444.7695 | 51444.7695 | C2016-06 Defense Building.xlsx
12 | 8 | Voorbereiding technieken | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 | 2014-03-04 08:00 | 27d | 18357 | 0 | 0 | 0 | 0 | 18357 | 0 | 1 | Finished | 18357 | 18357 | C2016-06 Defense Building.xlsx
13 | 9 | Voeding werfzone | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 | 2014-02-17 08:00 | 1d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2016-06 Defense Building.xlsx
14 | 10 | Plaatsen afvoeren | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-04-07 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 1 | Finished | 31746.2207 | 31746.2207 | C2016-06 Defense Building.xlsx
15 | 11 | Afbraak en/of omleggen bestaand bord | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 | 2014-03-06 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2016-06 Defense Building.xlsx
16 | 12 | Groepen plaatsen | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 | 2014-05-20 08:00 | 10d | 455069 | 0 | 0 | 0 | 0 | 455069 | 0 | 1 | Finished | 455069 | 455069 | C2016-06 Defense Building.xlsx
17 | 13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-03-19 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 1 | Finished | 31746.2207 | 31746.2207 | C2016-06 Defense Building.xlsx
18 | 14 | Kanalen | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 | 2014-03-17 08:00 | 20d | 285454.1875 | 0 | 0 | 0 | 0 | 285454.1875 | 0 | 1 | Finished | 285454.1875 | 285454.1875 | C2016-06 Defense Building.xlsx
19 | 15 | Plaatsen waterinstallatie in Techn Ruimte | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 | 2014-04-29 08:00 | 20d | 32234.1797 | 0 | 0 | 0 | 0 | 32234.1797 | 0 | 1 | Finished | 32234.1797 | 32234.1797 | C2016-06 Defense Building.xlsx
20 | 17 | Pleisterwerken | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 | 2014-03-31 08:00 | 15d | 18854.4697 | 0 | 0 | 0 | 0 | 18854.4697 | 0 | 1 | Finished | 18854.4697 | 18854.4697 | C2016-06 Defense Building.xlsx
21 | 18 | Plaatsen nieuwe centrale op niv -2 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 | 2014-03-31 08:00 | 5d | 12002.4004 | 0 | 0 | 0 | 0 | 12002.4004 | 0 | 1 | Finished | 12002.4004 | 12002.4004 | C2016-06 Defense Building.xlsx
22 | 16 | plaatsen stalen poutrellen ter versteviging | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 | 2014-03-17 08:00 | 2d | 21629.5098 | 0 | 0 | 0 | 0 | 21629.5098 | 0 | 1 | Finished | 21629.5098 | 21629.5098 | C2016-06 Defense Building.xlsx
23 | 19 | demonteren plafonds niv 0 | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 | 2014-03-31 08:00 | 3d | 3008 | 0 | 0 | 0 | 0 | 3008 | 0 | 1 | Finished | 3008 | 3008 | C2016-06 Defense Building.xlsx
24 | 20 | maken doorvoeren niv +1 -> gvl | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 | 2014-04-03 08:00 | 5d | 6670.9399 | 0 | 0 | 0 | 0 | 6670.9399 | 0 | 1 | Finished | 6670.9399 | 6670.9399 | C2016-06 Defense Building.xlsx
25 | 21 | Kabels naar bord verd -2 | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 | 2014-04-03 08:00 | 4d | 7207 | 0 | 0 | 0 | 0 | 7207 | 0 | 1 | Finished | 7207 | 7207 | C2016-06 Defense Building.xlsx
26 | 22 | Plaatsen toevoerleidingen + isolatie | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 | 2014-03-11 08:00 | 30d | 31746.2197 | 0 | 0 | 0 | 0 | 31746.2197 | 0 | 1 | Finished | 31746.2197 | 31746.2197 | C2016-06 Defense Building.xlsx
27 | 23 | Plaatsen leidingen | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 | 2014-03-11 08:00 | 31d | 17246.05 | 0 | 0 | 0 | 0 | 17246.05 | 0 | 1 | Finished | 17246.05 | 17246.05 | C2016-06 Defense Building.xlsx
28 | 24 | plaatsen afvoeren en aansluiten op niv 0 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 | 2014-04-10 08:00 | 20d | 5540.9199 | 0 | 0 | 0 | 0 | 5540.9199 | 0 | 1 | Finished | 5540.9199 | 5540.9199 | C2016-06 Defense Building.xlsx
29 | 25 | Maken doorvoeren dak -> niv +1 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 | 2014-04-10 08:00 | 2d | 11485.7998 | 0 | 0 | 0 | 0 | 11485.7998 | 0 | 1 | Finished | 11485.7998 | 11485.7998 | C2016-06 Defense Building.xlsx
30 | 26 | Aanpassingswerken dak | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 | 2014-04-22 08:00 | 5d | 1885.11 | 0 | 0 | 0 | 0 | 1885.11 | 0 | 1 | Finished | 1885.11 | 1885.11 | C2016-06 Defense Building.xlsx
31 | 27 | Chape | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 | 2014-04-29 08:00 | 5d | 30266.6895 | 0 | 0 | 0 | 0 | 30266.6895 | 0 | 1 | Finished | 30266.6895 | 30266.6895 | C2016-06 Defense Building.xlsx
32 | 28 | Piping | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 | 2014-05-08 08:00 | 30d | 92974.5781 | 0 | 0 | 0 | 0 | 92974.5781 | 0 | 1 | Finished | 92974.5781 | 92974.5781 | C2016-06 Defense Building.xlsx
33 | 29 | Bekabeling | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 | 2014-05-08 08:00 | 30d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 1 | Finished | 20000 | 20000 | C2016-06 Defense Building.xlsx
34 | 30 | Kabelgoten | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 | 2014-03-10 08:00 | 11d | 8577.6101 | 0 | 0 | 0 | 0 | 8577.6101 | 0 | 1 | Finished | 8577.6101 | 8577.6101 | C2016-06 Defense Building.xlsx
35 | 31 | Plaatsen leidingen | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 | 2014-05-08 08:00 | 11d | 27983.5 | 0 | 0 | 0 | 0 | 27983.5 | 0 | 1 | Finished | 27983.5 | 27983.5 | C2016-06 Defense Building.xlsx
36 | 32 | gipskartonwanden 1e zijde | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 | 2014-06-16 08:00 | 13d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 1 | Finished | 48507.7617 | 48507.7617 | C2016-06 Defense Building.xlsx
37 | 33 | dichtleggen plafond niv 0 | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 | 2014-05-20 08:00 | 1d | 2876 | 0 | 0 | 0 | 0 | 2876 | 0 | 1 | Finished | 2876 | 2876 | C2016-06 Defense Building.xlsx
38 | 34 | Alu buitenramen / roosters | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 | 2014-06-30 08:00 | 7d | 40211.3281 | 0 | 0 | 0 | 0 | 40211.3281 | 0 | 1 | Finished | 40211.3281 | 40211.3281 | C2016-06 Defense Building.xlsx
39 | 35 | Technieken in gipswanden | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 | 2014-07-07 08:00 | 14d | 34640 | 0 | 0 | 0 | 0 | 34640 | 0 | 1 | Finished | 34640 | 34640 | C2016-06 Defense Building.xlsx
40 | 36 | Leidingen trekken + inbouwbakjes | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 | 2014-05-08 08:00 | 19d | 44692.6992 | 0 | 0 | 0 | 0 | 44692.6992 | 0 | 1 | Finished | 44692.6992 | 44692.6992 | C2016-06 Defense Building.xlsx
41 | 37 | Plaatsen brandleiding + koppelingen | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 | 2014-04-30 08:00 | 10d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 1 | Finished | 31746.2207 | 31746.2207 | C2016-06 Defense Building.xlsx
42 | 38 | structuur voorzetwanden | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 | 2014-06-27 08:00 | 4d | 18409.8799 | 0 | 0 | 0 | 0 | 18409.8799 | 0 | 1 | Finished | 18409.8799 | 18409.8799 | C2016-06 Defense Building.xlsx
43 | 39 | Beglaasde binnenramen | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 | 2014-08-08 08:00 | 5d | 30766.0508 | 0 | 0 | 0 | 0 | 30766.0508 | 0 | 1 | Finished | 30766.0508 | 30766.0508 | C2016-06 Defense Building.xlsx
44 | 40 | Buitenzonnewering | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 | 2014-09-08 08:00 | 4d | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 1 | Finished | 4000 | 4000 | C2016-06 Defense Building.xlsx
45 | 41 | gipskartonwanden 2e zijde, incl plamuren | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-07-07 08:00 | 15d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 1 | Finished | 48507.7617 | 48507.7617 | C2016-06 Defense Building.xlsx
46 | 42 | Afmonteren data aansluitingen | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 | 2014-07-07 08:00 | 12d | 14837 | 0 | 0 | 0 | 0 | 14837 | 0 | 1 | Finished | 14837 | 14837 | C2016-06 Defense Building.xlsx
47 | 43 | Plaatsen leidingen branddetectie | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 | 2014-07-07 08:00 | 9d | 2908.17 | 0 | 0 | 0 | 0 | 2908.17 | 0 | 1 | Finished | 2908.17 | 2908.17 | C2016-06 Defense Building.xlsx
48 | 44 | Technieken boven valse plafonds | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 | 2014-08-07 08:00 | 20d | 14283 | 0 | 0 | 0 | 0 | 14283 | 0 | 1 | Finished | 14283 | 14283 | C2016-06 Defense Building.xlsx
49 | 45 | Dichtzetten voorzetwanden | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 | 2014-08-08 08:00 | 2d | 18409.8809 | 0 | 0 | 0 | 0 | 18409.8809 | 0 | 1 | Finished | 18409.8809 | 18409.8809 | C2016-06 Defense Building.xlsx
50 | 46 | Laufervloer | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 | 2014-03-17 08:00 | 2d | 1839.76 | 0 | 0 | 0 | 0 | 1839.76 | 0 | 1 | Finished | 1839.76 | 1839.76 | C2016-06 Defense Building.xlsx
51 | 47 | Afwerken dagkanten ramen | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 | 2014-08-12 08:00 | 5d | 17304 | 0 | 0 | 0 | 0 | 17304 | 0 | 1 | Finished | 17304 | 17304 | C2016-06 Defense Building.xlsx
52 | 48 | Hygienische coating Technische Ruimte | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 | 2014-05-13 08:00 | 5d | 5938 | 0 | 0 | 0 | 0 | 5938 | 0 | 1 | Finished | 5938 | 5938 | C2016-06 Defense Building.xlsx
53 | 49 | Wandbekleding binnenzijde gevel | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 | 2014-09-10 08:00 | 4d | 31558.2598 | 0 | 0 | 0 | 0 | 31558.2598 | 0 | 1 | Finished | 31558.2598 | 31558.2598 | C2016-06 Defense Building.xlsx
54 | 50 | Bekleden cleanroomwanden | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-08-26 08:00 | 15d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 1 | Finished | 48507.7617 | 48507.7617 | C2016-06 Defense Building.xlsx
55 | 51 | Plaatsen metalen deuromlijstingen | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 | 2014-08-25 08:00 | 4d | 254308.8125 | 0 | 0 | 0 | 0 | 254308.8125 | 0 | 1 | Finished | 254308.8125 | 254308.8125 | C2016-06 Defense Building.xlsx
56 | 52 | Beloopbaar verlaagd plafond Cleanroom | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 | 2014-06-02 08:00 | 15d | 6840 | 0 | 0 | 0 | 0 | 6840 | 0 | 1 | Finished | 6840 | 6840 | C2016-06 Defense Building.xlsx
57 | 53 | Plaatsen schakelaars, stopcontacten | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 | 2014-09-05 08:00 | 19d | 95912.8516 | 0 | 0 | 0 | 0 | 95912.8516 | 0 | 1 | Finished | 95912.8516 | 95912.8516 | C2016-06 Defense Building.xlsx
58 | 54 | Verlaagde plafonds | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 | 2014-10-28 08:00 | 4d | 224091.6562 | 0 | 0 | 0 | 0 | 224091.6562 | 0 | 1 | Finished | 224091.6562 | 224091.6562 | C2016-06 Defense Building.xlsx
59 | 55 | Plaatsen verlichtingsarmaturen | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 | 2014-09-11 08:00 | 27d | 5972.36 | 0 | 0 | 0 | 0 | 5972.36 | 0 | 1 | Finished | 5972.36 | 5972.36 | C2016-06 Defense Building.xlsx
60 | 56 | Plaatsen elektr borden | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 | 2014-09-11 08:00 | 3d | 15887.0703 | 0 | 0 | 0 | 0 | 15887.0703 | 0 | 1 | Finished | 15887.0703 | 15887.0703 | C2016-06 Defense Building.xlsx
61 | 57 | Aansluiten elektr bord | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 | 2014-09-12 08:00 | 15d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2016-06 Defense Building.xlsx
62 | 58 | Plaatsen kranenwerk, toestellen | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 | 2014-09-12 08:00 | 15d | 15905.8198 | 0 | 0 | 0 | 0 | 15905.8198 | 0 | 1 | Finished | 15905.8198 | 15905.8198 | C2016-06 Defense Building.xlsx
63 | 59 | Afwerking | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 | 2014-09-12 08:00 | 10d | 3924.88 | 0 | 0 | 0 | 0 | 3924.88 | 0 | 1 | Finished | 3924.88 | 3924.88 | C2016-06 Defense Building.xlsx
64 | 60 | Afgewerkte cleanroomwanden | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-09-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-06 Defense Building.xlsx
65 | 61 | Schilderwerken | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 | 2014-11-03 08:00 | 13d | 31979.1992 | 0 | 0 | 0 | 0 | 31979.1992 | 0 | 1 | Finished | 31979.1992 | 31979.1992 | C2016-06 Defense Building.xlsx
66 | 62 | Plaatsen sokkels meubilair | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 | 2014-08-25 08:00 | 3d | 2843 | 0 | 0 | 0 | 0 | 2843 | 0 | 1 | Finished | 2843 | 2843 | C2016-06 Defense Building.xlsx
67 | 63 | Elektronische borden | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 | 2014-09-16 08:00 | 3d | 218919.3594 | 0 | 0 | 0 | 0 | 218919.3594 | 0 | 1 | Finished | 218919.3594 | 218919.3594 | C2016-06 Defense Building.xlsx
68 | 64 | Testen deel 1 | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 | 2014-09-26 08:00 | 5d | 8293.3301 | 0 | 0 | 0 | 0 | 8293.3301 | 0 | 1 | Finished | 8293.3301 | 8293.3301 | C2016-06 Defense Building.xlsx
69 | 65 | Harsgebonden bedrijfsvloer | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 | 2014-09-22 08:00 | 10d | 99209.5 | 0 | 0 | 0 | 0 | 99209.5 | 0 | 1 | Finished | 99209.5 | 99209.5 | C2016-06 Defense Building.xlsx
70 | 66 | Synthetische vinyl vloerbekleding, incl plinten | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 | 2014-10-31 08:00 | 2d | 11064.3398 | 0 | 0 | 0 | 0 | 11064.3398 | 0 | 1 | Finished | 11064.3398 | 11064.3398 | C2016-06 Defense Building.xlsx
71 | 67 | Meubilair | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 | 2014-10-06 08:00 | 14d | 63322.1602 | 0 | 0 | 0 | 0 | 63322.1602 | 0 | 1 | Finished | 63322.1602 | 63322.1602 | C2016-06 Defense Building.xlsx
72 | 68 | Plaatsen toestellen | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 | 2014-10-06 08:00 | 24d | 588141.5 | 0 | 0 | 0 | 0 | 588141.5 | 0 | 1 | Finished | 588141.5 | 588141.5 | C2016-06 Defense Building.xlsx
73 | 69 | Data rack | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 | 2014-10-06 08:00 | 2d | 1717.6899 | 0 | 0 | 0 | 0 | 1717.6899 | 0 | 1 | Finished | 1717.6899 | 1717.6899 | C2016-06 Defense Building.xlsx
74 | 70 | Aansluiten data rack | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 | 2014-10-08 08:00 | 9d | 1717.69 | 0 | 0 | 0 | 0 | 1717.69 | 0 | 1 | Finished | 1717.69 | 1717.69 | C2016-06 Defense Building.xlsx
75 | 71 | Aansluiten toestellen | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 | 2014-10-17 08:00 | 15d | 196047.1719 | 0 | 0 | 0 | 0 | 196047.1719 | 0 | 1 | Finished | 196047.1719 | 196047.1719 | C2016-06 Defense Building.xlsx
76 | 72 | plaatsen sirenes, bord, brandmelders, … | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 | 2014-10-20 08:00 | 24d | 8716.96 | 0 | 0 | 0 | 0 | 8716.96 | 0 | 1 | Finished | 8716.96 | 8716.96 | C2016-06 Defense Building.xlsx
77 | 73 | Verbinding data en telefonie | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 | 2014-10-21 08:00 | 5d | 5206.42 | 0 | 0 | 0 | 0 | 5206.42 | 0 | 1 | Finished | 5206.42 | 5206.42 | C2016-06 Defense Building.xlsx
78 | 74 | Spiegel | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 | 2014-10-23 08:00 | 1d | 103.27 | 0 | 0 | 0 | 0 | 103.27 | 0 | 1 | Finished | 103.27 | 103.27 | C2016-06 Defense Building.xlsx
79 | 75 | Wand-en hoekbescherming | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 | 2014-10-24 08:00 | 5d | 12152.29 | 0 | 0 | 0 | 0 | 12152.29 | 0 | 1 | Finished | 12152.29 | 12152.29 | C2016-06 Defense Building.xlsx
80 | 76 | Algemene afwerkingen | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 | 2014-10-27 08:00 | 10d | 31206 | 0 | 0 | 0 | 0 | 31206 | 0 | 1 | Finished | 31206 | 31206 | C2016-06 Defense Building.xlsx
81 | 77 | Testen deel 2 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 | 2014-10-28 08:00 | 2d | 10312.7305 | 0 | 0 | 0 | 0 | 10312.7305 | 0 | 1 | Finished | 10312.7305 | 10312.7305 | C2016-06 Defense Building.xlsx
82 | 78 | Testen deel 3 | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 | 2014-10-28 08:00 | 1d | 37786.0117 | 0 | 0 | 0 | 0 | 37786.0117 | 0 | 1 | Finished | 37786.0117 | 37786.0117 | C2016-06 Defense Building.xlsx
83 | 79 | Keuringen en testen installatie | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 | 2014-11-17 08:00 | 14d | 8840 | 0 | 0 | 0 | 0 | 8840 | 0 | 1 | Finished | 8840 | 8840 | C2016-06 Defense Building.xlsx
84 | 80 | Testen deel 4 | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 | 2014-11-07 08:00 | 5d | 196047.1719 | 0 | 0 | 0 | 0 | 196047.1719 | 0 | 1 | Finished | 196047.1719 | 196047.1719 | C2016-06 Defense Building.xlsx
85 | 81 | Plaatsen tabletten | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 | 2014-09-15 08:00 | 5d | 9484 | 0 | 0 | 0 | 0 | 9484 | 0 | 1 | Finished | 9484 | 9484 | C2016-06 Defense Building.xlsx
86 | 82 | Signalisatie | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 | 2014-11-24 08:00 | 5d | 63074.5391 | 0 | 0 | 0 | 0 | 63074.5391 | 0 | 1 | Finished | 63074.5391 | 63074.5391 | C2016-06 Defense Building.xlsx
87 | 83 | Eerste Rondgang der werken | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 | 2014-11-24 08:00 | 5d | 2954 | 0 | 0 | 0 | 0 | 2954 | 0 | 1 | Finished | 2954 | 2954 | C2016-06 Defense Building.xlsx
88 | 84 | Eindschoonmaak | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 | 2014-11-24 08:00 | 5d | 3948 | 0 | 0 | 0 | 0 | 3948 | 0 | 1 | Finished | 3948 | 3948 | C2016-06 Defense Building.xlsx
89 | 85 | Wegwerken eventuele opmerkingen | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 | 2014-12-01 08:00 | 8d | 4207 | 0 | 0 | 0 | 0 | 4207 | 0 | 1 | Finished | 4207 | 4207 | C2016-06 Defense Building.xlsx
90 | 86 | Filters plaatsen + afwerking | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 | 2015-01-12 08:00 | 10d | 49453.4688 | 0 | 0 | 0 | 0 | 49453.4688 | 0 | 1 | Finished | 49453.4688 | 49453.4688 | C2016-06 Defense Building.xlsx
91 | 87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 | 2014-10-17 08:00 | 10d | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 1 | Finished | 4000 | 4000 | C2016-06 Defense Building.xlsx
92 | 88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-11 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 1 | Finished | 14240 | 14240 | C2016-06 Defense Building.xlsx
93 | 89 | Start validation | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-12-11 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-06 Defense Building.xlsx
94 | 90 | Verwijderen werfinrichting | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 | 2014-12-11 08:00 | 5d | 3048 | 0 | 0 | 0 | 0 | 3048 | 0 | 1 | Finished | 3048 | 3048 | C2016-06 Defense Building.xlsx
95 | 91 | Plaatsen deurbladen | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 | 2014-10-06 08:00 | 1d | 593 | 0 | 0 | 0 | 0 | 593 | 0 | 1 | Finished | 593 | 593 | C2016-06 Defense Building.xlsx
96 | 92 | Certificatietesten Cleanroom & HVAC | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-18 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 1 | Finished | 14240 | 14240 | C2016-06 Defense Building.xlsx
97 | 93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 | 2015-01-08 08:00 | 10d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 1 | Finished | 14240 | 14240 | C2016-06 Defense Building.xlsx
98 | 94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-11 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 1 | Finished | 14240 | 14240 | C2016-06 Defense Building.xlsx
99 | 95 | Nakijken van uitgevoerde testen door uitvoerders | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2015-01-08 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 1 | Finished | 14240 | 14240 | C2016-06 Defense Building.xlsx
100 | 96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-01 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 1 | Finished | 14240 | 14240 | C2016-06 Defense Building.xlsx
101 | 97 | Ondersteuning ontwikkeling SOP's | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 | 2015-01-12 08:00 | 20d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 1 | Finished | 14240 | 14240 | C2016-06 Defense Building.xlsx
102 | 98 | Verwijderen werfburelen | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 | 2015-02-09 08:00 | 5d | 1750 | 0 | 0 | 0 | 0 | 1750 | 0 | 1 | Finished | 1750 | 1750 | C2016-06 Defense Building.xlsx
4 | 0 | Shopping Village Walkways | 2014-05-09 08:00 | 2014-12-19 09:00 | 224d 1h |  |  | 899439.4919 |  |  | 930179.0931 |  | 316d | [5 empty] | 932757.2532 |  | 1 |  | 930179.0931 | 930179.0931 | C2016-07 Shopping Village Walkways.xlsx
5 | 123 | Site accomodation | 2014-05-09 08:00 | 2014-12-12 17:00 | 218d |  |  | 2750 |  |  | 33489.6011 |  | 316d | [5 empty] | 36067.7612 |  | 1 |  | 33489.6011 | 33489.6011 | C2016-07 Shopping Village Walkways.xlsx
6 | 3 | Assembly | 2014-05-09 08:00 | 2014-05-10 17:00 | 2d |  | 0 | 1375 | 0 | 0 | 1375 | 2014-05-09 08:00 | 2d | 1375 | 0 | 0 | 0 | 0 | 1375 | 0 | 1 | Finished | 1375 | 1375 | C2016-07 Shopping Village Walkways.xlsx
7 | 4 | Rent | 2014-05-09 08:00 | 2014-10-10 17:00 | 155d |  | 0 | 0 | 24.79 | 30739.6011 | 30739.6011 | 2014-05-09 08:00 | 168d | 33317.7612 | 0 | 0 | 0 | 0 | 33317.7612 | 0 | 1 | Finished | 30739.6011 | 30739.6011 | C2016-07 Shopping Village Walkways.xlsx
8 | 5 | Take-down | 2014-12-12 08:00 | 2014-12-12 17:00 | 1d |  | 0 | 1375 | 0 | 0 | 1375 | 2015-03-20 08:00 | 1d | 1375 | 0 | 0 | 0 | 0 | 1375 | 0 | 1 | Finished | 1375 | 1375 | C2016-07 Shopping Village Walkways.xlsx
9 | 136 | Paving | 2014-05-26 08:00 | 2014-11-03 17:00 | 162d |  |  | 896688.4919 |  |  | 896688.4919 |  | 277d | [5 empty] | 896688.4919 |  | 1 |  | 896688.4919 | 896688.4919 | C2016-07 Shopping Village Walkways.xlsx
10 | 124 | Zone A | 2014-05-26 08:00 | 2014-06-20 17:00 | 26d |  |  | 64688.7197 |  |  | 64688.7197 |  | 24d | [5 empty] | 64688.7197 |  | 1 |  | 64688.7197 | 64688.7197 | C2016-07 Shopping Village Walkways.xlsx
11 | 8 | Section 1 | 2014-05-26 08:00 | 2014-06-02 17:00 | 8d |  | 0 | 8639.0596 | 0 | 0 | 8639.0596 | 2014-05-27 08:00 | 8d | 8639.0596 | 0 | 0 | 0 | 0 | 8639.0596 | 0 | 1 | Finished | 8639.0596 | 8639.0596 | C2016-07 Shopping Village Walkways.xlsx
12 | 9 | Section 2 | 2014-05-27 08:00 | 2014-06-06 17:00 | 11d |  | 0 | 11899.3701 | 0 | 0 | 11899.3701 | 2014-05-28 08:00 | 10d | 11899.3701 | 0 | 0 | 0 | 0 | 11899.3701 | 0 | 1 | Finished | 11899.3701 | 11899.3701 | C2016-07 Shopping Village Walkways.xlsx
13 | 10 | Section 3 | 2014-05-28 08:00 | 2014-06-10 17:00 | 14d |  | 0 | 6690.3301 | 0 | 0 | 6690.3301 | 2014-05-29 08:00 | 12d | 6690.3301 | 0 | 0 | 0 | 0 | 6690.3301 | 0 | 1 | Finished | 6690.3301 | 6690.3301 | C2016-07 Shopping Village Walkways.xlsx
14 | 11 | Section 4 | 2014-06-04 08:00 | 2014-06-12 17:00 | 9d |  | 0 | 7679.1699 | 0 | 0 | 7679.1699 | 2014-06-05 08:00 | 8d | 7679.1699 | 0 | 0 | 0 | 0 | 7679.1699 | 0 | 1 | Finished | 7679.1699 | 7679.1699 | C2016-07 Shopping Village Walkways.xlsx
15 | 12 | Section 5 | 2014-06-05 08:00 | 2014-06-12 17:00 | 8d |  | 0 | 11229.5996 | 0 | 0 | 11229.5996 | 2014-06-06 08:00 | 11d | 11229.5996 | 0 | 0 | 0 | 0 | 11229.5996 | 0 | 1 | Finished | 11229.5996 | 11229.5996 | C2016-07 Shopping Village Walkways.xlsx
16 | 13 | Section 6 | 2014-06-06 08:00 | 2014-06-12 17:00 | 7d |  | 0 | 9743.5303 | 0 | 0 | 9743.5303 | 2014-06-10 08:00 | 8d | 9743.5303 | 0 | 0 | 0 | 0 | 9743.5303 | 0 | 1 | Finished | 9743.5303 | 9743.5303 | C2016-07 Shopping Village Walkways.xlsx
17 | 14 | Section 7 | 2014-06-09 08:00 | 2014-06-20 17:00 | 12d |  | 0 | 8807.6602 | 0 | 0 | 8807.6602 | 2014-06-11 08:00 | 9d | 8807.6602 | 0 | 0 | 0 | 0 | 8807.6602 | 0 | 1 | Finished | 8807.6602 | 8807.6602 | C2016-07 Shopping Village Walkways.xlsx
18 | 125 | Zone B | 2014-06-10 08:00 | 2014-07-03 17:00 | 24d |  |  | 92142.5786 |  |  | 92142.5786 |  | 81d | [5 empty] | 92142.5786 |  | 1 |  | 92142.5786 | 92142.5786 | C2016-07 Shopping Village Walkways.xlsx
19 | 16 | Section 8 | 2014-06-10 08:00 | 2014-06-20 17:00 | 11d |  | 0 | 8649.04 | 0 | 0 | 8649.04 | 2014-06-05 08:00 | 8d | 8649.04 | 0 | 0 | 0 | 0 | 8649.04 | 0 | 1 | Finished | 8649.04 | 8649.04 | C2016-07 Shopping Village Walkways.xlsx
20 | 17 | Section 9 | 2014-06-11 08:00 | 2014-06-17 17:00 | 7d |  | 0 | 11800.8799 | 0 | 0 | 11800.8799 | 2014-06-09 08:00 | 8d | 11800.8799 | 0 | 0 | 0 | 0 | 11800.8799 | 0 | 1 | Finished | 11800.8799 | 11800.8799 | C2016-07 Shopping Village Walkways.xlsx
21 | 18 | Section 10 | 2014-06-12 08:00 | 2014-06-18 17:00 | 7d |  | 0 | 7824.8701 | 0 | 0 | 7824.8701 | 2014-06-25 08:00 | 7d | 7824.8701 | 0 | 0 | 0 | 0 | 7824.8701 | 0 | 1 | Finished | 7824.8701 | 7824.8701 | C2016-07 Shopping Village Walkways.xlsx
22 | 19 | Section 11 | 2014-06-13 08:00 | 2014-06-21 17:00 | 9d |  | 0 | 8996.3604 | 0 | 0 | 8996.3604 | 2014-06-26 08:00 | 8d | 8996.3604 | 0 | 0 | 0 | 0 | 8996.3604 | 0 | 1 | Finished | 8996.3604 | 8996.3604 | C2016-07 Shopping Village Walkways.xlsx
23 | 20 | Section 12 | 2014-06-16 08:00 | 2014-06-26 17:00 | 11d |  | 0 | 8319.8496 | 0 | 0 | 8319.8496 | 2014-06-27 08:00 | 11d | 8319.8496 | 0 | 0 | 0 | 0 | 8319.8496 | 0 | 1 | Finished | 8319.8496 | 8319.8496 | C2016-07 Shopping Village Walkways.xlsx
24 | 21 | Section 13 | 2014-06-17 08:00 | 2014-06-24 17:00 | 8d |  | 0 | 7415.3101 | 0 | 0 | 7415.3101 | 2014-06-30 08:00 | 8d | 7415.3101 | 0 | 0 | 0 | 0 | 7415.3101 | 0 | 1 | Finished | 7415.3101 | 7415.3101 | C2016-07 Shopping Village Walkways.xlsx
25 | 22 | Section 14 | 2014-06-18 08:00 | 2014-06-24 17:00 | 7d |  | 0 | 7915.21 | 0 | 0 | 7915.21 | 2014-07-01 08:00 | 7d | 7915.21 | 0 | 0 | 0 | 0 | 7915.21 | 0 | 1 | Finished | 7915.21 | 7915.21 | C2016-07 Shopping Village Walkways.xlsx
26 | 23 | Section 15 | 2014-06-19 08:00 | 2014-06-25 17:00 | 7d |  | 0 | 10407.0195 | 0 | 0 | 10407.0195 | 2014-08-18 08:00 | 7d | 10407.0195 | 0 | 0 | 0 | 0 | 10407.0195 | 0 | 1 | Finished | 10407.0195 | 10407.0195 | C2016-07 Shopping Village Walkways.xlsx
27 | 24 | Section 16 | 2014-06-20 08:00 | 2014-06-28 17:00 | 9d |  | 0 | 10407.0195 | 0 | 0 | 10407.0195 | 2014-07-07 08:00 | 8d | 10407.0195 | 0 | 0 | 0 | 0 | 10407.0195 | 0 | 1 | Finished | 10407.0195 | 10407.0195 | C2016-07 Shopping Village Walkways.xlsx
28 | 25 | Section 17 | 2014-06-23 08:00 | 2014-07-03 17:00 | 11d |  | 0 | 10407.0195 | 0 | 0 | 10407.0195 | 2014-07-03 08:00 | 7d | 10407.0195 | 0 | 0 | 0 | 0 | 10407.0195 | 0 | 1 | Finished | 10407.0195 | 10407.0195 | C2016-07 Shopping Village Walkways.xlsx
29 | 126 | Zone C | 2014-06-24 08:00 | 2014-07-25 17:00 | 32d |  |  | 71938.5303 |  |  | 71938.5303 |  | 16d | [5 empty] | 71938.5303 |  | 1 |  | 71938.5303 | 71938.5303 | C2016-07 Shopping Village Walkways.xlsx
30 | 27 | Section 18 | 2014-06-24 08:00 | 2014-07-01 17:00 | 8d |  | 0 | 8140.29 | 0 | 0 | 8140.29 | 2014-08-06 08:00 | 8d | 8140.29 | 0 | 0 | 0 | 0 | 8140.29 | 0 | 1 | Finished | 8140.29 | 8140.29 | C2016-07 Shopping Village Walkways.xlsx
31 | 28 | Section 19 | 2014-06-25 08:00 | 2014-07-01 17:00 | 7d |  | 0 | 7802.5298 | 0 | 0 | 7802.5298 | 2014-08-05 08:00 | 7d | 7802.5298 | 0 | 0 | 0 | 0 | 7802.5298 | 0 | 1 | Finished | 7802.5298 | 7802.5298 | C2016-07 Shopping Village Walkways.xlsx
32 | 29 | Section 20 | 2014-06-26 08:00 | 2014-07-02 17:00 | 7d |  | 0 | 7946.1201 | 0 | 0 | 7946.1201 | 2014-08-06 08:00 | 7d | 7946.1201 | 0 | 0 | 0 | 0 | 7946.1201 | 0 | 1 | Finished | 7946.1201 | 7946.1201 | C2016-07 Shopping Village Walkways.xlsx
33 | 30 | Section 21 | 2014-06-27 08:00 | 2014-07-05 17:00 | 9d |  | 0 | 8602.5303 | 0 | 0 | 8602.5303 | 2014-08-06 08:00 | 9d | 8602.5303 | 0 | 0 | 0 | 0 | 8602.5303 | 0 | 1 | Finished | 8602.5303 | 8602.5303 | C2016-07 Shopping Village Walkways.xlsx
34 | 31 | Section 22 | 2014-06-30 08:00 | 2014-07-10 17:00 | 11d |  | 0 | 6604.48 | 0 | 0 | 6604.48 | 2014-08-04 08:00 | 8d | 6604.48 | 0 | 0 | 0 | 0 | 6604.48 | 0 | 1 | Finished | 6604.48 | 6604.48 | C2016-07 Shopping Village Walkways.xlsx
35 | 32 | Section 31 | 2014-07-11 08:00 | 2014-07-19 17:00 | 9d |  | 0 | 8550.4102 | 0 | 0 | 8550.4102 | 2014-08-07 08:00 | 7d | 8550.4102 | 0 | 0 | 0 | 0 | 8550.4102 | 0 | 1 | Finished | 8550.4102 | 8550.4102 | C2016-07 Shopping Village Walkways.xlsx
36 | 33 | Section 32 | 2014-07-14 08:00 | 2014-07-25 17:00 | 12d |  | 0 | 7885.2798 | 0 | 0 | 7885.2798 | 2014-08-08 08:00 | 7d | 7885.2798 | 0 | 0 | 0 | 0 | 7885.2798 | 0 | 1 | Finished | 7885.2798 | 7885.2798 | C2016-07 Shopping Village Walkways.xlsx
37 | 34 | Section 33 | 2014-07-15 08:00 | 2014-07-23 17:00 | 9d |  | 0 | 8837.1699 | 0 | 0 | 8837.1699 | 2014-08-11 08:00 | 8d | 8837.1699 | 0 | 0 | 0 | 0 | 8837.1699 | 0 | 1 | Finished | 8837.1699 | 8837.1699 | C2016-07 Shopping Village Walkways.xlsx
38 | 35 | Section 34 | 2014-07-16 08:00 | 2014-07-23 17:00 | 8d |  | 0 | 7569.7202 | 0 | 0 | 7569.7202 | 2014-08-12 08:00 | 8d | 7569.7202 | 0 | 0 | 0 | 0 | 7569.7202 | 0 | 1 | Finished | 7569.7202 | 7569.7202 | C2016-07 Shopping Village Walkways.xlsx
39 | 127 | Zone D | 2014-07-01 08:00 | 2014-08-12 17:00 | 43d |  |  | 127431.4019 |  |  | 127431.4019 |  | 41d | [5 empty] | 127431.4019 |  | 1 |  | 127431.4019 | 127431.4019 | C2016-07 Shopping Village Walkways.xlsx
40 | 37 | Section 23 | 2014-07-01 08:00 | 2014-07-08 17:00 | 8d |  | 0 | 13043.3203 | 0 | 0 | 13043.3203 | 2014-08-13 08:00 | 8d | 13043.3203 | 0 | 0 | 0 | 0 | 13043.3203 | 0 | 1 | Finished | 13043.3203 | 13043.3203 | C2016-07 Shopping Village Walkways.xlsx
41 | 38 | Section 24 | 2014-07-02 08:00 | 2014-07-08 17:00 | 7d |  | 0 | 11397.0801 | 0 | 0 | 11397.0801 | 2014-08-14 08:00 | 7d | 11397.0801 | 0 | 0 | 0 | 0 | 11397.0801 | 0 | 1 | Finished | 11397.0801 | 11397.0801 | C2016-07 Shopping Village Walkways.xlsx
42 | 39 | Section 35 | 2014-07-17 08:00 | 2014-07-23 17:00 | 7d |  | 0 | 7824.73 | 0 | 0 | 7824.73 | 2014-08-18 08:00 | 7d | 7824.73 | 0 | 0 | 0 | 0 | 7824.73 | 0 | 1 | Finished | 7824.73 | 7824.73 | C2016-07 Shopping Village Walkways.xlsx
43 | 40 | Section 36 | 2014-07-18 08:00 | 2014-07-29 17:00 | 12d |  | 0 | 8558.5596 | 0 | 0 | 8558.5596 | 2014-08-19 08:00 | 7d | 8558.5596 | 0 | 0 | 0 | 0 | 8558.5596 | 0 | 1 | Finished | 8558.5596 | 8558.5596 | C2016-07 Shopping Village Walkways.xlsx
44 | 41 | Section 37 | 2014-07-21 08:00 | 2014-07-31 17:00 | 11d |  | 0 | 7304.2402 | 0 | 0 | 7304.2402 | 2014-08-20 08:00 | 7d | 7304.2402 | 0 | 0 | 0 | 0 | 7304.2402 | 0 | 1 | Finished | 7304.2402 | 7304.2402 | C2016-07 Shopping Village Walkways.xlsx
45 | 42 | Section 38 | 2014-07-22 08:00 | 2014-07-28 17:00 | 7d |  | 0 | 7304.2402 | 0 | 0 | 7304.2402 | 2014-08-21 08:00 | 7d | 7304.2402 | 0 | 0 | 0 | 0 | 7304.2402 | 0 | 1 | Finished | 7304.2402 | 7304.2402 | C2016-07 Shopping Village Walkways.xlsx
46 | 43 | Section 39 | 2014-07-23 08:00 | 2014-07-29 17:00 | 7d |  | 0 | 9134.0498 | 0 | 0 | 9134.0498 | 2014-08-22 08:00 | 7d | 9134.0498 | 0 | 0 | 0 | 0 | 9134.0498 | 0 | 1 | Finished | 9134.0498 | 9134.0498 | C2016-07 Shopping Village Walkways.xlsx
47 | 44 | Section 40 | 2014-07-24 08:00 | 2014-08-01 17:00 | 9d |  | 0 | 8557.8604 | 0 | 0 | 8557.8604 | 2014-08-25 08:00 | 8d | 8557.8604 | 0 | 0 | 0 | 0 | 8557.8604 | 0 | 1 | Finished | 8557.8604 | 8557.8604 | C2016-07 Shopping Village Walkways.xlsx
48 | 45 | Section 41 | 2014-07-25 08:00 | 2014-08-04 17:00 | 11d |  | 0 | 8763.9697 | 0 | 0 | 8763.9697 | 2014-08-26 08:00 | 7d | 8763.9697 | 0 | 0 | 0 | 0 | 8763.9697 | 0 | 1 | Finished | 8763.9697 | 8763.9697 | C2016-07 Shopping Village Walkways.xlsx
49 | 46 | Section 42 | 2014-07-28 08:00 | 2014-08-04 17:00 | 8d |  | 0 | 8557.1504 | 0 | 0 | 8557.1504 | 2014-08-27 08:00 | 7d | 8557.1504 | 0 | 0 | 0 | 0 | 8557.1504 | 0 | 1 | Finished | 8557.1504 | 8557.1504 | C2016-07 Shopping Village Walkways.xlsx
50 | 47 | Section 43 | 2014-07-29 08:00 | 2014-08-04 17:00 | 7d |  | 0 | 9295.4805 | 0 | 0 | 9295.4805 | 2014-09-11 08:00 | 7d | 9295.4805 | 0 | 0 | 0 | 0 | 9295.4805 | 0 | 1 | Finished | 9295.4805 | 9295.4805 | C2016-07 Shopping Village Walkways.xlsx
51 | 48 | Section 45 | 2014-07-31 08:00 | 2014-08-08 17:00 | 9d |  | 0 | 9085.9902 | 0 | 0 | 9085.9902 | 2014-08-28 08:00 | 7d | 9085.9902 | 0 | 0 | 0 | 0 | 9085.9902 | 0 | 1 | Finished | 9085.9902 | 9085.9902 | C2016-07 Shopping Village Walkways.xlsx
52 | 49 | Section 47 | 2014-08-04 08:00 | 2014-08-11 17:00 | 8d |  | 0 | 7157.4902 | 0 | 0 | 7157.4902 | 2014-09-12 08:00 | 7d | 7157.4902 | 0 | 0 | 0 | 0 | 7157.4902 | 0 | 1 | Finished | 7157.4902 | 7157.4902 | C2016-07 Shopping Village Walkways.xlsx
53 | 50 | Section 49 | 2014-08-06 08:00 | 2014-08-12 17:00 | 7d |  | 0 | 11447.2402 | 0 | 0 | 11447.2402 | 2014-09-15 08:00 | 8d | 11447.2402 | 0 | 0 | 0 | 0 | 11447.2402 | 0 | 1 | Finished | 11447.2402 | 11447.2402 | C2016-07 Shopping Village Walkways.xlsx
54 | 128 | Zone E | 2014-09-29 08:00 | 2014-10-19 17:00 | 21d |  |  | 44850.5503 |  |  | 44850.5503 |  | 12d | [5 empty] | 44850.5503 |  | 1 |  | 44850.5503 | 44850.5503 | C2016-07 Shopping Village Walkways.xlsx
55 | 52 | Section 87 | 2014-09-29 08:00 | 2014-10-05 17:00 | 7d |  | 0 | 10208.0303 | 0 | 0 | 10208.0303 | 2015-02-02 08:00 | 8d | 10208.0303 | 0 | 0 | 0 | 0 | 10208.0303 | 0 | 1 | Finished | 10208.0303 | 10208.0303 | C2016-07 Shopping Village Walkways.xlsx
56 | 53 | Section 89 | 2014-10-01 08:00 | 2014-10-09 17:00 | 9d |  | 0 | 10007.6699 | 0 | 0 | 10007.6699 | 2015-02-03 08:00 | 8d | 10007.6699 | 0 | 0 | 0 | 0 | 10007.6699 | 0 | 1 | Finished | 10007.6699 | 10007.6699 | C2016-07 Shopping Village Walkways.xlsx
57 | 54 | Section 91 | 2014-10-03 08:00 | 2014-10-10 17:00 | 8d |  | 0 | 8399.3701 | 0 | 0 | 8399.3701 | 2015-02-04 08:00 | 8d | 8399.3701 | 0 | 0 | 0 | 0 | 8399.3701 | 0 | 1 | Finished | 8399.3701 | 8399.3701 | C2016-07 Shopping Village Walkways.xlsx
58 | 55 | Section 93 | 2014-10-07 08:00 | 2014-10-13 17:00 | 7d |  | 0 | 8388.4102 | 0 | 0 | 8388.4102 | 2015-02-05 08:00 | 7d | 8388.4102 | 0 | 0 | 0 | 0 | 8388.4102 | 0 | 1 | Finished | 8388.4102 | 8388.4102 | C2016-07 Shopping Village Walkways.xlsx
59 | 56 | Section 95 | 2014-10-09 08:00 | 2014-10-19 17:00 | 11d |  | 0 | 7847.0698 | 0 | 0 | 7847.0698 | 2015-02-06 08:00 | 8d | 7847.0698 | 0 | 0 | 0 | 0 | 7847.0698 | 0 | 1 | Finished | 7847.0698 | 7847.0698 | C2016-07 Shopping Village Walkways.xlsx
60 | 129 | Zone F | 2014-07-03 08:00 | 2014-11-03 17:00 | 124d |  |  | 58595.4004 |  |  | 58595.4004 |  | 161d | [5 empty] | 58595.4004 |  | 1 |  | 58595.4004 | 58595.4004 | C2016-07 Shopping Village Walkways.xlsx
61 | 58 | Section 25 | 2014-07-03 08:00 | 2014-07-09 17:00 | 7d |  | 0 | 8062.73 | 0 | 0 | 8062.73 | 2014-09-16 08:00 | 7d | 8062.73 | 0 | 0 | 0 | 0 | 8062.73 | 0 | 1 | Finished | 8062.73 | 8062.73 | C2016-07 Shopping Village Walkways.xlsx
62 | 59 | Section 26 | 2014-07-04 08:00 | 2014-07-12 17:00 | 9d |  | 0 | 8330.9502 | 0 | 0 | 8330.9502 | 2014-09-17 08:00 | 7d | 8330.9502 | 0 | 0 | 0 | 0 | 8330.9502 | 0 | 1 | Finished | 8330.9502 | 8330.9502 | C2016-07 Shopping Village Walkways.xlsx
63 | 60 | Section 101 | 2014-10-17 08:00 | 2014-10-24 17:00 | 8d |  | 0 | 6900.52 | 0 | 0 | 6900.52 | 2015-02-09 08:00 | 8d | 6900.52 | 0 | 0 | 0 | 0 | 6900.52 | 0 | 1 | Finished | 6900.52 | 6900.52 | C2016-07 Shopping Village Walkways.xlsx
64 | 61 | Section 102 | 2014-10-20 08:00 | 2014-10-26 17:00 | 7d |  | 0 | 8422.9805 | 0 | 0 | 8422.9805 | 2015-02-10 08:00 | 7d | 8422.9805 | 0 | 0 | 0 | 0 | 8422.9805 | 0 | 1 | Finished | 8422.9805 | 8422.9805 | C2016-07 Shopping Village Walkways.xlsx
65 | 62 | Section 103 | 2014-10-21 08:00 | 2014-10-27 17:00 | 7d |  | 0 | 9439.21 | 0 | 0 | 9439.21 | 2015-02-11 08:00 | 7d | 9439.21 | 0 | 0 | 0 | 0 | 9439.21 | 0 | 1 | Finished | 9439.21 | 9439.21 | C2016-07 Shopping Village Walkways.xlsx
66 | 63 | Section 104 | 2014-10-22 08:00 | 2014-10-30 17:00 | 9d |  | 0 | 8729.4102 | 0 | 0 | 8729.4102 | 2015-02-12 08:00 | 8d | 8729.4102 | 0 | 0 | 0 | 0 | 8729.4102 | 0 | 1 | Finished | 8729.4102 | 8729.4102 | C2016-07 Shopping Village Walkways.xlsx
67 | 64 | Section 105 | 2014-10-23 08:00 | 2014-11-03 17:00 | 12d |  | 0 | 4354.7998 | 0 | 0 | 4354.7998 | 2015-02-13 08:00 | 8d | 4354.7998 | 0 | 0 | 0 | 0 | 4354.7998 | 0 | 1 | Finished | 4354.7998 | 4354.7998 | C2016-07 Shopping Village Walkways.xlsx
68 | 65 | Section 106 | 2014-10-24 08:00 | 2014-11-01 17:00 | 9d |  | 0 | 4354.7998 | 0 | 0 | 4354.7998 | 2015-02-16 08:00 | 8d | 4354.7998 | 0 | 0 | 0 | 0 | 4354.7998 | 0 | 1 | Finished | 4354.7998 | 4354.7998 | C2016-07 Shopping Village Walkways.xlsx
69 | 130 | Zone G | 2014-08-11 08:00 | 2014-09-28 17:00 | 49d |  |  | 115484.4192 |  |  | 115484.4192 |  | 28d | [5 empty] | 115484.4192 |  | 1 |  | 115484.4192 | 115484.4192 | C2016-07 Shopping Village Walkways.xlsx
70 | 67 | Section 52 | 2014-08-11 08:00 | 2014-08-18 17:00 | 8d |  | 0 | 7377.0898 | 0 | 0 | 7377.0898 | 2014-09-18 08:00 | 8d | 7377.0898 | 0 | 0 | 0 | 0 | 7377.0898 | 0 | 1 | Finished | 7377.0898 | 7377.0898 | C2016-07 Shopping Village Walkways.xlsx
71 | 68 | Section 54 | 2014-08-13 08:00 | 2014-08-22 17:00 | 10d |  | 0 | 9227.7598 | 0 | 0 | 9227.7598 | 2014-09-19 08:00 | 8d | 9227.7598 | 0 | 0 | 0 | 0 | 9227.7598 | 0 | 1 | Finished | 9227.7598 | 9227.7598 | C2016-07 Shopping Village Walkways.xlsx
72 | 69 | Section 56 | 2014-08-15 08:00 | 2014-08-22 17:00 | 8d |  | 0 | 8120.3398 | 0 | 0 | 8120.3398 | 2014-09-22 08:00 | 8d | 8120.3398 | 0 | 0 | 0 | 0 | 8120.3398 | 0 | 1 | Finished | 8120.3398 | 8120.3398 | C2016-07 Shopping Village Walkways.xlsx
73 | 70 | Section 58 | 2014-08-19 08:00 | 2014-08-25 17:00 | 7d |  | 0 | 8108.3999 | 0 | 0 | 8108.3999 | 2014-09-23 08:00 | 7d | 8108.3999 | 0 | 0 | 0 | 0 | 8108.3999 | 0 | 1 | Finished | 8108.3999 | 8108.3999 | C2016-07 Shopping Village Walkways.xlsx
74 | 71 | Section 60 | 2014-08-21 08:00 | 2014-08-31 17:00 | 11d |  | 0 | 8639.9102 | 0 | 0 | 8639.9102 | 2014-09-24 08:00 | 8d | 8639.9102 | 0 | 0 | 0 | 0 | 8639.9102 | 0 | 1 | Finished | 8639.9102 | 8639.9102 | C2016-07 Shopping Village Walkways.xlsx
75 | 72 | Section 62 | 2014-08-25 08:00 | 2014-08-31 17:00 | 7d |  | 0 | 7642.0801 | 0 | 0 | 7642.0801 | 2014-09-25 08:00 | 7d | 7642.0801 | 0 | 0 | 0 | 0 | 7642.0801 | 0 | 1 | Finished | 7642.0801 | 7642.0801 | C2016-07 Shopping Village Walkways.xlsx
76 | 73 | Section 64 | 2014-08-27 08:00 | 2014-09-04 17:00 | 9d |  | 0 | 5001.52 | 0 | 0 | 5001.52 | 2014-09-26 08:00 | 7d | 5001.52 | 0 | 0 | 0 | 0 | 5001.52 | 0 | 1 | Finished | 5001.52 | 5001.52 | C2016-07 Shopping Village Walkways.xlsx
77 | 74 | Section 66 | 2014-08-29 08:00 | 2014-09-05 17:00 | 8d |  | 0 | 3892.4099 | 0 | 0 | 3892.4099 | 2014-09-29 08:00 | 8d | 3892.4099 | 0 | 0 | 0 | 0 | 3892.4099 | 0 | 1 | Finished | 3892.4099 | 3892.4099 | C2016-07 Shopping Village Walkways.xlsx
78 | 75 | Section 68 | 2014-09-02 08:00 | 2014-09-08 17:00 | 7d |  | 0 | 7035.2598 | 0 | 0 | 7035.2598 | 2014-09-30 08:00 | 7d | 7035.2598 | 0 | 0 | 0 | 0 | 7035.2598 | 0 | 1 | Finished | 7035.2598 | 7035.2598 | C2016-07 Shopping Village Walkways.xlsx
79 | 76 | Section 70 | 2014-09-04 08:00 | 2014-09-14 17:00 | 11d |  | 0 | 8444.75 | 0 | 0 | 8444.75 | 2014-10-01 08:00 | 7d | 8444.75 | 0 | 0 | 0 | 0 | 8444.75 | 0 | 1 | Finished | 8444.75 | 8444.75 | C2016-07 Shopping Village Walkways.xlsx
80 | 77 | Section 72 | 2014-09-08 08:00 | 2014-09-14 17:00 | 7d |  | 0 | 10053.4805 | 0 | 0 | 10053.4805 | 2014-10-02 08:00 | 7d | 10053.4805 | 0 | 0 | 0 | 0 | 10053.4805 | 0 | 1 | Finished | 10053.4805 | 10053.4805 | C2016-07 Shopping Village Walkways.xlsx
81 | 78 | Section 76 | 2014-09-12 08:00 | 2014-09-19 17:00 | 8d |  | 0 | 8695.9697 | 0 | 0 | 8695.9697 | 2014-10-03 08:00 | 7d | 8695.9697 | 0 | 0 | 0 | 0 | 8695.9697 | 0 | 1 | Finished | 8695.9697 | 8695.9697 | C2016-07 Shopping Village Walkways.xlsx
82 | 79 | Section 78 | 2014-09-16 08:00 | 2014-09-22 17:00 | 7d |  | 0 | 8380.2598 | 0 | 0 | 8380.2598 | 2014-10-06 08:00 | 7d | 8380.2598 | 0 | 0 | 0 | 0 | 8380.2598 | 0 | 1 | Finished | 8380.2598 | 8380.2598 | C2016-07 Shopping Village Walkways.xlsx
83 | 80 | Section 80 | 2014-09-18 08:00 | 2014-09-28 17:00 | 11d |  | 0 | 7714.8599 | 0 | 0 | 7714.8599 | 2014-10-07 08:00 | 8d | 7714.8599 | 0 | 0 | 0 | 0 | 7714.8599 | 0 | 1 | Finished | 7714.8599 | 7714.8599 | C2016-07 Shopping Village Walkways.xlsx
84 | 81 | Section 81 | 2014-09-19 08:00 | 2014-09-26 17:00 | 8d |  | 0 | 7150.3301 | 0 | 0 | 7150.3301 | 2014-10-08 08:00 | 8d | 7150.3301 | 0 | 0 | 0 | 0 | 7150.3301 | 0 | 1 | Finished | 7150.3301 | 7150.3301 | C2016-07 Shopping Village Walkways.xlsx
85 | 131 | Zone H | 2014-07-07 08:00 | 2014-10-26 17:00 | 112d |  |  | 177465.7222 |  |  | 177465.7222 |  | 163d | [5 empty] | 177465.7222 |  | 1 |  | 177465.7222 | 177465.7222 | C2016-07 Shopping Village Walkways.xlsx
86 | 83 | Section 27 | 2014-07-07 08:00 | 2014-07-17 17:00 | 11d |  | 0 | 8853.75 | 0 | 0 | 8853.75 | 2014-09-18 08:00 | 11d | 8853.75 | 0 | 0 | 0 | 0 | 8853.75 | 0 | 1 | Finished | 8853.75 | 8853.75 | C2016-07 Shopping Village Walkways.xlsx
87 | 84 | Section 71 | 2014-09-05 08:00 | 2014-09-12 17:00 | 8d |  | 0 | 8986.7998 | 0 | 0 | 8986.7998 | 2014-10-02 08:00 | 8d | 8986.7998 | 0 | 0 | 0 | 0 | 8986.7998 | 0 | 1 | Finished | 8986.7998 | 8986.7998 | C2016-07 Shopping Village Walkways.xlsx
88 | 85 | Section 73 | 2014-09-09 08:00 | 2014-09-15 17:00 | 7d |  | 0 | 8566.71 | 0 | 0 | 8566.71 | 2014-10-03 08:00 | 7d | 8566.71 | 0 | 0 | 0 | 0 | 8566.71 | 0 | 1 | Finished | 8566.71 | 8566.71 | C2016-07 Shopping Village Walkways.xlsx
89 | 86 | Section 74 | 2014-09-10 08:00 | 2014-09-18 17:00 | 9d |  | 0 | 9055.2305 | 0 | 0 | 9055.2305 | 2014-10-06 08:00 | 9d | 9055.2305 | 0 | 0 | 0 | 0 | 9055.2305 | 0 | 1 | Finished | 9055.2305 | 9055.2305 | C2016-07 Shopping Village Walkways.xlsx
90 | 87 | Section 75 | 2014-09-11 08:00 | 2014-09-21 17:00 | 11d |  | 0 | 8698.0703 | 0 | 0 | 8698.0703 | 2014-10-07 08:00 | 11d | 8698.0703 | 0 | 0 | 0 | 0 | 8698.0703 | 0 | 1 | Finished | 8698.0703 | 8698.0703 | C2016-07 Shopping Village Walkways.xlsx
91 | 88 | Section 77 | 2014-09-15 08:00 | 2014-09-21 17:00 | 7d |  | 0 | 8902.7803 | 0 | 0 | 8902.7803 | 2014-10-08 08:00 | 7d | 8902.7803 | 0 | 0 | 0 | 0 | 8902.7803 | 0 | 1 | Finished | 8902.7803 | 8902.7803 | C2016-07 Shopping Village Walkways.xlsx
92 | 89 | Section 79 | 2014-09-17 08:00 | 2014-09-25 17:00 | 9d |  | 0 | 8693.4404 | 0 | 0 | 8693.4404 | 2014-10-09 08:00 | 9d | 8693.4404 | 0 | 0 | 0 | 0 | 8693.4404 | 0 | 1 | Finished | 8693.4404 | 8693.4404 | C2016-07 Shopping Village Walkways.xlsx
93 | 90 | Section 82 | 2014-09-22 08:00 | 2014-09-28 17:00 | 7d |  | 0 | 7844.8198 | 0 | 0 | 7844.8198 | 2014-10-10 08:00 | 7d | 7844.8198 | 0 | 0 | 0 | 0 | 7844.8198 | 0 | 1 | Finished | 7844.8198 | 7844.8198 | C2016-07 Shopping Village Walkways.xlsx
94 | 91 | Section 83 | 2014-09-23 08:00 | 2014-09-29 17:00 | 7d |  | 0 | 8169.6499 | 0 | 0 | 8169.6499 | 2014-10-13 08:00 | 7d | 8169.6499 | 0 | 0 | 0 | 0 | 8169.6499 | 0 | 1 | Finished | 8169.6499 | 8169.6499 | C2016-07 Shopping Village Walkways.xlsx
95 | 92 | Section 84 | 2014-09-24 08:00 | 2014-10-02 17:00 | 9d |  | 0 | 9306.4404 | 0 | 0 | 9306.4404 | 2014-10-14 08:00 | 9d | 9306.4404 | 0 | 0 | 0 | 0 | 9306.4404 | 0 | 1 | Finished | 9306.4404 | 9306.4404 | C2016-07 Shopping Village Walkways.xlsx
96 | 93 | Section 85 | 2014-09-25 08:00 | 2014-10-05 17:00 | 11d |  | 0 | 8545.0703 | 0 | 0 | 8545.0703 | 2014-10-15 08:00 | 11d | 8545.0703 | 0 | 0 | 0 | 0 | 8545.0703 | 0 | 1 | Finished | 8545.0703 | 8545.0703 | C2016-07 Shopping Village Walkways.xlsx
97 | 94 | Section 86 | 2014-09-26 08:00 | 2014-10-03 17:00 | 8d |  | 0 | 7808.9902 | 0 | 0 | 7808.9902 | 2014-10-17 08:00 | 8d | 7808.9902 | 0 | 0 | 0 | 0 | 7808.9902 | 0 | 1 | Finished | 7808.9902 | 7808.9902 | C2016-07 Shopping Village Walkways.xlsx
98 | 95 | Section 88 | 2014-09-30 08:00 | 2014-10-06 17:00 | 7d |  | 0 | 6621.77 | 0 | 0 | 6621.77 | 2014-10-20 08:00 | 7d | 6621.77 | 0 | 0 | 0 | 0 | 6621.77 | 0 | 1 | Finished | 6621.77 | 6621.77 | C2016-07 Shopping Village Walkways.xlsx
99 | 96 | Section 90 | 2014-10-02 08:00 | 2014-10-12 17:00 | 11d |  | 0 | 7732.1401 | 0 | 0 | 7732.1401 | 2014-10-21 08:00 | 11d | 7732.1401 | 0 | 0 | 0 | 0 | 7732.1401 | 0 | 1 | Finished | 7732.1401 | 7732.1401 | C2016-07 Shopping Village Walkways.xlsx
100 | 97 | Section 92 | 2014-10-06 08:00 | 2014-10-12 17:00 | 7d |  | 0 | 8410.1904 | 0 | 0 | 8410.1904 | 2014-10-22 08:00 | 7d | 8410.1904 | 0 | 0 | 0 | 0 | 8410.1904 | 0 | 1 | Finished | 8410.1904 | 8410.1904 | C2016-07 Shopping Village Walkways.xlsx
101 | 98 | Section 94 | 2014-10-08 08:00 | 2014-10-16 17:00 | 9d |  | 0 | 8601.8301 | 0 | 0 | 8601.8301 | 2014-10-23 08:00 | 9d | 8601.8301 | 0 | 0 | 0 | 0 | 8601.8301 | 0 | 1 | Finished | 8601.8301 | 8601.8301 | C2016-07 Shopping Village Walkways.xlsx
102 | 99 | Section 96 | 2014-10-10 08:00 | 2014-10-17 17:00 | 8d |  | 0 | 8712.9697 | 0 | 0 | 8712.9697 | 2014-10-24 08:00 | 8d | 8712.9697 | 0 | 0 | 0 | 0 | 8712.9697 | 0 | 1 | Finished | 8712.9697 | 8712.9697 | C2016-07 Shopping Village Walkways.xlsx
103 | 100 | Section 97 | 2014-10-13 08:00 | 2014-10-19 17:00 | 7d |  | 0 | 8456.8398 | 0 | 0 | 8456.8398 | 2015-02-17 08:00 | 7d | 8456.8398 | 0 | 0 | 0 | 0 | 8456.8398 | 0 | 1 | Finished | 8456.8398 | 8456.8398 | C2016-07 Shopping Village Walkways.xlsx
104 | 101 | Section 98 | 2014-10-14 08:00 | 2014-10-20 17:00 | 7d |  | 0 | 9148.2402 | 0 | 0 | 9148.2402 | 2015-02-18 08:00 | 7d | 9148.2402 | 0 | 0 | 0 | 0 | 9148.2402 | 0 | 1 | Finished | 9148.2402 | 9148.2402 | C2016-07 Shopping Village Walkways.xlsx
105 | 102 | Section 99 | 2014-10-15 08:00 | 2014-10-23 17:00 | 9d |  | 0 | 8024.9399 | 0 | 0 | 8024.9399 | 2015-02-19 08:00 | 8d | 8024.9399 | 0 | 0 | 0 | 0 | 8024.9399 | 0 | 1 | Finished | 8024.9399 | 8024.9399 | C2016-07 Shopping Village Walkways.xlsx
106 | 103 | Section 100 | 2014-10-16 08:00 | 2014-10-26 17:00 | 11d |  | 0 | 8325.0498 | 0 | 0 | 8325.0498 | 2015-02-20 08:00 | 8d | 8325.0498 | 0 | 0 | 0 | 0 | 8325.0498 | 0 | 1 | Finished | 8325.0498 | 8325.0498 | C2016-07 Shopping Village Walkways.xlsx
107 | 132 | Zone I | 2014-08-07 08:00 | 2014-09-11 17:00 | 36d |  |  | 99150.7002 |  |  | 99150.7002 |  | 23d | [5 empty] | 99150.7002 |  | 1 |  | 99150.7002 | 99150.7002 | C2016-07 Shopping Village Walkways.xlsx
108 | 105 | Section 50 | 2014-08-07 08:00 | 2014-08-18 17:00 | 12d |  | 0 | 8970.6396 | 0 | 0 | 8970.6396 | 2014-09-16 08:00 | 12d | 8970.6396 | 0 | 0 | 0 | 0 | 8970.6396 | 0 | 1 | Finished | 8970.6396 | 8970.6396 | C2016-07 Shopping Village Walkways.xlsx
109 | 106 | Section 51 | 2014-08-08 08:00 | 2014-08-18 17:00 | 11d |  | 0 | 8770.8496 | 0 | 0 | 8770.8496 | 2014-09-17 08:00 | 11d | 8770.8496 | 0 | 0 | 0 | 0 | 8770.8496 | 0 | 1 | Finished | 8770.8496 | 8770.8496 | C2016-07 Shopping Village Walkways.xlsx
110 | 107 | Section 53 | 2014-08-12 08:00 | 2014-08-18 17:00 | 7d |  | 0 | 8504.6104 | 0 | 0 | 8504.6104 | 2014-09-19 08:00 | 7d | 8504.6104 | 0 | 0 | 0 | 0 | 8504.6104 | 0 | 1 | Finished | 8504.6104 | 8504.6104 | C2016-07 Shopping Village Walkways.xlsx
111 | 108 | Section 55 | 2014-08-14 08:00 | 2014-08-25 17:00 | 12d |  | 0 | 7981.6602 | 0 | 0 | 7981.6602 | 2014-09-22 08:00 | 12d | 7981.6602 | 0 | 0 | 0 | 0 | 7981.6602 | 0 | 1 | Finished | 7981.6602 | 7981.6602 | C2016-07 Shopping Village Walkways.xlsx
112 | 109 | Section 57 | 2014-08-18 08:00 | 2014-08-24 17:00 | 7d |  | 0 | 9716.1396 | 0 | 0 | 9716.1396 | 2014-09-23 08:00 | 7d | 9716.1396 | 0 | 0 | 0 | 0 | 9716.1396 | 0 | 1 | Finished | 9716.1396 | 9716.1396 | C2016-07 Shopping Village Walkways.xlsx
113 | 110 | Section 59 | 2014-08-20 08:00 | 2014-08-28 17:00 | 9d |  | 0 | 8627.1201 | 0 | 0 | 8627.1201 | 2014-09-24 08:00 | 9d | 8627.1201 | 0 | 0 | 0 | 0 | 8627.1201 | 0 | 1 | Finished | 8627.1201 | 8627.1201 | C2016-07 Shopping Village Walkways.xlsx
114 | 111 | Section 61 | 2014-08-22 08:00 | 2014-08-29 17:00 | 8d |  | 0 | 8489.71 | 0 | 0 | 8489.71 | 2014-09-25 08:00 | 8d | 8489.71 | 0 | 0 | 0 | 0 | 8489.71 | 0 | 1 | Finished | 8489.71 | 8489.71 | C2016-07 Shopping Village Walkways.xlsx
115 | 112 | Section 63 | 2014-08-26 08:00 | 2014-09-01 17:00 | 7d |  | 0 | 9745.0801 | 0 | 0 | 9745.0801 | 2014-09-26 08:00 | 7d | 9745.0801 | 0 | 0 | 0 | 0 | 9745.0801 | 0 | 1 | Finished | 9745.0801 | 9745.0801 | C2016-07 Shopping Village Walkways.xlsx
116 | 113 | Section 65 | 2014-08-28 08:00 | 2014-09-07 17:00 | 11d |  | 0 | 9664.1504 | 0 | 0 | 9664.1504 | 2014-09-29 08:00 | 8d | 9664.1504 | 0 | 0 | 0 | 0 | 9664.1504 | 0 | 1 | Finished | 9664.1504 | 9664.1504 | C2016-07 Shopping Village Walkways.xlsx
117 | 114 | Section 67 | 2014-09-01 08:00 | 2014-09-07 17:00 | 7d |  | 0 | 8592.8398 | 0 | 0 | 8592.8398 | 2014-09-30 08:00 | 8d | 8592.8398 | 0 | 0 | 0 | 0 | 8592.8398 | 0 | 1 | Finished | 8592.8398 | 8592.8398 | C2016-07 Shopping Village Walkways.xlsx
118 | 115 | Section 69 | 2014-09-03 08:00 | 2014-09-11 17:00 | 9d |  | 0 | 10087.9004 | 0 | 0 | 10087.9004 | 2014-10-01 08:00 | 8d | 10087.9004 | 0 | 0 | 0 | 0 | 10087.9004 | 0 | 1 | Finished | 10087.9004 | 10087.9004 | C2016-07 Shopping Village Walkways.xlsx
119 | 133 | Zone J | 2014-07-08 08:00 | 2014-08-11 17:00 | 35d |  |  | 44940.4692 |  |  | 44940.4692 |  | 25d | [5 empty] | 44940.4692 |  | 1 |  | 44940.4692 | 44940.4692 | C2016-07 Shopping Village Walkways.xlsx
120 | 117 | Section 28 | 2014-07-08 08:00 | 2014-07-15 17:00 | 8d |  | 0 | 8934.54 | 0 | 0 | 8934.54 | 2014-09-19 08:00 | 8d | 8934.54 | 0 | 0 | 0 | 0 | 8934.54 | 0 | 1 | Finished | 8934.54 | 8934.54 | C2016-07 Shopping Village Walkways.xlsx
121 | 118 | Section 29 | 2014-07-09 08:00 | 2014-07-15 17:00 | 7d |  | 0 | 5765.98 | 0 | 0 | 5765.98 | 2014-09-22 08:00 | 7d | 5765.98 | 0 | 0 | 0 | 0 | 5765.98 | 0 | 1 | Finished | 5765.98 | 5765.98 | C2016-07 Shopping Village Walkways.xlsx
122 | 119 | Section 30 | 2014-07-10 08:00 | 2014-07-16 17:00 | 7d |  | 0 | 8892.8096 | 0 | 0 | 8892.8096 | 2014-10-06 08:00 | 8d | 8892.8096 | 0 | 0 | 0 | 0 | 8892.8096 | 0 | 1 | Finished | 8892.8096 | 8892.8096 | C2016-07 Shopping Village Walkways.xlsx
123 | 120 | Section 44 | 2014-07-30 08:00 | 2014-08-05 17:00 | 7d |  | 0 | 8742.0498 | 0 | 0 | 8742.0498 | 2014-09-23 08:00 | 7d | 8742.0498 | 0 | 0 | 0 | 0 | 8742.0498 | 0 | 1 | Finished | 8742.0498 | 8742.0498 | C2016-07 Shopping Village Walkways.xlsx
124 | 121 | Section 46 | 2014-08-01 08:00 | 2014-08-11 17:00 | 11d |  | 0 | 6941.96 | 0 | 0 | 6941.96 | 2014-09-24 08:00 | 11d | 6941.96 | 0 | 0 | 0 | 0 | 6941.96 | 0 | 1 | Finished | 6941.96 | 6941.96 | C2016-07 Shopping Village Walkways.xlsx
125 | 122 | Section 48 | 2014-08-05 08:00 | 2014-08-11 17:00 | 7d |  | 0 | 5663.1299 | 0 | 0 | 5663.1299 | 2014-09-25 08:00 | 7d | 5663.1299 | 0 | 0 | 0 | 0 | 5663.1299 | 0 | 1 | Finished | 5663.1299 | 5663.1299 | C2016-07 Shopping Village Walkways.xlsx
126 | 134 | Snagging | 2014-10-24 08:00 | 2014-11-11 17:00 | 19d |  | 0 | 1 | 0 | 0 | 1 | 2014-10-20 08:00 | 19d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Finished | 1 | 1 | C2016-07 Shopping Village Walkways.xlsx
127 | 135 | Handover | 2014-12-19 09:00 | 2014-12-19 09:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2015-03-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-07 Shopping Village Walkways.xlsx
4 | 0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 725d | [5 empty] | 438741.6603 |  | 1 |  | 375253.3431 | 375253.3431 | C2016-08 SCM System.xlsx
5 | 1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
6 | 127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 1 |  | 44999.996 | 44999.996 | C2016-08 SCM System.xlsx
7 | 2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | Finished | 5000 | 5000 | C2016-08 SCM System.xlsx
8 | 3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
9 | 4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
10 | 5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 1 | Finished | 7500 | 7500 | C2016-08 SCM System.xlsx
11 | 6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
12 | 7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | Finished | 5000 | 5000 | C2016-08 SCM System.xlsx
13 | 8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 1 | Finished | 2499.996 | 2499.996 | C2016-08 SCM System.xlsx
14 | 9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 1 | Finished | 10000 | 10000 | C2016-08 SCM System.xlsx
15 | 10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 1 | Finished | 7500 | 7500 | C2016-08 SCM System.xlsx
16 | 11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
17 | 128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 1 |  | 73445.8833 | 73445.8833 | C2016-08 SCM System.xlsx
18 | 135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 1 |  | 73445.8833 | 73445.8833 | C2016-08 SCM System.xlsx
19 | 12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | Finished | 5000 | 5000 | C2016-08 SCM System.xlsx
20 | 13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
21 | 131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 1 |  | 11480 | 11480 | C2016-08 SCM System.xlsx
22 | 14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 1 | Finished | 1000 | 1000 | C2016-08 SCM System.xlsx
23 | 15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 1 | Finished | 3500 | 3500 | C2016-08 SCM System.xlsx
24 | 16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | Finished | 5000 | 5000 | C2016-08 SCM System.xlsx
25 | 17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 1 | Finished | 1000 | 1000 | C2016-08 SCM System.xlsx
26 | 18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 1 | Finished | 980 | 980 | C2016-08 SCM System.xlsx
27 | 19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 1 | Finished | 3000 | 3000 | C2016-08 SCM System.xlsx
28 | 132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 1 |  | 14989.0823 | 14989.0823 | C2016-08 SCM System.xlsx
29 | 20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
30 | 21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 1 | Finished | 7500 | 7500 | C2016-08 SCM System.xlsx
31 | 22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 1 | Finished | 1000 | 1000 | C2016-08 SCM System.xlsx
32 | 23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
33 | 24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 1 | Finished | 1489.0823 | 1489.0823 | C2016-08 SCM System.xlsx
34 | 133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 1 |  | 38976.8009 | 38976.8009 | C2016-08 SCM System.xlsx
35 | 25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
36 | 26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 1 | Finished | 15000 | 15000 | C2016-08 SCM System.xlsx
37 | 27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | Finished | 5000 | 5000 | C2016-08 SCM System.xlsx
38 | 28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
39 | 29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 1 | Finished | 10000 | 10000 | C2016-08 SCM System.xlsx
40 | 30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 1 | Finished | 3976.8009 | 3976.8009 | C2016-08 SCM System.xlsx
41 | 31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
42 | 129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 472d | [5 empty] | 223258.7086 |  | 1 |  | 191673.6874 | 191673.6874 | C2016-08 SCM System.xlsx
43 | 32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
44 | 136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 1 |  | 24000 | 24000 | C2016-08 SCM System.xlsx
45 | 33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 1 | Finished | 4000 | 4000 | C2016-08 SCM System.xlsx
46 | 34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
47 | 35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 1 | Finished | 7500 | 7500 | C2016-08 SCM System.xlsx
48 | 36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 1 | Finished | 5000 | 5000 | C2016-08 SCM System.xlsx
49 | 37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
50 | 38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
51 | 39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
52 | 137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 1 |  | 14669.8552 | 14669.8552 | C2016-08 SCM System.xlsx
53 | 148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 1 |  | 3125 | 3125 | C2016-08 SCM System.xlsx
54 | 40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | Finished | 125 | 125 | C2016-08 SCM System.xlsx
55 | 41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 1 | Finished | 1500 | 1500 | C2016-08 SCM System.xlsx
56 | 42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 1 | Finished | 1500 | 1500 | C2016-08 SCM System.xlsx
57 | 145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 1 |  | 6500 | 6500 | C2016-08 SCM System.xlsx
58 | 43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
59 | 44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
60 | 45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 1 | Finished | 1500 | 1500 | C2016-08 SCM System.xlsx
61 | 144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 1 |  | 3562.5 | 3562.5 | C2016-08 SCM System.xlsx
62 | 46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 62.5 | 62.5 | C2016-08 SCM System.xlsx
63 | 47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 1 | Finished | 2000 | 2000 | C2016-08 SCM System.xlsx
64 | 48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 1 | Finished | 1500 | 1500 | C2016-08 SCM System.xlsx
65 | 49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 1 | Finished | 1482.3552 | 1482.3552 | C2016-08 SCM System.xlsx
66 | 50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
67 | 138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 1 |  | 4480 | 4480 | C2016-08 SCM System.xlsx
68 | 51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
69 | 52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 1 | Finished | 1000 | 1000 | C2016-08 SCM System.xlsx
70 | 53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 1 | Finished | 1000 | 1000 | C2016-08 SCM System.xlsx
71 | 54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 1 | Finished | 1500 | 1500 | C2016-08 SCM System.xlsx
72 | 55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 1 | Finished | 980 | 980 | C2016-08 SCM System.xlsx
73 | 56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
74 | 139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 1 |  | 37511.6969 | 37511.6969 | C2016-08 SCM System.xlsx
75 | 57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
76 | 58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
77 | 59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 1 | Finished | 5000.0038 | 5000.0038 | C2016-08 SCM System.xlsx
78 | 60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
79 | 61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
80 | 62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 1 | Finished | 1500 | 1500 | C2016-08 SCM System.xlsx
81 | 63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 1 | Finished | 5000.0038 | 5000.0038 | C2016-08 SCM System.xlsx
82 | 64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 1 | Finished | 2499.996 | 2499.996 | C2016-08 SCM System.xlsx
83 | 65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
84 | 66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 1 | Finished | 2499.996 | 2499.996 | C2016-08 SCM System.xlsx
85 | 67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 1 | Finished | 10000.0076 | 10000.0076 | C2016-08 SCM System.xlsx
86 | 68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 1 | Finished | 3511.6897 | 3511.6897 | C2016-08 SCM System.xlsx
87 | 69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
88 | 140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 224d | [5 empty] | 43491.2703 |  | 1 |  | 46004.3158 | 46004.3158 | C2016-08 SCM System.xlsx
89 | 70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
90 | 71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
91 | 72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 1 | Finished | 2499.996 | 2499.996 | C2016-08 SCM System.xlsx
92 | 73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 1 | Finished | 4999.9919 | 4999.9919 | C2016-08 SCM System.xlsx
93 | 74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 45d | 10000.0079 | 0 | 0 | 0 | 0 | 10000.0079 | 0 | 1 | Finished | 10000.0079 | 10000.0079 | C2016-08 SCM System.xlsx
94 | 75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-08-03 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 1 | Finished | 4999.9919 | 4999.9919 | C2016-08 SCM System.xlsx
95 | 76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-09-14 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
96 | 77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-10-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
97 | 78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-10-12 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 1 | Finished | 5000.0038 | 5000.0038 | C2016-08 SCM System.xlsx
98 | 79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-11-02 08:00 | 30d | 10000.0076 | 0 | 0 | 0 | 0 | 10000.0076 | 0 | 1 | Finished | 10000.0076 | 10000.0076 | C2016-08 SCM System.xlsx
99 | 80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 179d | 2657.9351 | 0 | 0 | 0 | 0 | 2657.9351 | 0 | 1 | Finished | 3504.3167 | 3504.3167 | C2016-08 SCM System.xlsx
100 | 81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
101 | 141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 172d | [5 empty] | 34811.0986 |  | 1 |  | 40016.6554 | 40016.6554 | C2016-08 SCM System.xlsx
102 | 82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
103 | 83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
104 | 84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 | 2012-08-24 08:00 | 25d | 6250 | 0 | 0 | 0 | 0 | 6250 | 0 | 1 | Finished | 7500 | 7500 | C2016-08 SCM System.xlsx
105 | 85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-09-28 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
106 | 86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-09-28 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 1 | Finished | 5000 | 5000 | C2016-08 SCM System.xlsx
107 | 87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-10-19 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
108 | 88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 | 2012-10-26 08:00 | 10d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 1 | Finished | 3500 | 3500 | C2016-08 SCM System.xlsx
109 | 89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-11-09 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
110 | 90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-11-16 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 1500 | 1500 | C2016-08 SCM System.xlsx
111 | 91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
112 | 92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
113 | 93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-08-24 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | Finished | 5000 | 5000 | C2016-08 SCM System.xlsx
114 | 94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 | 2012-08-10 08:00 | 143d | 5561.0986 | 0 | 0 | 0 | 0 | 5561.0986 | 0 | 1 | Finished | 5016.6554 | 5016.6554 | C2016-08 SCM System.xlsx
115 | 95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-02-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
116 | 142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 125d | [5 empty] | 20567 |  | 1 |  | 24991.1641 | 24991.1641 | C2016-08 SCM System.xlsx
117 | 96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
118 | 97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 | 2012-07-02 08:00 | 25d | 1785.7201 | 0 | 0 | 0 | 0 | 1785.7201 | 0 | 1 | Finished | 2500.0081 | 2500.0081 | C2016-08 SCM System.xlsx
119 | 98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-07-02 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 1 | Finished | 1500 | 1500 | C2016-08 SCM System.xlsx
120 | 99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 | 2012-07-23 08:00 | 25d | 4285.7201 | 0 | 0 | 0 | 0 | 4285.7201 | 0 | 1 | Finished | 6000.0081 | 6000.0081 | C2016-08 SCM System.xlsx
121 | 100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-07-23 08:00 | 15d | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
122 | 101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-08-27 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 1500 | 1500 | C2016-08 SCM System.xlsx
123 | 102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 | 2012-09-03 08:00 | 20d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 1 | Finished | 3000 | 3000 | C2016-08 SCM System.xlsx
124 | 103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 | 2012-10-01 08:00 | 10d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 1 | Finished | 1500 | 1500 | C2016-08 SCM System.xlsx
125 | 104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
126 | 105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-12-03 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 1 | Finished | 1500 | 1500 | C2016-08 SCM System.xlsx
127 | 106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2012-12-17 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
128 | 107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 | 2012-07-02 08:00 | 120d | 2470.5599 | 0 | 0 | 0 | 0 | 2470.5599 | 0 | 1 | Finished | 2491.1479 | 2491.1479 | C2016-08 SCM System.xlsx
129 | 108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
130 | 109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
131 | 130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 145d | [5 empty] | 65133.7764 |  | 1 |  | 65133.7764 | 65133.7764 | C2016-08 SCM System.xlsx
132 | 152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 25d | [5 empty] | 10000 |  | 1 |  | 10000 | 10000 | C2016-08 SCM System.xlsx
133 | 110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2012-12-24 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 1 | Finished | 1000 | 1000 | C2016-08 SCM System.xlsx
134 | 111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2012-12-31 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 1 | Finished | 7500 | 7500 | C2016-08 SCM System.xlsx
135 | 112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2013-01-21 08:00 | 5d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 1 | Finished | 1500 | 1500 | C2016-08 SCM System.xlsx
136 | 113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
137 | 153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 120d | [5 empty] | 55133.7764 |  | 1 |  | 55133.7764 | 55133.7764 | C2016-08 SCM System.xlsx
138 | 114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
139 | 115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-01-28 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
140 | 116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 | 2013-02-04 08:00 | 40d | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 | 1 | Finished | 16000 | 16000 | C2016-08 SCM System.xlsx
141 | 117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2013-04-01 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 1 | Finished | 5000.0038 | 5000.0038 | C2016-08 SCM System.xlsx
142 | 118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-04-22 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
143 | 119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2013-04-29 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 1 | Finished | 7500 | 7500 | C2016-08 SCM System.xlsx
144 | 120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-05-20 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
145 | 121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-05-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
146 | 122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-05-27 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2016-08 SCM System.xlsx
147 | 123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 | 2013-06-03 08:00 | 29d | 10150 | 0 | 0 | 0 | 0 | 10150 | 0 | 1 | Finished | 10150 | 10150 | C2016-08 SCM System.xlsx
148 | 124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 | 2013-01-28 08:00 | 114d | 6483.7726 | 0 | 0 | 0 | 0 | 6483.7726 | 0 | 1 | Finished | 6483.7726 | 6483.7726 | C2016-08 SCM System.xlsx
149 | 125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-07-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
150 | 126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-07-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-08 SCM System.xlsx
4 | 0 | Data Loss Prevention System | 2013-04-10 08:00 | 2014-01-07 17:00 | 195d |  |  | 0 |  |  | 584951.7689 |  | 189d | [5 empty] | 1425155.9614 |  | 1 |  | 584951.7689 | 584298.0089 | C2016-09 Data Loss Prevention System.xlsx
5 | 1 | MS Kick off meeting | 2013-04-10 08:00 | 2013-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-04-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-09 Data Loss Prevention System.xlsx
6 | 2 | DLP workshop | 2013-04-15 08:00 | 2013-04-15 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-04-15 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
7 | 3 | study existing documentation | 2013-04-16 08:00 | 2013-04-22 17:00 | 5d |  | 0 | 0 | 408.6 | 16344.0002 | 16344.0002 | 2013-04-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 1 | Finished | 16344.0002 | 16344.0002 | C2016-09 Data Loss Prevention System.xlsx
8 | 120 | Milestones | 2013-05-03 17:00 | 2013-12-30 17:00 | 171d |  |  | 0 |  |  | 0 |  | 171d | [5 empty] | 0 |  | 0 |  | 0 | 0 | C2016-09 Data Loss Prevention System.xlsx
9 | 4 | MS Start specific design | 2013-05-03 17:00 | 2013-05-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-05-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-09 Data Loss Prevention System.xlsx
10 | 5 | MS testing start | 2013-07-05 17:00 | 2013-07-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-09 Data Loss Prevention System.xlsx
11 | 6 | MS testing end | 2013-09-13 17:00 | 2013-09-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-09-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-09 Data Loss Prevention System.xlsx
12 | 7 | MS Deployment start | 2013-09-30 17:00 | 2013-09-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-10-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-09 Data Loss Prevention System.xlsx
13 | 8 | MS Deployment end | 2013-12-30 17:00 | 2013-12-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2016-09 Data Loss Prevention System.xlsx
14 | 121 | A. DLP Strategy | 2013-05-10 08:00 | 2013-07-24 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 61d | [5 empty] | 68317.921 |  | 1 |  | 67010.401 | 67010.401 | C2016-09 Data Loss Prevention System.xlsx
15 | 9 | Define DLP Strategy output | 2013-05-10 08:00 | 2013-05-10 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-10 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
16 | 10 | Initial DLP Strategy workshop | 2013-05-16 08:00 | 2013-05-20 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-16 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 1 | Finished | 9806.4001 | 9806.4001 | C2016-09 Data Loss Prevention System.xlsx
17 | 129 | DLP Strategy Document writing | 2013-05-21 08:00 | 2013-06-18 17:00 | 21d |  |  | 0 |  |  | 31053.6005 |  | 5d | [5 empty] | 31053.6005 |  | 1 |  | 31053.6005 | 31053.6005 | C2016-09 Data Loss Prevention System.xlsx
18 | 11 | A.1 Technical and Organizational inputs | 2013-05-21 08:00 | 2013-05-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
19 | 12 | A.2 Data loss/leakage prevention Strategy | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
20 | 15 | Follow-up DLP Strategy workshop | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-05-21 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 1 | Finished | 4903.2001 | 4903.2001 | C2016-09 Data Loss Prevention System.xlsx
21 | 13 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-10 08:00 | 2013-06-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
22 | 14 | A.4 Overarching technical policies | 2013-06-12 08:00 | 2013-06-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-24 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
23 | 130 | DLP Strategy Document writing | 2013-06-21 08:00 | 2013-06-26 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 2d | [5 empty] | 13075.2002 |  | 1 |  | 13075.2002 | 13075.2002 | C2016-09 Data Loss Prevention System.xlsx
24 | 16 | A.1 Technical and Organizational inputs | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
25 | 17 | A.2 Data loss/leakage prevention Strategy | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
26 | 18 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
27 | 19 | A.4 Overarching technical policies | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
28 | 20 | DLP Strategy Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-06-25 08:00 | 6d | 3922.5601 | 0 | 0 | 0 | 0 | 3922.5601 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
29 | 21 | DLP Strategy Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-15 10:00 | 8d 5h | 5638.6801 | 0 | 0 | 0 | 0 | 5638.6801 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
30 | 22 | DLP Strategy approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-07-29 10:00 | 4d 6h | 1552.68 | 0 | 0 | 0 | 0 | 1552.68 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
31 | 122 | B. High level implementation plan | 2013-05-09 08:00 | 2013-07-24 17:00 | 55d |  |  | 0 |  |  | 67010.401 |  | 53d 3h | [5 empty] | 75877.0211 |  | 1 |  | 67010.401 | 67010.401 | C2016-09 Data Loss Prevention System.xlsx
32 | 23 | Define HL Implementation plan output | 2013-05-09 08:00 | 2013-05-09 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-09 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
33 | 24 | Initial HL Implementation plan workshop | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 1 | Finished | 9806.4001 | 9806.4001 | C2016-09 Data Loss Prevention System.xlsx
34 | 131 | HL Implementation plan Document writing | 2013-05-23 08:00 | 2013-06-03 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 8d | [5 empty] | 39225.6006 |  | 1 |  | 26150.4004 | 26150.4004 | C2016-09 Data Loss Prevention System.xlsx
35 | 25 | B.1 Roadmap towards a full DLP implementation | 2013-05-23 08:00 | 2013-05-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-23 08:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
36 | 26 | B.2 Communication plan to stakeholders | 2013-05-27 08:00 | 2013-05-28 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
37 | 27 | B.3 integration in exisiting architecture | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-29 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
38 | 28 | B.4 Security controls for the enforcement of the policy | 2013-05-31 08:00 | 2013-06-03 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-31 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
39 | 29 | Follow-up HL Implementation plan workshop | 2013-06-12 08:00 | 2013-06-14 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-11 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 1 | Finished | 4903.2001 | 4903.2001 | C2016-09 Data Loss Prevention System.xlsx
40 | 132 | HL Implementation plan Document writing | 2013-06-17 08:00 | 2013-06-20 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 3d | [5 empty] | 11440.8002 |  | 1 |  | 13075.2002 | 13075.2002 | C2016-09 Data Loss Prevention System.xlsx
41 | 30 | B.1 Roadmap towards a full DLP implementation | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
42 | 31 | B.2 Communication plan to stakeholders | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
43 | 32 | B.3 integration in existing architecture | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
44 | 33 | B.4 Security controls for the enforcement of the policy | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1d | 1634.4 | 0 | 0 | 0 | 0 | 1634.4 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
45 | 34 | HL Implementation plan Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-01 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
46 | 35 | HL Implementation plan Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-15 10:00 | 6d | 3922.5601 | 0 | 0 | 0 | 0 | 3922.5601 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
47 | 36 | HL Implementation plan approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-07-23 10:00 | 1h | 40.86 | 0 | 0 | 0 | 0 | 40.86 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
48 | 123 | D. Technical directives | 2013-06-27 08:00 | 2013-09-10 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 87d 5h | [5 empty] | 131814.362 |  | 1 |  | 67010.401 | 67010.401 | C2016-09 Data Loss Prevention System.xlsx
49 | 37 | Define Technical directives output | 2013-06-27 08:00 | 2013-06-27 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-07-01 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
50 | 38 | Initial Technical directives workshop | 2013-06-28 08:00 | 2013-07-02 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 1 | Finished | 9806.4001 | 9806.4001 | C2016-09 Data Loss Prevention System.xlsx
51 | 133 | Technical directives Document writing | 2013-07-03 08:00 | 2013-07-18 17:00 | 12d |  |  | 0 |  |  | 22881.6003 |  | 6d | [5 empty] | 65376.001 |  | 1 |  | 22881.6003 | 22881.6003 | C2016-09 Data Loss Prevention System.xlsx
52 | 39 | D.1 Device/Port control rules | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-16 08:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
53 | 40 | D.2 DLP rules | 2013-07-09 08:00 | 2013-07-10 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
54 | 41 | D.3 Encryption rules | 2013-07-17 08:00 | 2013-07-18 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
55 | 42 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 6d | 19612.8003 | 0 | 0 | 0 | 0 | 19612.8003 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
56 | 43 | Rule set v1 | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1h | 408.6 | 0 | 0 | 0 | 0 | 408.6 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
57 | 44 | Follow-up Technical directives workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-07-22 08:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 1 | Finished | 4903.2001 | 4903.2001 | C2016-09 Data Loss Prevention System.xlsx
58 | 134 | Technical directives Document writing | 2013-07-24 08:00 | 2013-07-26 17:00 | 3d |  |  | 0 |  |  | 13075.2002 |  | 8d | [5 empty] | 32688.0005 |  | 1 |  | 13075.2002 | 13075.2002 | C2016-09 Data Loss Prevention System.xlsx
59 | 45 | D.1 Device /Port control rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
60 | 46 | D.2 DLP rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
61 | 47 | D.3 Encryption rules | 2013-07-25 08:00 | 2013-07-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 8d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
62 | 48 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-08-01 16:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
63 | 49 | Technical directives Document review | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-08 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
64 | 50 | Technical directives Fix document | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-15 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
65 | 51 | Technical directives approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-08-22 14:00 | 17d | 5556.9601 | 0 | 0 | 0 | 0 | 5556.9601 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
66 | 124 | C. High Level Solution Design for Data Tagging and Information Classification | 2013-05-03 08:00 | 2013-09-10 17:00 | 93d |  |  | 0 |  |  | 67010.401 |  | 69d | [5 empty] | 94795.2014 |  | 1 |  | 67010.401 | 67010.401 | C2016-09 Data Loss Prevention System.xlsx
67 | 52 | Define Data tagging HL Solution output | 2013-07-04 08:00 | 2013-07-04 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-19 09:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
68 | 53 | Initial Data tagging HL Solution workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-17 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 1 | Finished | 9806.4001 | 9806.4001 | C2016-09 Data Loss Prevention System.xlsx
69 | 135 | DLP Data tagging HL Solution Document writing | 2013-07-26 08:00 | 2013-08-06 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 5d | [5 empty] | 13075.2002 |  | 1 |  | 26150.4004 | 26150.4004 | C2016-09 Data Loss Prevention System.xlsx
70 | 54 | C.1 High-level solution design | 2013-07-26 08:00 | 2013-07-29 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-22 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
71 | 55 | C.2 Organization & Roles | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
72 | 56 | C.3 Discovery of Classified Information | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
73 | 57 | C.4 Control for tagging and classification | 2013-08-05 08:00 | 2013-08-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-28 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
74 | 58 | Follow-up Data tagging HL Solution workshop | 2013-08-07 08:00 | 2013-08-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-07-11 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 4903.2001 | 4903.2001 | C2016-09 Data Loss Prevention System.xlsx
75 | 136 | DLP Data tagging HL Solution Document writing | 2013-05-03 08:00 | 2013-08-13 17:00 | 73d |  |  | 0 |  |  | 13075.2002 |  | 9d | [5 empty] | 58838.4009 |  | 1 |  | 13075.2002 | 13075.2002 | C2016-09 Data Loss Prevention System.xlsx
76 | 59 | C.1 High-level solution design | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
77 | 60 | C.2 Organization & Roles | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
78 | 61 | C.3 Discovery of Classified Information | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
79 | 62 | C.4 Control for tagging and classification | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
80 | 63 | DLP Data tagging HL Solution Document review | 2013-08-14 08:00 | 2013-08-20 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-09 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
81 | 64 | DLP Data tagging HL Solution Fix document | 2013-08-21 08:00 | 2013-08-27 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-16 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
82 | 65 | DLP Data tagging HL Solution approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-08-23 08:00 | 2d | 653.76 | 0 | 0 | 0 | 0 | 653.76 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
83 | 125 | H. Migration Strategy and a high level Implementation Package | 2013-05-03 08:00 | 2013-11-12 17:00 | 138d |  |  | 0 |  |  | 97737.1215 |  | 141d 4h | [5 empty] | 722077.9308 |  | 1 |  | 97737.1215 | 97737.1215 | C2016-09 Data Loss Prevention System.xlsx
84 | 66 | Define Migration Strategy output | 2013-08-20 08:00 | 2013-08-20 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-08-20 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
85 | 67 | Initial Migration Strategy workshop | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-09-02 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 9806.4001 | 9806.4001 | C2016-09 Data Loss Prevention System.xlsx
86 | 137 | Migration Strategy Document writing | 2013-05-03 08:00 | 2013-09-23 17:00 | 102d |  |  | 0 |  |  | 39225.6006 |  | 52d | [5 empty] | 679910.4102 |  | 1 |  | 39225.6006 | 39225.6006 | C2016-09 Data Loss Prevention System.xlsx
87 | 68 | H.1 Preparation guide | 2013-09-10 08:00 | 2013-09-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 46d | 150364.8022 | 0 | 0 | 0 | 0 | 150364.8022 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
88 | 69 | H.2 Installation guide | 2013-09-12 08:00 | 2013-09-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 52d | 169977.6025 | 0 | 0 | 0 | 0 | 169977.6025 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
89 | 70 | H.5 Uninstallation guide | 2013-09-16 08:00 | 2013-09-17 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 52d | 169977.6025 | 0 | 0 | 0 | 0 | 169977.6025 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
90 | 71 | H.6 Training Needs Analysis | 2013-09-18 08:00 | 2013-09-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 12d | 39225.6006 | 0 | 0 | 0 | 0 | 39225.6006 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
91 | 72 | H.7 Dashboards | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 22d | 71913.6011 | 0 | 0 | 0 | 0 | 71913.6011 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
92 | 73 | H.8 Measurement Methods | 2013-09-20 08:00 | 2013-09-23 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 24d | 78451.2012 | 0 | 0 | 0 | 0 | 78451.2012 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
93 | 74 | Follow-up Migration Strategy workshop | 2013-09-30 08:00 | 2013-10-02 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-25 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 1 | Finished | 4903.2001 | 4903.2001 | C2016-09 Data Loss Prevention System.xlsx
94 | 138 | Migration Strategy Document writing | 2013-05-07 08:00 | 2013-10-08 17:00 | 111d |  |  | 0 |  |  | 17651.5203 |  | 42d | [5 empty] | 17651.5203 |  | 1 |  | 17651.5203 | 17651.5203 | C2016-09 Data Loss Prevention System.xlsx
95 | 75 | H.1 Preparation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
96 | 76 | H.2 Installation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
97 | 77 | H.3 Configuration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-02 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
98 | 78 | H.4 Migration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-02 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
99 | 79 | H.5 Uninstallation guide | 2013-05-07 08:00 | 2013-05-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
100 | 80 | H.6 Training Needs Analysis | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 81.72 | 1307.52 | 1307.52 | 2013-06-28 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 1 | Finished | 1307.52 | 1307.52 | C2016-09 Data Loss Prevention System.xlsx
101 | 81 | Migration Strategy Document review | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-23 08:00 | 10d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
102 | 82 | Migration Strategy Fix document | 2013-10-16 08:00 | 2013-10-22 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-11-07 08:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
103 | 83 | Migration Strategy approval | 2013-10-30 08:00 | 2013-11-12 17:00 | 10d |  | 0 | 0 | 204.3 | 16344.0002 | 16344.0002 | 2013-11-18 13:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 16344.0002 | 16344.0002 | C2016-09 Data Loss Prevention System.xlsx
104 | 126 | E. DLP Control and Enforcement | 2013-08-14 08:00 | 2013-10-25 17:00 | 53d |  |  | 0 |  |  | 81393.1213 |  | 74d 6h | [5 empty] | 161805.6025 |  | 1 |  | 81393.1213 | 81393.1213 | C2016-09 Data Loss Prevention System.xlsx
105 | 84 | Define DLP Control and Enforcement output | 2013-08-14 08:00 | 2013-08-14 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-08-14 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
106 | 85 | Initial DLP Control and Enforcement workshop | 2013-08-15 08:00 | 2013-08-19 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-08-28 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 1 | Finished | 9806.4001 | 9806.4001 | C2016-09 Data Loss Prevention System.xlsx
107 | 86 | DLP Control and Enforcement Document writing | 2013-08-21 08:00 | 2013-08-30 17:00 | 8d |  | 0 | 0 | 408.6 | 26150.4004 | 26150.4004 | 2013-09-02 08:00 | 8d | 26150.4004 | 0 | 0 | 0 | 0 | 26150.4004 | 0 | 1 | Finished | 26150.4004 | 26150.4004 | C2016-09 Data Loss Prevention System.xlsx
108 | 87 | E.1 Comparion systems | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-09-02 08:00 | 8d | 26150.4004 | 0 | 0 | 0 | 0 | 26150.4004 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
109 | 88 | Follow-up DLP Control and Enforcement workshop | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-09-18 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 1 | Finished | 4903.2001 | 4903.2001 | C2016-09 Data Loss Prevention System.xlsx
110 | 89 | DLP Control and Enforcement Document writing | 2013-09-24 08:00 | 2013-09-27 17:00 | 4d |  | 0 | 0 | 408.6 | 13075.2002 | 13075.2002 | 2013-10-07 10:00 | 19d | 62107.2009 | 0 | 0 | 0 | 0 | 62107.2009 | 0 | 1 | Finished | 13075.2002 | 13075.2002 | C2016-09 Data Loss Prevention System.xlsx
111 | 90 | E.1 Comparion systems | 2013-09-24 08:00 | 2013-09-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-07 10:00 | 8d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
112 | 91 | DLP Control and Enforcement Document review | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-11-01 10:00 | 3d | 1961.28 | 0 | 0 | 0 | 0 | 1961.28 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
113 | 92 | DLP Control and Enforcement Fix document | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-11-05 15:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
114 | 93 | DLP Control and Enforcement approval | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 98.064 | 7845.1202 | 7845.1202 | 2013-11-12 15:00 | 10d | 7845.1202 | 0 | 0 | 0 | 0 | 7845.1202 | 0 | 1 | Finished | 7845.1202 | 7845.1202 | C2016-09 Data Loss Prevention System.xlsx
115 | 127 | F. Centralized Management and Monitoring Architecture for DLP | 2013-04-12 08:00 | 2013-11-22 17:00 | 161d |  |  | 0 |  |  | 81720.0012 |  | 138d | [5 empty] | 114408.0017 |  | 1 |  | 81720.0012 | 81720.0012 | C2016-09 Data Loss Prevention System.xlsx
116 | 94 | Define Mgt & Monitoring Architecture output | 2013-04-12 08:00 | 2013-04-12 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
117 | 95 | Initial Mgt & Monitoring Architecture workshop | 2013-04-15 08:00 | 2013-04-17 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-24 08:00 | 6d | 19612.8003 | 0 | 0 | 0 | 0 | 19612.8003 | 0 | 1 | Finished | 9806.4001 | 9806.4001 | C2016-09 Data Loss Prevention System.xlsx
118 | 139 | Mgt & Monitoring Architecture Document writing | 2013-04-18 08:00 | 2013-10-14 17:00 | 128d |  |  | 0 |  |  | 32688.0005 |  | 56d 5h | [5 empty] | 55569.6008 |  | 1 |  | 32688.0005 | 32688.0005 | C2016-09 Data Loss Prevention System.xlsx
119 | 96 | F.1 Definition of organisation & roles | 2013-04-23 08:00 | 2013-04-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
120 | 97 | F.2 log specs & formats | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-07-04 14:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
121 | 98 | F.3 Central management design | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
122 | 99 | F.4 Log collection design | 2013-10-11 08:00 | 2013-10-14 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-25 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
123 | 100 | F.5 Integration | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-07-04 14:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
124 | 101 | Follow-up Mgt & Monitoring Architecture workshop | 2013-04-22 08:00 | 2013-04-24 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-10-01 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 1 | Finished | 4903.2001 | 4903.2001 | C2016-09 Data Loss Prevention System.xlsx
125 | 140 | Mgt & Monitoring Architecture Document writing | 2013-04-25 08:00 | 2013-11-01 17:00 | 137d |  |  | 0 |  |  | 16344.0002 |  | 118d | [5 empty] | 16344.0002 |  | 1 |  | 16344.0002 | 16344.0002 | C2016-09 Data Loss Prevention System.xlsx
126 | 102 | F.1 Definition of organisation & roles | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
127 | 103 | F.2 log specs & formats | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-04 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
128 | 104 | F.3 Central management design | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
129 | 105 | F.4 Log collection design | 2013-10-29 08:00 | 2013-10-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-29 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
130 | 106 | F.5 Integration | 2013-10-31 08:00 | 2013-11-01 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-04 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
131 | 107 | Mgt & Monitoring Architecture Document review | 2013-10-22 08:00 | 2013-10-28 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-04 08:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
132 | 108 | Mgt & Monitoring Architecture Fix document | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 204.3 | 8172.0001 | 8172.0001 | 2013-10-11 08:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 1 | Finished | 8172.0001 | 8172.0001 | C2016-09 Data Loss Prevention System.xlsx
133 | 109 | Mgt & Monitoring Architecture approval | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-10-18 08:00 | 10d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
134 | 128 | G. High Level Solution for Network based DLP | 2013-11-25 08:00 | 2014-01-07 17:00 | 32d |  |  | 0 |  |  | 36447.1205 |  | 45d 4h | [5 empty] | 36447.1205 |  | 1 |  | 36447.1205 | 35793.3605 | C2016-09 Data Loss Prevention System.xlsx
135 | 110 | Define HL Solution for NW based DLP output | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-09-12 13:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
136 | 111 | Initial HL Solution for NW based DLP workshop | 2013-11-26 08:00 | 2013-11-28 17:00 | 3d |  | 0 | 0 | 20.43 | 490.32 | 490.32 | 2013-09-13 13:00 | 3d | 490.32 | 0 | 0 | 0 | 0 | 490.32 | 0 | 1 | Finished | 490.32 | 490.32 | C2016-09 Data Loss Prevention System.xlsx
137 | 141 | HL Solution for NW based DLP Document writing | 2013-11-29 08:00 | 2013-12-04 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 4d | [5 empty] | 13075.2002 |  | 1 |  | 13075.2002 | 13075.2002 | C2016-09 Data Loss Prevention System.xlsx
138 | 112 | G.1 Solution Design | 2013-11-29 08:00 | 2013-12-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-09-25 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
139 | 113 | G.2 Gap analysis | 2013-12-03 08:00 | 2013-12-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-09-27 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 1 | Finished | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
140 | 114 | Follow-up HL Solution for NW based DLP workshop | 2013-12-05 08:00 | 2013-12-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-01 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
141 | 142 | HL Solution for NW based DLP Document writing | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  |  | 0 |  |  | 6537.6001 |  | 4d | [5 empty] | 6537.6001 |  | 1 |  | 6537.6001 | 6537.6001 | C2016-09 Data Loss Prevention System.xlsx
142 | 115 | G.1 Solution Design | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-03 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
143 | 116 | G.2 Gap analysis | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-07 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
144 | 117 | HL Solution for NW based DLP Document review | 2013-12-11 08:00 | 2013-12-17 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-09 08:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
145 | 118 | HL Solution for NW based DLP Fix document | 2013-12-18 08:00 | 2013-12-24 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-16 08:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 3268.8 | C2016-09 Data Loss Prevention System.xlsx
146 | 119 | HL Solution for NW based DLP approval | 2013-12-25 08:00 | 2014-01-07 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-11-01 08:00 | 10d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 1 | Finished | 3268.8 | 2615.04 | C2016-09 Data Loss Prevention System.xlsx
4 | 0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 374d 8h | [5 empty] | 14466100 |  | 1 |  | 14362625 | 14362625 | C2016-10 Biofuel Refinery.xlsx
5 | 1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 253d 5h | 5857050 | 0 | 0 | 0 | 0 | 5857050 | 0 | 1 | Finished | 5856025 | 5856025 | C2016-10 Biofuel Refinery.xlsx
6 | 26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 | 2016-02-12 07:00 | 1d 5h | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 1 | Finished | 1350 | 1350 | C2016-10 Biofuel Refinery.xlsx
7 | 2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 1 | Finished | 10125 | 10125 | C2016-10 Biofuel Refinery.xlsx
8 | 3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 313d 7h | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | 1 | Finished | 500000 | 500000 | C2016-10 Biofuel Refinery.xlsx
9 | 24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 | 2016-02-15 07:00 | 20d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 1 | Finished | 50000 | 50000 | C2016-10 Biofuel Refinery.xlsx
10 | 5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 | 2016-02-15 07:00 | 84d 4h | 272000 | 0 | 0 | 0 | 0 | 272000 | 0 | 1 | Finished | 237000 | 237000 | C2016-10 Biofuel Refinery.xlsx
11 | 25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 | 2016-05-17 07:00 | 20d | 76000 | 0 | 0 | 0 | 0 | 76000 | 0 | 1 | Finished | 76000 | 76000 | C2016-10 Biofuel Refinery.xlsx
12 | 7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 | 2016-05-16 07:00 | 59d 8h | 161700 | 0 | 0 | 0 | 0 | 161700 | 0 | 1 | Finished | 121500 | 121500 | C2016-10 Biofuel Refinery.xlsx
13 | 8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 82d 1h | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | 1 | Finished | 600000 | 600000 | C2016-10 Biofuel Refinery.xlsx
14 | 9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 2015-08-31 07:00 | 155d 3h | 104850 | 0 | 0 | 0 | 0 | 104850 | 0 | 1 | Finished | 94500 | 94500 | C2016-10 Biofuel Refinery.xlsx
15 | 10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 | 2015-11-30 07:00 | 7d | 88150 | 0 | 0 | 0 | 0 | 88150 | 0 | 1 | Finished | 87250 | 87250 | C2016-10 Biofuel Refinery.xlsx
16 | 11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 85d | 1338250 | 0 | 0 | 0 | 0 | 1338250 | 0 | 1 | Finished | 1338250 | 1338250 | C2016-10 Biofuel Refinery.xlsx
17 | 13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 | 2015-10-12 07:00 | 80d | 360000 | 0 | 0 | 0 | 0 | 360000 | 0 | 1 | Finished | 360000 | 360000 | C2016-10 Biofuel Refinery.xlsx
18 | 14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 | 2015-10-12 07:00 | 100d | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 1 | Finished | 240000 | 240000 | C2016-10 Biofuel Refinery.xlsx
19 | 15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 175d | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | 1 | Finished | 800000 | 800000 | C2016-10 Biofuel Refinery.xlsx
20 | 16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 | 2016-02-29 07:00 | 56d 7h | 102200 | 0 | 0 | 0 | 0 | 102200 | 0 | 1 | Finished | 99000 | 99000 | C2016-10 Biofuel Refinery.xlsx
21 | 17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 135d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 1 | Finished | 400000 | 400000 | C2016-10 Biofuel Refinery.xlsx
22 | 18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 | 2016-04-04 07:00 | 56d 7h | 25550 | 0 | 0 | 0 | 0 | 25550 | 0 | 1 | Finished | 13500 | 13500 | C2016-10 Biofuel Refinery.xlsx
23 | 19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 220d | 129500 | 0 | 0 | 0 | 0 | 129500 | 0 | 1 | Finished | 129500 | 129500 | C2016-10 Biofuel Refinery.xlsx
24 | 20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 | 2016-05-02 07:00 | 20d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 1 | Finished | 4500 | 4500 | C2016-10 Biofuel Refinery.xlsx
25 | 21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 260d | 138500 | 0 | 0 | 0 | 0 | 138500 | 0 | 1 | Finished | 138500 | 138500 | C2016-10 Biofuel Refinery.xlsx
26 | 22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 | 2016-05-30 07:00 | 25d | 5625 | 0 | 0 | 0 | 0 | 5625 | 0 | 1 | Finished | 5625 | 5625 | C2016-10 Biofuel Refinery.xlsx
27 | 23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 | 2015-09-28 07:00 | 164d | 3200000 | 0 | 0 | 0 | 0 | 3200000 | 0 | 1 | Finished | 3200000 | 3200000 | C2016-10 Biofuel Refinery.xlsx
4 | 0 | Residential House (1) | 2016-03-08 08:00 | 2017-02-07 17:00 | 241d |  |  | 162472 |  |  | 162472 |  | 254d | [5 empty] | 163189 |  | 1 |  | 162472 | 162472 | C2016-11 Residential House (1).xlsx
5 | 56 | Voorbereiding | 2016-03-08 08:00 | 2016-04-06 17:00 | 22d |  |  | 14539 |  |  | 14539 |  | 22d | [5 empty] | 13303 |  | 1 |  | 14539 | 14539 | C2016-11 Residential House (1).xlsx
6 | 1 | Werfinrichting, werftoiletten | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 2848 | 0 | 0 | 2848 | 2016-03-08 08:00 | 4d | 2848 | 0 | 0 | -267 | 0 | 2581 | 0 | 1 | Finished | 2848 | 2848 | C2016-11 Residential House (1).xlsx
7 | 2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 30 | 0 | 0 | 30 | 2016-03-08 08:00 | 1d | 30 | 0 | 0 | -1 | 0 | 29 | 0 | 1 | Finished | 30 | 30 | C2016-11 Residential House (1).xlsx
8 | 3 | Transportkosten | 2016-03-08 08:00 | 2016-03-10 17:00 | 3d |  | 0 | 790 | 0 | 0 | 790 | 2016-03-08 08:00 | 1d | 790 | 0 | 0 | -687 | 0 | 103 | 0 | 1 | Finished | 790 | 790 | C2016-11 Residential House (1).xlsx
9 | 4 | Rijtijden ploegen | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 2016-03-08 08:00 | 1d | 100 | 0 | 0 | 2 | 0 | 102 | 0 | 1 | Finished | 100 | 100 | C2016-11 Residential House (1).xlsx
10 | 5 | Magazijn | 2016-03-08 08:00 | 2016-03-11 17:00 | 4d |  | 0 | 943 | 0 | 0 | 943 | 2016-03-08 08:00 | 2d | 943 | 0 | 0 | -480 | 0 | 463 | 0 | 1 | Finished | 943 | 943 | C2016-11 Residential House (1).xlsx
11 | 6 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-23 17:00 | 12d |  | 0 | 3318 | 0 | 0 | 3318 | 2016-03-08 08:00 | 10d | 3318 | 0 | 0 | 207 | 0 | 3525 | 0 | 1 | Finished | 3318 | 3318 | C2016-11 Residential House (1).xlsx
12 | 7 | Studiekosten aannemer | 2016-03-08 08:00 | 2016-04-06 17:00 | 22d |  | 0 | 6510 | 0 | 0 | 6510 | 2016-03-08 08:00 | 22d | 6510 | 0 | 0 | -10 | 0 | 6500 | 0 | 1 | Finished | 6510 | 6510 | C2016-11 Residential House (1).xlsx
13 | 57 | Funderingen | 2016-04-07 08:00 | 2016-05-10 17:00 | 24d |  |  | 11167 |  |  | 11167 |  | 28d | [5 empty] | 12263 |  | 1 |  | 11167 | 11167 | C2016-11 Residential House (1).xlsx
14 | 8 | Funderingen | 2016-04-07 08:00 | 2016-05-10 17:00 | 24d |  | 0 | 11167 | 0 | 0 | 11167 | 2016-04-07 08:00 | 28d | 11167 | 0 | 0 | 1096 | 0 | 12263 | 0 | 1 | Finished | 11167 | 11167 | C2016-11 Residential House (1).xlsx
15 | 58 | Ruwbouw | 2016-05-11 08:00 | 2016-08-12 17:00 | 68d |  |  | 46742 |  |  | 46742 |  | 68d | [5 empty] | 46399 |  | 1 |  | 46742 | 46742 | C2016-11 Residential House (1).xlsx
16 | 9 | GEWA/Metselwerk | 2016-05-11 08:00 | 2016-06-02 17:00 | 17d |  | 0 | 13968 | 0 | 0 | 13968 | 2016-05-17 08:00 | 16d | 13968 | 0 | 0 | -536 | 0 | 13432 | 0 | 1 | Finished | 13968 | 13968 | C2016-11 Residential House (1).xlsx
17 | 10 | Gewelven/Structuur | 2016-06-03 08:00 | 2016-06-07 17:00 | 3d |  | 0 | 5417 | 0 | 0 | 5417 | 2016-06-08 08:00 | 3d | 5417 | 0 | 0 | 0 | 0 | 5417 | 0 | 1 | Finished | 5417 | 5417 | C2016-11 Residential House (1).xlsx
18 | 11 | Uitbranden GEWA | 2016-06-03 08:00 | 2016-06-03 17:00 | 1d |  | 0 | 341 | 0 | 0 | 341 | 2016-06-08 08:00 | 1d | 341 | 0 | 0 | 0 | 0 | 341 | 0 | 1 | Finished | 341 | 341 | C2016-11 Residential House (1).xlsx
19 | 12 | Isolatie | 2016-06-08 08:00 | 2016-06-15 17:00 | 6d |  | 0 | 4629 | 0 | 0 | 4629 | 2016-06-13 08:00 | 6d | 4629 | 0 | 0 | 0 | 0 | 4629 | 0 | 1 | Finished | 4629 | 4629 | C2016-11 Residential House (1).xlsx
20 | 13 | Parament | 2016-06-16 08:00 | 2016-07-22 17:00 | 27d |  | 0 | 15804 | 0 | 0 | 15804 | 2016-06-21 08:00 | 27d | 15804 | 0 | 0 | 92 | 0 | 15896 | 0 | 1 | Finished | 15804 | 15804 | C2016-11 Residential House (1).xlsx
21 | 14 | Ytong/gipswanden | 2016-07-25 08:00 | 2016-07-28 17:00 | 4d |  | 0 | 2696 | 0 | 0 | 2696 | 2016-07-28 08:00 | 4d | 2696 | 0 | 0 | 0 | 0 | 2696 | 0 | 1 | Finished | 2696 | 2696 | C2016-11 Residential House (1).xlsx
22 | 15 | Dorpels | 2016-07-29 08:00 | 2016-07-29 17:00 | 1d |  | 0 | 646 | 0 | 0 | 646 | 2016-08-03 08:00 | 1d | 646 | 0 | 0 | 0 | 0 | 646 | 0 | 1 | Finished | 646 | 646 | C2016-11 Residential House (1).xlsx
23 | 16 | Voegwerk | 2016-07-29 08:00 | 2016-08-08 17:00 | 7d |  | 0 | 1821 | 0 | 0 | 1821 | 2016-08-03 08:00 | 8d | 1821 | 0 | 0 | 312 | 0 | 2133 | 0 | 1 | Finished | 1821 | 1821 | C2016-11 Residential House (1).xlsx
24 | 17 | Stelling | 2016-08-09 08:00 | 2016-08-12 17:00 | 4d |  | 0 | 1420 | 0 | 0 | 1420 | 2016-08-15 08:00 | 4d | 1420 | 0 | 0 | -211 | 0 | 1209 | 0 | 1 | Finished | 1420 | 1420 | C2016-11 Residential House (1).xlsx
25 | 59 | Dakwerken | 2016-08-15 08:00 | 2016-09-26 17:00 | 31d |  |  | 17795 |  |  | 17795 |  | 32d | [5 empty] | 19201 |  | 1 |  | 17795 | 17795 | C2016-11 Residential House (1).xlsx
26 | 18 | Daktimmer traditioneel / prefabkap | 2016-08-15 08:00 | 2016-09-02 17:00 | 15d |  | 0 | 9252 | 0 | 0 | 9252 | 2016-08-19 08:00 | 16d | 9252 | 0 | 0 | 691 | 0 | 9943 | 0 | 1 | Finished | 9252 | 9252 | C2016-11 Residential House (1).xlsx
27 | 19 | Dakdekken | 2016-09-05 08:00 | 2016-09-08 17:00 | 4d |  | 0 | 2317 | 0 | 0 | 2317 | 2016-09-12 08:00 | 4d | 2317 | 0 | 0 | 0 | 0 | 2317 | 0 | 1 | Finished | 2317 | 2317 | C2016-11 Residential House (1).xlsx
28 | 20 | Goten & afleiders | 2016-09-09 08:00 | 2016-09-09 17:00 | 1d |  | 0 | 177 | 0 | 0 | 177 | 2016-09-16 08:00 | 2d | 177 | 0 | 0 | 143 | 0 | 320 | 0 | 1 | Finished | 177 | 177 | C2016-11 Residential House (1).xlsx
29 | 21 | Zonnepanelen | 2016-09-09 08:00 | 2016-09-09 17:00 | 1d |  | 0 | 245 | 0 | 0 | 245 | 2016-09-16 08:00 | 1d | 245 | 0 | 0 | 4 | 0 | 249 | 0 | 1 | Finished | 245 | 245 | C2016-11 Residential House (1).xlsx
30 | 22 | Oversteken / gevelbekleding | 2016-09-09 08:00 | 2016-09-14 17:00 | 4d |  | 0 | 1509 | 0 | 0 | 1509 | 2016-09-16 08:00 | 4d | 1509 | 0 | 0 | 14 | 0 | 1523 | 0 | 1 | Finished | 1509 | 1509 | C2016-11 Residential House (1).xlsx
31 | 23 | Afdichting/Groendaken/Plat dak | 2016-09-15 08:00 | 2016-09-26 17:00 | 8d |  | 0 | 3438 | 0 | 0 | 3438 | 2016-09-22 08:00 | 8d | 3438 | 0 | 0 | 21 | 0 | 3459 | 0 | 1 | Finished | 3438 | 3438 | C2016-11 Residential House (1).xlsx
32 | 24 | Dakvlakramen | 2016-09-15 08:00 | 2016-09-19 17:00 | 3d |  | 0 | 857 | 0 | 0 | 857 | 2016-09-22 08:00 | 5d | 857 | 0 | 0 | 533 | 0 | 1390 | 0 | 1 | Finished | 857 | 857 | C2016-11 Residential House (1).xlsx
33 | 60 | Buitenschrijnwerk | 2016-09-27 08:00 | 2016-10-10 17:00 | 10d |  |  | 11316 |  |  | 11316 |  | 10d | [5 empty] | 11207 |  | 1 |  | 11316 | 11316 | C2016-11 Residential House (1).xlsx
34 | 25 | Kader buitenschrijnwerk Wachtbuizen | 2016-09-27 08:00 | 2016-09-30 17:00 | 4d |  | 0 | 1783 | 0 | 0 | 1783 | 2016-10-04 08:00 | 4d | 1783 | 0 | 0 | 16 | 0 | 1799 | 0 | 1 | Finished | 1783 | 1783 | C2016-11 Residential House (1).xlsx
35 | 26 | Buitenschrijnwerk plaatsen | 2016-10-03 08:00 | 2016-10-07 17:00 | 5d |  | 0 | 8910 | 0 | 0 | 8910 | 2016-10-10 08:00 | 5d | 8910 | 0 | 0 | -136 | 0 | 8774 | 0 | 1 | Finished | 8910 | 8910 | C2016-11 Residential House (1).xlsx
36 | 27 | Elastische voegen | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 | 2016-10-17 08:00 | 1d | 50 | 0 | 0 | 5 | 0 | 55 | 0 | 1 | Finished | 50 | 50 | C2016-11 Residential House (1).xlsx
37 | 28 | Ballustrades/trapleuningen | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 297 | 0 | 0 | 297 | 2016-10-17 08:00 | 1d | 297 | 0 | 0 | 3 | 0 | 300 | 0 | 1 | Finished | 297 | 297 | C2016-11 Residential House (1).xlsx
38 | 29 | Poort | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 276 | 0 | 0 | 276 | 2016-10-17 08:00 | 1d | 276 | 0 | 0 | 3 | 0 | 279 | 0 | 1 | Finished | 276 | 276 | C2016-11 Residential House (1).xlsx
39 | 61 | Binnenafwerking | 2016-11-10 08:00 | 2017-01-11 17:00 | 45d |  |  | 28749 |  |  | 28749 |  | 53d | [5 empty] | 30821 |  | 1 |  | 28749 | 28749 | C2016-11 Residential House (1).xlsx
40 | 30 | Plakwerken | 2016-11-10 08:00 | 2016-11-23 17:00 | 10d |  | 0 | 6891 | 0 | 0 | 6891 | 2016-11-18 08:00 | 9d | 6891 | 0 | 0 | -347 | 0 | 6544 | 0 | 1 | Finished | 6891 | 6891 | C2016-11 Residential House (1).xlsx
41 | 31 | Chapes | 2016-11-24 08:00 | 2016-12-12 17:00 | 13d |  | 0 | 4779 | 0 | 0 | 4779 | 2016-12-01 08:00 | 16d | 4779 | 0 | 0 | 782 | 0 | 5561 | 0 | 1 | Finished | 4779 | 4779 | C2016-11 Residential House (1).xlsx
42 | 32 | Vloerisolatie | 2016-12-14 08:00 | 2016-12-15 17:00 | 2d |  | 0 | 2697 | 0 | 0 | 2697 | 2016-12-28 08:00 | 3d | 2697 | 0 | 0 | 65 | 0 | 2762 | 0 | 1 | Finished | 2697 | 2697 | C2016-11 Residential House (1).xlsx
43 | 33 | Tegelwerken | 2016-12-16 08:00 | 2016-12-30 17:00 | 11d |  | 0 | 3027 | 0 | 0 | 3027 | 2017-01-02 08:00 | 14d | 3027 | 0 | 0 | 662 | 0 | 3689 | 0 | 1 | Finished | 3027 | 3027 | C2016-11 Residential House (1).xlsx
44 | 34 | Buisbek/zoldluik/platen zold/stijl | 2017-01-02 08:00 | 2017-01-02 17:00 | 1d |  | 0 | 227 | 0 | 0 | 227 | 2017-01-20 08:00 | 3d | 227 | 0 | 0 | 553 | 0 | 780 | 0 | 1 | Finished | 227 | 227 | C2016-11 Residential House (1).xlsx
45 | 35 | Binnendeuren/Uitbekledingen | 2017-01-02 08:00 | 2017-01-05 17:00 | 4d |  | 0 | 987 | 0 | 0 | 987 | 2017-01-20 08:00 | 4d | 987 | 0 | 0 | 7 | 0 | 994 | 0 | 1 | Finished | 987 | 987 | C2016-11 Residential House (1).xlsx
46 | 36 | Trap | 2017-01-02 08:00 | 2017-01-11 17:00 | 8d |  | 0 | 2150 | 0 | 0 | 2150 | 2017-01-20 08:00 | 8d | 2150 | 0 | 0 | -58 | 0 | 2092 | 0 | 1 | Finished | 2150 | 2150 | C2016-11 Residential House (1).xlsx
47 | 37 | Luchtdichten | 2017-01-02 08:00 | 2017-01-03 17:00 | 2d |  | 0 | 491 | 0 | 0 | 491 | 2017-01-20 08:00 | 3d | 491 | 0 | 0 | 408 | 0 | 899 | 0 | 1 | Finished | 491 | 491 | C2016-11 Residential House (1).xlsx
48 | 38 | Keuken (laminaat, kasten) | 2017-01-02 08:00 | 2017-01-10 17:00 | 7d |  | 0 | 7500 | 0 | 0 | 7500 | 2017-01-20 08:00 | 7d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 1 | Finished | 7500 | 7500 | C2016-11 Residential House (1).xlsx
49 | 62 | Technieken | 2016-10-10 08:00 | 2017-01-31 17:00 | 82d |  |  | 30762 |  |  | 30762 |  | 89d | [5 empty] | 28290 |  | 1 |  | 30762 | 30762 | C2016-11 Residential House (1).xlsx
50 | 39 | UZL | 2016-10-10 08:00 | 2016-10-12 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 | 2016-10-17 08:00 | 3d | 888 | 0 | 0 | 0 | 0 | 888 | 0 | 1 | Finished | 888 | 888 | C2016-11 Residential House (1).xlsx
51 | 40 | Betonplexplaten | 2016-10-10 08:00 | 2016-10-12 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 | 2016-10-17 08:00 | 1d | 625 | 0 | 0 | -370 | 0 | 255 | 0 | 1 | Finished | 625 | 625 | C2016-11 Residential House (1).xlsx
52 | 41 | Slijpen technieken / boringen | 2016-10-13 08:00 | 2016-10-19 17:00 | 5d |  | 0 | 1300 | 0 | 0 | 1300 | 2016-10-20 08:00 | 5d | 1300 | 0 | 0 | 25 | 0 | 1325 | 0 | 1 | Finished | 1300 | 1300 | C2016-11 Residential House (1).xlsx
53 | 42 | Bad en douche | 2016-12-13 08:00 | 2016-12-13 17:00 | 1d |  | 0 | 1152 | 0 | 0 | 1152 | 2016-12-23 08:00 | 3d | 1152 | 0 | 0 | -69 | 0 | 1083 | 0 | 1 | Finished | 1152 | 1152 | C2016-11 Residential House (1).xlsx
54 | 43 | Leidingen ventilatie | 2016-10-20 08:00 | 2016-10-24 17:00 | 3d |  | 0 | 1926 | 0 | 0 | 1926 | 2016-10-27 08:00 | 4d | 1926 | 0 | 0 | -59 | 0 | 1867 | 0 | 1 | Finished | 1926 | 1926 | C2016-11 Residential House (1).xlsx
55 | 44 | Leidingen san/CV/WP | 2016-10-25 08:00 | 2016-10-28 17:00 | 4d |  | 0 | 2481 | 0 | 0 | 2481 | 2016-11-02 08:00 | 4d | 2481 | 0 | 0 | -265 | 0 | 2216 | 0 | 1 | Finished | 2481 | 2481 | C2016-11 Residential House (1).xlsx
56 | 45 | Leidingen vloerverwarming | 2016-10-31 08:00 | 2016-11-03 17:00 | 4d |  | 0 | 2102 | 0 | 0 | 2102 | 2016-11-08 08:00 | 4d | 2102 | 0 | 0 | -215 | 0 | 1887 | 0 | 1 | Finished | 2102 | 2102 | C2016-11 Residential House (1).xlsx
57 | 46 | Afwerken ventilatie | 2017-01-02 08:00 | 2017-01-03 17:00 | 2d |  | 0 | 1899 | 0 | 0 | 1899 | 2017-01-20 08:00 | 1d | 1899 | 0 | 0 | -372 | 0 | 1527 | 0 | 1 | Finished | 1899 | 1899 | C2016-11 Residential House (1).xlsx
58 | 47 | Afwerken sanitair | 2017-01-04 08:00 | 2017-01-05 17:00 | 2d |  | 0 | 2565 | 0 | 0 | 2565 | 2017-01-23 08:00 | 4d | 2565 | 0 | 0 | 148 | 0 | 2713 | 0 | 1 | Finished | 2565 | 2565 | C2016-11 Residential House (1).xlsx
59 | 48 | Afwerken CV/WP | 2017-01-06 08:00 | 2017-01-11 17:00 | 4d |  | 0 | 6352 | 0 | 0 | 6352 | 2017-01-27 08:00 | 3d | 6352 | 0 | 0 | 0 | 0 | 6352 | 0 | 1 | Finished | 6352 | 6352 | C2016-11 Residential House (1).xlsx
60 | 49 | Leidingen electro | 2016-11-04 08:00 | 2016-11-09 17:00 | 4d |  | 0 | 2594 | 0 | 0 | 2594 | 2016-11-14 08:00 | 4d | 2594 | 0 | 0 | -920 | 0 | 1674 | 0 | 1 | Finished | 2594 | 2594 | C2016-11 Residential House (1).xlsx
61 | 50 | Afwerken electro | 2017-01-12 08:00 | 2017-01-18 17:00 | 5d |  | 0 | 3608 | 0 | 0 | 3608 | 2017-02-01 08:00 | 3d | 3608 | 0 | 0 | -274 | 0 | 3334 | 0 | 1 | Finished | 3608 | 3608 | C2016-11 Residential House (1).xlsx
62 | 51 | Verlichting | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 | 2017-02-06 08:00 | 1d | 50 | 0 | 0 | -20 | 0 | 30 | 0 | 1 | Finished | 50 | 50 | C2016-11 Residential House (1).xlsx
63 | 52 | Programmatie domotica | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 600 | 0 | 0 | 600 | 2017-02-06 08:00 | 1d | 600 | 0 | 0 | 6 | 0 | 606 | 0 | 1 | Finished | 600 | 600 | C2016-11 Residential House (1).xlsx
64 | 53 | Diepsondering, bron en aansluiting | 2017-01-19 08:00 | 2017-01-31 17:00 | 9d |  | 0 | 2460 | 0 | 0 | 2460 | 2017-02-06 08:00 | 9d | 2460 | 0 | 0 | -89 | 0 | 2371 | 0 | 1 | Finished | 2460 | 2460 | C2016-11 Residential House (1).xlsx
65 | 54 | Karweien | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 160 | 0 | 0 | 160 | 2017-02-06 08:00 | 1d | 160 | 0 | 0 | 2 | 0 | 162 | 0 | 1 | Finished | 160 | 160 | C2016-11 Residential House (1).xlsx
66 | 63 | Omgevingswerken | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d |  |  | 1402 |  |  | 1402 |  | 6d | [5 empty] | 1705 |  | 1 |  | 1402 | 1402 | C2016-11 Residential House (1).xlsx
67 | 55 | Opkuis werk (afvoer puin en afval) | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d |  | 0 | 1402 | 0 | 0 | 1402 | 2017-02-17 08:00 | 6d | 1402 | 0 | 0 | 303 | 0 | 1705 | 0 | 1 | Finished | 1402 | 1402 | C2016-11 Residential House (1).xlsx
4 | 0 | Residential House (2) | 2016-03-08 08:00 | 2017-04-18 17:00 | 291d |  |  | 222858 |  |  | 222858 |  | 291d | [5 empty] | 226285 |  | 1 |  | 222858 | 222858 | C2016-12 Residential House (2).xlsx
5 | 66 | Voorbereiding | 2016-03-08 08:00 | 2016-04-13 17:00 | 27d |  |  | 15468 |  |  | 15468 |  | 25d | [5 empty] | 15972 |  | 1 |  | 15468 | 15468 | C2016-12 Residential House (2).xlsx
6 | 1 | Werfinrichting/Werftoiletten | 2016-03-08 08:00 | 2016-03-09 17:00 | 2d |  | 0 | 350 | 0 | 0 | 350 | 2016-03-08 08:00 | 3d | 350 | 0 | 0 | 270 | 0 | 620 | 0 | 1 | Finished | 350 | 350 | C2016-12 Residential House (2).xlsx
7 | 2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 187 | 0 | 0 | 187 | 2016-03-08 08:00 | 1d | 187 | 0 | 0 | 0 | 0 | 187 | 0 | 1 | Finished | 187 | 187 | C2016-12 Residential House (2).xlsx
8 | 3 | Transportkosten | 2016-03-08 08:00 | 2016-03-15 17:00 | 6d |  | 0 | 1725 | 0 | 0 | 1725 | 2016-03-08 08:00 | 6d | 1725 | 0 | 0 | 24 | 0 | 1749 | 0 | 1 | Finished | 1725 | 1725 | C2016-12 Residential House (2).xlsx
9 | 4 | Magazijn | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 1192 | 0 | 0 | 1192 | 2016-03-08 08:00 | 5d | 1192 | 0 | 0 | 57 | 0 | 1249 | 0 | 1 | Finished | 1192 | 1192 | C2016-12 Residential House (2).xlsx
10 | 5 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-25 17:00 | 14d |  | 0 | 4128 | 0 | 0 | 4128 | 2016-03-08 08:00 | 15d | 4128 | 0 | 0 | 839 | 0 | 4967 | 0 | 1 | Finished | 4128 | 4128 | C2016-12 Residential House (2).xlsx
11 | 6 | Studiekosten aannemer | 2016-03-08 08:00 | 2016-04-13 17:00 | 27d |  | 0 | 7886 | 0 | 0 | 7886 | 2016-03-08 08:00 | 25d | 7886 | 0 | 0 | -686 | 0 | 7200 | 0 | 1 | Finished | 7886 | 7886 | C2016-12 Residential House (2).xlsx
12 | 67 | Funderingen | 2016-04-14 08:00 | 2016-05-25 17:00 | 30d |  |  | 8767 |  |  | 8767 |  | 28d | [5 empty] | 9270 |  | 1 |  | 8767 | 8767 | C2016-12 Residential House (2).xlsx
13 | 7 | Funderingen | 2016-04-14 08:00 | 2016-05-25 17:00 | 30d |  | 0 | 8767 | 0 | 0 | 8767 | 2016-04-12 08:00 | 28d | 8767 | 0 | 0 | 503 | 0 | 9270 | 0 | 1 | Finished | 8767 | 8767 | C2016-12 Residential House (2).xlsx
14 | 68 | Ruwbouw | 2016-05-26 08:00 | 2016-09-16 17:00 | 82d |  |  | 57970 |  |  | 57970 |  | 81d | [5 empty] | 58045 |  | 1 |  | 57970 | 57970 | C2016-12 Residential House (2).xlsx
15 | 8 | Gewa/Metselwerk | 2016-05-26 08:00 | 2016-06-24 17:00 | 22d |  | 0 | 18103 | 0 | 0 | 18103 | 2016-05-20 08:00 | 21d | 18103 | 0 | 0 | 96 | 0 | 18199 | 0 | 1 | Finished | 18103 | 18103 | C2016-12 Residential House (2).xlsx
16 | 9 | Gewelven/Structuur | 2016-06-27 08:00 | 2016-06-30 17:00 | 4d |  | 0 | 7328 | 0 | 0 | 7328 | 2016-06-20 08:00 | 5d | 7328 | 0 | 0 | 31 | 0 | 7359 | 0 | 1 | Finished | 7328 | 7328 | C2016-12 Residential House (2).xlsx
17 | 10 | Uitbranden GEWA | 2016-06-27 08:00 | 2016-06-27 17:00 | 1d |  | 0 | 479 | 0 | 0 | 479 | 2016-06-20 08:00 | 1d | 479 | 0 | 0 | -9 | 0 | 470 | 0 | 1 | Finished | 479 | 479 | C2016-12 Residential House (2).xlsx
18 | 11 | Isolatie | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 4451 | 0 | 0 | 4451 | 2016-06-27 08:00 | 5d | 4451 | 0 | 0 | -11 | 0 | 4440 | 0 | 1 | Finished | 4451 | 4451 | C2016-12 Residential House (2).xlsx
19 | 12 | Parament | 2016-07-08 08:00 | 2016-08-24 17:00 | 34d |  | 0 | 19722 | 0 | 0 | 19722 | 2016-07-04 08:00 | 34d | 19722 | 0 | 0 | 169 | 0 | 19891 | 0 | 1 | Finished | 19722 | 19722 | C2016-12 Residential House (2).xlsx
20 | 13 | Ytong/Gipswanden | 2016-08-25 08:00 | 2016-08-29 17:00 | 3d |  | 0 | 2447 | 0 | 0 | 2447 | 2016-08-19 08:00 | 3d | 2447 | 0 | 0 | 22 | 0 | 2469 | 0 | 1 | Finished | 2447 | 2447 | C2016-12 Residential House (2).xlsx
21 | 14 | Dorpels | 2016-08-30 08:00 | 2016-08-31 17:00 | 2d |  | 0 | 1065 | 0 | 0 | 1065 | 2016-08-24 08:00 | 2d | 1065 | 0 | 0 | 5 | 0 | 1070 | 0 | 1 | Finished | 1065 | 1065 | C2016-12 Residential House (2).xlsx
22 | 15 | Voegwerk | 2016-08-30 08:00 | 2016-09-08 17:00 | 8d |  | 0 | 2246 | 0 | 0 | 2246 | 2016-08-24 08:00 | 8d | 2246 | 0 | 0 | -171 | 0 | 2075 | 0 | 1 | Finished | 2246 | 2246 | C2016-12 Residential House (2).xlsx
23 | 16 | Stelling | 2016-09-09 08:00 | 2016-09-15 17:00 | 5d |  | 0 | 1836 | 0 | 0 | 1836 | 2016-09-05 08:00 | 4d | 1836 | 0 | 0 | -57 | 0 | 1779 | 0 | 1 | Finished | 1836 | 1836 | C2016-12 Residential House (2).xlsx
24 | 17 | Karweien | 2016-09-16 08:00 | 2016-09-16 17:00 | 1d |  | 0 | 293 | 0 | 0 | 293 | 2016-09-09 08:00 | 1d | 293 | 0 | 0 | 0 | 0 | 293 | 0 | 1 | Finished | 293 | 293 | C2016-12 Residential House (2).xlsx
25 | 69 | Dakwerken | 2016-09-19 08:00 | 2016-11-07 17:00 | 36d |  |  | 23852 |  |  | 23852 |  | 30d | [5 empty] | 22976 |  | 1 |  | 23852 | 23852 | C2016-12 Residential House (2).xlsx
26 | 18 | Daktimmer traditioneel/prefabkap | 2016-09-19 08:00 | 2016-10-14 17:00 | 20d |  | 0 | 11226 | 0 | 0 | 11226 | 2016-09-19 08:00 | 20d | 11226 | 0 | 0 | 0 | 0 | 11226 | 0 | 1 | Finished | 11226 | 11226 | C2016-12 Residential House (2).xlsx
27 | 19 | Dakdekken | 2016-10-17 08:00 | 2016-10-21 17:00 | 5d |  | 0 | 2752 | 0 | 0 | 2752 | 2016-10-10 08:00 | 4d | 2752 | 0 | 0 | -52 | 0 | 2700 | 0 | 1 | Finished | 2752 | 2752 | C2016-12 Residential House (2).xlsx
28 | 20 | Goten en afleiders | 2016-10-24 08:00 | 2016-10-25 17:00 | 2d |  | 0 | 321 | 0 | 0 | 321 | 2016-10-14 08:00 | 2d | 321 | 0 | 0 | 0 | 0 | 321 | 0 | 1 | Finished | 321 | 321 | C2016-12 Residential House (2).xlsx
29 | 21 | Zonnepanelen | 2016-10-24 08:00 | 2016-10-24 17:00 | 1d |  | 0 | 422 | 0 | 0 | 422 | 2016-10-14 08:00 | 1d | 422 | 0 | 0 | -3 | 0 | 419 | 0 | 1 | Finished | 422 | 422 | C2016-12 Residential House (2).xlsx
30 | 22 | Afdichting/groendaken/plat dak | 2016-10-26 08:00 | 2016-11-02 17:00 | 6d |  | 0 | 2677 | 0 | 0 | 2677 | 2016-10-18 08:00 | 3d | 2677 | 0 | 0 | -837 | 0 | 1840 | 0 | 1 | Finished | 2677 | 2677 | C2016-12 Residential House (2).xlsx
31 | 23 | Dakvlakramen | 2016-10-26 08:00 | 2016-11-07 17:00 | 9d |  | 0 | 4783 | 0 | 0 | 4783 | 2016-10-18 08:00 | 9d | 4783 | 0 | 0 | 16 | 0 | 4799 | 0 | 1 | Finished | 4783 | 4783 | C2016-12 Residential House (2).xlsx
32 | 24 | Karwei dakwerk | 2016-10-26 08:00 | 2016-11-02 17:00 | 6d |  | 0 | 1671 | 0 | 0 | 1671 | 2016-10-18 08:00 | 6d | 1671 | 0 | 0 | 0 | 0 | 1671 | 0 | 1 | Finished | 1671 | 1671 | C2016-12 Residential House (2).xlsx
33 | 70 | Buitenschrijnwerk | 2016-11-03 08:00 | 2016-11-18 17:00 | 12d |  |  | 4284 |  |  | 4284 |  | 13d | [5 empty] | 4162 |  | 1 |  | 4284 | 4284 | C2016-12 Residential House (2).xlsx
34 | 25 | Kader buitenschrijnwerk Wachtbuizen | 2016-11-03 08:00 | 2016-11-03 17:00 | 1d |  | 0 | 118 | 0 | 0 | 118 | 2016-10-21 08:00 | 1d | 118 | 0 | 0 | 0 | 0 | 118 | 0 | 1 | Finished | 118 | 118 | C2016-12 Residential House (2).xlsx
35 | 26 | Buitenschrijnwerk plaatsen | 2016-11-04 08:00 | 2016-11-15 17:00 | 8d |  | 0 | 2256 | 0 | 0 | 2256 | 2016-10-24 08:00 | 8d | 2256 | 0 | 0 | -7 | 0 | 2249 | 0 | 1 | Finished | 2256 | 2256 | C2016-12 Residential House (2).xlsx
36 | 27 | Elastische voegen | 2016-11-16 08:00 | 2016-11-16 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 | 2016-11-04 08:00 | 1d | 50 | 0 | 0 | 5 | 0 | 55 | 0 | 1 | Finished | 50 | 50 | C2016-12 Residential House (2).xlsx
37 | 28 | Ballustrades/Trapleuningen | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 710 | 0 | 0 | 710 | 2016-11-04 08:00 | 3d | 710 | 0 | 0 | -10 | 0 | 700 | 0 | 1 | Finished | 710 | 710 | C2016-12 Residential House (2).xlsx
38 | 29 | Poort | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 900 | 0 | 0 | 900 | 2016-11-04 08:00 | 3d | 900 | 0 | 0 | -110 | 0 | 790 | 0 | 1 | Finished | 900 | 900 | C2016-12 Residential House (2).xlsx
39 | 30 | Karwei binnenschrijnwerk | 2016-11-16 08:00 | 2016-11-16 17:00 | 1d |  | 0 | 250 | 0 | 0 | 250 | 2016-11-04 08:00 | 1d | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 1 | Finished | 250 | 250 | C2016-12 Residential House (2).xlsx
40 | 71 | Binnenafwerking | 2016-12-19 08:00 | 2017-03-06 17:00 | 56d |  |  | 43144 |  |  | 43144 |  | 61d | [5 empty] | 44937 |  | 1 |  | 43144 | 43144 | C2016-12 Residential House (2).xlsx
41 | 31 | Plakwerken | 2016-12-19 08:00 | 2016-12-30 17:00 | 10d |  | 0 | 8700 | 0 | 0 | 8700 | 2016-12-14 08:00 | 12d | 8700 | 0 | 0 | 780 | 0 | 9480 | 0 | 1 | Finished | 8700 | 8700 | C2016-12 Residential House (2).xlsx
42 | 32 | Chapes | 2017-01-02 08:00 | 2017-01-17 17:00 | 12d |  | 0 | 4025 | 0 | 0 | 4025 | 2016-12-30 08:00 | 14d | 4025 | 0 | 0 | 1104 | 0 | 5129 | 0 | 1 | Finished | 4025 | 4025 | C2016-12 Residential House (2).xlsx
43 | 33 | Vloerisolatie | 2017-01-19 08:00 | 2017-01-20 17:00 | 2d |  | 0 | 2245 | 0 | 0 | 2245 | 2017-01-20 08:00 | 2d | 2245 | 0 | 0 | -244 | 0 | 2001 | 0 | 1 | Finished | 2245 | 2245 | C2016-12 Residential House (2).xlsx
44 | 34 | Tegelwerken | 2017-01-23 08:00 | 2017-02-20 17:00 | 21d |  | 0 | 8951 | 0 | 0 | 8951 | 2017-01-24 08:00 | 22d | 8951 | 0 | 0 | -219 | 0 | 8732 | 0 | 1 | Finished | 8951 | 8951 | C2016-12 Residential House (2).xlsx
45 | 35 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-02-21 08:00 | 2017-02-23 17:00 | 3d |  | 0 | 600 | 0 | 0 | 600 | 2017-02-23 08:00 | 3d | 600 | 0 | 0 | 26 | 0 | 626 | 0 | 1 | Finished | 600 | 600 | C2016-12 Residential House (2).xlsx
46 | 36 | Binnendeuren/uitbekledingen | 2017-02-21 08:00 | 2017-02-27 17:00 | 5d |  | 0 | 1269 | 0 | 0 | 1269 | 2017-02-23 08:00 | 6d | 1269 | 0 | 0 | 308 | 0 | 1577 | 0 | 1 | Finished | 1269 | 1269 | C2016-12 Residential House (2).xlsx
47 | 37 | Trap | 2017-02-21 08:00 | 2017-03-02 17:00 | 8d |  | 0 | 2312 | 0 | 0 | 2312 | 2017-02-23 08:00 | 8d | 2312 | 0 | 0 | 38 | 0 | 2350 | 0 | 1 | Finished | 2312 | 2312 | C2016-12 Residential House (2).xlsx
48 | 38 | Luchtdichten | 2017-02-21 08:00 | 2017-02-22 17:00 | 2d |  | 0 | 549 | 0 | 0 | 549 | 2017-02-23 08:00 | 2d | 549 | 0 | 0 | 0 | 0 | 549 | 0 | 1 | Finished | 549 | 549 | C2016-12 Residential House (2).xlsx
49 | 39 | Keuken (laminaat, kasten) | 2017-02-21 08:00 | 2017-03-06 17:00 | 10d |  | 0 | 14493 | 0 | 0 | 14493 | 2017-02-23 08:00 | 10d | 14493 | 0 | 0 | 0 | 0 | 14493 | 0 | 1 | Finished | 14493 | 14493 | C2016-12 Residential House (2).xlsx
50 | 72 | Technieken | 2016-11-16 08:00 | 2017-03-14 17:00 | 85d |  |  | 37540 |  |  | 37540 |  | 93d | [5 empty] | 39090 |  | 1 |  | 37540 | 37540 | C2016-12 Residential House (2).xlsx
51 | 40 | UZL | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 | 2016-11-04 08:00 | 3d | 888 | 0 | 0 | 12 | 0 | 900 | 0 | 1 | Finished | 888 | 888 | C2016-12 Residential House (2).xlsx
52 | 41 | Betonplexplaten | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 | 2016-11-04 08:00 | 2d | 625 | 0 | 0 | -330 | 0 | 295 | 0 | 1 | Finished | 625 | 625 | C2016-12 Residential House (2).xlsx
53 | 42 | Slijpen technieken/boringen | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 1300 | 0 | 0 | 1300 | 2016-11-08 08:00 | 5d | 1300 | 0 | 0 | 150 | 0 | 1450 | 0 | 1 | Finished | 1300 | 1300 | C2016-12 Residential House (2).xlsx
54 | 43 | Bad en douche | 2017-01-18 08:00 | 2017-01-18 17:00 | 1d |  | 0 | 1152 | 0 | 0 | 1152 | 2017-01-19 08:00 | 1d | 1152 | 0 | 0 | -152 | 0 | 1000 | 0 | 1 | Finished | 1152 | 1152 | C2016-12 Residential House (2).xlsx
55 | 44 | Leidingen ventilatie | 2016-11-28 08:00 | 2016-11-30 17:00 | 3d |  | 0 | 1926 | 0 | 0 | 1926 | 2016-11-15 08:00 | 5d | 1926 | 0 | 0 | 1761 | 0 | 3687 | 0 | 1 | Finished | 1926 | 1926 | C2016-12 Residential House (2).xlsx
56 | 45 | Leidingen san/WP/CV | 2016-12-01 08:00 | 2016-12-06 17:00 | 4d |  | 0 | 2481 | 0 | 0 | 2481 | 2016-11-22 08:00 | 7d | 2481 | 0 | 0 | 934 | 0 | 3415 | 0 | 1 | Finished | 2481 | 2481 | C2016-12 Residential House (2).xlsx
57 | 46 | Leidingen vloerverwarming | 2016-12-07 08:00 | 2016-12-12 17:00 | 4d |  | 0 | 2557 | 0 | 0 | 2557 | 2016-12-01 08:00 | 5d | 2557 | 0 | 0 | 862 | 0 | 3419 | 0 | 1 | Finished | 2557 | 2557 | C2016-12 Residential House (2).xlsx
58 | 47 | Afwerken ventilatie | 2017-02-21 08:00 | 2017-02-22 17:00 | 2d |  | 0 | 1899 | 0 | 0 | 1899 | 2017-02-23 08:00 | 2d | 1899 | 0 | 0 | 0 | 0 | 1899 | 0 | 1 | Finished | 1899 | 1899 | C2016-12 Residential House (2).xlsx
59 | 48 | Afwerken sanitair | 2017-02-23 08:00 | 2017-02-24 17:00 | 2d |  | 0 | 2565 | 0 | 0 | 2565 | 2017-02-27 08:00 | 2d | 2565 | 0 | 0 | 130 | 0 | 2695 | 0 | 1 | Finished | 2565 | 2565 | C2016-12 Residential House (2).xlsx
60 | 49 | Afwerken CV/WP | 2017-02-27 08:00 | 2017-03-02 17:00 | 4d |  | 0 | 6352 | 0 | 0 | 6352 | 2017-03-01 08:00 | 3d | 6352 | 0 | 0 | -1446 | 0 | 4906 | 0 | 1 | Finished | 6352 | 6352 | C2016-12 Residential House (2).xlsx
61 | 50 | Leidingen electro | 2016-12-13 08:00 | 2016-12-16 17:00 | 4d |  | 0 | 2594 | 0 | 0 | 2594 | 2016-12-08 08:00 | 4d | 2594 | 0 | 0 | 6 | 0 | 2600 | 0 | 1 | Finished | 2594 | 2594 | C2016-12 Residential House (2).xlsx
62 | 51 | Afwerken electro | 2017-03-03 08:00 | 2017-03-09 17:00 | 5d |  | 0 | 3608 | 0 | 0 | 3608 | 2017-03-06 08:00 | 4d | 3608 | 0 | 0 | -486 | 0 | 3122 | 0 | 1 | Finished | 3608 | 3608 | C2016-12 Residential House (2).xlsx
63 | 52 | Verlichting | 2017-03-10 08:00 | 2017-03-13 17:00 | 2d |  | 0 | 6653 | 0 | 0 | 6653 | 2017-03-10 08:00 | 2d | 6653 | 0 | 0 | -29 | 0 | 6624 | 0 | 1 | Finished | 6653 | 6653 | C2016-12 Residential House (2).xlsx
64 | 53 | Diepsondering, bron en aansluiting | 2017-03-10 08:00 | 2017-03-14 17:00 | 3d |  | 0 | 2460 | 0 | 0 | 2460 | 2017-03-10 08:00 | 3d | 2460 | 0 | 0 | 138 | 0 | 2598 | 0 | 1 | Finished | 2460 | 2460 | C2016-12 Residential House (2).xlsx
65 | 54 | Karweien | 2017-03-10 08:00 | 2017-03-13 17:00 | 2d |  | 0 | 480 | 0 | 0 | 480 | 2017-03-10 08:00 | 2d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 1 | Finished | 480 | 480 | C2016-12 Residential House (2).xlsx
66 | 73 | Omgevingswerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  |  | 15833 |  |  | 15833 |  | 25d | [5 empty] | 15833 |  | 1 |  | 15833 | 15833 | C2016-12 Residential House (2).xlsx
67 | 55 | Opkuis werf (afvoer puin & afval) | 2017-03-15 08:00 | 2017-03-21 17:00 | 5d |  | 0 | 1400 | 0 | 0 | 1400 | 2017-03-15 08:00 | 5d | 1400 | 0 | 0 | 0 | 0 | 1400 | 0 | 1 | Finished | 1400 | 1400 | C2016-12 Residential House (2).xlsx
68 | 56 | Grondafvoer | 2017-03-15 08:00 | 2017-03-15 17:00 | 1d |  | 0 | 280 | 0 | 0 | 280 | 2017-03-15 08:00 | 1d | 280 | 0 | 0 | 0 | 0 | 280 | 0 | 1 | Finished | 280 | 280 | C2016-12 Residential House (2).xlsx
69 | 57 | Opritten en terassen | 2017-03-22 08:00 | 2017-04-18 17:00 | 20d |  | 0 | 6995 | 0 | 0 | 6995 | 2017-03-22 08:00 | 20d | 6995 | 0 | 0 | 0 | 0 | 6995 | 0 | 1 | Finished | 6995 | 6995 | C2016-12 Residential House (2).xlsx
70 | 58 | Tuinaanleg | 2017-03-22 08:00 | 2017-04-18 17:00 | 20d |  | 0 | 7158 | 0 | 0 | 7158 | 2017-03-22 08:00 | 20d | 7158 | 0 | 0 | 0 | 0 | 7158 | 0 | 1 | Finished | 7158 | 7158 | C2016-12 Residential House (2).xlsx
71 | 74 | Schilderwerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  |  | 16000 |  |  | 16000 |  | 25d | [5 empty] | 16000 |  | 1 |  | 16000 | 16000 | C2016-12 Residential House (2).xlsx
72 | 59 | Schilderwerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  | 0 | 16000 | 0 | 0 | 16000 | 2017-03-15 08:00 | 25d | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 | 1 | Finished | 16000 | 16000 | C2016-12 Residential House (2).xlsx
4 | 0 | Residential House (3) | 2016-03-08 08:00 | 2017-05-09 17:00 | 306d |  |  | 367952 |  |  | 367952 |  | 330d | [5 empty] | 379300 |  | 1 |  | 367952 | 367952 | C2016-13 Residential House (3).xlsx
5 | 53 | Voorbereiding | 2016-03-08 08:00 | 2016-03-18 17:00 | 9d |  |  | 34516 |  |  | 34516 |  | 13d | [5 empty] | 35174 |  | 1 |  | 34516 | 34516 | C2016-13 Residential House (3).xlsx
6 | 1 | Werfinrichting/Werftoiletten | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 29347 | 0 | 0 | 29347 | 2016-03-08 08:00 | 5d | 29347 | 0 | 0 | 7 | 0 | 29354 | 0 | 1 | Finished | 29347 | 29347 | C2016-13 Residential House (3).xlsx
7 | 2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-09 17:00 | 2d |  | 0 | 450 | 0 | 0 | 450 | 2016-03-08 08:00 | 3d | 450 | 0 | 0 | 378 | 0 | 828 | 0 | 1 | Finished | 450 | 450 | C2016-13 Residential House (3).xlsx
8 | 3 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-18 17:00 | 9d |  | 0 | 2517 | 0 | 0 | 2517 | 2016-03-08 08:00 | 13d | 2517 | 0 | 0 | 1675 | 0 | 4192 | 0 | 1 | Finished | 2517 | 2517 | C2016-13 Residential House (3).xlsx
9 | 4 | Passief | 2016-03-08 08:00 | 2016-03-17 17:00 | 8d |  | 0 | 2202 | 0 | 0 | 2202 | 2016-03-08 08:00 | 3d | 2202 | 0 | 0 | -1402 | 0 | 800 | 0 | 1 | Finished | 2202 | 2202 | C2016-13 Residential House (3).xlsx
10 | 54 | Funderingen | 2016-03-21 08:00 | 2016-04-26 17:00 | 27d |  |  | 12709 |  |  | 12709 |  | 32d | [5 empty] | 14531 |  | 1 |  | 12709 | 12709 | C2016-13 Residential House (3).xlsx
11 | 5 | Funderingen | 2016-03-21 08:00 | 2016-04-26 17:00 | 27d |  | 0 | 12709 | 0 | 0 | 12709 | 2016-03-25 08:00 | 32d | 12709 | 0 | 0 | 1822 | 0 | 14531 | 0 | 1 | Finished | 12709 | 12709 | C2016-13 Residential House (3).xlsx
12 | 55 | Ruwbouw | 2016-04-27 08:00 | 2016-09-28 17:00 | 111d |  |  | 93013 |  |  | 93013 |  | 111d | [5 empty] | 84768 |  | 1 |  | 93013 | 93013 | C2016-13 Residential House (3).xlsx
13 | 6 | GEWA/Metselwerken | 2016-04-27 08:00 | 2016-05-24 17:00 | 20d |  | 0 | 17864 | 0 | 0 | 17864 | 2016-05-10 08:00 | 17d | 17864 | 0 | 0 | -5192 | 0 | 12672 | 0 | 1 | Finished | 17864 | 17864 | C2016-13 Residential House (3).xlsx
14 | 7 | Gewelven/Structuur | 2016-05-25 08:00 | 2016-06-16 17:00 | 17d |  | 0 | 15388 | 0 | 0 | 15388 | 2016-06-02 08:00 | 16d | 15388 | 0 | 0 | -2976 | 0 | 12412 | 0 | 1 | Finished | 15388 | 15388 | C2016-13 Residential House (3).xlsx
15 | 8 | Uitbranden GEWA | 2016-05-25 08:00 | 2016-05-26 17:00 | 2d |  | 0 | 562 | 0 | 0 | 562 | 2016-06-02 08:00 | 2d | 562 | 0 | 0 | -262 | 0 | 300 | 0 | 1 | Finished | 562 | 562 | C2016-13 Residential House (3).xlsx
16 | 9 | Isolatie | 2016-06-17 08:00 | 2016-07-01 17:00 | 11d |  | 0 | 10384 | 0 | 0 | 10384 | 2016-06-24 08:00 | 9d | 10384 | 0 | 0 | -1829 | 0 | 8555 | 0 | 1 | Finished | 10384 | 10384 | C2016-13 Residential House (3).xlsx
17 | 10 | Parament | 2016-07-04 08:00 | 2016-08-29 17:00 | 41d |  | 0 | 37120 | 0 | 0 | 37120 | 2016-07-07 08:00 | 49d | 37120 | 0 | 0 | -1023 | 0 | 36097 | 0 | 1 | Finished | 37120 | 37120 | C2016-13 Residential House (3).xlsx
18 | 11 | Ytong/Gipswanden | 2016-08-30 08:00 | 2016-09-01 17:00 | 3d |  | 0 | 2517 | 0 | 0 | 2517 | 2016-09-14 08:00 | 3d | 2517 | 0 | 0 | -17 | 0 | 2500 | 0 | 1 | Finished | 2517 | 2517 | C2016-13 Residential House (3).xlsx
19 | 12 | Dorpels | 2016-09-02 08:00 | 2016-09-07 17:00 | 4d |  | 0 | 3081 | 0 | 0 | 3081 | 2016-09-19 08:00 | 6d | 3081 | 0 | 0 | 4237 | 0 | 7318 | 0 | 1 | Finished | 3081 | 3081 | C2016-13 Residential House (3).xlsx
20 | 13 | Voegwerk | 2016-09-02 08:00 | 2016-09-16 17:00 | 11d |  | 0 | 3082 | 0 | 0 | 3082 | 2016-09-19 08:00 | 11d | 3082 | 0 | 0 | 93 | 0 | 3175 | 0 | 1 | Finished | 3082 | 3082 | C2016-13 Residential House (3).xlsx
21 | 14 | Stelling | 2016-09-19 08:00 | 2016-09-27 17:00 | 7d |  | 0 | 2815 | 0 | 0 | 2815 | 2016-10-04 08:00 | 5d | 2815 | 0 | 0 | -1621 | 0 | 1194 | 0 | 1 | Finished | 2815 | 2815 | C2016-13 Residential House (3).xlsx
22 | 15 | Karweien | 2016-09-28 08:00 | 2016-09-28 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 | 2016-10-11 08:00 | 1d | 200 | 0 | 0 | 345 | 0 | 545 | 0 | 1 | Finished | 200 | 200 | C2016-13 Residential House (3).xlsx
23 | 56 | Dakwerken | 2016-09-29 08:00 | 2016-12-07 17:00 | 50d |  |  | 45039 |  |  | 45039 |  | 56d | [5 empty] | 47398 |  | 1 |  | 45039 | 45039 | C2016-13 Residential House (3).xlsx
24 | 16 | Daktimmer traditioneel/prefabkap | 2016-09-29 08:00 | 2016-11-21 17:00 | 38d |  | 0 | 38651 | 0 | 0 | 38651 | 2016-10-12 08:00 | 35d | 38651 | 0 | 0 | -1663 | 0 | 36988 | 0 | 1 | Finished | 38651 | 38651 | C2016-13 Residential House (3).xlsx
25 | 17 | Dakdekken | 2016-11-22 08:00 | 2016-12-02 17:00 | 9d |  | 0 | 5171 | 0 | 0 | 5171 | 2016-11-30 08:00 | 14d | 5171 | 0 | 0 | 1815 | 0 | 6986 | 0 | 1 | Finished | 5171 | 5171 | C2016-13 Residential House (3).xlsx
26 | 18 | Goten & afleiders | 2016-12-05 08:00 | 2016-12-07 17:00 | 3d |  | 0 | 1217 | 0 | 0 | 1217 | 2016-12-20 08:00 | 7d | 1217 | 0 | 0 | 2207 | 0 | 3424 | 0 | 1 | Finished | 1217 | 1217 | C2016-13 Residential House (3).xlsx
27 | 57 | Buitenschrijnwerk | 2016-12-08 08:00 | 2016-12-28 17:00 | 15d |  |  | 25604 |  |  | 25604 |  | 18d | [5 empty] | 28044 |  | 1 |  | 25604 | 25604 | C2016-13 Residential House (3).xlsx
28 | 19 | Kader buitenschrijnwerk / Wachtbuizen | 2016-12-08 08:00 | 2016-12-09 17:00 | 2d |  | 0 | 1895 | 0 | 0 | 1895 | 2016-12-29 08:00 | 1d | 1895 | 0 | 0 | -1651 | 0 | 244 | 0 | 1 | Finished | 1895 | 1895 | C2016-13 Residential House (3).xlsx
29 | 20 | Buitenschrijnwerk plaatsen | 2016-12-12 08:00 | 2016-12-22 17:00 | 9d |  | 0 | 18502 | 0 | 0 | 18502 | 2016-12-30 08:00 | 12d | 18502 | 0 | 0 | 3344 | 0 | 21846 | 0 | 1 | Finished | 18502 | 18502 | C2016-13 Residential House (3).xlsx
30 | 21 | Elastische voegen | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 657 | 0 | 0 | 657 | 2017-01-17 08:00 | 2d | 657 | 0 | 0 | -190 | 0 | 467 | 0 | 1 | Finished | 657 | 657 | C2016-13 Residential House (3).xlsx
31 | 22 | Poort | 2016-12-23 08:00 | 2016-12-28 17:00 | 4d |  | 0 | 3650 | 0 | 0 | 3650 | 2017-01-17 08:00 | 5d | 3650 | 0 | 0 | 957 | 0 | 4607 | 0 | 1 | Finished | 3650 | 3650 | C2016-13 Residential House (3).xlsx
32 | 23 | Karwei buitenschrijnwerk | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 900 | 0 | 0 | 900 | 2017-01-17 08:00 | 3d | 900 | 0 | 0 | -20 | 0 | 880 | 0 | 1 | Finished | 900 | 900 | C2016-13 Residential House (3).xlsx
33 | 58 | Binnenafwerking | 2017-01-27 08:00 | 2017-04-04 17:00 | 48d |  |  | 58308 |  |  | 58308 |  | 49d | [5 empty] | 61856 |  | 1 |  | 58308 | 58308 | C2016-13 Residential House (3).xlsx
34 | 24 | Plakwerken | 2017-01-27 08:00 | 2017-02-13 17:00 | 12d |  | 0 | 10564 | 0 | 0 | 10564 | 2017-02-20 08:00 | 15d | 10564 | 0 | 0 | 3832 | 0 | 14396 | 0 | 1 | Finished | 10564 | 10564 | C2016-13 Residential House (3).xlsx
35 | 25 | Chapes | 2017-02-14 08:00 | 2017-02-20 17:00 | 5d |  | 0 | 6259 | 0 | 0 | 6259 | 2017-03-13 08:00 | 10d | 6259 | 0 | 0 | 2067 | 0 | 8326 | 0 | 1 | Finished | 6259 | 6259 | C2016-13 Residential House (3).xlsx
36 | 26 | Vloerisolatie | 2017-02-22 08:00 | 2017-03-01 17:00 | 6d |  | 0 | 5374 | 0 | 0 | 5374 | 2017-03-22 08:00 | 5d | 5374 | 0 | 0 | -1120 | 0 | 4254 | 0 | 1 | Finished | 5374 | 5374 | C2016-13 Residential House (3).xlsx
37 | 27 | Tegelwerken | 2017-03-02 08:00 | 2017-03-22 17:00 | 15d |  | 0 | 17507 | 0 | 0 | 17507 | 2017-03-29 08:00 | 15d | 17507 | 0 | 0 | -563 | 0 | 16944 | 0 | 1 | Finished | 17507 | 17507 | C2016-13 Residential House (3).xlsx
38 | 28 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-03-23 08:00 | 2017-03-27 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 | 2017-04-19 08:00 | 2d | 625 | 0 | 0 | 32 | 0 | 657 | 0 | 1 | Finished | 625 | 625 | C2016-13 Residential House (3).xlsx
39 | 29 | Binnendeuren/Uitbekledingen | 2017-03-23 08:00 | 2017-03-29 17:00 | 5d |  | 0 | 8030 | 0 | 0 | 8030 | 2017-04-19 08:00 | 5d | 8030 | 0 | 0 | 0 | 0 | 8030 | 0 | 1 | Finished | 8030 | 8030 | C2016-13 Residential House (3).xlsx
40 | 30 | Trap | 2017-03-23 08:00 | 2017-03-27 17:00 | 3d |  | 0 | 6700 | 0 | 0 | 6700 | 2017-04-19 08:00 | 3d | 6700 | 0 | 0 | -624 | 0 | 6076 | 0 | 1 | Finished | 6700 | 6700 | C2016-13 Residential House (3).xlsx
41 | 31 | Luchtdichten | 2017-03-23 08:00 | 2017-04-04 17:00 | 9d |  | 0 | 2849 | 0 | 0 | 2849 | 2017-04-19 08:00 | 7d | 2849 | 0 | 0 | -55 | 0 | 2794 | 0 | 1 | Finished | 2849 | 2849 | C2016-13 Residential House (3).xlsx
42 | 32 | Karweiploeg | 2017-03-23 08:00 | 2017-03-24 17:00 | 2d |  | 0 | 400 | 0 | 0 | 400 | 2017-04-19 08:00 | 2d | 400 | 0 | 0 | -21 | 0 | 379 | 0 | 1 | Finished | 400 | 400 | C2016-13 Residential House (3).xlsx
43 | 59 | Technieken | 2016-12-23 08:00 | 2017-04-18 17:00 | 83d |  |  | 44115 |  |  | 44115 |  | 90d | [5 empty] | 52945 |  | 1 |  | 44115 | 44115 | C2016-13 Residential House (3).xlsx
44 | 33 | UZL | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 846 | 0 | 0 | 846 | 2017-01-17 08:00 | 4d | 846 | 0 | 0 | 446 | 0 | 1292 | 0 | 1 | Finished | 846 | 846 | C2016-13 Residential House (3).xlsx
45 | 34 | Betonplexplaten | 2016-12-23 08:00 | 2016-12-26 17:00 | 2d |  | 0 | 300 | 0 | 0 | 300 | 2017-01-17 08:00 | 2d | 300 | 0 | 0 | 1 | 0 | 301 | 0 | 1 | Finished | 300 | 300 | C2016-13 Residential House (3).xlsx
46 | 35 | Slijpen technieken/boringen | 2016-12-28 08:00 | 2017-01-03 17:00 | 5d |  | 0 | 6473 | 0 | 0 | 6473 | 2017-01-23 08:00 | 5d | 6473 | 0 | 0 | 261 | 0 | 6734 | 0 | 1 | Finished | 6473 | 6473 | C2016-13 Residential House (3).xlsx
47 | 36 | Bad en douche | 2017-02-21 08:00 | 2017-02-21 17:00 | 1d |  | 0 | 342 | 0 | 0 | 342 | 2017-03-20 08:00 | 2d | 342 | 0 | 0 | 52 | 0 | 394 | 0 | 1 | Finished | 342 | 342 | C2016-13 Residential House (3).xlsx
48 | 37 | Leidingen ventilatie | 2017-01-04 08:00 | 2017-01-06 17:00 | 3d |  | 0 | 1927 | 0 | 0 | 1927 | 2017-01-30 08:00 | 2d | 1927 | 0 | 0 | -114 | 0 | 1813 | 0 | 1 | Finished | 1927 | 1927 | C2016-13 Residential House (3).xlsx
49 | 38 | Leidingen san/WP/CV | 2017-01-09 08:00 | 2017-01-12 17:00 | 4d |  | 0 | 2454 | 0 | 0 | 2454 | 2017-02-01 08:00 | 4d | 2454 | 0 | 0 | 372 | 0 | 2826 | 0 | 1 | Finished | 2454 | 2454 | C2016-13 Residential House (3).xlsx
50 | 39 | Leidingen vloerverwarming | 2017-01-13 08:00 | 2017-01-20 17:00 | 6d |  | 0 | 5467 | 0 | 0 | 5467 | 2017-02-07 08:00 | 5d | 5467 | 0 | 0 | -934 | 0 | 4533 | 0 | 1 | Finished | 5467 | 5467 | C2016-13 Residential House (3).xlsx
51 | 40 | Afwerken ventilatie | 2017-03-23 08:00 | 2017-03-24 17:00 | 2d |  | 0 | 1887 | 0 | 0 | 1887 | 2017-04-19 08:00 | 1d | 1887 | 0 | 0 | 60 | 0 | 1947 | 0 | 1 | Finished | 1887 | 1887 | C2016-13 Residential House (3).xlsx
52 | 41 | Afwerken sanitair | 2017-03-27 08:00 | 2017-03-29 17:00 | 3d |  | 0 | 3539 | 0 | 0 | 3539 | 2017-04-20 08:00 | 4d | 3539 | 0 | 0 | 686 | 0 | 4225 | 0 | 1 | Finished | 3539 | 3539 | C2016-13 Residential House (3).xlsx
53 | 42 | Afwerken CV/WP | 2017-03-30 08:00 | 2017-04-04 17:00 | 4d |  | 0 | 5752 | 0 | 0 | 5752 | 2017-04-26 08:00 | 5d | 5752 | 0 | 0 | 3970 | 0 | 9722 | 0 | 1 | Finished | 5752 | 5752 | C2016-13 Residential House (3).xlsx
54 | 43 | Leidingen electro | 2017-01-23 08:00 | 2017-01-26 17:00 | 4d |  | 0 | 2737 | 0 | 0 | 2737 | 2017-02-14 08:00 | 4d | 2737 | 0 | 0 | -198 | 0 | 2539 | 0 | 1 | Finished | 2737 | 2737 | C2016-13 Residential House (3).xlsx
55 | 44 | Afwerken electro | 2017-04-05 08:00 | 2017-04-11 17:00 | 5d |  | 0 | 4986 | 0 | 0 | 4986 | 2017-05-03 08:00 | 8d | 4986 | 0 | 0 | 3896 | 0 | 8882 | 0 | 1 | Finished | 4986 | 4986 | C2016-13 Residential House (3).xlsx
56 | 45 | Verlichting | 2017-04-12 08:00 | 2017-04-13 17:00 | 2d |  | 0 | 1500 | 0 | 0 | 1500 | 2017-05-15 08:00 | 2d | 1500 | 0 | 0 | 16 | 0 | 1516 | 0 | 1 | Finished | 1500 | 1500 | C2016-13 Residential House (3).xlsx
57 | 46 | Diepsondering, bron en aansluiting | 2017-04-12 08:00 | 2017-04-18 17:00 | 5d |  | 0 | 4905 | 0 | 0 | 4905 | 2017-05-15 08:00 | 5d | 4905 | 0 | 0 | -405 | 0 | 4500 | 0 | 1 | Finished | 4905 | 4905 | C2016-13 Residential House (3).xlsx
58 | 47 | Karweien | 2017-04-12 08:00 | 2017-04-18 17:00 | 5d |  | 0 | 1000 | 0 | 0 | 1000 | 2017-05-15 08:00 | 6d | 1000 | 0 | 0 | 721 | 0 | 1721 | 0 | 1 | Finished | 1000 | 1000 | C2016-13 Residential House (3).xlsx
59 | 60 | Omgevingswerken | 2017-04-19 08:00 | 2017-04-26 17:00 | 6d |  |  | 2885 |  |  | 2885 |  | 6d | [5 empty] | 2700 |  | 1 |  | 2885 | 2885 | C2016-13 Residential House (3).xlsx
60 | 48 | Opkuis werf (afvoer puin en afval) | 2017-04-19 08:00 | 2017-04-25 17:00 | 5d |  | 0 | 1398 | 0 | 0 | 1398 | 2017-05-23 08:00 | 5d | 1398 | 0 | 0 | -98 | 0 | 1300 | 0 | 1 | Finished | 1398 | 1398 | C2016-13 Residential House (3).xlsx
61 | 50 | Grondafvoer | 2017-04-19 08:00 | 2017-04-26 17:00 | 6d |  | 0 | 1487 | 0 | 0 | 1487 | 2017-05-23 08:00 | 6d | 1487 | 0 | 0 | -87 | 0 | 1400 | 0 | 1 | Finished | 1487 | 1487 | C2016-13 Residential House (3).xlsx
62 | 61 | Schilderwerken | 2017-04-19 08:00 | 2017-05-02 17:00 | 10d |  |  | 6000 |  |  | 6000 |  | 10d | [5 empty] | 6121 |  | 1 |  | 6000 | 6000 | C2016-13 Residential House (3).xlsx
63 | 51 | Schilderwerken | 2017-04-19 08:00 | 2017-05-02 17:00 | 10d |  | 0 | 6000 | 0 | 0 | 6000 | 2017-05-23 08:00 | 10d | 6000 | 0 | 0 | 121 | 0 | 6121 | 0 | 1 | Finished | 6000 | 6000 | C2016-13 Residential House (3).xlsx
64 | 62 | Restklasse | 2017-05-03 08:00 | 2017-05-09 17:00 | 5d |  |  | 45763 |  |  | 45763 |  | 5d | [5 empty] | 45763 |  | 1 |  | 45763 | 45763 | C2016-13 Residential House (3).xlsx
65 | 52 | Rest | 2017-05-03 08:00 | 2017-05-09 17:00 | 5d |  | 0 | 45763 | 0 | 0 | 45763 | 2017-06-06 08:00 | 5d | 45763 | 0 | 0 | 0 | 0 | 45763 | 0 | 1 | Finished | 45763 | 45763 | C2016-13 Residential House (3).xlsx
4 | 0 | Residential House (4) | 2016-03-07 08:00 | 2017-05-29 17:00 | 321d |  |  | 218366 |  |  | 218366 |  | 320d | [5 empty] | 222021.78 |  | 1 |  | 218366 | 218366 | C2016-14 Residential House (4).xlsx
5 | 49 | Voorbereiding | 2016-03-07 08:00 | 2016-03-21 17:00 | 11d |  |  | 11265 |  |  | 11265 |  | 10d | [5 empty] | 12992 |  | 1 |  | 11265 | 11265 | C2016-14 Residential House (4).xlsx
6 | 1 | Werfinrichting | 2016-03-07 08:00 | 2016-03-09 17:00 | 3d |  | 0 | 3642 | 0 | 0 | 3642 | 2016-03-07 08:00 | 6d | 3642 | 0 | 0 | 1721 | 0 | 5363 | 0 | 1 | Finished | 3642 | 3642 | C2016-14 Residential House (4).xlsx
7 | 2 | Transportkosten | 2016-03-07 08:00 | 2016-03-15 17:00 | 7d |  | 0 | 2202 | 0 | 0 | 2202 | 2016-03-07 08:00 | 8d | 2202 | 0 | 0 | -56 | 0 | 2146 | 0 | 1 | Finished | 2202 | 2202 | C2016-14 Residential House (4).xlsx
8 | 3 | Rijtijden ploegen | 2016-03-07 08:00 | 2016-03-16 17:00 | 8d |  | 0 | 2190 | 0 | 0 | 2190 | 2016-03-07 08:00 | 7d | 2190 | 0 | 0 | -154 | 0 | 2036 | 0 | 1 | Finished | 2190 | 2190 | C2016-14 Residential House (4).xlsx
9 | 4 | Studiekosten | 2016-03-07 08:00 | 2016-03-21 17:00 | 11d |  | 0 | 3231 | 0 | 0 | 3231 | 2016-03-07 08:00 | 10d | 3231 | 0 | 0 | 216 | 0 | 3447 | 0 | 1 | Finished | 3231 | 3231 | C2016-14 Residential House (4).xlsx
10 | 50 | Funderingen | 2016-03-22 08:00 | 2016-05-02 17:00 | 30d |  |  | 12319 |  |  | 12319 |  | 30d | [5 empty] | 12361 |  | 1 |  | 12319 | 12319 | C2016-14 Residential House (4).xlsx
11 | 5 | Funderingen | 2016-03-22 08:00 | 2016-05-02 17:00 | 30d |  | 0 | 12319 | 0 | 0 | 12319 | 2016-03-21 08:00 | 30d | 12319 | 0 | 0 | 42 | 0 | 12361 | 0 | 1 | Finished | 12319 | 12319 | C2016-14 Residential House (4).xlsx
12 | 51 | Ruwbouw | 2016-05-03 08:00 | 2016-08-25 17:00 | 83d |  |  | 48401 |  |  | 48401 |  | 91d | [5 empty] | 52494 |  | 1 |  | 48401 | 48401 | C2016-14 Residential House (4).xlsx
13 | 6 | Gewa/metselwerk | 2016-05-03 08:00 | 2016-05-27 17:00 | 19d |  | 0 | 12997 | 0 | 0 | 12997 | 2016-05-02 08:00 | 19d | 12997 | 0 | 0 | 580 | 0 | 13577 | 0 | 1 | Finished | 12997 | 12997 | C2016-14 Residential House (4).xlsx
14 | 7 | Gewelven/Structuur | 2016-05-30 08:00 | 2016-06-07 17:00 | 7d |  | 0 | 5432 | 0 | 0 | 5432 | 2016-05-27 08:00 | 7d | 5432 | 0 | 0 | 0 | 0 | 5432 | 0 | 1 | Finished | 5432 | 5432 | C2016-14 Residential House (4).xlsx
15 | 8 | Uitbranden GEWA | 2016-05-30 08:00 | 2016-05-30 17:00 | 1d |  | 0 | 533 | 0 | 0 | 533 | 2016-05-27 08:00 | 1d | 533 | 0 | 0 | 819 | 0 | 1352 | 0 | 1 | Finished | 533 | 533 | C2016-14 Residential House (4).xlsx
16 | 9 | Isolatie | 2016-06-08 08:00 | 2016-06-14 17:00 | 5d |  | 0 | 1324 | 0 | 0 | 1324 | 2016-06-07 08:00 | 6d | 1324 | 0 | 0 | 292 | 0 | 1616 | 0 | 1 | Finished | 1324 | 1324 | C2016-14 Residential House (4).xlsx
17 | 10 | Parament | 2016-06-15 08:00 | 2016-08-02 17:00 | 35d |  | 0 | 19883 | 0 | 0 | 19883 | 2016-06-15 08:00 | 33d | 19883 | 0 | 0 | 464 | 0 | 20347 | 0 | 1 | Finished | 19883 | 19883 | C2016-14 Residential House (4).xlsx
18 | 11 | Ytong | 2016-08-03 08:00 | 2016-08-08 17:00 | 4d |  | 0 | 2879 | 0 | 0 | 2879 | 2016-08-01 08:00 | 5d | 2879 | 0 | 0 | 7 | 0 | 2886 | 0 | 1 | Finished | 2879 | 2879 | C2016-14 Residential House (4).xlsx
19 | 12 | Dorpels | 2016-08-09 08:00 | 2016-08-11 17:00 | 3d |  | 0 | 1934 | 0 | 0 | 1934 | 2016-08-08 08:00 | 2d | 1934 | 0 | 0 | -637 | 0 | 1297 | 0 | 1 | Finished | 1934 | 1934 | C2016-14 Residential House (4).xlsx
20 | 13 | Voegwerk | 2016-08-09 08:00 | 2016-08-16 17:00 | 6d |  | 0 | 1493 | 0 | 0 | 1493 | 2016-08-08 08:00 | 7d | 1493 | 0 | 0 | 568 | 0 | 2061 | 0 | 1 | Finished | 1493 | 1493 | C2016-14 Residential House (4).xlsx
21 | 14 | Stelling | 2016-08-17 08:00 | 2016-08-22 17:00 | 4d |  | 0 | 1392 | 0 | 0 | 1392 | 2016-08-17 08:00 | 9d | 1392 | 0 | 0 | 1258 | 0 | 2650 | 0 | 1 | Finished | 1392 | 1392 | C2016-14 Residential House (4).xlsx
22 | 15 | Crepi+Isolatie | 2016-08-23 08:00 | 2016-08-24 17:00 | 2d |  | 0 | 334 | 0 | 0 | 334 | 2016-08-30 08:00 | 1d | 334 | 0 | 0 | -234 | 0 | 100 | 0 | 1 | Finished | 334 | 334 | C2016-14 Residential House (4).xlsx
23 | 16 | Karweien | 2016-08-25 08:00 | 2016-08-25 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 | 2016-08-31 08:00 | 4d | 200 | 0 | 0 | 976 | 0 | 1176 | 0 | 1 | Finished | 200 | 200 | C2016-14 Residential House (4).xlsx
24 | 52 | Dakwerken | 2016-08-26 08:00 | 2016-12-05 17:00 | 72d |  |  | 39200 |  |  | 39200 |  | 65d | [5 empty] | 37877.78 |  | 1 |  | 39200 | 39200 | C2016-14 Residential House (4).xlsx
25 | 17 | Daktimmer traditioneel/prefabkap | 2016-08-26 08:00 | 2016-10-13 17:00 | 35d |  | 0 | 13456 | 0 | 0 | 13456 | 2016-09-06 08:00 | 34d | 13456 | 0 | 0 | -809.22 | 0 | 12646.78 | 0 | 1 | Finished | 13456 | 13456 | C2016-14 Residential House (4).xlsx
26 | 18 | Dakdekken | 2016-10-14 08:00 | 2016-11-10 17:00 | 20d |  | 0 | 15873 | 0 | 0 | 15873 | 2016-10-24 08:00 | 18d | 15873 | 0 | 0 | -584 | 0 | 15289 | 0 | 1 | Finished | 15873 | 15873 | C2016-14 Residential House (4).xlsx
27 | 19 | Goten & Afleiders | 2016-11-11 08:00 | 2016-11-15 17:00 | 3d |  | 0 | 1282 | 0 | 0 | 1282 | 2016-11-17 08:00 | 3d | 1282 | 0 | 0 | 52 | 0 | 1334 | 0 | 1 | Finished | 1282 | 1282 | C2016-14 Residential House (4).xlsx
28 | 20 | Oversteken/Gevelbekleding | 2016-11-11 08:00 | 2016-12-02 17:00 | 16d |  | 0 | 6265 | 0 | 0 | 6265 | 2016-11-17 08:00 | 12d | 6265 | 0 | 0 | -178 | 0 | 6087 | 0 | 1 | Finished | 6265 | 6265 | C2016-14 Residential House (4).xlsx
29 | 21 | Dakvlakramen | 2016-12-05 08:00 | 2016-12-05 17:00 | 1d |  | 0 | 2324 | 0 | 0 | 2324 | 2016-12-05 08:00 | 1d | 2324 | 0 | 0 | 197 | 0 | 2521 | 0 | 1 | Finished | 2324 | 2324 | C2016-14 Residential House (4).xlsx
30 | 53 | Buitenschrijnwerk | 2016-12-06 08:00 | 2016-12-26 17:00 | 15d |  |  | 23493 |  |  | 23493 |  | 16d | [5 empty] | 23840 |  | 1 |  | 23493 | 23493 | C2016-14 Residential House (4).xlsx
31 | 22 | Buitenschrijnwerk plaatsen | 2016-12-06 08:00 | 2016-12-26 17:00 | 15d |  | 0 | 23493 | 0 | 0 | 23493 | 2016-12-06 08:00 | 16d | 23493 | 0 | 0 | 347 | 0 | 23840 | 0 | 1 | Finished | 23493 | 23493 | C2016-14 Residential House (4).xlsx
32 | 54 | Binnenafwerking | 2017-01-23 08:00 | 2017-04-05 17:00 | 53d |  |  | 30237 |  |  | 30237 |  | 53d | [5 empty] | 31324 |  | 1 |  | 30237 | 30237 | C2016-14 Residential House (4).xlsx
33 | 23 | Plakwerken | 2017-01-23 08:00 | 2017-02-07 17:00 | 12d |  | 0 | 9564 | 0 | 0 | 9564 | 2017-01-26 08:00 | 12d | 9564 | 0 | 0 | 10 | 0 | 9574 | 0 | 1 | Finished | 9564 | 9564 | C2016-14 Residential House (4).xlsx
34 | 24 | Chapes/uitvullingen | 2017-02-08 08:00 | 2017-02-14 17:00 | 5d |  | 0 | 2432 | 0 | 0 | 2432 | 2017-02-13 08:00 | 5d | 2432 | 0 | 0 | 1 | 0 | 2433 | 0 | 1 | Finished | 2432 | 2432 | C2016-14 Residential House (4).xlsx
35 | 25 | Vloerisolatie | 2017-02-16 08:00 | 2017-03-01 17:00 | 10d |  | 0 | 2739 | 0 | 0 | 2739 | 2017-02-21 08:00 | 10d | 2739 | 0 | 0 | 2 | 0 | 2741 | 0 | 1 | Finished | 2739 | 2739 | C2016-14 Residential House (4).xlsx
36 | 26 | Tegelwerken | 2017-03-02 08:00 | 2017-03-10 17:00 | 7d |  | 0 | 3633 | 0 | 0 | 3633 | 2017-03-07 08:00 | 7d | 3633 | 0 | 0 | 705 | 0 | 4338 | 0 | 1 | Finished | 3633 | 3633 | C2016-14 Residential House (4).xlsx
37 | 27 | Voorbereiding+Gyplat | 2017-03-13 08:00 | 2017-03-22 17:00 | 8d |  | 0 | 2792 | 0 | 0 | 2792 | 2017-03-16 08:00 | 6d | 2792 | 0 | 0 | -1102 | 0 | 1690 | 0 | 1 | Finished | 2792 | 2792 | C2016-14 Residential House (4).xlsx
38 | 28 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-03-13 08:00 | 2017-03-16 17:00 | 4d |  | 0 | 837 | 0 | 0 | 837 | 2017-03-16 08:00 | 4d | 837 | 0 | 0 | 258 | 0 | 1095 | 0 | 1 | Finished | 837 | 837 | C2016-14 Residential House (4).xlsx
39 | 29 | Binnendeuren/Uitbekleding | 2017-03-23 08:00 | 2017-03-28 17:00 | 4d |  | 0 | 1021 | 0 | 0 | 1021 | 2017-03-24 08:00 | 3d | 1021 | 0 | 0 | -133 | 0 | 888 | 0 | 1 | Finished | 1021 | 1021 | C2016-14 Residential House (4).xlsx
40 | 30 | Trap | 2017-03-23 08:00 | 2017-03-30 17:00 | 6d |  | 0 | 1650 | 0 | 0 | 1650 | 2017-03-24 08:00 | 6d | 1650 | 0 | 0 | 68 | 0 | 1718 | 0 | 1 | Finished | 1650 | 1650 | C2016-14 Residential House (4).xlsx
41 | 31 | Luchtdichten | 2017-03-23 08:00 | 2017-04-05 17:00 | 10d |  | 0 | 5569 | 0 | 0 | 5569 | 2017-03-24 08:00 | 12d | 5569 | 0 | 0 | 1278 | 0 | 6847 | 0 | 1 | Finished | 5569 | 5569 | C2016-14 Residential House (4).xlsx
42 | 55 | Technieken | 2016-12-27 08:00 | 2017-04-07 17:00 | 74d |  |  | 38827 |  |  | 38827 |  | 72d | [5 empty] | 36416 |  | 1 |  | 38827 | 38827 | C2016-14 Residential House (4).xlsx
43 | 32 | UZL | 2016-12-27 08:00 | 2016-12-29 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 | 2016-12-28 08:00 | 3d | 888 | 0 | 0 | -56 | 0 | 832 | 0 | 1 | Finished | 888 | 888 | C2016-14 Residential House (4).xlsx
44 | 33 | Betonplexplaten | 2016-12-27 08:00 | 2016-12-27 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 2016-12-28 08:00 | 1d | 100 | 0 | 0 | 149 | 0 | 249 | 0 | 1 | Finished | 100 | 100 | C2016-14 Residential House (4).xlsx
45 | 34 | Slijpen technieken/Boringen | 2016-12-30 08:00 | 2017-01-04 17:00 | 4d |  | 0 | 1296 | 0 | 0 | 1296 | 2017-01-02 08:00 | 7d | 1296 | 0 | 0 | 603 | 0 | 1899 | 0 | 1 | Finished | 1296 | 1296 | C2016-14 Residential House (4).xlsx
46 | 35 | Bad &amp; douche | 2017-02-15 08:00 | 2017-02-15 17:00 | 1d |  | 0 | 320 | 0 | 0 | 320 | 2017-02-20 08:00 | 1d | 320 | 0 | 0 | 90 | 0 | 410 | 0 | 1 | Finished | 320 | 320 | C2016-14 Residential House (4).xlsx
47 | 36 | Leidingen vent | 2017-01-05 08:00 | 2017-01-09 17:00 | 3d |  | 0 | 2580 | 0 | 0 | 2580 | 2017-01-11 08:00 | 2d | 2580 | 0 | 0 | -1280 | 0 | 1300 | 0 | 1 | Finished | 2580 | 2580 | C2016-14 Residential House (4).xlsx
48 | 37 | Leidingen san/WP/CV | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d |  | 0 | 3711 | 0 | 0 | 3711 | 2017-01-13 08:00 | 6d | 3711 | 0 | 0 | -443 | 0 | 3268 | 0 | 1 | Finished | 3711 | 3711 | C2016-14 Residential House (4).xlsx
49 | 38 | Afwerken ventilatie | 2017-03-13 08:00 | 2017-03-14 17:00 | 2d |  | 0 | 2317 | 0 | 0 | 2317 | 2017-03-16 08:00 | 3d | 2317 | 0 | 0 | -266 | 0 | 2051 | 0 | 1 | Finished | 2317 | 2317 | C2016-14 Residential House (4).xlsx
50 | 39 | Afwerken sanitair | 2017-03-15 08:00 | 2017-03-17 17:00 | 3d |  | 0 | 6472 | 0 | 0 | 6472 | 2017-03-21 08:00 | 1d | 6472 | 0 | 0 | -460 | 0 | 6012 | 0 | 1 | Finished | 6472 | 6472 | C2016-14 Residential House (4).xlsx
51 | 40 | Afwerken CV/WP | 2017-03-20 08:00 | 2017-03-21 17:00 | 2d |  | 0 | 5903 | 0 | 0 | 5903 | 2017-03-22 08:00 | 1d | 5903 | 0 | 0 | -281 | 0 | 5622 | 0 | 1 | Finished | 5903 | 5903 | C2016-14 Residential House (4).xlsx
52 | 41 | Leidingen electro | 2017-01-17 08:00 | 2017-01-20 17:00 | 4d |  | 0 | 2701 | 0 | 0 | 2701 | 2017-01-23 08:00 | 3d | 2701 | 0 | 0 | -153 | 0 | 2548 | 0 | 1 | Finished | 2701 | 2701 | C2016-14 Residential House (4).xlsx
53 | 42 | Afwerken electro | 2017-03-22 08:00 | 2017-03-27 17:00 | 4d |  | 0 | 3807 | 0 | 0 | 3807 | 2017-03-23 08:00 | 3d | 3807 | 0 | 0 | -229 | 0 | 3578 | 0 | 1 | Finished | 3807 | 3807 | C2016-14 Residential House (4).xlsx
54 | 43 | Zonneboiler | 2017-03-28 08:00 | 2017-03-28 17:00 | 1d |  | 0 | 455 | 0 | 0 | 455 | 2017-03-28 08:00 | 2d | 455 | 0 | 0 | 0 | 0 | 455 | 0 | 1 | Finished | 455 | 455 | C2016-14 Residential House (4).xlsx
55 | 44 | PV panelen | 2017-03-28 08:00 | 2017-03-30 17:00 | 3d |  | 0 | 4950 | 0 | 0 | 4950 | 2017-03-28 08:00 | 3d | 4950 | 0 | 0 | 0 | 0 | 4950 | 0 | 1 | Finished | 4950 | 4950 | C2016-14 Residential House (4).xlsx
56 | 45 | Verlichting | 2017-03-28 08:00 | 2017-03-28 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 2017-03-28 08:00 | 1d | 100 | 0 | 0 | 22 | 0 | 122 | 0 | 1 | Finished | 100 | 100 | C2016-14 Residential House (4).xlsx
57 | 46 | Karweien | 2017-03-28 08:00 | 2017-04-07 17:00 | 9d |  | 0 | 3227 | 0 | 0 | 3227 | 2017-03-28 08:00 | 8d | 3227 | 0 | 0 | -107 | 0 | 3120 | 0 | 1 | Finished | 3227 | 3227 | C2016-14 Residential House (4).xlsx
58 | 56 | Omgevingswerken | 2017-04-10 08:00 | 2017-04-14 17:00 | 5d |  |  | 1406 |  |  | 1406 |  | 5d | [5 empty] | 1499 |  | 1 |  | 1406 | 1406 | C2016-14 Residential House (4).xlsx
59 | 47 | Opkuis werf (afvoeren puin & afval) | 2017-04-10 08:00 | 2017-04-14 17:00 | 5d |  | 0 | 1406 | 0 | 0 | 1406 | 2017-04-07 08:00 | 5d | 1406 | 0 | 0 | 93 | 0 | 1499 | 0 | 1 | Finished | 1406 | 1406 | C2016-14 Residential House (4).xlsx
60 | 57 | Restklasse | 2017-04-17 08:00 | 2017-05-29 17:00 | 31d |  |  | 13218 |  |  | 13218 |  | 31d | [5 empty] | 13218 |  | 1 |  | 13218 | 13218 | C2016-14 Residential House (4).xlsx
61 | 48 | Rest | 2017-04-17 08:00 | 2017-05-29 17:00 | 31d |  | 0 | 13218 | 0 | 0 | 13218 | 2017-04-14 08:00 | 31d | 13218 | 0 | 0 | 0 | 0 | 13218 | 0 | 1 | Finished | 13218 | 13218 | C2016-14 Residential House (4).xlsx
4 | 0 | Residential House Structural Work | 2016-03-07 08:00 | 2016-08-29 17:00 | 126d |  |  | 95694 |  |  | 95694 |  | 130d | [5 empty] | 100763 |  | 1 |  | 95694 | 95694 | C2016-15 Residential House Structural Work.xlsx
5 | 20 | Voorbereiding | 2016-03-07 08:00 | 2016-03-31 17:00 | 19d |  |  | 6220 |  |  | 6220 |  | 10d | [5 empty] | 6799 |  | 1 |  | 6220 | 6220 | C2016-15 Residential House Structural Work.xlsx
6 | 1 | Transportkosten | 2016-03-07 08:00 | 2016-03-09 17:00 | 3d |  | 0 | 750 | 0 | 0 | 750 | 2016-03-07 08:00 | 10d | 750 | 0 | 0 | 2131 | 0 | 2881 | 0 | 1 | Finished | 750 | 750 | C2016-15 Residential House Structural Work.xlsx
7 | 2 | Studiekosten | 2016-03-07 08:00 | 2016-03-31 17:00 | 19d |  | 0 | 5470 | 0 | 0 | 5470 | 2016-03-07 08:00 | 10d | 5470 | 0 | 0 | -1552 | 0 | 3918 | 0 | 1 | Finished | 5470 | 5470 | C2016-15 Residential House Structural Work.xlsx
8 | 21 | Funderingen | 2016-04-01 08:00 | 2016-05-09 17:00 | 27d |  |  | 12241 |  |  | 12241 |  | 31d | [5 empty] | 13891 |  | 1 |  | 12241 | 12241 | C2016-15 Residential House Structural Work.xlsx
9 | 3 | Funderingen | 2016-04-01 08:00 | 2016-05-09 17:00 | 27d |  | 0 | 12241 | 0 | 0 | 12241 | 2016-03-21 08:00 | 31d | 12241 | 0 | 0 | 1650 | 0 | 13891 | 0 | 1 | Finished | 12241 | 12241 | C2016-15 Residential House Structural Work.xlsx
10 | 22 | Ruwbouw | 2016-05-10 08:00 | 2016-08-29 17:00 | 80d |  |  | 77233 |  |  | 77233 |  | 89d | [5 empty] | 80073 |  | 1 |  | 77233 | 77233 | C2016-15 Residential House Structural Work.xlsx
11 | 4 | Gewa/Metselwerk | 2016-05-10 08:00 | 2016-06-09 17:00 | 23d |  | 0 | 22982 | 0 | 0 | 22982 | 2016-05-03 08:00 | 26d | 22982 | 0 | 0 | 827 | 0 | 23809 | 0 | 1 | Finished | 22982 | 22982 | C2016-15 Residential House Structural Work.xlsx
12 | 5 | Gewelven/Structuur | 2016-06-10 08:00 | 2016-06-21 17:00 | 8d |  | 0 | 10216 | 0 | 0 | 10216 | 2016-06-08 08:00 | 3d | 10216 | 0 | 0 | -2411 | 0 | 7805 | 0 | 1 | Finished | 10216 | 10216 | C2016-15 Residential House Structural Work.xlsx
13 | 6 | Uitbranden GEWA | 2016-06-10 08:00 | 2016-06-13 17:00 | 2d |  | 0 | 528 | 0 | 0 | 528 | 2016-06-08 08:00 | 2d | 528 | 0 | 0 | -162 | 0 | 366 | 0 | 1 | Finished | 528 | 528 | C2016-15 Residential House Structural Work.xlsx
14 | 7 | Isolatie | 2016-06-22 08:00 | 2016-07-01 17:00 | 8d |  | 0 | 5773 | 0 | 0 | 5773 | 2016-06-13 08:00 | 8d | 5773 | 0 | 0 | 555 | 0 | 6328 | 0 | 1 | Finished | 5773 | 5773 | C2016-15 Residential House Structural Work.xlsx
15 | 8 | Parament | 2016-07-04 08:00 | 2016-08-03 17:00 | 23d |  | 0 | 27764 | 0 | 0 | 27764 | 2016-06-23 08:00 | 25d | 27764 | 0 | 0 | 1221 | 0 | 28985 | 0 | 1 | Finished | 27764 | 27764 | C2016-15 Residential House Structural Work.xlsx
16 | 9 | Ytong | 2016-08-04 08:00 | 2016-08-15 17:00 | 8d |  | 0 | 2276 | 0 | 0 | 2276 | 2016-07-28 08:00 | 14d | 2276 | 0 | 0 | 1864 | 0 | 4140 | 0 | 1 | Finished | 2276 | 2276 | C2016-15 Residential House Structural Work.xlsx
17 | 10 | Dorpels | 2016-08-16 08:00 | 2016-08-17 17:00 | 2d |  | 0 | 2878 | 0 | 0 | 2878 | 2016-08-17 08:00 | 4d | 2878 | 0 | 0 | 201 | 0 | 3079 | 0 | 1 | Finished | 2878 | 2878 | C2016-15 Residential House Structural Work.xlsx
18 | 11 | Voegwerk | 2016-08-16 08:00 | 2016-08-25 17:00 | 8d |  | 0 | 2191 | 0 | 0 | 2191 | 2016-08-17 08:00 | 5d | 2191 | 0 | 0 | -178 | 0 | 2013 | 0 | 1 | Finished | 2191 | 2191 | C2016-15 Residential House Structural Work.xlsx
19 | 12 | Stelling | 2016-08-16 08:00 | 2016-08-26 17:00 | 9d |  | 0 | 2425 | 0 | 0 | 2425 | 2016-08-17 08:00 | 11d | 2425 | 0 | 0 | 686 | 0 | 3111 | 0 | 1 | Finished | 2425 | 2425 | C2016-15 Residential House Structural Work.xlsx
20 | 13 | Karweien | 2016-08-29 08:00 | 2016-08-29 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 | 2016-09-01 08:00 | 2d | 200 | 0 | 0 | 237 | 0 | 437 | 0 | 1 | Finished | 200 | 200 | C2016-15 Residential House Structural Work.xlsx
4 | 0 | Residential House Finishing Works (1) | 2016-03-11 08:00 | 2016-07-14 17:00 | 90d |  |  | 54577.7601 |  |  | 54577.7601 |  | 90d | [5 empty] | 64526.7601 |  | 1 |  | 54577.7601 | 54577.7601 | C2016-16 Residential House Finishing Works (1).xlsx
5 | 27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-21 17:00 | 30d |  |  | 9025.5699 |  |  | 9025.5699 |  | 30d | [5 empty] | 11810.5699 |  | 1 |  | 9025.5699 | 9025.5699 | C2016-16 Residential House Finishing Works (1).xlsx
6 | 1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 1 | Finished | 772.5 | 772.5 | C2016-16 Residential House Finishing Works (1).xlsx
7 | 2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | 129 | 0 | 1417.55 | 0 | 1 | Finished | 1288.55 | 1288.55 | C2016-16 Residential House Finishing Works (1).xlsx
8 | 3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 852.14 | 0 | 0 | 852.14 | 2016-03-25 08:00 | 5d | 852.14 | 0 | 0 | 476 | 0 | 1328.14 | 0 | 1 | Finished | 852.14 | 852.14 | C2016-16 Residential House Finishing Works (1).xlsx
9 | 4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 605 | 0 | 1565 | 0 | 1 | Finished | 960 | 960 | C2016-16 Residential House Finishing Works (1).xlsx
10 | 5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2576.1899 | 0 | 0 | 2576.1899 | 2016-04-01 08:00 | 10d | 2576.1899 | 0 | 0 | 908 | 0 | 3484.1899 | 0 | 1 | Finished | 2576.1899 | 2576.1899 | C2016-16 Residential House Finishing Works (1).xlsx
11 | 6 | F1 pleister | 2016-04-15 08:00 | 2016-04-21 17:00 | 5d |  | 0 | 2576.1899 | 0 | 0 | 2576.1899 | 2016-04-15 08:00 | 5d | 2576.1899 | 0 | 0 | 689 | 0 | 3265.1899 | 0 | 1 | Finished | 2576.1899 | 2576.1899 | C2016-16 Residential House Finishing Works (1).xlsx
12 | 28 | Fase 2 | 2016-04-22 08:00 | 2016-05-26 17:00 | 25d |  |  | 13051.47 |  |  | 13051.47 |  | 25d | [5 empty] | 15894.47 |  | 1 |  | 13051.47 | 13051.47 | C2016-16 Residential House Finishing Works (1).xlsx
13 | 7 | Opm keuken | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-22 08:00 | 5d | 2231.25 | 0 | 0 | 582 | 0 | 2813.25 | 0 | 1 | Finished | 2231.25 | 2231.25 | C2016-16 Residential House Finishing Works (1).xlsx
14 | 25 | F2 san/cv | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-22 08:00 | 5d | 1932.83 | 0 | 0 | 194 | 0 | 2126.83 | 0 | 1 | Finished | 1932.83 | 1932.83 | C2016-16 Residential House Finishing Works (1).xlsx
15 | 8 | F2 ventilatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-04-29 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 1 | Finished | 1158.75 | 1158.75 | C2016-16 Residential House Finishing Works (1).xlsx
16 | 9 | Vloerisolatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 3108.8701 | 0 | 0 | 3108.8701 | 2016-04-29 08:00 | 5d | 3108.8701 | 0 | 0 | 367 | 0 | 3475.8701 | 0 | 1 | Finished | 3108.8701 | 3108.8701 | C2016-16 Residential House Finishing Works (1).xlsx
17 | 10 | Chape | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1966.48 | 0 | 0 | 1966.48 | 2016-05-06 08:00 | 5d | 1966.48 | 0 | 0 | 496 | 0 | 2462.48 | 0 | 1 | Finished | 1966.48 | 1966.48 | C2016-16 Residential House Finishing Works (1).xlsx
18 | 11 | Opm Binnenschr | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1056.33 | 0 | 0 | 1056.33 | 2016-05-13 08:00 | 5d | 1056.33 | 0 | 0 | 322 | 0 | 1378.33 | 0 | 1 | Finished | 1056.33 | 1056.33 | C2016-16 Residential House Finishing Works (1).xlsx
19 | 12 | F2 elektr | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1278.21 | 0 | 0 | 1278.21 | 2016-05-13 08:00 | 5d | 1278.21 | 0 | 0 | 714 | 0 | 1992.21 | 0 | 1 | Finished | 1278.21 | 1278.21 | C2016-16 Residential House Finishing Works (1).xlsx
20 | 13 | openen E/G/W | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-20 08:00 | 5d | 318.75 | 0 | 0 | 201 | 0 | 519.75 | 0 | 1 | Finished | 318.75 | 318.75 | C2016-16 Residential House Finishing Works (1).xlsx
21 | 29 | Fase 3 | 2016-05-27 08:00 | 2016-06-30 17:00 | 25d |  |  | 13380 |  |  | 13380 |  | 25d | [5 empty] | 15717 |  | 1 |  | 13380 | 13380 | C2016-16 Residential House Finishing Works (1).xlsx
22 | 14 | F3 san/cv | 2016-05-27 08:00 | 2016-06-02 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-27 08:00 | 5d | 3221.3799 | 0 | 0 | 323 | 0 | 3544.3799 | 0 | 1 | Finished | 3221.3799 | 3221.3799 | C2016-16 Residential House Finishing Works (1).xlsx
23 | 15 | Vloerwerken | 2016-06-03 08:00 | 2016-06-09 17:00 | 5d |  | 0 | 2072.5801 | 0 | 0 | 2072.5801 | 2016-06-03 08:00 | 5d | 2072.5801 | 0 | 0 | -286 | 0 | 1786.5801 | 0 | 1 | Finished | 2072.5801 | 2072.5801 | C2016-16 Residential House Finishing Works (1).xlsx
24 | 16 | Trappen | 2016-06-10 08:00 | 2016-06-16 17:00 | 5d |  | 0 | 2676.55 | 0 | 0 | 2676.55 | 2016-06-10 08:00 | 5d | 2676.55 | 0 | 0 | 817 | 0 | 3493.55 | 0 | 1 | Finished | 2676.55 | 2676.55 | C2016-16 Residential House Finishing Works (1).xlsx
25 | 17 | Binnenschrijnwerk | 2016-06-17 08:00 | 2016-06-23 17:00 | 5d |  | 0 | 1584.49 | 0 | 0 | 1584.49 | 2016-06-17 08:00 | 5d | 1584.49 | 0 | 0 | 484 | 0 | 2068.49 | 0 | 1 | Finished | 1584.49 | 1584.49 | C2016-16 Residential House Finishing Works (1).xlsx
26 | 18 | Keuken | 2016-06-24 08:00 | 2016-06-30 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-24 08:00 | 5d | 3825 | 0 | 0 | 999 | 0 | 4824 | 0 | 1 | Finished | 3825 | 3825 | C2016-16 Residential House Finishing Works (1).xlsx
27 | 30 | Finale Afwerking | 2016-07-01 08:00 | 2016-07-14 17:00 | 10d |  |  | 19120.7202 |  |  | 19120.7202 |  | 10d | [5 empty] | 21104.7202 |  | 1 |  | 19120.7202 | 19120.7202 | C2016-16 Residential House Finishing Works (1).xlsx
28 | 19 | Afw ventilatie | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 2016-07-01 08:00 | 5d | 1931.25 | 0 | 0 | -56 | 0 | 1875.25 | 0 | 1 | Finished | 1931.25 | 1931.25 | C2016-16 Residential House Finishing Works (1).xlsx
29 | 20 | Afw elektr | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 2130.3501 | 0 | 0 | 2130.3501 | 2016-07-01 08:00 | 5d | 2130.3501 | 0 | 0 | 1190 | 0 | 3320.3501 | 0 | 1 | Finished | 2130.3501 | 2130.3501 | C2016-16 Residential House Finishing Works (1).xlsx
30 | 21 | Afw san/cv | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 2016-07-08 08:00 | 5d | 6442.75 | 0 | 0 | 647 | 0 | 7089.75 | 0 | 1 | Finished | 6442.75 | 6442.75 | C2016-16 Residential House Finishing Works (1).xlsx
31 | 26 | Afw vloer | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 5181.4502 | 0 | 0 | 5181.4502 | 2016-07-08 08:00 | 5d | 5181.4502 | 0 | 0 | -716 | 0 | 4465.4502 | 0 | 1 | Finished | 5181.4502 | 5181.4502 | C2016-16 Residential House Finishing Works (1).xlsx
32 | 24 | Afw pleister | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 3434.9199 | 0 | 0 | 3434.9199 | 2016-07-08 08:00 | 5d | 3434.9199 | 0 | 0 | 919 | 0 | 4353.9199 | 0 | 1 | Finished | 3434.9199 | 3434.9199 | C2016-16 Residential House Finishing Works (1).xlsx
4 | 0 | Residential House Finishing Works (2) | 2016-03-11 08:00 | 2016-07-08 17:00 | 86d |  |  | 54703.1698 |  |  | 54703.1698 |  | 86d | [5 empty] | 64580.1698 |  | 1 |  | 54703.1698 | 54703.1698 | C2016-17 Residential House Finishing Works (2).xlsx
5 | 27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-21 17:00 | 30d |  |  | 9153.99 |  |  | 9153.99 |  | 30d | [5 empty] | 11980.99 |  | 1 |  | 9153.99 | 9153.99 | C2016-17 Residential House Finishing Works (2).xlsx
6 | 1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 1 | Finished | 772.5 | 772.5 | C2016-17 Residential House Finishing Works (2).xlsx
7 | 2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | 129 | 0 | 1417.55 | 0 | 1 | Finished | 1288.55 | 1288.55 | C2016-17 Residential House Finishing Works (2).xlsx
8 | 3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 858.98 | 0 | 0 | 858.98 | 2016-03-25 08:00 | 5d | 858.98 | 0 | 0 | 480 | 0 | 1338.98 | 0 | 1 | Finished | 858.98 | 858.98 | C2016-17 Residential House Finishing Works (2).xlsx
9 | 4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 605 | 0 | 1565 | 0 | 1 | Finished | 960 | 960 | C2016-17 Residential House Finishing Works (2).xlsx
10 | 5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2636.98 | 0 | 0 | 2636.98 | 2016-04-01 08:00 | 10d | 2636.98 | 0 | 0 | 930 | 0 | 3566.98 | 0 | 1 | Finished | 2636.98 | 2636.98 | C2016-17 Residential House Finishing Works (2).xlsx
11 | 6 | F1 pleister | 2016-04-15 08:00 | 2016-04-21 17:00 | 5d |  | 0 | 2636.98 | 0 | 0 | 2636.98 | 2016-04-15 08:00 | 5d | 2636.98 | 0 | 0 | 705 | 0 | 3341.98 | 0 | 1 | Finished | 2636.98 | 2636.98 | C2016-17 Residential House Finishing Works (2).xlsx
12 | 28 | Fase 2 | 2016-04-22 08:00 | 2016-05-20 17:00 | 21d |  |  | 13151.0599 |  |  | 13151.0599 |  | 21d | [5 empty] | 16010.0599 |  | 1 |  | 13151.0599 | 13151.0599 | C2016-17 Residential House Finishing Works (2).xlsx
13 | 7 | Opm keuken | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-22 08:00 | 5d | 2231.25 | 0 | 0 | 582 | 0 | 2813.25 | 0 | 1 | Finished | 2231.25 | 2231.25 | C2016-17 Residential House Finishing Works (2).xlsx
14 | 25 | F2 san/cv | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-22 08:00 | 5d | 1932.83 | 0 | 0 | 194 | 0 | 2126.83 | 0 | 1 | Finished | 1932.83 | 1932.83 | C2016-17 Residential House Finishing Works (2).xlsx
15 | 8 | F2 ventilatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-04-29 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 1 | Finished | 1158.75 | 1158.75 | C2016-17 Residential House Finishing Works (2).xlsx
16 | 9 | Vloerisolatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 3204.76 | 0 | 0 | 3204.76 | 2016-04-29 08:00 | 5d | 3204.76 | 0 | 0 | 378 | 0 | 3582.76 | 0 | 1 | Finished | 3204.76 | 3204.76 | C2016-17 Residential House Finishing Works (2).xlsx
17 | 10 | Chape | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1959.92 | 0 | 0 | 1959.92 | 2016-05-06 08:00 | 5d | 1959.92 | 0 | 0 | 495 | 0 | 2454.92 | 0 | 1 | Finished | 1959.92 | 1959.92 | C2016-17 Residential House Finishing Works (2).xlsx
18 | 11 | Opm Binnenschr | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1056.33 | 0 | 0 | 1056.33 | 2016-05-13 08:00 | 5d | 1056.33 | 0 | 0 | 322 | 0 | 1378.33 | 0 | 1 | Finished | 1056.33 | 1056.33 | C2016-17 Residential House Finishing Works (2).xlsx
19 | 12 | F2 elektr | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1288.47 | 0 | 0 | 1288.47 | 2016-05-13 08:00 | 5d | 1288.47 | 0 | 0 | 720 | 0 | 2008.47 | 0 | 1 | Finished | 1288.47 | 1288.47 | C2016-17 Residential House Finishing Works (2).xlsx
20 | 13 | openen E/G/W | 2016-05-20 08:00 | 2016-05-20 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-20 08:00 | 1d | 318.75 | 0 | 0 | 201 | 0 | 519.75 | 0 | 1 | Finished | 318.75 | 318.75 | C2016-17 Residential House Finishing Works (2).xlsx
21 | 29 | Fase 3 | 2016-05-23 08:00 | 2016-06-24 17:00 | 25d |  |  | 13019.49 |  |  | 13019.49 |  | 25d | [5 empty] | 15218.49 |  | 1 |  | 13019.49 | 13019.49 | C2016-17 Residential House Finishing Works (2).xlsx
22 | 14 | F3 san/cv | 2016-05-23 08:00 | 2016-05-27 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-23 08:00 | 5d | 3221.3799 | 0 | 0 | 323 | 0 | 3544.3799 | 0 | 1 | Finished | 3221.3799 | 3221.3799 | C2016-17 Residential House Finishing Works (2).xlsx
23 | 15 | Vloerwerken | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 2136.51 | 0 | 0 | 2136.51 | 2016-05-30 08:00 | 5d | 2136.51 | 0 | 0 | -295 | 0 | 1841.51 | 0 | 1 | Finished | 2136.51 | 2136.51 | C2016-17 Residential House Finishing Works (2).xlsx
24 | 16 | Trappen | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 2252.1101 | 0 | 0 | 2252.1101 | 2016-06-06 08:00 | 5d | 2252.1101 | 0 | 0 | 688 | 0 | 2940.1101 | 0 | 1 | Finished | 2252.1101 | 2252.1101 | C2016-17 Residential House Finishing Works (2).xlsx
25 | 17 | Binnenschrijnwerk | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 1584.49 | 0 | 0 | 1584.49 | 2016-06-13 08:00 | 5d | 1584.49 | 0 | 0 | 484 | 0 | 2068.49 | 0 | 1 | Finished | 1584.49 | 1584.49 | C2016-17 Residential House Finishing Works (2).xlsx
26 | 18 | Keuken | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-20 08:00 | 5d | 3825 | 0 | 0 | 999 | 0 | 4824 | 0 | 1 | Finished | 3825 | 3825 | C2016-17 Residential House Finishing Works (2).xlsx
27 | 30 | Finale Afwerking | 2016-06-27 08:00 | 2016-07-08 17:00 | 10d |  |  | 19378.6299 |  |  | 19378.6299 |  | 10d | [5 empty] | 21370.6299 |  | 1 |  | 19378.6299 | 19378.6299 | C2016-17 Residential House Finishing Works (2).xlsx
28 | 19 | Afw ventilatie | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 2016-06-27 08:00 | 5d | 1931.25 | 0 | 0 | -56 | 0 | 1875.25 | 0 | 1 | Finished | 1931.25 | 1931.25 | C2016-17 Residential House Finishing Works (2).xlsx
29 | 20 | Afw elektr | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 2147.45 | 0 | 0 | 2147.45 | 2016-06-27 08:00 | 5d | 2147.45 | 0 | 0 | 1200 | 0 | 3347.45 | 0 | 1 | Finished | 2147.45 | 2147.45 | C2016-17 Residential House Finishing Works (2).xlsx
30 | 21 | Afw san/cv | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 2016-07-04 08:00 | 5d | 6442.75 | 0 | 0 | 647 | 0 | 7089.75 | 0 | 1 | Finished | 6442.75 | 6442.75 | C2016-17 Residential House Finishing Works (2).xlsx
31 | 26 | Afw vloer | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 5341.27 | 0 | 0 | 5341.27 | 2016-07-04 08:00 | 5d | 5341.27 | 0 | 0 | -739 | 0 | 4602.27 | 0 | 1 | Finished | 5341.27 | 5341.27 | C2016-17 Residential House Finishing Works (2).xlsx
32 | 24 | Afw pleister | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 3515.9099 | 0 | 0 | 3515.9099 | 2016-07-04 08:00 | 5d | 3515.9099 | 0 | 0 | 940 | 0 | 4455.9099 | 0 | 1 | Finished | 3515.9099 | 3515.9099 | C2016-17 Residential House Finishing Works (2).xlsx
4 | 0 | Residential House Finishing Works (3) | 2016-03-11 08:00 | 2016-07-15 17:00 | 91d |  |  | 51115.5195 |  |  | 51115.5195 |  | 91d | [5 empty] | 60829.5195 |  | 1 |  | 51115.5195 | 51115.5195 | C2016-18 Residential House Finishing Works (3).xlsx
5 | 28 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-21 17:00 | 30d |  |  | 8068.52 |  |  | 8068.52 |  | 30d | [5 empty] | 10544.52 |  | 1 |  | 8068.52 | 8068.52 | C2016-18 Residential House Finishing Works (3).xlsx
6 | 1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 1 | Finished | 772.5 | 772.5 | C2016-18 Residential House Finishing Works (3).xlsx
7 | 2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | 129 | 0 | 1417.55 | 0 | 1 | Finished | 1288.55 | 1288.55 | C2016-18 Residential House Finishing Works (3).xlsx
8 | 3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 804.51 | 0 | 0 | 804.51 | 2016-03-25 08:00 | 5d | 804.51 | 0 | 0 | 449 | 0 | 1253.51 | 0 | 1 | Finished | 804.51 | 804.51 | C2016-18 Residential House Finishing Works (3).xlsx
9 | 4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 605 | 0 | 1565 | 0 | 1 | Finished | 960 | 960 | C2016-18 Residential House Finishing Works (3).xlsx
10 | 5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 2121.48 | 0 | 0 | 2121.48 | 2016-04-01 08:00 | 5d | 2121.48 | 0 | 0 | 748 | 0 | 2869.48 | 0 | 1 | Finished | 2121.48 | 2121.48 | C2016-18 Residential House Finishing Works (3).xlsx
11 | 6 | F1 pleister | 2016-04-08 08:00 | 2016-04-21 17:00 | 10d |  | 0 | 2121.48 | 0 | 0 | 2121.48 | 2016-04-08 08:00 | 10d | 2121.48 | 0 | 0 | 567 | 0 | 2688.48 | 0 | 1 | Finished | 2121.48 | 2121.48 | C2016-18 Residential House Finishing Works (3).xlsx
12 | 29 | Fase 2 | 2016-04-22 08:00 | 2016-05-27 17:00 | 26d |  |  | 12773.3098 |  |  | 12773.3098 |  | 26d | [5 empty] | 15445.3098 |  | 1 |  | 12773.3098 | 12773.3098 | C2016-18 Residential House Finishing Works (3).xlsx
13 | 7 | Opm keuken | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-22 08:00 | 5d | 2231.25 | 0 | 0 | 582 | 0 | 2813.25 | 0 | 1 | Finished | 2231.25 | 2231.25 | C2016-18 Residential House Finishing Works (3).xlsx
14 | 25 | F2 san/cv | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-22 08:00 | 5d | 1932.83 | 0 | 0 | 194 | 0 | 2126.83 | 0 | 1 | Finished | 1932.83 | 1932.83 | C2016-18 Residential House Finishing Works (3).xlsx
15 | 8 | F2 ventilatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-04-29 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 1 | Finished | 1158.75 | 1158.75 | C2016-18 Residential House Finishing Works (3).xlsx
16 | 9 | Vloerisolatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1716.95 | 0 | 0 | 1716.95 | 2016-04-29 08:00 | 5d | 1716.95 | 0 | 0 | 202 | 0 | 1918.95 | 0 | 1 | Finished | 1716.95 | 1716.95 | C2016-18 Residential House Finishing Works (3).xlsx
17 | 27 | Vloerverwarming | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1716.95 | 0 | 0 | 1716.95 | 2016-05-06 08:00 | 5d | 1716.95 | 0 | 0 | 172 | 0 | 1888.95 | 0 | 1 | Finished | 1716.95 | 1716.95 | C2016-18 Residential House Finishing Works (3).xlsx
18 | 10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1511.08 | 0 | 0 | 1511.08 | 2016-05-13 08:00 | 5d | 1511.08 | 0 | 0 | 381 | 0 | 1892.08 | 0 | 1 | Finished | 1511.08 | 1511.08 | C2016-18 Residential House Finishing Works (3).xlsx
19 | 11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 979.98 | 0 | 0 | 979.98 | 2016-05-20 08:00 | 5d | 979.98 | 0 | 0 | 299 | 0 | 1278.98 | 0 | 1 | Finished | 979.98 | 979.98 | C2016-18 Residential House Finishing Works (3).xlsx
20 | 12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1206.77 | 0 | 0 | 1206.77 | 2016-05-20 08:00 | 5d | 1206.77 | 0 | 0 | 674 | 0 | 1880.77 | 0 | 1 | Finished | 1206.77 | 1206.77 | C2016-18 Residential House Finishing Works (3).xlsx
21 | 13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | 201 | 0 | 519.75 | 0 | 1 | Finished | 318.75 | 318.75 | C2016-18 Residential House Finishing Works (3).xlsx
22 | 30 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 13196.6399 |  |  | 13196.6399 |  | 25d | [5 empty] | 15825.6399 |  | 1 |  | 13196.6399 | 13196.6399 | C2016-18 Residential House Finishing Works (3).xlsx
23 | 14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-30 08:00 | 5d | 3221.3799 | 0 | 0 | 323 | 0 | 3544.3799 | 0 | 1 | Finished | 3221.3799 | 3221.3799 | C2016-18 Residential House Finishing Works (3).xlsx
24 | 15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 1287.71 | 0 | 0 | 1287.71 | 2016-06-06 08:00 | 5d | 1287.71 | 0 | 0 | -178 | 0 | 1109.71 | 0 | 1 | Finished | 1287.71 | 1287.71 | C2016-18 Residential House Finishing Works (3).xlsx
25 | 16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 3392.5801 | 0 | 0 | 3392.5801 | 2016-06-13 08:00 | 5d | 3392.5801 | 0 | 0 | 1036 | 0 | 4428.5801 | 0 | 1 | Finished | 3392.5801 | 3392.5801 | C2016-18 Residential House Finishing Works (3).xlsx
26 | 17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1469.97 | 0 | 0 | 1469.97 | 2016-06-20 08:00 | 5d | 1469.97 | 0 | 0 | 449 | 0 | 1918.97 | 0 | 1 | Finished | 1469.97 | 1469.97 | C2016-18 Residential House Finishing Works (3).xlsx
27 | 18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-27 08:00 | 5d | 3825 | 0 | 0 | 999 | 0 | 4824 | 0 | 1 | Finished | 3825 | 3825 | C2016-18 Residential House Finishing Works (3).xlsx
28 | 31 | Finale afwerking | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  |  | 17077.0498 |  |  | 17077.0498 |  | 10d | [5 empty] | 19014.0498 |  | 1 |  | 17077.0498 | 17077.0498 | C2016-18 Residential House Finishing Works (3).xlsx
29 | 19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 2016-07-04 08:00 | 5d | 1931.25 | 0 | 0 | -56 | 0 | 1875.25 | 0 | 1 | Finished | 1931.25 | 1931.25 | C2016-18 Residential House Finishing Works (3).xlsx
30 | 20 | Afw elektr | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 2011.29 | 0 | 0 | 2011.29 | 2016-07-04 08:00 | 5d | 2011.29 | 0 | 0 | 1124 | 0 | 3135.29 | 0 | 1 | Finished | 2011.29 | 2011.29 | C2016-18 Residential House Finishing Works (3).xlsx
31 | 21 | Afw san/cv | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 2016-07-11 08:00 | 5d | 6442.75 | 0 | 0 | 647 | 0 | 7089.75 | 0 | 1 | Finished | 6442.75 | 6442.75 | C2016-18 Residential House Finishing Works (3).xlsx
32 | 26 | Afw vloer | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 3863.1299 | 0 | 0 | 3863.1299 | 2016-07-11 08:00 | 5d | 3863.1299 | 0 | 0 | -534 | 0 | 3329.1299 | 0 | 1 | Finished | 3863.1299 | 3863.1299 | C2016-18 Residential House Finishing Works (3).xlsx
33 | 24 | Afw pleister | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 2828.6299 | 0 | 0 | 2828.6299 | 2016-07-11 08:00 | 5d | 2828.6299 | 0 | 0 | 756 | 0 | 3584.6299 | 0 | 1 | Finished | 2828.6299 | 2828.6299 | C2016-18 Residential House Finishing Works (3).xlsx
4 | 0 | Residential House Finishing Works (4) | 2016-03-11 08:00 | 2016-07-15 17:00 | 91d |  |  | 51303.3801 |  |  | 51303.3801 |  | 91d | [5 empty] | 53351.3801 |  | 1 |  | 51303.3801 | 51303.3801 | C2016-19 Residential House Finishing Works (4).xlsx
5 | 28 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-21 17:00 | 30d |  |  | 8127.5303 |  |  | 8127.5303 |  | 30d | [5 empty] | 8368.5303 |  | 1 |  | 8127.5303 | 8127.5303 | C2016-19 Residential House Finishing Works (4).xlsx
6 | 1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 1 | Finished | 772.5 | 772.5 | C2016-19 Residential House Finishing Works (4).xlsx
7 | 2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -11 | 0 | 1277.55 | 0 | 1 | Finished | 1288.55 | 1288.55 | C2016-19 Residential House Finishing Works (4).xlsx
8 | 3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 814.26 | 0 | 0 | 814.26 | 2016-03-25 08:00 | 5d | 814.26 | 0 | 0 | 220 | 0 | 1034.26 | 0 | 1 | Finished | 814.26 | 814.26 | C2016-19 Residential House Finishing Works (4).xlsx
9 | 4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | -7 | 0 | 953 | 0 | 1 | Finished | 960 | 960 | C2016-19 Residential House Finishing Works (4).xlsx
10 | 5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 2146.1101 | 0 | 0 | 2146.1101 | 2016-04-01 08:00 | 5d | 2146.1101 | 0 | 0 | -271 | 0 | 1875.1101 | 0 | 1 | Finished | 2146.1101 | 2146.1101 | C2016-19 Residential House Finishing Works (4).xlsx
11 | 6 | F1 pleister | 2016-04-08 08:00 | 2016-04-21 17:00 | 10d |  | 0 | 2146.1101 | 0 | 0 | 2146.1101 | 2016-04-08 08:00 | 10d | 2146.1101 | 0 | 0 | 332 | 0 | 2478.1101 | 0 | 1 | Finished | 2146.1101 | 2146.1101 | C2016-19 Residential House Finishing Works (4).xlsx
12 | 29 | Fase 2 | 2016-04-22 08:00 | 2016-05-27 17:00 | 26d |  |  | 12833.7399 |  |  | 12833.7399 |  | 26d | [5 empty] | 12629.7399 |  | 1 |  | 12833.7399 | 12833.7399 | C2016-19 Residential House Finishing Works (4).xlsx
13 | 7 | Opm keuken | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-22 08:00 | 5d | 2231.25 | 0 | 0 | 753 | 0 | 2984.25 | 0 | 1 | Finished | 2231.25 | 2231.25 | C2016-19 Residential House Finishing Works (4).xlsx
14 | 25 | F2 san/cv | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-22 08:00 | 5d | 1932.83 | 0 | 0 | -17 | 0 | 1915.83 | 0 | 1 | Finished | 1932.83 | 1932.83 | C2016-19 Residential House Finishing Works (4).xlsx
15 | 8 | F2 ventilatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-04-29 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 1 | Finished | 1158.75 | 1158.75 | C2016-19 Residential House Finishing Works (4).xlsx
16 | 9 | Vloerisolatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1720.6899 | 0 | 0 | 1720.6899 | 2016-04-29 08:00 | 5d | 1720.6899 | 0 | 0 | -1164 | 0 | 556.6899 | 0 | 1 | Finished | 1720.6899 | 1720.6899 | C2016-19 Residential House Finishing Works (4).xlsx
17 | 27 | Vloerverwarming | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1720.6899 | 0 | 0 | 1720.6899 | 2016-05-06 08:00 | 5d | 1720.6899 | 0 | 0 | -15 | 0 | 1705.6899 | 0 | 1 | Finished | 1720.6899 | 1720.6899 | C2016-19 Residential House Finishing Works (4).xlsx
18 | 10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1549.41 | 0 | 0 | 1549.41 | 2016-05-13 08:00 | 5d | 1549.41 | 0 | 0 | -228 | 0 | 1321.41 | 0 | 1 | Finished | 1549.41 | 1549.41 | C2016-19 Residential House Finishing Works (4).xlsx
19 | 11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 979.98 | 0 | 0 | 979.98 | 2016-05-20 08:00 | 5d | 979.98 | 0 | 0 | 171 | 0 | 1150.98 | 0 | 1 | Finished | 979.98 | 979.98 | C2016-19 Residential House Finishing Works (4).xlsx
20 | 12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1221.39 | 0 | 0 | 1221.39 | 2016-05-20 08:00 | 5d | 1221.39 | 0 | 0 | 331 | 0 | 1552.39 | 0 | 1 | Finished | 1221.39 | 1221.39 | C2016-19 Residential House Finishing Works (4).xlsx
21 | 13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | -2 | 0 | 316.75 | 0 | 1 | Finished | 318.75 | 318.75 | C2016-19 Residential House Finishing Works (4).xlsx
22 | 30 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 13199.4399 |  |  | 13199.4399 |  | 25d | [5 empty] | 15064.4399 |  | 1 |  | 13199.4399 | 13199.4399 | C2016-19 Residential House Finishing Works (4).xlsx
23 | 14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-30 08:00 | 5d | 3221.3799 | 0 | 0 | -28 | 0 | 3193.3799 | 0 | 1 | Finished | 3221.3799 | 3221.3799 | C2016-19 Residential House Finishing Works (4).xlsx
24 | 15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 1290.51 | 0 | 0 | 1290.51 | 2016-06-06 08:00 | 5d | 1290.51 | 0 | 0 | -245 | 0 | 1045.51 | 0 | 1 | Finished | 1290.51 | 1290.51 | C2016-19 Residential House Finishing Works (4).xlsx
25 | 16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 3392.5801 | 0 | 0 | 3392.5801 | 2016-06-13 08:00 | 5d | 3392.5801 | 0 | 0 | 592 | 0 | 3984.5801 | 0 | 1 | Finished | 3392.5801 | 3392.5801 | C2016-19 Residential House Finishing Works (4).xlsx
26 | 17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1469.97 | 0 | 0 | 1469.97 | 2016-06-20 08:00 | 5d | 1469.97 | 0 | 0 | 256 | 0 | 1725.97 | 0 | 1 | Finished | 1469.97 | 1469.97 | C2016-19 Residential House Finishing Works (4).xlsx
27 | 18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-27 08:00 | 5d | 3825 | 0 | 0 | 1290 | 0 | 5115 | 0 | 1 | Finished | 3825 | 3825 | C2016-19 Residential House Finishing Works (4).xlsx
28 | 31 | Finale afwerking | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  |  | 17142.67 |  |  | 17142.67 |  | 10d | [5 empty] | 17288.67 |  | 1 |  | 17142.67 | 17142.67 | C2016-19 Residential House Finishing Works (4).xlsx
29 | 19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 2016-07-04 08:00 | 5d | 1931.25 | 0 | 0 | -56 | 0 | 1875.25 | 0 | 1 | Finished | 1931.25 | 1931.25 | C2016-19 Residential House Finishing Works (4).xlsx
30 | 20 | Afw elektr | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 2035.65 | 0 | 0 | 2035.65 | 2016-07-04 08:00 | 5d | 2035.65 | 0 | 0 | 551 | 0 | 2586.65 | 0 | 1 | Finished | 2035.65 | 2035.65 | C2016-19 Residential House Finishing Works (4).xlsx
31 | 21 | Afw san/cv | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 2016-07-11 08:00 | 5d | 6442.75 | 0 | 0 | -57 | 0 | 6385.75 | 0 | 1 | Finished | 6442.75 | 6442.75 | C2016-19 Residential House Finishing Works (4).xlsx
32 | 26 | Afw vloer | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 3871.54 | 0 | 0 | 3871.54 | 2016-07-11 08:00 | 5d | 3871.54 | 0 | 0 | -735 | 0 | 3136.54 | 0 | 1 | Finished | 3871.54 | 3871.54 | C2016-19 Residential House Finishing Works (4).xlsx
33 | 24 | Afw pleister | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 2861.48 | 0 | 0 | 2861.48 | 2016-07-11 08:00 | 5d | 2861.48 | 0 | 0 | 443 | 0 | 3304.48 | 0 | 1 | Finished | 2861.48 | 2861.48 | C2016-19 Residential House Finishing Works (4).xlsx
4 | 0 | Residential House Finishing Works (5) | 2016-03-11 08:00 | 2016-07-15 17:00 | 91d |  |  | 52021.2802 |  |  | 52021.2802 |  | 91d | [5 empty] | 53783.2802 |  | 1 |  | 52021.2802 | 52021.2802 | C2016-20 Residential House Finishing Works (5).xlsx
5 | 28 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-21 17:00 | 30d |  |  | 8584.8802 |  |  | 8584.8802 |  | 30d | [5 empty] | 8828.8802 |  | 1 |  | 8584.8802 | 8584.8802 | C2016-20 Residential House Finishing Works (5).xlsx
6 | 1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 1 | Finished | 772.5 | 772.5 | C2016-20 Residential House Finishing Works (5).xlsx
7 | 2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -11 | 0 | 1277.55 | 0 | 1 | Finished | 1288.55 | 1288.55 | C2016-20 Residential House Finishing Works (5).xlsx
8 | 3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 797.63 | 0 | 0 | 797.63 | 2016-03-25 08:00 | 5d | 797.63 | 0 | 0 | 216 | 0 | 1013.63 | 0 | 1 | Finished | 797.63 | 797.63 | C2016-20 Residential House Finishing Works (5).xlsx
9 | 4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | -7 | 0 | 953 | 0 | 1 | Finished | 960 | 960 | C2016-20 Residential House Finishing Works (5).xlsx
10 | 5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 2383.1001 | 0 | 0 | 2383.1001 | 2016-04-01 08:00 | 5d | 2383.1001 | 0 | 0 | -301 | 0 | 2082.1001 | 0 | 1 | Finished | 2383.1001 | 2383.1001 | C2016-20 Residential House Finishing Works (5).xlsx
11 | 6 | F1 pleister | 2016-04-08 08:00 | 2016-04-21 17:00 | 10d |  | 0 | 2383.1001 | 0 | 0 | 2383.1001 | 2016-04-08 08:00 | 10d | 2383.1001 | 0 | 0 | 369 | 0 | 2752.1001 | 0 | 1 | Finished | 2383.1001 | 2383.1001 | C2016-20 Residential House Finishing Works (5).xlsx
12 | 29 | Fase 2 | 2016-04-22 08:00 | 2016-05-27 17:00 | 26d |  |  | 13344.01 |  |  | 13344.01 |  | 26d | [5 empty] | 13045.01 |  | 1 |  | 13344.01 | 13344.01 | C2016-20 Residential House Finishing Works (5).xlsx
13 | 7 | Opm keuken | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-22 08:00 | 5d | 2231.25 | 0 | 0 | 753 | 0 | 2984.25 | 0 | 1 | Finished | 2231.25 | 2231.25 | C2016-20 Residential House Finishing Works (5).xlsx
14 | 25 | F2 san/cv | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-22 08:00 | 5d | 1932.83 | 0 | 0 | -17 | 0 | 1915.83 | 0 | 1 | Finished | 1932.83 | 1932.83 | C2016-20 Residential House Finishing Works (5).xlsx
15 | 8 | F2 ventilatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-04-29 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 1 | Finished | 1158.75 | 1158.75 | C2016-20 Residential House Finishing Works (5).xlsx
16 | 9 | Vloerisolatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1849.78 | 0 | 0 | 1849.78 | 2016-04-29 08:00 | 5d | 1849.78 | 0 | 0 | -1259 | 0 | 590.78 | 0 | 1 | Finished | 1849.78 | 1849.78 | C2016-20 Residential House Finishing Works (5).xlsx
17 | 27 | Vloerverwarming | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1849.78 | 0 | 0 | 1849.78 | 2016-05-06 08:00 | 5d | 1849.78 | 0 | 0 | -16 | 0 | 1833.78 | 0 | 1 | Finished | 1849.78 | 1849.78 | C2016-20 Residential House Finishing Works (5).xlsx
18 | 10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1673.75 | 0 | 0 | 1673.75 | 2016-05-13 08:00 | 5d | 1673.75 | 0 | 0 | -246 | 0 | 1427.75 | 0 | 1 | Finished | 1673.75 | 1673.75 | C2016-20 Residential House Finishing Works (5).xlsx
19 | 11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1132.67 | 0 | 0 | 1132.67 | 2016-05-20 08:00 | 5d | 1132.67 | 0 | 0 | 197 | 0 | 1329.67 | 0 | 1 | Finished | 1132.67 | 1132.67 | C2016-20 Residential House Finishing Works (5).xlsx
20 | 12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1196.45 | 0 | 0 | 1196.45 | 2016-05-20 08:00 | 5d | 1196.45 | 0 | 0 | 324 | 0 | 1520.45 | 0 | 1 | Finished | 1196.45 | 1196.45 | C2016-20 Residential House Finishing Works (5).xlsx
21 | 13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | -2 | 0 | 316.75 | 0 | 1 | Finished | 318.75 | 318.75 | C2016-20 Residential House Finishing Works (5).xlsx
22 | 30 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 12384.83 |  |  | 12384.83 |  | 25d | [5 empty] | 14072.83 |  | 1 |  | 12384.83 | 12384.83 | C2016-20 Residential House Finishing Works (5).xlsx
23 | 14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-30 08:00 | 5d | 3221.3799 | 0 | 0 | -28 | 0 | 3193.3799 | 0 | 1 | Finished | 3221.3799 | 3221.3799 | C2016-20 Residential House Finishing Works (5).xlsx
24 | 15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 1387.33 | 0 | 0 | 1387.33 | 2016-06-06 08:00 | 5d | 1387.33 | 0 | 0 | -263 | 0 | 1124.33 | 0 | 1 | Finished | 1387.33 | 1387.33 | C2016-20 Residential House Finishing Works (5).xlsx
25 | 16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 2252.1101 | 0 | 0 | 2252.1101 | 2016-06-13 08:00 | 5d | 2252.1101 | 0 | 0 | 393 | 0 | 2645.1101 | 0 | 1 | Finished | 2252.1101 | 2252.1101 | C2016-20 Residential House Finishing Works (5).xlsx
26 | 17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1699.01 | 0 | 0 | 1699.01 | 2016-06-20 08:00 | 5d | 1699.01 | 0 | 0 | 296 | 0 | 1995.01 | 0 | 1 | Finished | 1699.01 | 1699.01 | C2016-20 Residential House Finishing Works (5).xlsx
27 | 18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-27 08:00 | 5d | 3825 | 0 | 0 | 1290 | 0 | 5115 | 0 | 1 | Finished | 3825 | 3825 | C2016-20 Residential House Finishing Works (5).xlsx
28 | 31 | Finale afwerking | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  |  | 17707.5599 |  |  | 17707.5599 |  | 10d | [5 empty] | 17836.5599 |  | 1 |  | 17707.5599 | 17707.5599 | C2016-20 Residential House Finishing Works (5).xlsx
29 | 19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 2016-07-04 08:00 | 5d | 1931.25 | 0 | 0 | -56 | 0 | 1875.25 | 0 | 1 | Finished | 1931.25 | 1931.25 | C2016-20 Residential House Finishing Works (5).xlsx
30 | 20 | Afw elektr | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1994.09 | 0 | 0 | 1994.09 | 2016-07-04 08:00 | 5d | 1994.09 | 0 | 0 | 540 | 0 | 2534.09 | 0 | 1 | Finished | 1994.09 | 1994.09 | C2016-20 Residential House Finishing Works (5).xlsx
31 | 21 | Afw san/cv | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 2016-07-11 08:00 | 5d | 6442.75 | 0 | 0 | -57 | 0 | 6385.75 | 0 | 1 | Finished | 6442.75 | 6442.75 | C2016-20 Residential House Finishing Works (5).xlsx
32 | 26 | Afw vloer | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 4162 | 0 | 0 | 4162 | 2016-07-11 08:00 | 5d | 4162 | 0 | 0 | -790 | 0 | 3372 | 0 | 1 | Finished | 4162 | 4162 | C2016-20 Residential House Finishing Works (5).xlsx
33 | 24 | Afw pleister | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 3177.47 | 0 | 0 | 3177.47 | 2016-07-11 08:00 | 5d | 3177.47 | 0 | 0 | 492 | 0 | 3669.47 | 0 | 1 | Finished | 3177.47 | 3177.47 | C2016-20 Residential House Finishing Works (5).xlsx
4 | 0 | Residential House Finishing Works (6) | 2016-03-11 08:00 | 2016-07-29 17:00 | 101d |  |  | 54324.22 |  |  | 54324.22 |  | 101d | [5 empty] | 54996.22 |  | 1 |  | 54324.22 | 54324.22 | C2016-21 Residential House Finishing Works (6).xlsx
5 | 27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8318.5699 |  |  | 8318.5699 |  | 35d | [5 empty] | 8570.5699 |  | 1 |  | 8318.5699 | 8318.5699 | C2016-21 Residential House Finishing Works (6).xlsx
6 | 1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 1 | Finished | 772.5 | 772.5 | C2016-21 Residential House Finishing Works (6).xlsx
7 | 2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -11 | 0 | 1277.55 | 0 | 1 | Finished | 1288.55 | 1288.55 | C2016-21 Residential House Finishing Works (6).xlsx
8 | 3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 841.7 | 0 | 0 | 841.7 | 2016-03-25 08:00 | 5d | 841.7 | 0 | 0 | 228 | 0 | 1069.7 | 0 | 1 | Finished | 841.7 | 841.7 | C2016-21 Residential House Finishing Works (6).xlsx
9 | 4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | -7 | 0 | 953 | 0 | 1 | Finished | 960 | 960 | C2016-21 Residential House Finishing Works (6).xlsx
10 | 5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2227.9099 | 0 | 0 | 2227.9099 | 2016-04-01 08:00 | 10d | 2227.9099 | 0 | 0 | -281 | 0 | 1946.9099 | 0 | 1 | Finished | 2227.9099 | 2227.9099 | C2016-21 Residential House Finishing Works (6).xlsx
11 | 6 | F1 pleister | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2227.9099 | 0 | 0 | 2227.9099 | 2016-04-15 08:00 | 10d | 2227.9099 | 0 | 0 | 345 | 0 | 2572.9099 | 0 | 1 | Finished | 2227.9099 | 2227.9099 | C2016-21 Residential House Finishing Works (6).xlsx
12 | 28 | Fase 2 | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 13098.23 |  |  | 13098.23 |  | 21d | [5 empty] | 11882.23 |  | 1 |  | 13098.23 | 13098.23 | C2016-21 Residential House Finishing Works (6).xlsx
13 | 7 | Opm keuken | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-29 08:00 | 5d | 2231.25 | 0 | 0 | 753 | 0 | 2984.25 | 0 | 1 | Finished | 2231.25 | 2231.25 | C2016-21 Residential House Finishing Works (6).xlsx
14 | 25 | F2 san/cv | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-29 08:00 | 5d | 1932.83 | 0 | 0 | -17 | 0 | 1915.83 | 0 | 1 | Finished | 1932.83 | 1932.83 | C2016-21 Residential House Finishing Works (6).xlsx
15 | 8 | F2 ventilatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-05-06 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 1 | Finished | 1158.75 | 1158.75 | C2016-21 Residential House Finishing Works (6).xlsx
16 | 9 | Vloerisolatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 3186.51 | 0 | 0 | 3186.51 | 2016-05-06 08:00 | 5d | 3186.51 | 0 | 0 | -2156 | 0 | 1030.51 | 0 | 1 | Finished | 3186.51 | 3186.51 | C2016-21 Residential House Finishing Works (6).xlsx
17 | 10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1951.26 | 0 | 0 | 1951.26 | 2016-05-13 08:00 | 5d | 1951.26 | 0 | 0 | -287 | 0 | 1664.26 | 0 | 1 | Finished | 1951.26 | 1951.26 | C2016-21 Residential House Finishing Works (6).xlsx
18 | 11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1056.33 | 0 | 0 | 1056.33 | 2016-05-20 08:00 | 5d | 1056.33 | 0 | 0 | 184 | 0 | 1240.33 | 0 | 1 | Finished | 1056.33 | 1056.33 | C2016-21 Residential House Finishing Works (6).xlsx
19 | 12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1262.55 | 0 | 0 | 1262.55 | 2016-05-20 08:00 | 5d | 1262.55 | 0 | 0 | 342 | 0 | 1604.55 | 0 | 1 | Finished | 1262.55 | 1262.55 | C2016-21 Residential House Finishing Works (6).xlsx
20 | 13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | -2 | 0 | 316.75 | 0 | 1 | Finished | 318.75 | 318.75 | C2016-21 Residential House Finishing Works (6).xlsx
21 | 29 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 14147.79 |  |  | 14147.79 |  | 25d | [5 empty] | 15874.79 |  | 1 |  | 14147.79 | 14147.79 | C2016-21 Residential House Finishing Works (6).xlsx
22 | 14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-30 08:00 | 5d | 3221.3799 | 0 | 0 | -28 | 0 | 3193.3799 | 0 | 1 | Finished | 3221.3799 | 3221.3799 | C2016-21 Residential House Finishing Works (6).xlsx
23 | 15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 2124.3401 | 0 | 0 | 2124.3401 | 2016-06-06 08:00 | 5d | 2124.3401 | 0 | 0 | -403 | 0 | 1721.3401 | 0 | 1 | Finished | 2124.3401 | 2124.3401 | C2016-21 Residential House Finishing Works (6).xlsx
24 | 16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 3392.5801 | 0 | 0 | 3392.5801 | 2016-06-13 08:00 | 5d | 3392.5801 | 0 | 0 | 592 | 0 | 3984.5801 | 0 | 1 | Finished | 3392.5801 | 3392.5801 | C2016-21 Residential House Finishing Works (6).xlsx
25 | 17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1584.49 | 0 | 0 | 1584.49 | 2016-06-20 08:00 | 5d | 1584.49 | 0 | 0 | 276 | 0 | 1860.49 | 0 | 1 | Finished | 1584.49 | 1584.49 | C2016-21 Residential House Finishing Works (6).xlsx
26 | 18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-27 08:00 | 5d | 3825 | 0 | 0 | 1290 | 0 | 5115 | 0 | 1 | Finished | 3825 | 3825 | C2016-21 Residential House Finishing Works (6).xlsx
27 | 30 | Finale afwerking | 2016-07-04 08:00 | 2016-07-29 17:00 | 20d |  |  | 18759.6301 |  |  | 18759.6301 |  | 20d | [5 empty] | 18668.6301 |  | 1 |  | 18759.6301 | 18759.6301 | C2016-21 Residential House Finishing Works (6).xlsx
28 | 19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 2016-07-04 08:00 | 10d | 1931.25 | 0 | 0 | -56 | 0 | 1875.25 | 0 | 1 | Finished | 1931.25 | 1931.25 | C2016-21 Residential House Finishing Works (6).xlsx
29 | 20 | Afw elektr | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 2104.24 | 0 | 0 | 2104.24 | 2016-07-04 08:00 | 10d | 2104.24 | 0 | 0 | 570 | 0 | 2674.24 | 0 | 1 | Finished | 2104.24 | 2104.24 | C2016-21 Residential House Finishing Works (6).xlsx
30 | 21 | Afw san/cv | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 2016-07-18 08:00 | 10d | 6442.75 | 0 | 0 | -57 | 0 | 6385.75 | 0 | 1 | Finished | 6442.75 | 6442.75 | C2016-21 Residential House Finishing Works (6).xlsx
31 | 26 | Afw vloer | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 5310.8501 | 0 | 0 | 5310.8501 | 2016-07-18 08:00 | 10d | 5310.8501 | 0 | 0 | -1008 | 0 | 4302.8501 | 0 | 1 | Finished | 5310.8501 | 5310.8501 | C2016-21 Residential House Finishing Works (6).xlsx
32 | 24 | Afw pleister | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 2970.54 | 0 | 0 | 2970.54 | 2016-07-18 08:00 | 10d | 2970.54 | 0 | 0 | 460 | 0 | 3430.54 | 0 | 1 | Finished | 2970.54 | 2970.54 | C2016-21 Residential House Finishing Works (6).xlsx
4 | 0 | Residential House Finishing Works (7) | 2016-03-11 08:00 | 2016-07-29 17:00 | 101d |  |  | 56969.3998 |  |  | 56969.3998 |  | 101d | [5 empty] | 57822.3998 |  | 1 |  | 56969.3998 | 56969.3998 | C2016-22 Residential House Finishing Works (7).xlsx
5 | 27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8829.0399 |  |  | 8829.0399 |  | 35d | [5 empty] | 9077.0399 |  | 1 |  | 8829.0399 | 8829.0399 | C2016-22 Residential House Finishing Works (7).xlsx
6 | 1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 1 | Finished | 772.5 | 772.5 | C2016-22 Residential House Finishing Works (7).xlsx
7 | 2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -11 | 0 | 1277.55 | 0 | 1 | Finished | 1288.55 | 1288.55 | C2016-22 Residential House Finishing Works (7).xlsx
8 | 3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 875.63 | 0 | 0 | 875.63 | 2016-03-25 08:00 | 5d | 875.63 | 0 | 0 | 237 | 0 | 1112.63 | 0 | 1 | Finished | 875.63 | 875.63 | C2016-22 Residential House Finishing Works (7).xlsx
9 | 4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | -7 | 0 | 953 | 0 | 1 | Finished | 960 | 960 | C2016-22 Residential House Finishing Works (7).xlsx
10 | 5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2466.1799 | 0 | 0 | 2466.1799 | 2016-04-01 08:00 | 10d | 2466.1799 | 0 | 0 | -331 | 0 | 2135.1799 | 0 | 1 | Finished | 2466.1799 | 2466.1799 | C2016-22 Residential House Finishing Works (7).xlsx
11 | 6 | F1 pleister | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2466.1799 | 0 | 0 | 2466.1799 | 2016-04-15 08:00 | 10d | 2466.1799 | 0 | 0 | 382 | 0 | 2848.1799 | 0 | 1 | Finished | 2466.1799 | 2466.1799 | C2016-22 Residential House Finishing Works (7).xlsx
12 | 28 | Fase 2 | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 13641.1499 |  |  | 13641.1499 |  | 21d | [5 empty] | 12397.1499 |  | 1 |  | 13641.1499 | 13641.1499 | C2016-22 Residential House Finishing Works (7).xlsx
13 | 7 | Opm keuken | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-29 08:00 | 5d | 2231.25 | 0 | 0 | 753 | 0 | 2984.25 | 0 | 1 | Finished | 2231.25 | 2231.25 | C2016-22 Residential House Finishing Works (7).xlsx
14 | 25 | F2 san/cv | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-29 08:00 | 5d | 1932.83 | 0 | 0 | -17 | 0 | 1915.83 | 0 | 1 | Finished | 1932.83 | 1932.83 | C2016-22 Residential House Finishing Works (7).xlsx
15 | 8 | F2 ventilatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-05-06 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 1 | Finished | 1158.75 | 1158.75 | C2016-22 Residential House Finishing Works (7).xlsx
16 | 9 | Vloerisolatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 3264.23 | 0 | 0 | 3264.23 | 2016-05-06 08:00 | 5d | 3264.23 | 0 | 0 | -2209 | 0 | 1055.23 | 0 | 1 | Finished | 3264.23 | 3264.23 | C2016-22 Residential House Finishing Works (7).xlsx
17 | 10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 2145.03 | 0 | 0 | 2145.03 | 2016-05-13 08:00 | 5d | 2145.03 | 0 | 0 | -315 | 0 | 1830.03 | 0 | 1 | Finished | 2145.03 | 2145.03 | C2016-22 Residential House Finishing Works (7).xlsx
18 | 11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1276.87 | 0 | 0 | 1276.87 | 2016-05-20 08:00 | 5d | 1276.87 | 0 | 0 | 223 | 0 | 1499.87 | 0 | 1 | Finished | 1276.87 | 1276.87 | C2016-22 Residential House Finishing Works (7).xlsx
19 | 12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1313.4399 | 0 | 0 | 1313.4399 | 2016-05-20 08:00 | 5d | 1313.4399 | 0 | 0 | 356 | 0 | 1669.4399 | 0 | 1 | Finished | 1313.4399 | 1313.4399 | C2016-22 Residential House Finishing Works (7).xlsx
20 | 13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | -2 | 0 | 316.75 | 0 | 1 | Finished | 318.75 | 318.75 | C2016-22 Residential House Finishing Works (7).xlsx
21 | 29 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 15207.5198 |  |  | 15207.5198 |  | 25d | [5 empty] | 17100.5198 |  | 1 |  | 15207.5198 | 15207.5198 | C2016-22 Residential House Finishing Works (7).xlsx
22 | 14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-30 08:00 | 5d | 3221.3799 | 0 | 0 | -28 | 0 | 3193.3799 | 0 | 1 | Finished | 3221.3799 | 3221.3799 | C2016-22 Residential House Finishing Works (7).xlsx
23 | 15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 2176.1599 | 0 | 0 | 2176.1599 | 2016-06-06 08:00 | 5d | 2176.1599 | 0 | 0 | -413 | 0 | 1763.1599 | 0 | 1 | Finished | 2176.1599 | 2176.1599 | C2016-22 Residential House Finishing Works (7).xlsx
24 | 16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 4069.6699 | 0 | 0 | 4069.6699 | 2016-06-13 08:00 | 5d | 4069.6699 | 0 | 0 | 710 | 0 | 4779.6699 | 0 | 1 | Finished | 4069.6699 | 4069.6699 | C2016-22 Residential House Finishing Works (7).xlsx
25 | 17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1915.3101 | 0 | 0 | 1915.3101 | 2016-06-20 08:00 | 5d | 1915.3101 | 0 | 0 | 334 | 0 | 2249.3101 | 0 | 1 | Finished | 1915.3101 | 1915.3101 | C2016-22 Residential House Finishing Works (7).xlsx
26 | 18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-27 08:00 | 5d | 3825 | 0 | 0 | 1290 | 0 | 5115 | 0 | 1 | Finished | 3825 | 3825 | C2016-22 Residential House Finishing Works (7).xlsx
27 | 30 | Finale afwerking | 2016-07-04 08:00 | 2016-07-29 17:00 | 20d |  |  | 19291.6902 |  |  | 19291.6902 |  | 20d | [5 empty] | 19247.6902 |  | 1 |  | 19291.6902 | 19291.6902 | C2016-22 Residential House Finishing Works (7).xlsx
28 | 19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 2016-07-04 08:00 | 10d | 1931.25 | 0 | 0 | -56 | 0 | 1875.25 | 0 | 1 | Finished | 1931.25 | 1931.25 | C2016-22 Residential House Finishing Works (7).xlsx
29 | 20 | Afw elektr | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 2189.0601 | 0 | 0 | 2189.0601 | 2016-07-04 08:00 | 10d | 2189.0601 | 0 | 0 | 593 | 0 | 2782.0601 | 0 | 1 | Finished | 2189.0601 | 2189.0601 | C2016-22 Residential House Finishing Works (7).xlsx
30 | 21 | Afw san/cv | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 2016-07-18 08:00 | 10d | 6442.75 | 0 | 0 | -57 | 0 | 6385.75 | 0 | 1 | Finished | 6442.75 | 6442.75 | C2016-22 Residential House Finishing Works (7).xlsx
31 | 26 | Afw vloer | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 5440.3901 | 0 | 0 | 5440.3901 | 2016-07-18 08:00 | 10d | 5440.3901 | 0 | 0 | -1033 | 0 | 4407.3901 | 0 | 1 | Finished | 5440.3901 | 5440.3901 | C2016-22 Residential House Finishing Works (7).xlsx
32 | 24 | Afw pleister | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 3288.24 | 0 | 0 | 3288.24 | 2016-07-18 08:00 | 10d | 3288.24 | 0 | 0 | 509 | 0 | 3797.24 | 0 | 1 | Finished | 3288.24 | 3288.24 | C2016-22 Residential House Finishing Works (7).xlsx
4 | 0 | Residential House Finishing Works (8) | 2016-03-11 08:00 | 2016-07-29 17:00 | 101d |  |  | 56182.7098 |  |  | 56182.7098 |  | 101d | [5 empty] | 56645.7098 |  | 1 |  | 56182.7098 | 56182.7098 | C2016-23 Residential House Finishing Works (8).xlsx
5 | 27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8857.6801 |  |  | 8857.6801 |  | 35d | [5 empty] | 9128.6801 |  | 1 |  | 8857.6801 | 8857.6801 | C2016-23 Residential House Finishing Works (8).xlsx
6 | 1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 1 | Finished | 772.5 | 772.5 | C2016-23 Residential House Finishing Works (8).xlsx
7 | 2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -11 | 0 | 1277.55 | 0 | 1 | Finished | 1288.55 | 1288.55 | C2016-23 Residential House Finishing Works (8).xlsx
8 | 3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 887.61 | 0 | 0 | 887.61 | 2016-03-25 08:00 | 5d | 887.61 | 0 | 0 | 240 | 0 | 1127.61 | 0 | 1 | Finished | 887.61 | 887.61 | C2016-23 Residential House Finishing Works (8).xlsx
9 | 4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | -7 | 0 | 953 | 0 | 1 | Finished | 960 | 960 | C2016-23 Residential House Finishing Works (8).xlsx
10 | 5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2474.51 | 0 | 0 | 2474.51 | 2016-04-01 08:00 | 10d | 2474.51 | 0 | 0 | -312 | 0 | 2162.51 | 0 | 1 | Finished | 2474.51 | 2474.51 | C2016-23 Residential House Finishing Works (8).xlsx
11 | 6 | F1 pleister | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2474.51 | 0 | 0 | 2474.51 | 2016-04-15 08:00 | 10d | 2474.51 | 0 | 0 | 383 | 0 | 2857.51 | 0 | 1 | Finished | 2474.51 | 2474.51 | C2016-23 Residential House Finishing Works (8).xlsx
12 | 28 | Fase 2 | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 13798.5601 |  |  | 13798.5601 |  | 21d | [5 empty] | 12466.5601 |  | 1 |  | 13798.5601 | 13798.5601 | C2016-23 Residential House Finishing Works (8).xlsx
13 | 7 | Opm keuken | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-29 08:00 | 5d | 2231.25 | 0 | 0 | 753 | 0 | 2984.25 | 0 | 1 | Finished | 2231.25 | 2231.25 | C2016-23 Residential House Finishing Works (8).xlsx
14 | 25 | F2 san/cv | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-29 08:00 | 5d | 1932.83 | 0 | 0 | -17 | 0 | 1915.83 | 0 | 1 | Finished | 1932.83 | 1932.83 | C2016-23 Residential House Finishing Works (8).xlsx
15 | 8 | F2 ventilatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-05-06 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 1 | Finished | 1158.75 | 1158.75 | C2016-23 Residential House Finishing Works (8).xlsx
16 | 9 | Vloerisolatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 3451.52 | 0 | 0 | 3451.52 | 2016-05-06 08:00 | 5d | 3451.52 | 0 | 0 | -2336 | 0 | 1115.52 | 0 | 1 | Finished | 3451.52 | 3451.52 | C2016-23 Residential House Finishing Works (8).xlsx
17 | 10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 2010.53 | 0 | 0 | 2010.53 | 2016-05-13 08:00 | 5d | 2010.53 | 0 | 0 | -296 | 0 | 1714.53 | 0 | 1 | Finished | 2010.53 | 2010.53 | C2016-23 Residential House Finishing Works (8).xlsx
18 | 11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1363.51 | 0 | 0 | 1363.51 | 2016-05-20 08:00 | 5d | 1363.51 | 0 | 0 | 238 | 0 | 1601.51 | 0 | 1 | Finished | 1363.51 | 1363.51 | C2016-23 Residential House Finishing Works (8).xlsx
19 | 12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1331.42 | 0 | 0 | 1331.42 | 2016-05-20 08:00 | 5d | 1331.42 | 0 | 0 | 361 | 0 | 1692.42 | 0 | 1 | Finished | 1331.42 | 1331.42 | C2016-23 Residential House Finishing Works (8).xlsx
20 | 13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | -2 | 0 | 316.75 | 0 | 1 | Finished | 318.75 | 318.75 | C2016-23 Residential House Finishing Works (8).xlsx
21 | 29 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 13881.5498 |  |  | 13881.5498 |  | 25d | [5 empty] | 15498.5498 |  | 1 |  | 13881.5498 | 13881.5498 | C2016-23 Residential House Finishing Works (8).xlsx
22 | 14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-30 08:00 | 5d | 3221.3799 | 0 | 0 | -28 | 0 | 3193.3799 | 0 | 1 | Finished | 3221.3799 | 3221.3799 | C2016-23 Residential House Finishing Works (8).xlsx
23 | 15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 2301.01 | 0 | 0 | 2301.01 | 2016-06-06 08:00 | 5d | 2301.01 | 0 | 0 | -436 | 0 | 1865.01 | 0 | 1 | Finished | 2301.01 | 2301.01 | C2016-23 Residential House Finishing Works (8).xlsx
24 | 16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 2488.8899 | 0 | 0 | 2488.8899 | 2016-06-13 08:00 | 5d | 2488.8899 | 0 | 0 | 434 | 0 | 2922.8899 | 0 | 1 | Finished | 2488.8899 | 2488.8899 | C2016-23 Residential House Finishing Works (8).xlsx
25 | 17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 2045.27 | 0 | 0 | 2045.27 | 2016-06-20 08:00 | 5d | 2045.27 | 0 | 0 | 357 | 0 | 2402.27 | 0 | 1 | Finished | 2045.27 | 2045.27 | C2016-23 Residential House Finishing Works (8).xlsx
26 | 18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-27 08:00 | 5d | 3825 | 0 | 0 | 1290 | 0 | 5115 | 0 | 1 | Finished | 3825 | 3825 | C2016-23 Residential House Finishing Works (8).xlsx
27 | 30 | Finale afwerking | 2016-07-04 08:00 | 2016-07-29 17:00 | 20d |  |  | 19644.9199 |  |  | 19644.9199 |  | 20d | [5 empty] | 19551.9199 |  | 1 |  | 19644.9199 | 19644.9199 | C2016-23 Residential House Finishing Works (8).xlsx
28 | 19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 2016-07-04 08:00 | 10d | 1931.25 | 0 | 0 | -56 | 0 | 1875.25 | 0 | 1 | Finished | 1931.25 | 1931.25 | C2016-23 Residential House Finishing Works (8).xlsx
29 | 20 | Afw elektr | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 2219.04 | 0 | 0 | 2219.04 | 2016-07-04 08:00 | 10d | 2219.04 | 0 | 0 | 601 | 0 | 2820.04 | 0 | 1 | Finished | 2219.04 | 2219.04 | C2016-23 Residential House Finishing Works (8).xlsx
30 | 21 | Afw san/cv | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 2016-07-18 08:00 | 10d | 6442.75 | 0 | 0 | -57 | 0 | 6385.75 | 0 | 1 | Finished | 6442.75 | 6442.75 | C2016-23 Residential House Finishing Works (8).xlsx
31 | 26 | Afw vloer | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 5752.5298 | 0 | 0 | 5752.5298 | 2016-07-18 08:00 | 10d | 5752.5298 | 0 | 0 | -1092 | 0 | 4660.5298 | 0 | 1 | Finished | 5752.5298 | 5752.5298 | C2016-23 Residential House Finishing Works (8).xlsx
32 | 24 | Afw pleister | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 3299.3501 | 0 | 0 | 3299.3501 | 2016-07-18 08:00 | 10d | 3299.3501 | 0 | 0 | 511 | 0 | 3810.3501 | 0 | 1 | Finished | 3299.3501 | 3299.3501 | C2016-23 Residential House Finishing Works (8).xlsx
4 | 0 | Residential House Finishing Works (9) | 2016-03-11 08:00 | 2016-07-29 17:00 | 101d |  |  | 52262.8298 |  |  | 52262.8298 |  | 101d | [5 empty] | 53176.8298 |  | 1 |  | 52262.8298 | 52262.8298 | C2016-24 Residential House Finishing Works (9).xlsx
5 | 27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8620.22 |  |  | 8620.22 |  | 35d | [5 empty] | 8869.22 |  | 1 |  | 8620.22 | 8620.22 | C2016-24 Residential House Finishing Works (9).xlsx
6 | 1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 1 | Finished | 772.5 | 772.5 | C2016-24 Residential House Finishing Works (9).xlsx
7 | 2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -11 | 0 | 1277.55 | 0 | 1 | Finished | 1288.55 | 1288.55 | C2016-24 Residential House Finishing Works (9).xlsx
8 | 3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 818.19 | 0 | 0 | 818.19 | 2016-03-25 08:00 | 5d | 818.19 | 0 | 0 | 221 | 0 | 1039.19 | 0 | 1 | Finished | 818.19 | 818.19 | C2016-24 Residential House Finishing Works (9).xlsx
9 | 4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | -7 | 0 | 953 | 0 | 1 | Finished | 960 | 960 | C2016-24 Residential House Finishing Works (9).xlsx
10 | 5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2390.49 | 0 | 0 | 2390.49 | 2016-04-01 08:00 | 10d | 2390.49 | 0 | 0 | -302 | 0 | 2088.49 | 0 | 1 | Finished | 2390.49 | 2390.49 | C2016-24 Residential House Finishing Works (9).xlsx
11 | 6 | F1 pleister | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2390.49 | 0 | 0 | 2390.49 | 2016-04-15 08:00 | 10d | 2390.49 | 0 | 0 | 370 | 0 | 2760.49 | 0 | 1 | Finished | 2390.49 | 2390.49 | C2016-24 Residential House Finishing Works (9).xlsx
12 | 28 | Fase 2 | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 12430.04 |  |  | 12430.04 |  | 21d | [5 empty] | 11462.04 |  | 1 |  | 12430.04 | 12430.04 | C2016-24 Residential House Finishing Works (9).xlsx
13 | 7 | Opm keuken | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-29 08:00 | 5d | 2231.25 | 0 | 0 | 753 | 0 | 2984.25 | 0 | 1 | Finished | 2231.25 | 2231.25 | C2016-24 Residential House Finishing Works (9).xlsx
14 | 25 | F2 san/cv | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-29 08:00 | 5d | 1932.83 | 0 | 0 | -17 | 0 | 1915.83 | 0 | 1 | Finished | 1932.83 | 1932.83 | C2016-24 Residential House Finishing Works (9).xlsx
15 | 8 | F2 ventilatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-05-06 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 1 | Finished | 1158.75 | 1158.75 | C2016-24 Residential House Finishing Works (9).xlsx
16 | 9 | Vloerisolatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 2828.8 | 0 | 0 | 2828.8 | 2016-05-06 08:00 | 5d | 2828.8 | 0 | 0 | -1914 | 0 | 914.8 | 0 | 1 | Finished | 2828.8 | 2828.8 | C2016-24 Residential House Finishing Works (9).xlsx
17 | 10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1752.39 | 0 | 0 | 1752.39 | 2016-05-13 08:00 | 5d | 1752.39 | 0 | 0 | -258 | 0 | 1494.39 | 0 | 1 | Finished | 1752.39 | 1752.39 | C2016-24 Residential House Finishing Works (9).xlsx
18 | 11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 979.98 | 0 | 0 | 979.98 | 2016-05-20 08:00 | 5d | 979.98 | 0 | 0 | 171 | 0 | 1150.98 | 0 | 1 | Finished | 979.98 | 979.98 | C2016-24 Residential House Finishing Works (9).xlsx
19 | 12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1227.29 | 0 | 0 | 1227.29 | 2016-05-20 08:00 | 5d | 1227.29 | 0 | 0 | 332 | 0 | 1559.29 | 0 | 1 | Finished | 1227.29 | 1227.29 | C2016-24 Residential House Finishing Works (9).xlsx
20 | 13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | -2 | 0 | 316.75 | 0 | 1 | Finished | 318.75 | 318.75 | C2016-24 Residential House Finishing Works (9).xlsx
21 | 29 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 12891.1097 |  |  | 12891.1097 |  | 25d | [5 empty] | 14485.1097 |  | 1 |  | 12891.1097 | 12891.1097 | C2016-24 Residential House Finishing Works (9).xlsx
22 | 14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-30 08:00 | 5d | 3221.3799 | 0 | 0 | -28 | 0 | 3193.3799 | 0 | 1 | Finished | 3221.3799 | 3221.3799 | C2016-24 Residential House Finishing Works (9).xlsx
23 | 15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 1885.87 | 0 | 0 | 1885.87 | 2016-06-06 08:00 | 5d | 1885.87 | 0 | 0 | -358 | 0 | 1527.87 | 0 | 1 | Finished | 1885.87 | 1885.87 | C2016-24 Residential House Finishing Works (9).xlsx
24 | 16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 2488.8899 | 0 | 0 | 2488.8899 | 2016-06-13 08:00 | 5d | 2488.8899 | 0 | 0 | 434 | 0 | 2922.8899 | 0 | 1 | Finished | 2488.8899 | 2488.8899 | C2016-24 Residential House Finishing Works (9).xlsx
25 | 17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1469.97 | 0 | 0 | 1469.97 | 2016-06-20 08:00 | 5d | 1469.97 | 0 | 0 | 256 | 0 | 1725.97 | 0 | 1 | Finished | 1469.97 | 1469.97 | C2016-24 Residential House Finishing Works (9).xlsx
26 | 18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-27 08:00 | 5d | 3825 | 0 | 0 | 1290 | 0 | 5115 | 0 | 1 | Finished | 3825 | 3825 | C2016-24 Residential House Finishing Works (9).xlsx
27 | 30 | Finale afwerking | 2016-07-04 08:00 | 2016-07-29 17:00 | 20d |  |  | 18321.46 |  |  | 18321.46 |  | 20d | [5 empty] | 18360.46 |  | 1 |  | 18321.46 | 18321.46 | C2016-24 Residential House Finishing Works (9).xlsx
28 | 19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 2016-07-04 08:00 | 10d | 1931.25 | 0 | 0 | -56 | 0 | 1875.25 | 0 | 1 | Finished | 1931.25 | 1931.25 | C2016-24 Residential House Finishing Works (9).xlsx
29 | 20 | Afw elektr | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 2045.48 | 0 | 0 | 2045.48 | 2016-07-04 08:00 | 10d | 2045.48 | 0 | 0 | 554 | 0 | 2599.48 | 0 | 1 | Finished | 2045.48 | 2045.48 | C2016-24 Residential House Finishing Works (9).xlsx
30 | 21 | Afw san/cv | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 2016-07-18 08:00 | 10d | 6442.75 | 0 | 0 | -57 | 0 | 6385.75 | 0 | 1 | Finished | 6442.75 | 6442.75 | C2016-24 Residential House Finishing Works (9).xlsx
31 | 26 | Afw vloer | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 4714.6699 | 0 | 0 | 4714.6699 | 2016-07-18 08:00 | 10d | 4714.6699 | 0 | 0 | -895 | 0 | 3819.6699 | 0 | 1 | Finished | 4714.6699 | 4714.6699 | C2016-24 Residential House Finishing Works (9).xlsx
32 | 24 | Afw pleister | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 3187.3101 | 0 | 0 | 3187.3101 | 2016-07-18 08:00 | 10d | 3187.3101 | 0 | 0 | 493 | 0 | 3680.3101 | 0 | 1 | Finished | 3187.3101 | 3187.3101 | C2016-24 Residential House Finishing Works (9).xlsx
4 | 0 | Residential House Finishing Works (10) | 2016-03-11 08:00 | 2016-07-15 17:00 | 91d |  |  | 54580.3294 |  |  | 54580.3294 |  | 91d | [5 empty] | 56748.3294 |  | 1 |  | 54580.3294 | 54580.3294 | C2016-25 Residential House Finishing Works (10).xlsx
5 | 27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8362.4698 |  |  | 8362.4698 |  | 35d | [5 empty] | 9795.4698 |  | 1 |  | 8362.4698 | 8362.4698 | C2016-25 Residential House Finishing Works (10).xlsx
6 | 1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 1 | Finished | 772.5 | 772.5 | C2016-25 Residential House Finishing Works (10).xlsx
7 | 2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -35 | 0 | 1253.55 | 0 | 1 | Finished | 1288.55 | 1288.55 | C2016-25 Residential House Finishing Works (10).xlsx
8 | 3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 876.16 | 0 | 0 | 876.16 | 2016-03-25 08:00 | 5d | 876.16 | 0 | 0 | 100 | 0 | 976.16 | 0 | 1 | Finished | 876.16 | 876.16 | C2016-25 Residential House Finishing Works (10).xlsx
9 | 4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 193 | 0 | 1153 | 0 | 1 | Finished | 960 | 960 | C2016-25 Residential House Finishing Works (10).xlsx
10 | 5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2232.6299 | 0 | 0 | 2232.6299 | 2016-04-01 08:00 | 10d | 2232.6299 | 0 | 0 | 206 | 0 | 2438.6299 | 0 | 1 | Finished | 2232.6299 | 2232.6299 | C2016-25 Residential House Finishing Works (10).xlsx
11 | 6 | F1 pleister | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2232.6299 | 0 | 0 | 2232.6299 | 2016-04-15 08:00 | 10d | 2232.6299 | 0 | 0 | 991 | 0 | 3223.6299 | 0 | 1 | Finished | 2232.6299 | 2232.6299 | C2016-25 Residential House Finishing Works (10).xlsx
12 | 28 | Fase 2 | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 13673.3699 |  |  | 13673.3699 |  | 21d | [5 empty] | 11828.3699 |  | 1 |  | 13673.3699 | 13673.3699 | C2016-25 Residential House Finishing Works (10).xlsx
13 | 7 | Opm keuken | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-29 08:00 | 5d | 2231.25 | 0 | 0 | -464 | 0 | 1767.25 | 0 | 1 | Finished | 2231.25 | 2231.25 | C2016-25 Residential House Finishing Works (10).xlsx
14 | 25 | F2 san/cv | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-29 08:00 | 5d | 1932.83 | 0 | 0 | -53 | 0 | 1879.83 | 0 | 1 | Finished | 1932.83 | 1932.83 | C2016-25 Residential House Finishing Works (10).xlsx
15 | 8 | F2 ventilatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-05-06 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 1 | Finished | 1158.75 | 1158.75 | C2016-25 Residential House Finishing Works (10).xlsx
16 | 9 | Vloerisolatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 3230.24 | 0 | 0 | 3230.24 | 2016-05-06 08:00 | 5d | 3230.24 | 0 | 0 | -2325 | 0 | 905.24 | 0 | 1 | Finished | 3230.24 | 3230.24 | C2016-25 Residential House Finishing Works (10).xlsx
17 | 10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 2200.1399 | 0 | 0 | 2200.1399 | 2016-05-13 08:00 | 5d | 2200.1399 | 0 | 0 | 247 | 0 | 2447.1399 | 0 | 1 | Finished | 2200.1399 | 2200.1399 | C2016-25 Residential House Finishing Works (10).xlsx
18 | 11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1287.17 | 0 | 0 | 1287.17 | 2016-05-20 08:00 | 5d | 1287.17 | 0 | 0 | 569 | 0 | 1856.17 | 0 | 1 | Finished | 1287.17 | 1287.17 | C2016-25 Residential House Finishing Works (10).xlsx
19 | 12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1314.24 | 0 | 0 | 1314.24 | 2016-05-20 08:00 | 5d | 1314.24 | 0 | 0 | 150 | 0 | 1464.24 | 0 | 1 | Finished | 1314.24 | 1314.24 | C2016-25 Residential House Finishing Works (10).xlsx
20 | 13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | 64 | 0 | 382.75 | 0 | 1 | Finished | 318.75 | 318.75 | C2016-25 Residential House Finishing Works (10).xlsx
21 | 29 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 13619.5198 |  |  | 13619.5198 |  | 25d | [5 empty] | 14737.5198 |  | 1 |  | 13619.5198 | 13619.5198 | C2016-25 Residential House Finishing Works (10).xlsx
22 | 14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-30 08:00 | 5d | 3221.3799 | 0 | 0 | -89 | 0 | 3132.3799 | 0 | 1 | Finished | 3221.3799 | 3221.3799 | C2016-25 Residential House Finishing Works (10).xlsx
23 | 15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 2153.49 | 0 | 0 | 2153.49 | 2016-06-06 08:00 | 5d | 2153.49 | 0 | 0 | 50 | 0 | 2203.49 | 0 | 1 | Finished | 2153.49 | 2153.49 | C2016-25 Residential House Finishing Works (10).xlsx
24 | 16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 2488.8899 | 0 | 0 | 2488.8899 | 2016-06-13 08:00 | 5d | 2488.8899 | 0 | 0 | 1100 | 0 | 3588.8899 | 0 | 1 | Finished | 2488.8899 | 2488.8899 | C2016-25 Residential House Finishing Works (10).xlsx
25 | 17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1930.76 | 0 | 0 | 1930.76 | 2016-06-20 08:00 | 5d | 1930.76 | 0 | 0 | 853 | 0 | 2783.76 | 0 | 1 | Finished | 1930.76 | 1930.76 | C2016-25 Residential House Finishing Works (10).xlsx
26 | 18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-27 08:00 | 5d | 3825 | 0 | 0 | -796 | 0 | 3029 | 0 | 1 | Finished | 3825 | 3825 | C2016-25 Residential House Finishing Works (10).xlsx
27 | 30 | Finale afwerking | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  |  | 18924.97 |  |  | 18924.97 |  | 10d | [5 empty] | 20386.97 |  | 1 |  | 18924.97 | 18924.97 | C2016-25 Residential House Finishing Works (10).xlsx
28 | 19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 2016-07-04 08:00 | 5d | 1931.25 | 0 | 0 | -56 | 0 | 1875.25 | 0 | 1 | Finished | 1931.25 | 1931.25 | C2016-25 Residential House Finishing Works (10).xlsx
29 | 20 | Afw elektr | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 2190.3999 | 0 | 0 | 2190.3999 | 2016-07-04 08:00 | 5d | 2190.3999 | 0 | 0 | 251 | 0 | 2441.3999 | 0 | 1 | Finished | 2190.3999 | 2190.3999 | C2016-25 Residential House Finishing Works (10).xlsx
30 | 21 | Afw san/cv | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 2016-07-11 08:00 | 5d | 6442.75 | 0 | 0 | -179 | 0 | 6263.75 | 0 | 1 | Finished | 6442.75 | 6442.75 | C2016-25 Residential House Finishing Works (10).xlsx
31 | 26 | Afw vloer | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 5383.73 | 0 | 0 | 5383.73 | 2016-07-11 08:00 | 5d | 5383.73 | 0 | 0 | 125 | 0 | 5508.73 | 0 | 1 | Finished | 5383.73 | 5383.73 | C2016-25 Residential House Finishing Works (10).xlsx
32 | 24 | Afw pleister | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 2976.8401 | 0 | 0 | 2976.8401 | 2016-07-11 08:00 | 5d | 2976.8401 | 0 | 0 | 1321 | 0 | 4297.8401 | 0 | 1 | Finished | 2976.8401 | 2976.8401 | C2016-25 Residential House Finishing Works (10).xlsx
4 | 0 | Residential House Finishing Works (11) | 2016-03-11 08:00 | 2016-07-15 17:00 | 91d |  |  | 51286.2396 |  |  | 51286.2396 |  | 91d | [5 empty] | 53319.2396 |  | 1 |  | 51286.2396 | 51286.2396 | C2016-26 Residential House Finishing Works (11).xlsx
5 | 27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8126.8201 |  |  | 8126.8201 |  | 35d | [5 empty] | 9505.8201 |  | 1 |  | 8126.8201 | 8126.8201 | C2016-26 Residential House Finishing Works (11).xlsx
6 | 1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 1 | Finished | 772.5 | 772.5 | C2016-26 Residential House Finishing Works (11).xlsx
7 | 2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -35 | 0 | 1253.55 | 0 | 1 | Finished | 1288.55 | 1288.55 | C2016-26 Residential House Finishing Works (11).xlsx
8 | 3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 818.19 | 0 | 0 | 818.19 | 2016-03-25 08:00 | 5d | 818.19 | 0 | 0 | 93 | 0 | 911.19 | 0 | 1 | Finished | 818.19 | 818.19 | C2016-26 Residential House Finishing Works (11).xlsx
9 | 4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 193 | 0 | 1153 | 0 | 1 | Finished | 960 | 960 | C2016-26 Residential House Finishing Works (11).xlsx
10 | 5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2143.79 | 0 | 0 | 2143.79 | 2016-04-01 08:00 | 10d | 2143.79 | 0 | 0 | 198 | 0 | 2341.79 | 0 | 1 | Finished | 2143.79 | 2143.79 | C2016-26 Residential House Finishing Works (11).xlsx
11 | 6 | F1 pleister | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2143.79 | 0 | 0 | 2143.79 | 2016-04-15 08:00 | 10d | 2143.79 | 0 | 0 | 952 | 0 | 3095.79 | 0 | 1 | Finished | 2143.79 | 2143.79 | C2016-26 Residential House Finishing Works (11).xlsx
12 | 28 | Fase 2 | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 12260.5099 |  |  | 12260.5099 |  | 21d | [5 empty] | 10550.5099 |  | 1 |  | 12260.5099 | 12260.5099 | C2016-26 Residential House Finishing Works (11).xlsx
13 | 7 | Opm keuken | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-29 08:00 | 5d | 2231.25 | 0 | 0 | -464 | 0 | 1767.25 | 0 | 1 | Finished | 2231.25 | 2231.25 | C2016-26 Residential House Finishing Works (11).xlsx
14 | 25 | F2 san/cv | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-29 08:00 | 5d | 1932.83 | 0 | 0 | -53 | 0 | 1879.83 | 0 | 1 | Finished | 1932.83 | 1932.83 | C2016-26 Residential House Finishing Works (11).xlsx
15 | 8 | F2 ventilatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-05-06 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 1 | Finished | 1158.75 | 1158.75 | C2016-26 Residential House Finishing Works (11).xlsx
16 | 9 | Vloerisolatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 2754.9099 | 0 | 0 | 2754.9099 | 2016-05-06 08:00 | 5d | 2754.9099 | 0 | 0 | -1983 | 0 | 771.9099 | 0 | 1 | Finished | 2754.9099 | 2754.9099 | C2016-26 Residential House Finishing Works (11).xlsx
17 | 10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1656.75 | 0 | 0 | 1656.75 | 2016-05-13 08:00 | 5d | 1656.75 | 0 | 0 | 186 | 0 | 1842.75 | 0 | 1 | Finished | 1656.75 | 1656.75 | C2016-26 Residential House Finishing Works (11).xlsx
18 | 11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 979.98 | 0 | 0 | 979.98 | 2016-05-20 08:00 | 5d | 979.98 | 0 | 0 | 433 | 0 | 1412.98 | 0 | 1 | Finished | 979.98 | 979.98 | C2016-26 Residential House Finishing Works (11).xlsx
19 | 12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1227.29 | 0 | 0 | 1227.29 | 2016-05-20 08:00 | 5d | 1227.29 | 0 | 0 | 140 | 0 | 1367.29 | 0 | 1 | Finished | 1227.29 | 1227.29 | C2016-26 Residential House Finishing Works (11).xlsx
20 | 13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | 64 | 0 | 382.75 | 0 | 1 | Finished | 318.75 | 318.75 | C2016-26 Residential House Finishing Works (11).xlsx
21 | 29 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 13029.5099 |  |  | 13029.5099 |  | 25d | [5 empty] | 14019.5099 |  | 1 |  | 13029.5099 | 13029.5099 | C2016-26 Residential House Finishing Works (11).xlsx
22 | 14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-30 08:00 | 5d | 3221.3799 | 0 | 0 | -89 | 0 | 3132.3799 | 0 | 1 | Finished | 3221.3799 | 3221.3799 | C2016-26 Residential House Finishing Works (11).xlsx
23 | 15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 1836.61 | 0 | 0 | 1836.61 | 2016-06-06 08:00 | 5d | 1836.61 | 0 | 0 | 42 | 0 | 1878.61 | 0 | 1 | Finished | 1836.61 | 1836.61 | C2016-26 Residential House Finishing Works (11).xlsx
24 | 16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 2676.55 | 0 | 0 | 2676.55 | 2016-06-13 08:00 | 5d | 2676.55 | 0 | 0 | 1183 | 0 | 3859.55 | 0 | 1 | Finished | 2676.55 | 2676.55 | C2016-26 Residential House Finishing Works (11).xlsx
25 | 17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1469.97 | 0 | 0 | 1469.97 | 2016-06-20 08:00 | 5d | 1469.97 | 0 | 0 | 650 | 0 | 2119.97 | 0 | 1 | Finished | 1469.97 | 1469.97 | C2016-26 Residential House Finishing Works (11).xlsx
26 | 18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-27 08:00 | 5d | 3825 | 0 | 0 | -796 | 0 | 3029 | 0 | 1 | Finished | 3825 | 3825 | C2016-26 Residential House Finishing Works (11).xlsx
27 | 30 | Finale afwerking | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  |  | 17869.3997 |  |  | 17869.3997 |  | 10d | [5 empty] | 19243.3997 |  | 1 |  | 17869.3997 | 17869.3997 | C2016-26 Residential House Finishing Works (11).xlsx
28 | 19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 2016-07-04 08:00 | 5d | 1931.25 | 0 | 0 | -56 | 0 | 1875.25 | 0 | 1 | Finished | 1931.25 | 1931.25 | C2016-26 Residential House Finishing Works (11).xlsx
29 | 20 | Afw elektr | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 2045.48 | 0 | 0 | 2045.48 | 2016-07-04 08:00 | 5d | 2045.48 | 0 | 0 | 234 | 0 | 2279.48 | 0 | 1 | Finished | 2045.48 | 2045.48 | C2016-26 Residential House Finishing Works (11).xlsx
30 | 21 | Afw san/cv | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 6442.7598 | 0 | 0 | 6442.7598 | 2016-07-11 08:00 | 5d | 6442.7598 | 0 | 0 | -179 | 0 | 6263.7598 | 0 | 1 | Finished | 6442.7598 | 6442.7598 | C2016-26 Residential House Finishing Works (11).xlsx
31 | 26 | Afw vloer | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 4591.52 | 0 | 0 | 4591.52 | 2016-07-11 08:00 | 5d | 4591.52 | 0 | 0 | 106 | 0 | 4697.52 | 0 | 1 | Finished | 4591.52 | 4591.52 | C2016-26 Residential House Finishing Works (11).xlsx
32 | 24 | Afw pleister | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 2858.3899 | 0 | 0 | 2858.3899 | 2016-07-11 08:00 | 5d | 2858.3899 | 0 | 0 | 1269 | 0 | 4127.3899 | 0 | 1 | Finished | 2858.3899 | 2858.3899 | C2016-26 Residential House Finishing Works (11).xlsx
4 | 0 | Apartment Building Foundations | 2016-03-21 08:00 | 2016-07-06 17:00 | 78d |  |  | 813663.0605 |  |  | 813663.0605 |  | 88d | [5 empty] | 879701.0605 |  | 1 |  | 813663.0605 | 813663.0605 | C2016-27 Apartment Building Foundations.xlsx
5 | 21 | Voorbereidende werken | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  |  | 20245 |  |  | 20245 |  | 6d | [5 empty] | 18869 |  | 1 |  | 20245 | 20245 | C2016-27 Apartment Building Foundations.xlsx
6 | 2 | rooien bomen en struiken terrein + afvoer | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 18345 | 0 | 0 | 18345 | 2016-03-21 08:00 | 5d | 18345 | 0 | 0 | -1392 | 0 | 16953 | 0 | 1 | Finished | 18345 | 18345 | C2016-27 Apartment Building Foundations.xlsx
7 | 3 | werfinrichting : hekkens, keten, signalisatie | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 1900 | 0 | 0 | 1900 | 2016-03-21 08:00 | 6d | 1900 | 0 | 0 | 16 | 0 | 1916 | 0 | 1 | Finished | 1900 | 1900 | C2016-27 Apartment Building Foundations.xlsx
8 | 24 | Afbraak, realisatie bouwput en beschoeiing | 2016-03-28 08:00 | 2016-07-06 17:00 | 73d |  |  | 793418.0605 |  |  | 793418.0605 |  | 82d | [5 empty] | 860832.0605 |  | 1 |  | 793418.0605 | 793418.0605 | C2016-27 Apartment Building Foundations.xlsx
9 | 22 | sloopwerken | 2016-03-28 08:00 | 2016-04-15 17:00 | 15d |  |  | 79341 |  |  | 79341 |  | 18d | [5 empty] | 78521 |  | 1 |  | 79341 | 79341 | C2016-27 Apartment Building Foundations.xlsx
10 | 6 | afbraak herenhuis, scheimuur midden | 2016-03-28 08:00 | 2016-04-15 17:00 | 15d |  | 0 | 79341 | 0 | 0 | 79341 | 2016-03-29 08:00 | 18d | 79341 | 0 | 0 | -820 | 0 | 78521 | 0 | 1 | Finished | 79341 | 79341 | C2016-27 Apartment Building Foundations.xlsx
11 | 23 | Grondwerken, beschoeiing en funderingspalen | 2016-03-28 08:00 | 2016-07-06 17:00 | 73d |  |  | 714077.0605 |  |  | 714077.0605 |  | 82d | [5 empty] | 782311.0605 |  | 1 |  | 714077.0605 | 714077.0605 | C2016-27 Apartment Building Foundations.xlsx
12 | 8 | voorafgraving terrein voor beschoeiing + geleidebalken | 2016-03-28 08:00 | 2016-04-22 17:00 | 20d |  | 0 | 16046.6797 | 0 | 0 | 16046.6797 | 2016-03-29 08:00 | 20d | 16046.6797 | 0 | 0 | -251 | 0 | 15795.6797 | 0 | 1 | Finished | 16046.6797 | 16046.6797 | C2016-27 Apartment Building Foundations.xlsx
13 | 9 | installatie bemaling rondom bouwput | 2016-03-31 08:00 | 2016-04-04 17:00 | 3d |  | 0 | 24070.0098 | 0 | 0 | 24070.0098 | 2016-04-01 08:00 | 4d | 24070.0098 | 0 | 0 | 3876 | 0 | 27946.0098 | 0 | 1 | Finished | 24070.0098 | 24070.0098 | C2016-27 Apartment Building Foundations.xlsx
14 | 10 | werfinstallatie beschoeiing | 2016-04-07 08:00 | 2016-04-08 17:00 | 2d |  | 0 | 40116.6914 | 0 | 0 | 40116.6914 | 2016-04-08 08:00 | 3d | 40116.6914 | 0 | 0 | 9056 | 0 | 49172.6914 | 0 | 1 | Finished | 40116.6914 | 40116.6914 | C2016-27 Apartment Building Foundations.xlsx
15 | 11 | uitvoering beschoeiing tussen as Ab-Hb (zone blok B) | 2016-04-11 08:00 | 2016-04-26 17:00 | 12d |  | 0 | 80233.3828 | 0 | 0 | 80233.3828 | 2016-04-13 08:00 | 14d | 80233.3828 | 0 | 0 | 11134 | 0 | 91367.3828 | 0 | 1 | Finished | 80233.3828 | 80233.3828 | C2016-27 Apartment Building Foundations.xlsx
16 | 12 | uitvoering beschoeiing tussen as Aa-Ab (zone blok A) | 2016-04-27 08:00 | 2016-05-10 17:00 | 10d |  | 0 | 96280.0469 | 0 | 0 | 96280.0469 | 2016-05-03 08:00 | 11d | 96280.0469 | 0 | 0 | -4799 | 0 | 91481.0469 | 0 | 1 | Finished | 96280.0469 | 96280.0469 | C2016-27 Apartment Building Foundations.xlsx
17 | 13 | uitgraving bouwput zone as Ab-Hb | 2016-05-06 08:00 | 2016-05-17 17:00 | 8d |  | 0 | 64186.6992 | 0 | 0 | 64186.6992 | 2016-05-06 08:00 | 8d | 64186.6992 | 0 | 0 | 2627 | 0 | 66813.6992 | 0 | 1 | Finished | 64186.6992 | 64186.6992 | C2016-27 Apartment Building Foundations.xlsx
18 | 14 | uitgraving bouwput zone as Aa-Ab | 2016-05-25 08:00 | 2016-06-14 17:00 | 15d |  | 0 | 80233.3828 | 0 | 0 | 80233.3828 | 2016-06-01 08:00 | 15d | 80233.3828 | 0 | 0 | 3881 | 0 | 84114.3828 | 0 | 1 | Finished | 80233.3828 | 80233.3828 | C2016-27 Apartment Building Foundations.xlsx
19 | 15 | uitgraving inrit garage | 2016-06-15 08:00 | 2016-06-20 17:00 | 4d |  | 0 | 20058.3398 | 0 | 0 | 20058.3398 | 2016-06-22 08:00 | 4d | 20058.3398 | 0 | 0 | -1687 | 0 | 18371.3398 | 0 | 1 | Finished | 20058.3398 | 20058.3398 | C2016-27 Apartment Building Foundations.xlsx
20 | 16 | werfinstallatie palenmachine | 2016-06-13 08:00 | 2016-06-14 17:00 | 2d |  | 0 | 28081.6797 | 0 | 0 | 28081.6797 | 2016-06-20 08:00 | 2d | 28081.6797 | 0 | 0 | 2275 | 0 | 30356.6797 | 0 | 1 | Finished | 28081.6797 | 28081.6797 | C2016-27 Apartment Building Foundations.xlsx
21 | 17 | uitvoering funderingspalen tussen as Ab-Hb | 2016-06-15 08:00 | 2016-06-21 17:00 | 5d |  | 0 | 72210.0391 | 0 | 0 | 72210.0391 | 2016-06-22 08:00 | 7d | 72210.0391 | 0 | 0 | 9800 | 0 | 82010.0391 | 0 | 1 | Finished | 72210.0391 | 72210.0391 | C2016-27 Apartment Building Foundations.xlsx
22 | 18 | uitvoering funderingspalen tussen as Aa-Ab | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 88256.7188 | 0 | 0 | 88256.7188 | 2016-07-01 08:00 | 7d | 88256.7188 | 0 | 0 | 17452 | 0 | 105708.7188 | 0 | 1 | Finished | 88256.7188 | 88256.7188 | C2016-27 Apartment Building Foundations.xlsx
23 | 19 | Uitgraven paalkoppen as Ab-Hb | 2016-06-28 08:00 | 2016-06-29 17:00 | 2d |  | 0 | 44128.3594 | 0 | 0 | 44128.3594 | 2016-07-07 08:00 | 3d | 44128.3594 | 0 | 0 | 8561 | 0 | 52689.3594 | 0 | 1 | Finished | 44128.3594 | 44128.3594 | C2016-27 Apartment Building Foundations.xlsx
24 | 20 | Uitgraven paalkoppen as Aa-Ab | 2016-06-30 08:00 | 2016-07-06 17:00 | 5d |  | 0 | 60175.0312 | 0 | 0 | 60175.0312 | 2016-07-12 08:00 | 7d | 60175.0312 | 0 | 0 | 6309 | 0 | 66484.0312 | 0 | 1 | Finished | 60175.0312 | 60175.0312 | C2016-27 Apartment Building Foundations.xlsx
4 | 0 | Apartment Building Structural Work (1) | 2016-03-21 08:00 | 2016-06-27 17:00 | 71d |  |  | 569177.85 |  |  | 569177.85 |  | 79d | [5 empty] | 586086.85 |  | 1 |  | 569177.85 | 569177.85 | C2016-28 Apartment Building Structural Work (1).xlsx
5 | 1 | betonnen paalkoppen tss as Ab-Hb | 2016-03-21 08:00 | 2016-03-28 17:00 | 6d |  | 0 | 4919.4302 | 0 | 0 | 4919.4302 | 2016-03-21 08:00 | 5d | 4919.4302 | 0 | 0 | 33 | 0 | 4952.4302 | 0 | 1 | Finished | 4919.4302 | 4919.4302 | C2016-28 Apartment Building Structural Work (1).xlsx
6 | 2 | betonneren paalkoppen tss as Aa-Ab | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 5903.3101 | 0 | 0 | 5903.3101 | 2016-03-21 08:00 | 12d | 5903.3101 | 0 | 0 | 774 | 0 | 6677.3101 | 0 | 1 | Finished | 5903.3101 | 5903.3101 | C2016-28 Apartment Building Structural Work (1).xlsx
7 | 3 | plaatsen riolering onder radier tss as Ab-Hb | 2016-03-29 08:00 | 2016-03-31 17:00 | 3d |  | 0 | 19677.7109 | 0 | 0 | 19677.7109 | 2016-03-28 08:00 | 4d | 19677.7109 | 0 | 0 | 1778 | 0 | 21455.7109 | 0 | 1 | Finished | 19677.7109 | 19677.7109 | C2016-28 Apartment Building Structural Work (1).xlsx
8 | 4 | plaatsen riolering onder radier tss as Aa-Ab | 2016-04-04 08:00 | 2016-04-08 17:00 | 5d |  | 0 | 22137.4297 | 0 | 0 | 22137.4297 | 2016-04-06 08:00 | 6d | 22137.4297 | 0 | 0 | 544 | 0 | 22681.4297 | 0 | 1 | Finished | 22137.4297 | 22137.4297 | C2016-28 Apartment Building Structural Work (1).xlsx
9 | 5 | fijnnivelleren en zuiverheidsbeton vloer tss as Ab-Hb | 2016-04-01 08:00 | 2016-04-04 17:00 | 2d |  | 0 | 39355.4297 | 0 | 0 | 39355.4297 | 2016-04-01 08:00 | 2d | 39355.4297 | 0 | 0 | -3378 | 0 | 35977.4297 | 0 | 1 | Finished | 39355.4297 | 39355.4297 | C2016-28 Apartment Building Structural Work (1).xlsx
10 | 6 | fijnnivelleren en zuiverheidsbeton vloer tss as Aa-Ab | 2016-04-11 08:00 | 2016-04-12 17:00 | 2d |  | 0 | 44274.8516 | 0 | 0 | 44274.8516 | 2016-04-14 08:00 | 2d | 44274.8516 | 0 | 0 | -566 | 0 | 43708.8516 | 0 | 1 | Finished | 44274.8516 | 44274.8516 | C2016-28 Apartment Building Structural Work (1).xlsx
11 | 7 | vlechten, storten, pollieren kelder vloerplaat tss as Ab-Hb | 2016-04-05 08:00 | 2016-04-14 17:00 | 8d |  | 0 | 36895.7109 | 0 | 0 | 36895.7109 | 2016-04-05 08:00 | 9d | 36895.7109 | 0 | 0 | -660 | 0 | 36235.7109 | 0 | 1 | Finished | 36895.7109 | 36895.7109 | C2016-28 Apartment Building Structural Work (1).xlsx
12 | 8 | vlechten, storten, pollieren kelder vloerplaat tss as Aa-Ab | 2016-04-13 08:00 | 2016-04-28 17:00 | 12d |  | 0 | 41815.1406 | 0 | 0 | 41815.1406 | 2016-04-18 08:00 | 13d | 41815.1406 | 0 | 0 | 4377 | 0 | 46192.1406 | 0 | 1 | Finished | 41815.1406 | 41815.1406 | C2016-28 Apartment Building Structural Work (1).xlsx
13 | 9 | kelderwand buitenomtrek tss as Ab-Hb | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 31484.3398 | 0 | 0 | 31484.3398 | 2016-04-18 08:00 | 10d | 31484.3398 | 0 | 0 | 2136 | 0 | 33620.3398 | 0 | 1 | Finished | 31484.3398 | 31484.3398 | C2016-28 Apartment Building Structural Work (1).xlsx
14 | 10 | kelderwand buitenomtrek tss as Aa-Ab | 2016-04-29 08:00 | 2016-05-19 17:00 | 15d |  | 0 | 34927.9414 | 0 | 0 | 34927.9414 | 2016-05-05 08:00 | 15d | 34927.9414 | 0 | 0 | 2100 | 0 | 37027.9414 | 0 | 1 | Finished | 34927.9414 | 34927.9414 | C2016-28 Apartment Building Structural Work (1).xlsx
15 | 11 | binnenwanden in beton tss as Ab-Hb | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 51654 | 0 | 0 | 51654 | 2016-04-25 08:00 | 4d | 51654 | 0 | 0 | -6049 | 0 | 45605 | 0 | 1 | Finished | 51654 | 51654 | C2016-28 Apartment Building Structural Work (1).xlsx
16 | 12 | binnenwanden in beton tss as Aa-Ab | 2016-05-06 08:00 | 2016-05-19 17:00 | 10d |  | 0 | 59033.1406 | 0 | 0 | 59033.1406 | 2016-05-12 08:00 | 9d | 59033.1406 | 0 | 0 | -6301 | 0 | 52732.1406 | 0 | 1 | Finished | 59033.1406 | 59033.1406 | C2016-28 Apartment Building Structural Work (1).xlsx
17 | 13 | kolommen en balken tss as Ab-Hb | 2016-04-22 08:00 | 2016-05-05 17:00 | 10d |  | 0 | 23121.3105 | 0 | 0 | 23121.3105 | 2016-04-25 08:00 | 13d | 23121.3105 | 0 | 0 | 3931 | 0 | 27052.3105 | 0 | 1 | Finished | 23121.3105 | 23121.3105 | C2016-28 Apartment Building Structural Work (1).xlsx
18 | 14 | kolommen en balken tss as Aa-Ab | 2016-05-06 08:00 | 2016-05-19 17:00 | 10d |  | 0 | 26072.9707 | 0 | 0 | 26072.9707 | 2016-05-12 08:00 | 13d | 26072.9707 | 0 | 0 | 3662 | 0 | 29734.9707 | 0 | 1 | Finished | 26072.9707 | 26072.9707 | C2016-28 Apartment Building Structural Work (1).xlsx
19 | 15 | predallen + opstort tss as Ab-Hb | 2016-05-06 08:00 | 2016-05-13 17:00 | 6d |  | 0 | 32960.1719 | 0 | 0 | 32960.1719 | 2016-05-12 08:00 | 10d | 32960.1719 | 0 | 0 | 6211 | 0 | 39171.1719 | 0 | 1 | Finished | 32960.1719 | 32960.1719 | C2016-28 Apartment Building Structural Work (1).xlsx
20 | 16 | welfsels + opstort tss as Aa-Ab | 2016-05-20 08:00 | 2016-05-30 17:00 | 7d |  | 0 | 11314.6797 | 0 | 0 | 11314.6797 | 2016-05-31 08:00 | 6d | 11314.6797 | 0 | 0 | -509 | 0 | 10805.6797 | 0 | 1 | Finished | 11314.6797 | 11314.6797 | C2016-28 Apartment Building Structural Work (1).xlsx
21 | 17 | ontkisten kelder en proper maken | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 3443.6001 | 0 | 0 | 3443.6001 | 2016-06-08 08:00 | 5d | 3443.6001 | 0 | 0 | 117 | 0 | 3560.6001 | 0 | 1 | Finished | 3443.6001 | 3443.6001 | C2016-28 Apartment Building Structural Work (1).xlsx
22 | 18 | uitvoeren van metselwerken kelder | 2016-06-07 08:00 | 2016-06-20 17:00 | 10d |  | 0 | 78710.8516 | 0 | 0 | 78710.8516 | 2016-06-15 08:00 | 12d | 78710.8516 | 0 | 0 | 8673 | 0 | 87383.8516 | 0 | 1 | Finished | 78710.8516 | 78710.8516 | C2016-28 Apartment Building Structural Work (1).xlsx
23 | 19 | opkuis voor start techniekers | 2016-06-21 08:00 | 2016-06-27 17:00 | 5d |  | 0 | 1475.83 | 0 | 0 | 1475.83 | 2016-07-01 08:00 | 5d | 1475.83 | 0 | 0 | 36 | 0 | 1511.83 | 0 | 1 | Finished | 1475.83 | 1475.83 | C2016-28 Apartment Building Structural Work (1).xlsx
4 | 0 | Apartment Building Structural Work (2) | 2016-03-21 08:00 | 2016-09-15 17:00 | 129d |  |  | 1797873.6172 |  |  | 1797873.6172 |  | 148d | [5 empty] | 1860330.6172 |  | 1 |  | 1797873.6172 | 1797873.6172 | C2016-29 Apartment Building Structural Work (2).xlsx
5 | 20 | betonstructuur blok A gelijkvloers | 2016-03-21 08:00 | 2016-05-17 17:00 | 42d |  |  | 468163.2734 |  |  | 468163.2734 |  | 46d | [5 empty] | 465147.2734 |  | 1 |  | 468163.2734 | 468163.2734 | C2016-29 Apartment Building Structural Work (2).xlsx
6 | 1 | kolommen gelijkvloers blok A | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 78027.2109 | 0 | 0 | 78027.2109 | 2016-03-21 08:00 | 10d | 78027.2109 | 0 | 0 | 7245 | 0 | 85272.2109 | 0 | 1 | Finished | 78027.2109 | 78027.2109 | C2016-29 Apartment Building Structural Work (2).xlsx
7 | 2 | wanden gelijkvloers blok A | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 93632.6484 | 0 | 0 | 93632.6484 | 2016-03-21 08:00 | 15d | 93632.6484 | 0 | 0 | -5585 | 0 | 88047.6484 | 0 | 1 | Finished | 93632.6484 | 93632.6484 | C2016-29 Apartment Building Structural Work (2).xlsx
8 | 3 | balken/liggers boven gelijkvloers blok A | 2016-03-28 08:00 | 2016-04-29 17:00 | 25d |  | 0 | 101435.3828 | 0 | 0 | 101435.3828 | 2016-03-28 08:00 | 29d | 101435.3828 | 0 | 0 | 12833 | 0 | 114268.3828 | 0 | 1 | Finished | 101435.3828 | 101435.3828 | C2016-29 Apartment Building Structural Work (2).xlsx
9 | 4 | afdek gelijkvloers blok A welfsels + opstort druklaag | 2016-05-02 08:00 | 2016-05-17 17:00 | 12d |  | 0 | 195068.0312 | 0 | 0 | 195068.0312 | 2016-05-06 08:00 | 12d | 195068.0312 | 0 | 0 | -17509 | 0 | 177559.0312 | 0 | 1 | Finished | 195068.0312 | 195068.0312 | C2016-29 Apartment Building Structural Work (2).xlsx
10 | 21 | betonstructuur blok A nivo +1 | 2016-05-18 08:00 | 2016-06-20 17:00 | 24d |  |  | 355516.9922 |  |  | 355516.9922 |  | 29d | [5 empty] | 380451.9922 |  | 1 |  | 355516.9922 | 355516.9922 | C2016-29 Apartment Building Structural Work (2).xlsx
11 | 5 | kolommen +1 blok A | 2016-05-18 08:00 | 2016-05-24 17:00 | 5d |  | 0 | 39904.9688 | 0 | 0 | 39904.9688 | 2016-05-24 08:00 | 5d | 39904.9688 | 0 | 0 | 2082 | 0 | 41986.9688 | 0 | 1 | Finished | 39904.9688 | 39904.9688 | C2016-29 Apartment Building Structural Work (2).xlsx
12 | 6 | wanden kernen +1 blok A | 2016-05-18 08:00 | 2016-05-31 17:00 | 10d |  | 0 | 47160.4219 | 0 | 0 | 47160.4219 | 2016-05-24 08:00 | 10d | 47160.4219 | 0 | 0 | 3191 | 0 | 50351.4219 | 0 | 1 | Finished | 47160.4219 | 47160.4219 | C2016-29 Apartment Building Structural Work (2).xlsx
13 | 7 | dragend metselwerk snelbouw +1 blok A | 2016-05-18 08:00 | 2016-06-10 17:00 | 18d |  | 0 | 119714.8984 | 0 | 0 | 119714.8984 | 2016-05-24 08:00 | 22d | 119714.8984 | 0 | 0 | 11258 | 0 | 130972.8984 | 0 | 1 | Finished | 119714.8984 | 119714.8984 | C2016-29 Apartment Building Structural Work (2).xlsx
14 | 8 | balken/liggers boven +1 blok A | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 50788.1406 | 0 | 0 | 50788.1406 | 2016-06-16 08:00 | 6d | 50788.1406 | 0 | 0 | 2533 | 0 | 53321.1406 | 0 | 1 | Finished | 50788.1406 | 50788.1406 | C2016-29 Apartment Building Structural Work (2).xlsx
15 | 9 | afdek verdieping +1 blok A welfsels + opstort druklaag | 2016-06-13 08:00 | 2016-06-20 17:00 | 6d |  | 0 | 97948.5625 | 0 | 0 | 97948.5625 | 2016-06-24 08:00 | 6d | 97948.5625 | 0 | 0 | 5871 | 0 | 103819.5625 | 0 | 1 | Finished | 97948.5625 | 97948.5625 | C2016-29 Apartment Building Structural Work (2).xlsx
16 | 22 | betonstructuur blok A nivo +2 | 2016-07-05 08:00 | 2016-08-09 17:00 | 26d |  |  | 386431.4922 |  |  | 386431.4922 |  | 31d | [5 empty] | 407093.4922 |  | 1 |  | 386431.4922 | 386431.4922 | C2016-29 Apartment Building Structural Work (2).xlsx
17 | 10 | kolommen +2 blok A | 2016-07-05 08:00 | 2016-07-11 17:00 | 5d |  | 0 | 43374.9609 | 0 | 0 | 43374.9609 | 2016-07-18 08:00 | 5d | 43374.9609 | 0 | 0 | 3848 | 0 | 47222.9609 | 0 | 1 | Finished | 43374.9609 | 43374.9609 | C2016-29 Apartment Building Structural Work (2).xlsx
18 | 11 | wanden kernen +2 blok A | 2016-07-05 08:00 | 2016-07-11 17:00 | 5d |  | 0 | 51261.3203 | 0 | 0 | 51261.3203 | 2016-07-18 08:00 | 5d | 51261.3203 | 0 | 0 | 3207 | 0 | 54468.3203 | 0 | 1 | Finished | 51261.3203 | 51261.3203 | C2016-29 Apartment Building Structural Work (2).xlsx
19 | 12 | dragend metselwerk snelbouw +2 blok A | 2016-07-05 08:00 | 2016-07-26 17:00 | 16d |  | 0 | 130124.8906 | 0 | 0 | 130124.8906 | 2016-07-18 08:00 | 20d | 130124.8906 | 0 | 0 | 13412 | 0 | 143536.8906 | 0 | 1 | Finished | 130124.8906 | 130124.8906 | C2016-29 Apartment Building Structural Work (2).xlsx
20 | 13 | balken/liggers boven +2 blok A | 2016-07-20 08:00 | 2016-08-01 17:00 | 9d |  | 0 | 55204.5 | 0 | 0 | 55204.5 | 2016-08-08 08:00 | 10d | 55204.5 | 0 | 0 | 7243 | 0 | 62447.5 | 0 | 1 | Finished | 55204.5 | 55204.5 | C2016-29 Apartment Building Structural Work (2).xlsx
21 | 14 | afdek verdieping +2 blok A welfsels + opstort druklaag | 2016-08-02 08:00 | 2016-08-09 17:00 | 6d |  | 0 | 106465.8203 | 0 | 0 | 106465.8203 | 2016-08-22 08:00 | 6d | 106465.8203 | 0 | 0 | -7048 | 0 | 99417.8203 | 0 | 1 | Finished | 106465.8203 | 106465.8203 | C2016-29 Apartment Building Structural Work (2).xlsx
22 | 23 | betonstructuur blok A nivo +3 | 2016-08-10 08:00 | 2016-09-15 17:00 | 27d |  |  | 587761.8594 |  |  | 587761.8594 |  | 32d | [5 empty] | 607637.8594 |  | 1 |  | 587761.8594 | 587761.8594 | C2016-29 Apartment Building Structural Work (2).xlsx
23 | 15 | kolommen +3 blok A | 2016-08-10 08:00 | 2016-08-12 17:00 | 3d |  | 0 | 65973.2734 | 0 | 0 | 65973.2734 | 2016-08-30 08:00 | 3d | 65973.2734 | 0 | 0 | 6166 | 0 | 72139.2734 | 0 | 1 | Finished | 65973.2734 | 65973.2734 | C2016-29 Apartment Building Structural Work (2).xlsx
24 | 16 | wanden kernen +3 blok A | 2016-08-10 08:00 | 2016-08-12 17:00 | 3d |  | 0 | 77968.4062 | 0 | 0 | 77968.4062 | 2016-08-30 08:00 | 3d | 77968.4062 | 0 | 0 | -342 | 0 | 77626.4062 | 0 | 1 | Finished | 77968.4062 | 77968.4062 | C2016-29 Apartment Building Structural Work (2).xlsx
25 | 17 | dragend metselwerk snelbouw +3 blok A | 2016-08-10 08:00 | 2016-08-31 17:00 | 16d |  | 0 | 197919.8125 | 0 | 0 | 197919.8125 | 2016-08-30 08:00 | 16d | 197919.8125 | 0 | 0 | 30192 | 0 | 228111.8125 | 0 | 1 | Finished | 197919.8125 | 197919.8125 | C2016-29 Apartment Building Structural Work (2).xlsx
26 | 18 | balken/liggers boven +3 blok A | 2016-08-26 08:00 | 2016-09-07 17:00 | 9d |  | 0 | 83965.9766 | 0 | 0 | 83965.9766 | 2016-09-21 08:00 | 10d | 83965.9766 | 0 | 0 | -1552 | 0 | 82413.9766 | 0 | 1 | Finished | 83965.9766 | 83965.9766 | C2016-29 Apartment Building Structural Work (2).xlsx
27 | 19 | afdek verdieping +3 blok A welfsels + opstort druklaag | 2016-09-08 08:00 | 2016-09-15 17:00 | 6d |  | 0 | 161934.3906 | 0 | 0 | 161934.3906 | 2016-10-05 08:00 | 6d | 161934.3906 | 0 | 0 | -14588 | 0 | 147346.3906 | 0 | 1 | Finished | 161934.3906 | 161934.3906 | C2016-29 Apartment Building Structural Work (2).xlsx
4 | 0 | Apartment Building Structural Work (3) | 2016-03-21 08:00 | 2016-07-15 17:00 | 85d |  |  | 1319736.291 |  |  | 1319736.291 |  | 96d | [5 empty] | 1353361.291 |  | 1 |  | 1319736.291 | 1319736.291 | C2016-30 Apartment Building Structural Work (3).xlsx
5 | 24 | betonstructuur blok B gelijkvloers | 2016-03-21 08:00 | 2016-04-22 17:00 | 25d |  |  | 350722.9453 |  |  | 350722.9453 |  | 28d | [5 empty] | 348020.9453 |  | 1 |  | 350722.9453 | 350722.9453 | C2016-30 Apartment Building Structural Work (3).xlsx
6 | 1 | kolommen gelijkvloers blok B | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 38969.2188 | 0 | 0 | 38969.2188 | 2016-03-21 08:00 | 5d | 38969.2188 | 0 | 0 | -3776 | 0 | 35193.2188 | 0 | 1 | Finished | 38969.2188 | 38969.2188 | C2016-30 Apartment Building Structural Work (3).xlsx
7 | 2 | wanden gelijkvloers blok B | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 46763.0586 | 0 | 0 | 46763.0586 | 2016-03-21 08:00 | 4d | 46763.0586 | 0 | 0 | -3558 | 0 | 43205.0586 | 0 | 1 | Finished | 46763.0586 | 46763.0586 | C2016-30 Apartment Building Structural Work (3).xlsx
8 | 3 | dragend metselwerk snelbouw gelijkvloers blok B | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 116907.6484 | 0 | 0 | 116907.6484 | 2016-03-21 08:00 | 17d | 116907.6484 | 0 | 0 | 190 | 0 | 117097.6484 | 0 | 1 | Finished | 116907.6484 | 116907.6484 | C2016-30 Apartment Building Structural Work (3).xlsx
9 | 4 | balken/liggers boven gelijkvloers blok B | 2016-04-05 08:00 | 2016-04-15 17:00 | 9d |  | 0 | 50659.9805 | 0 | 0 | 50659.9805 | 2016-04-07 08:00 | 10d | 50659.9805 | 0 | 0 | 6783 | 0 | 57442.9805 | 0 | 1 | Finished | 50659.9805 | 50659.9805 | C2016-30 Apartment Building Structural Work (3).xlsx
10 | 5 | afdek gelijkvloers blok B welfsels + opstort druklaag | 2016-04-18 08:00 | 2016-04-22 17:00 | 5d |  | 0 | 97423.0391 | 0 | 0 | 97423.0391 | 2016-04-21 08:00 | 5d | 97423.0391 | 0 | 0 | -2341 | 0 | 95082.0391 | 0 | 1 | Finished | 97423.0391 | 97423.0391 | C2016-30 Apartment Building Structural Work (3).xlsx
11 | 25 | betonstructuur blok B nivo +1 | 2016-04-25 08:00 | 2016-05-30 17:00 | 26d |  |  | 309145.2007 |  |  | 309145.2007 |  | 29d | [5 empty] | 308583.2007 |  | 1 |  | 309145.2007 | 309145.2007 | C2016-30 Apartment Building Structural Work (3).xlsx
12 | 6 | kolommen +1 blok B | 2016-04-25 08:00 | 2016-04-29 17:00 | 5d |  | 0 | 34005.9688 | 0 | 0 | 34005.9688 | 2016-04-28 08:00 | 5d | 34005.9688 | 0 | 0 | 823 | 0 | 34828.9688 | 0 | 1 | Finished | 34005.9688 | 34005.9688 | C2016-30 Apartment Building Structural Work (3).xlsx
13 | 7 | wanden kernen +1 blok B | 2016-04-25 08:00 | 2016-04-29 17:00 | 5d |  | 0 | 40188.8789 | 0 | 0 | 40188.8789 | 2016-04-28 08:00 | 4d | 40188.8789 | 0 | 0 | -6113 | 0 | 34075.8789 | 0 | 1 | Finished | 40188.8789 | 40188.8789 | C2016-30 Apartment Building Structural Work (3).xlsx
14 | 8 | dragend metselwerk snelbouw +1 blok B | 2016-04-25 08:00 | 2016-05-13 17:00 | 15d |  | 0 | 102017.9219 | 0 | 0 | 102017.9219 | 2016-04-28 08:00 | 17d | 102017.9219 | 0 | 0 | -310 | 0 | 101707.9219 | 0 | 1 | Finished | 102017.9219 | 102017.9219 | C2016-30 Apartment Building Structural Work (3).xlsx
15 | 9 | balken/liggers boven +1 blok B | 2016-05-10 08:00 | 2016-05-20 17:00 | 9d |  | 0 | 43280.3281 | 0 | 0 | 43280.3281 | 2016-05-17 08:00 | 10d | 43280.3281 | 0 | 0 | 3524 | 0 | 46804.3281 | 0 | 1 | Finished | 43280.3281 | 43280.3281 | C2016-30 Apartment Building Structural Work (3).xlsx
16 | 10 | afdek verdieping +1 blok B welfsels + opstort druklaag | 2016-05-23 08:00 | 2016-05-30 17:00 | 6d |  | 0 | 83469.2031 | 0 | 0 | 83469.2031 | 2016-05-31 08:00 | 6d | 83469.2031 | 0 | 0 | 2038 | 0 | 85507.2031 | 0 | 1 | Finished | 83469.2031 | 83469.2031 | C2016-30 Apartment Building Structural Work (3).xlsx
17 | 11 | platen tpg d=17 en d=21 boven +1 | 2016-05-25 08:00 | 2016-05-30 17:00 | 4d |  | 0 | 6182.8999 | 0 | 0 | 6182.8999 | 2016-06-02 08:00 | 4d | 6182.8999 | 0 | 0 | -524 | 0 | 5658.8999 | 0 | 1 | Finished | 6182.8999 | 6182.8999 | C2016-30 Apartment Building Structural Work (3).xlsx
18 | 26 | betonstructuur blok B nivo +2 | 2016-05-31 08:00 | 2016-07-05 17:00 | 26d |  |  | 309145.2007 |  |  | 309145.2007 |  | 29d | [5 empty] | 328262.2007 |  | 1 |  | 309145.2007 | 309145.2007 | C2016-30 Apartment Building Structural Work (3).xlsx
19 | 12 | kolommen +2 blok B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 34005.9688 | 0 | 0 | 34005.9688 | 2016-06-08 08:00 | 5d | 34005.9688 | 0 | 0 | 254 | 0 | 34259.9688 | 0 | 1 | Finished | 34005.9688 | 34005.9688 | C2016-30 Apartment Building Structural Work (3).xlsx
20 | 13 | wanden kernen +2 blok B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 40188.8789 | 0 | 0 | 40188.8789 | 2016-06-08 08:00 | 4d | 40188.8789 | 0 | 0 | 454 | 0 | 40642.8789 | 0 | 1 | Finished | 40188.8789 | 40188.8789 | C2016-30 Apartment Building Structural Work (3).xlsx
21 | 14 | dragend metselwerk snelbouw +2 blok B | 2016-05-31 08:00 | 2016-06-20 17:00 | 15d |  | 0 | 102017.9219 | 0 | 0 | 102017.9219 | 2016-06-08 08:00 | 17d | 102017.9219 | 0 | 0 | 12063 | 0 | 114080.9219 | 0 | 1 | Finished | 102017.9219 | 102017.9219 | C2016-30 Apartment Building Structural Work (3).xlsx
22 | 15 | balken/liggers boven +2 blok B | 2016-06-15 08:00 | 2016-06-27 17:00 | 9d |  | 0 | 43280.3281 | 0 | 0 | 43280.3281 | 2016-06-27 08:00 | 10d | 43280.3281 | 0 | 0 | 4649 | 0 | 47929.3281 | 0 | 1 | Finished | 43280.3281 | 43280.3281 | C2016-30 Apartment Building Structural Work (3).xlsx
23 | 16 | afdek verdieping +2 blok B welfsels + opstort druklaag | 2016-06-28 08:00 | 2016-07-05 17:00 | 6d |  | 0 | 83469.2031 | 0 | 0 | 83469.2031 | 2016-07-11 08:00 | 6d | 83469.2031 | 0 | 0 | 2197 | 0 | 85666.2031 | 0 | 1 | Finished | 83469.2031 | 83469.2031 | C2016-30 Apartment Building Structural Work (3).xlsx
24 | 17 | platen tpg d=17 en d=21 boven +2 | 2016-06-30 08:00 | 2016-07-05 17:00 | 4d |  | 0 | 6182.8999 | 0 | 0 | 6182.8999 | 2016-07-13 08:00 | 4d | 6182.8999 | 0 | 0 | -500 | 0 | 5682.8999 | 0 | 1 | Finished | 6182.8999 | 6182.8999 | C2016-30 Apartment Building Structural Work (3).xlsx
25 | 27 | betonstructuur blok B nivo +3 | 2016-07-06 08:00 | 2016-07-15 17:00 | 8d |  |  | 350722.9443 |  |  | 350722.9443 |  | 10d | [5 empty] | 368494.9443 |  | 1 |  | 350722.9443 | 350722.9443 | C2016-30 Apartment Building Structural Work (3).xlsx
26 | 18 | kolommen +3 blok B | 2016-07-06 08:00 | 2016-07-08 17:00 | 3d |  | 0 | 38579.5195 | 0 | 0 | 38579.5195 | 2016-07-19 08:00 | 3d | 38579.5195 | 0 | 0 | 2544 | 0 | 41123.5195 | 0 | 1 | Finished | 38579.5195 | 38579.5195 | C2016-30 Apartment Building Structural Work (3).xlsx
27 | 19 | wanden kernen +3 blok B | 2016-07-06 08:00 | 2016-07-08 17:00 | 3d |  | 0 | 45593.9805 | 0 | 0 | 45593.9805 | 2016-07-19 08:00 | 4d | 45593.9805 | 0 | 0 | 0 | 0 | 45593.9805 | 0 | 1 | Finished | 45593.9805 | 45593.9805 | C2016-30 Apartment Building Structural Work (3).xlsx
28 | 20 | dragend metselwerk snelbouw +3 blok B | 2016-07-06 08:00 | 2016-07-14 17:00 | 7d |  | 0 | 115738.5703 | 0 | 0 | 115738.5703 | 2016-07-19 08:00 | 9d | 115738.5703 | 0 | 0 | 1617 | 0 | 117355.5703 | 0 | 1 | Finished | 115738.5703 | 115738.5703 | C2016-30 Apartment Building Structural Work (3).xlsx
29 | 21 | balken/liggers boven +3 blok B | 2016-07-11 08:00 | 2016-07-13 17:00 | 3d |  | 0 | 49101.2109 | 0 | 0 | 49101.2109 | 2016-07-26 08:00 | 3d | 49101.2109 | 0 | 0 | 6738 | 0 | 55839.2109 | 0 | 1 | Finished | 49101.2109 | 49101.2109 | C2016-30 Apartment Building Structural Work (3).xlsx
30 | 22 | afdek verdieping +3 blok B welfsels + opstort druklaag | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 94695.2031 | 0 | 0 | 94695.2031 | 2016-07-26 08:00 | 5d | 94695.2031 | 0 | 0 | 7014 | 0 | 101709.2031 | 0 | 1 | Finished | 94695.2031 | 94695.2031 | C2016-30 Apartment Building Structural Work (3).xlsx
31 | 23 | platen tpg d=15 boven +3 | 2016-07-13 08:00 | 2016-07-15 17:00 | 3d |  | 0 | 7014.46 | 0 | 0 | 7014.46 | 2016-07-28 08:00 | 3d | 7014.46 | 0 | 0 | -141 | 0 | 6873.46 | 0 | 1 | Finished | 7014.46 | 7014.46 | C2016-30 Apartment Building Structural Work (3).xlsx
4 | 0 | Apartment Building Finishing Works (1) | 2016-03-21 08:00 | 2016-08-12 17:00 | 105d |  |  | 488936 |  |  | 488936 |  | 117d | [5 empty] | 498473 |  | 1 |  | 488936 | 488936 | C2016-31 Apartment Building Finishing Works (1).xlsx
5 | 24 | gelijkvloers blok A | 2016-03-21 08:00 | 2016-07-08 17:00 | 80d |  |  | 263062 |  |  | 263062 |  | 92d | [5 empty] | 267887 |  | 1 |  | 263062 | 263062 | C2016-31 Apartment Building Finishing Works (1).xlsx
6 | 1 | pleisterwerken wanden 0A | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 20070 | 0 | 0 | 20070 | 2016-03-21 08:00 | 17d | 20070 | 0 | 0 | -351 | 0 | 19719 | 0 | 1 | Finished | 20070 | 20070 | C2016-31 Apartment Building Finishing Works (1).xlsx
7 | 2 | pleisterwerken plafonds 0A | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 25805 | 0 | 0 | 25805 | 2016-03-21 08:00 | 7d | 25805 | 0 | 0 | 4770 | 0 | 30575 | 0 | 1 | Finished | 25805 | 25805 | C2016-31 Apartment Building Finishing Works (1).xlsx
8 | 3 | lichte scheidingswanden 0A | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 6594 | 0 | 0 | 6594 | 2016-03-23 08:00 | 10d | 6594 | 0 | 0 | -632 | 0 | 5962 | 0 | 1 | Finished | 6594 | 6594 | C2016-31 Apartment Building Finishing Works (1).xlsx
9 | 4 | gespoten PU isolatie en uitvullingen 0A | 2016-04-04 08:00 | 2016-04-06 17:00 | 3d |  | 0 | 10035 | 0 | 0 | 10035 | 2016-04-06 08:00 | 5d | 10035 | 0 | 0 | 2089 | 0 | 12124 | 0 | 1 | Finished | 10035 | 10035 | C2016-31 Apartment Building Finishing Works (1).xlsx
10 | 5 | chape 0A | 2016-04-07 08:00 | 2016-04-13 17:00 | 5d |  | 0 | 4300 | 0 | 0 | 4300 | 2016-04-13 08:00 | 5d | 4300 | 0 | 0 | -48 | 0 | 4252 | 0 | 1 | Finished | 4300 | 4300 | C2016-31 Apartment Building Finishing Works (1).xlsx
11 | 6 | plaatsen keramische tegels 0A | 2016-04-28 08:00 | 2016-05-11 17:00 | 10d |  | 0 | 37273 | 0 | 0 | 37273 | 2016-05-04 08:00 | 10d | 37273 | 0 | 0 | -2668 | 0 | 34605 | 0 | 1 | Finished | 37273 | 37273 | C2016-31 Apartment Building Finishing Works (1).xlsx
12 | 7 | plaatsen faience 0A | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 15626 | 0 | 0 | 15626 | 2016-05-11 08:00 | 10d | 15626 | 0 | 0 | -874 | 0 | 14752 | 0 | 1 | Finished | 15626 | 15626 | C2016-31 Apartment Building Finishing Works (1).xlsx
13 | 8 | verlaagde plafonds 0A | 2016-04-21 08:00 | 2016-05-18 17:00 | 20d |  | 0 | 14336 | 0 | 0 | 14336 | 2016-04-27 08:00 | 20d | 14336 | 0 | 0 | 1256 | 0 | 15592 | 0 | 1 | Finished | 14336 | 14336 | C2016-31 Apartment Building Finishing Works (1).xlsx
14 | 9 | zachte vloerbekleding 0A | 2016-05-26 08:00 | 2016-06-10 17:00 | 12d |  | 0 | 11468 | 0 | 0 | 11468 | 2016-06-01 08:00 | 15d | 11468 | 0 | 0 | 1334 | 0 | 12802 | 0 | 1 | Finished | 11468 | 11468 | C2016-31 Apartment Building Finishing Works (1).xlsx
15 | 10 | binnenschrijnwerk 0A | 2016-06-13 08:00 | 2016-06-22 17:00 | 8d |  | 0 | 40141 | 0 | 0 | 40141 | 2016-06-22 08:00 | 10d | 40141 | 0 | 0 | 449 | 0 | 40590 | 0 | 1 | Finished | 40141 | 40141 | C2016-31 Apartment Building Finishing Works (1).xlsx
16 | 11 | schilderwerken wanden en plafonds 0A | 2016-06-13 08:00 | 2016-07-08 17:00 | 20d |  | 0 | 34406 | 0 | 0 | 34406 | 2016-06-22 08:00 | 25d | 34406 | 0 | 0 | 2697 | 0 | 37103 | 0 | 1 | Finished | 34406 | 34406 | C2016-31 Apartment Building Finishing Works (1).xlsx
17 | 12 | binnenmeubilair 0A | 2016-06-13 08:00 | 2016-06-24 17:00 | 10d |  | 0 | 43008 | 0 | 0 | 43008 | 2016-06-22 08:00 | 10d | 43008 | 0 | 0 | -3197 | 0 | 39811 | 0 | 1 | Finished | 43008 | 43008 | C2016-31 Apartment Building Finishing Works (1).xlsx
18 | 25 | nivo +1 blok A | 2016-04-11 08:00 | 2016-08-12 17:00 | 90d |  |  | 225874 |  |  | 225874 |  | 100d | [5 empty] | 230586 |  | 1 |  | 225874 | 225874 | C2016-31 Apartment Building Finishing Works (1).xlsx
19 | 13 | pleisterwerken wanden 1A | 2016-04-11 08:00 | 2016-04-22 17:00 | 10d |  | 0 | 18547 | 0 | 0 | 18547 | 2016-04-13 08:00 | 10d | 18547 | 0 | 0 | 405 | 0 | 18952 | 0 | 1 | Finished | 18547 | 18547 | C2016-31 Apartment Building Finishing Works (1).xlsx
20 | 14 | pleisterwerken plafonds 1A | 2016-04-11 08:00 | 2016-04-29 17:00 | 15d |  | 0 | 23846 | 0 | 0 | 23846 | 2016-04-13 08:00 | 15d | 23846 | 0 | 0 | -1160 | 0 | 22686 | 0 | 1 | Finished | 23846 | 23846 | C2016-31 Apartment Building Finishing Works (1).xlsx
21 | 15 | lichte scheidingswanden 1A | 2016-04-25 08:00 | 2016-05-06 17:00 | 10d |  | 0 | 6094 | 0 | 0 | 6094 | 2016-04-27 08:00 | 10d | 6094 | 0 | 0 | -349 | 0 | 5745 | 0 | 1 | Finished | 6094 | 6094 | C2016-31 Apartment Building Finishing Works (1).xlsx
22 | 16 | vloer uitvullingen 1A | 2016-05-09 08:00 | 2016-05-11 17:00 | 3d |  | 0 | 3974 | 0 | 0 | 3974 | 2016-05-11 08:00 | 5d | 3974 | 0 | 0 | 1028 | 0 | 5002 | 0 | 1 | Finished | 3974 | 3974 | C2016-31 Apartment Building Finishing Works (1).xlsx
23 | 17 | chape 1A | 2016-05-12 08:00 | 2016-05-18 17:00 | 5d |  | 0 | 34444 | 0 | 0 | 34444 | 2016-05-18 08:00 | 5d | 34444 | 0 | 0 | 2235 | 0 | 36679 | 0 | 1 | Finished | 34444 | 34444 | C2016-31 Apartment Building Finishing Works (1).xlsx
24 | 18 | plaatsen keramische tegels 1A | 2016-06-02 08:00 | 2016-06-15 17:00 | 10d |  | 0 | 14440 | 0 | 0 | 14440 | 2016-06-08 08:00 | 10d | 14440 | 0 | 0 | -1302 | 0 | 13138 | 0 | 1 | Finished | 14440 | 14440 | C2016-31 Apartment Building Finishing Works (1).xlsx
25 | 19 | plaatsen faience 1A | 2016-06-09 08:00 | 2016-06-22 17:00 | 10d |  | 0 | 13247 | 0 | 0 | 13247 | 2016-06-15 08:00 | 10d | 13247 | 0 | 0 | -877 | 0 | 12370 | 0 | 1 | Finished | 13247 | 13247 | C2016-31 Apartment Building Finishing Works (1).xlsx
26 | 20 | zachte vloerbekleding 1A | 2016-06-30 08:00 | 2016-07-15 17:00 | 12d |  | 0 | 10598 | 0 | 0 | 10598 | 2016-07-06 08:00 | 15d | 10598 | 0 | 0 | 838 | 0 | 11436 | 0 | 1 | Finished | 10598 | 10598 | C2016-31 Apartment Building Finishing Works (1).xlsx
27 | 21 | binnenschrijnwerk 1A | 2016-07-18 08:00 | 2016-07-27 17:00 | 8d |  | 0 | 37094 | 0 | 0 | 37094 | 2016-07-27 08:00 | 10d | 37094 | 0 | 0 | -504 | 0 | 36590 | 0 | 1 | Finished | 37094 | 37094 | C2016-31 Apartment Building Finishing Works (1).xlsx
28 | 22 | schilderwerken wanden en plafonds 1A | 2016-07-18 08:00 | 2016-08-12 17:00 | 20d |  | 0 | 31795 | 0 | 0 | 31795 | 2016-07-27 08:00 | 25d | 31795 | 0 | 0 | 4718 | 0 | 36513 | 0 | 1 | Finished | 31795 | 31795 | C2016-31 Apartment Building Finishing Works (1).xlsx
29 | 23 | binnenmeubilair 1A | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 31795 | 0 | 0 | 31795 | 2016-07-27 08:00 | 10d | 31795 | 0 | 0 | -320 | 0 | 31475 | 0 | 1 | Finished | 31795 | 31795 | C2016-31 Apartment Building Finishing Works (1).xlsx
4 | 0 | Apartment Building Finishing Works (2) | 2016-03-21 08:00 | 2016-07-21 17:00 | 89d |  |  | 477381 |  |  | 477381 |  | 97d | [5 empty] | 496991 |  | 1 |  | 477381 | 477381 | C2016-32 Apartment Building Finishing Works (2).xlsx
5 | 23 | nivo +2 blok A | 2016-03-21 08:00 | 2016-07-15 17:00 | 85d |  |  | 233822 |  |  | 233822 |  | 97d | [5 empty] | 245743 |  | 1 |  | 233822 | 233822 | C2016-32 Apartment Building Finishing Works (2).xlsx
6 | 1 | pleisterwerken wanden 2A | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 18547 | 0 | 0 | 18547 | 2016-03-21 08:00 | 17d | 18547 | 0 | 0 | -213 | 0 | 18334 | 0 | 1 | Finished | 18547 | 18547 | C2016-32 Apartment Building Finishing Works (2).xlsx
7 | 2 | pleisterwerken plafonds 2A | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 23846 | 0 | 0 | 23846 | 2016-03-21 08:00 | 12d | 23846 | 0 | 0 | 3541 | 0 | 27387 | 0 | 1 | Finished | 23846 | 23846 | C2016-32 Apartment Building Finishing Works (2).xlsx
8 | 3 | lichte scheidingswanden 2A | 2016-03-28 08:00 | 2016-04-08 17:00 | 10d |  | 0 | 6094 | 0 | 0 | 6094 | 2016-03-30 08:00 | 10d | 6094 | 0 | 0 | 35 | 0 | 6129 | 0 | 1 | Finished | 6094 | 6094 | C2016-32 Apartment Building Finishing Works (2).xlsx
9 | 4 | vloer uitvullingen 2A | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3974 | 0 | 0 | 3974 | 2016-04-13 08:00 | 5d | 3974 | 0 | 0 | 185 | 0 | 4159 | 0 | 1 | Finished | 3974 | 3974 | C2016-32 Apartment Building Finishing Works (2).xlsx
10 | 5 | chape 2A | 2016-04-14 08:00 | 2016-04-20 17:00 | 5d |  | 0 | 34444 | 0 | 0 | 34444 | 2016-04-20 08:00 | 5d | 34444 | 0 | 0 | -251 | 0 | 34193 | 0 | 1 | Finished | 34444 | 34444 | C2016-32 Apartment Building Finishing Works (2).xlsx
11 | 6 | plaatsen keramische tegels 2A | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 14440 | 0 | 0 | 14440 | 2016-05-11 08:00 | 10d | 14440 | 0 | 0 | 376 | 0 | 14816 | 0 | 1 | Finished | 14440 | 14440 | C2016-32 Apartment Building Finishing Works (2).xlsx
12 | 7 | plaatsen faience 2A | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 13247 | 0 | 0 | 13247 | 2016-05-18 08:00 | 10d | 13247 | 0 | 0 | 218 | 0 | 13465 | 0 | 1 | Finished | 13247 | 13247 | C2016-32 Apartment Building Finishing Works (2).xlsx
13 | 8 | zachte vloerbekleding 2A | 2016-06-02 08:00 | 2016-06-17 17:00 | 12d |  | 0 | 10598 | 0 | 0 | 10598 | 2016-06-08 08:00 | 15d | 10598 | 0 | 0 | 388 | 0 | 10986 | 0 | 1 | Finished | 10598 | 10598 | C2016-32 Apartment Building Finishing Works (2).xlsx
14 | 9 | binnenschrijnwerk 2A | 2016-06-20 08:00 | 2016-06-29 17:00 | 8d |  | 0 | 37094 | 0 | 0 | 37094 | 2016-06-29 08:00 | 10d | 37094 | 0 | 0 | 1257 | 0 | 38351 | 0 | 1 | Finished | 37094 | 37094 | C2016-32 Apartment Building Finishing Works (2).xlsx
15 | 10 | schilderwerken wanden en plafonds 2A | 2016-06-20 08:00 | 2016-07-15 17:00 | 20d |  | 0 | 31795 | 0 | 0 | 31795 | 2016-06-29 08:00 | 25d | 31795 | 0 | 0 | 2577 | 0 | 34372 | 0 | 1 | Finished | 31795 | 31795 | C2016-32 Apartment Building Finishing Works (2).xlsx
16 | 11 | binnenmeubilair 2A | 2016-06-20 08:00 | 2016-07-01 17:00 | 10d |  | 0 | 39743 | 0 | 0 | 39743 | 2016-06-29 08:00 | 10d | 39743 | 0 | 0 | 3808 | 0 | 43551 | 0 | 1 | Finished | 39743 | 39743 | C2016-32 Apartment Building Finishing Works (2).xlsx
17 | 24 | nivo +3 blok A | 2016-04-21 08:00 | 2016-07-21 17:00 | 66d |  |  | 243559 |  |  | 243559 |  | 70d | [5 empty] | 251248 |  | 1 |  | 243559 | 243559 | C2016-32 Apartment Building Finishing Works (2).xlsx
18 | 12 | pleisterwerken wanden 3A | 2016-04-21 08:00 | 2016-05-04 17:00 | 10d |  | 0 | 19319 | 0 | 0 | 19319 | 2016-04-27 08:00 | 10d | 19319 | 0 | 0 | 88 | 0 | 19407 | 0 | 1 | Finished | 19319 | 19319 | C2016-32 Apartment Building Finishing Works (2).xlsx
19 | 13 | pleisterwerken plafonds 3A | 2016-04-21 08:00 | 2016-04-27 17:00 | 5d |  | 0 | 24839 | 0 | 0 | 24839 | 2016-04-27 08:00 | 5d | 24839 | 0 | 0 | -732 | 0 | 24107 | 0 | 1 | Finished | 24839 | 24839 | C2016-32 Apartment Building Finishing Works (2).xlsx
20 | 14 | lichte scheidingswanden 3A | 2016-04-21 08:00 | 2016-05-04 17:00 | 10d |  | 0 | 6347 | 0 | 0 | 6347 | 2016-04-27 08:00 | 10d | 6347 | 0 | 0 | -159 | 0 | 6188 | 0 | 1 | Finished | 6347 | 6347 | C2016-32 Apartment Building Finishing Works (2).xlsx
21 | 15 | vloer uitvullingen 3A | 2016-05-05 08:00 | 2016-05-09 17:00 | 3d |  | 0 | 4139 | 0 | 0 | 4139 | 2016-05-11 08:00 | 5d | 4139 | 0 | 0 | 757 | 0 | 4896 | 0 | 1 | Finished | 4139 | 4139 | C2016-32 Apartment Building Finishing Works (2).xlsx
22 | 16 | chape 3A | 2016-05-10 08:00 | 2016-05-12 17:00 | 3d |  | 0 | 35879 | 0 | 0 | 35879 | 2016-05-18 08:00 | 5d | 35879 | 0 | 0 | 4859 | 0 | 40738 | 0 | 1 | Finished | 35879 | 35879 | C2016-32 Apartment Building Finishing Works (2).xlsx
23 | 17 | plaatsen keramische tegels 3A | 2016-05-27 08:00 | 2016-06-07 17:00 | 8d |  | 0 | 15041 | 0 | 0 | 15041 | 2016-06-08 08:00 | 10d | 15041 | 0 | 0 | 2053 | 0 | 17094 | 0 | 1 | Finished | 15041 | 15041 | C2016-32 Apartment Building Finishing Works (2).xlsx
24 | 18 | plaatsen faience 3A | 2016-06-01 08:00 | 2016-06-10 17:00 | 8d |  | 0 | 13799 | 0 | 0 | 13799 | 2016-06-15 08:00 | 10d | 13799 | 0 | 0 | 22 | 0 | 13821 | 0 | 1 | Finished | 13799 | 13799 | C2016-32 Apartment Building Finishing Works (2).xlsx
25 | 19 | zachte vloerbekleding 3A | 2016-06-24 08:00 | 2016-07-07 17:00 | 10d |  | 0 | 11039 | 0 | 0 | 11039 | 2016-07-06 08:00 | 10d | 11039 | 0 | 0 | -885 | 0 | 10154 | 0 | 1 | Finished | 11039 | 11039 | C2016-32 Apartment Building Finishing Works (2).xlsx
26 | 20 | binnenschrijnwerk 3A | 2016-07-08 08:00 | 2016-07-19 17:00 | 8d |  | 0 | 38639 | 0 | 0 | 38639 | 2016-07-20 08:00 | 10d | 38639 | 0 | 0 | 2721 | 0 | 41360 | 0 | 1 | Finished | 38639 | 38639 | C2016-32 Apartment Building Finishing Works (2).xlsx
27 | 21 | schilderwerken wanden en plafonds 3A | 2016-07-08 08:00 | 2016-07-21 17:00 | 10d |  | 0 | 33119 | 0 | 0 | 33119 | 2016-07-20 08:00 | 10d | 33119 | 0 | 0 | -1300 | 0 | 31819 | 0 | 1 | Finished | 33119 | 33119 | C2016-32 Apartment Building Finishing Works (2).xlsx
28 | 22 | binnenmeubilair 3A | 2016-07-08 08:00 | 2016-07-19 17:00 | 8d |  | 0 | 41399 | 0 | 0 | 41399 | 2016-07-20 08:00 | 10d | 41399 | 0 | 0 | 265 | 0 | 41664 | 0 | 1 | Finished | 41399 | 41399 | C2016-32 Apartment Building Finishing Works (2).xlsx
4 | 0 | Apartment Building Finishing Works (3) | 2016-03-21 08:00 | 2016-08-29 17:00 | 116d |  |  | 377282 |  |  | 377282 |  | 129d | [5 empty] | 394829 |  | 1 |  | 377282 | 377282 | C2016-33 Apartment Building Finishing Works (3).xlsx
5 | 25 | gelijkvloers blok B | 2016-03-21 08:00 | 2016-07-20 17:00 | 88d |  |  | 199743 |  |  | 199743 |  | 97d | [5 empty] | 204250 |  | 1 |  | 199743 | 199743 | C2016-33 Apartment Building Finishing Works (3).xlsx
6 | 1 | pleisterwerken wanden 0 B | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 15239 | 0 | 0 | 15239 | 2016-03-21 08:00 | 18d | 15239 | 0 | 0 | -87 | 0 | 15152 | 0 | 1 | Finished | 15239 | 15239 | C2016-33 Apartment Building Finishing Works (3).xlsx
7 | 2 | pleisterwerken plafonds 0 B | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 19593 | 0 | 0 | 19593 | 2016-03-21 08:00 | 7d | 19593 | 0 | 0 | 3828 | 0 | 23421 | 0 | 1 | Finished | 19593 | 19593 | C2016-33 Apartment Building Finishing Works (3).xlsx
8 | 3 | lichte scheidingswanden 0 B | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 5007 | 0 | 0 | 5007 | 2016-03-23 08:00 | 10d | 5007 | 0 | 0 | 148 | 0 | 5155 | 0 | 1 | Finished | 5007 | 5007 | C2016-33 Apartment Building Finishing Works (3).xlsx
9 | 4 | gespoten PU isolaie en uitvullingen 0 B | 2016-04-04 08:00 | 2016-04-06 17:00 | 3d |  | 0 | 7619 | 0 | 0 | 7619 | 2016-04-06 08:00 | 5d | 7619 | 0 | 0 | 1470 | 0 | 9089 | 0 | 1 | Finished | 7619 | 7619 | C2016-33 Apartment Building Finishing Works (3).xlsx
10 | 5 | chape 0 B | 2016-04-07 08:00 | 2016-04-13 17:00 | 5d |  | 0 | 3265 | 0 | 0 | 3265 | 2016-04-13 08:00 | 5d | 3265 | 0 | 0 | 206 | 0 | 3471 | 0 | 1 | Finished | 3265 | 3265 | C2016-33 Apartment Building Finishing Works (3).xlsx
11 | 6 | plaatsen keramsiche tegels 0 B | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 28302 | 0 | 0 | 28302 | 2016-05-18 08:00 | 10d | 28302 | 0 | 0 | -1014 | 0 | 27288 | 0 | 1 | Finished | 28302 | 28302 | C2016-33 Apartment Building Finishing Works (3).xlsx
12 | 7 | plaatsen faience 0 B | 2016-05-19 08:00 | 2016-06-01 17:00 | 10d |  | 0 | 11865 | 0 | 0 | 11865 | 2016-05-25 08:00 | 10d | 11865 | 0 | 0 | -713 | 0 | 11152 | 0 | 1 | Finished | 11865 | 11865 | C2016-33 Apartment Building Finishing Works (3).xlsx
13 | 8 | verlaagde plafonds 0 B | 2016-05-05 08:00 | 2016-06-01 17:00 | 20d |  | 0 | 10885 | 0 | 0 | 10885 | 2016-05-11 08:00 | 20d | 10885 | 0 | 0 | 352 | 0 | 11237 | 0 | 1 | Finished | 10885 | 10885 | C2016-33 Apartment Building Finishing Works (3).xlsx
14 | 9 | zachte vloerbekleding 0 B | 2016-06-09 08:00 | 2016-06-22 17:00 | 10d |  | 0 | 8708 | 0 | 0 | 8708 | 2016-06-15 08:00 | 10d | 8708 | 0 | 0 | -500 | 0 | 8208 | 0 | 1 | Finished | 8708 | 8708 | C2016-33 Apartment Building Finishing Works (3).xlsx
15 | 10 | binnenschrijnwerk 0 B | 2016-06-23 08:00 | 2016-07-04 17:00 | 8d |  | 0 | 30479 | 0 | 0 | 30479 | 2016-06-29 08:00 | 10d | 30479 | 0 | 0 | -370 | 0 | 30109 | 0 | 1 | Finished | 30479 | 30479 | C2016-33 Apartment Building Finishing Works (3).xlsx
16 | 11 | schilderwerken wanden en plafonds 0 B | 2016-06-23 08:00 | 2016-07-20 17:00 | 20d |  | 0 | 26125 | 0 | 0 | 26125 | 2016-06-29 08:00 | 25d | 26125 | 0 | 0 | 1412 | 0 | 27537 | 0 | 1 | Finished | 26125 | 26125 | C2016-33 Apartment Building Finishing Works (3).xlsx
17 | 12 | binnenmeubilair 0 B | 2016-06-23 08:00 | 2016-07-06 17:00 | 10d |  | 0 | 32656 | 0 | 0 | 32656 | 2016-06-29 08:00 | 10d | 32656 | 0 | 0 | -225 | 0 | 32431 | 0 | 1 | Finished | 32656 | 32656 | C2016-33 Apartment Building Finishing Works (3).xlsx
18 | 26 | nivo +1 blok B | 2016-05-05 08:00 | 2016-08-29 17:00 | 83d |  |  | 177539 |  |  | 177539 |  | 92d | [5 empty] | 190579 |  | 1 |  | 177539 | 177539 | C2016-33 Apartment Building Finishing Works (3).xlsx
19 | 13 | pleisterwerken wanden 1 B | 2016-05-05 08:00 | 2016-05-25 17:00 | 15d |  | 0 | 14082 | 0 | 0 | 14082 | 2016-05-11 08:00 | 18d | 14082 | 0 | 0 | 2028 | 0 | 16110 | 0 | 1 | Finished | 14082 | 14082 | C2016-33 Apartment Building Finishing Works (3).xlsx
20 | 14 | pleisterwerken plafonds 1 B | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 18106 | 0 | 0 | 18106 | 2016-05-11 08:00 | 12d | 18106 | 0 | 0 | 871 | 0 | 18977 | 0 | 1 | Finished | 18106 | 18106 | C2016-33 Apartment Building Finishing Works (3).xlsx
21 | 15 | lichte scheidingswanden 1 B | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 4627 | 0 | 0 | 4627 | 2016-05-20 08:00 | 10d | 4627 | 0 | 0 | -427 | 0 | 4200 | 0 | 1 | Finished | 4627 | 4627 | C2016-33 Apartment Building Finishing Works (3).xlsx
22 | 16 | vloer uitvullingen 1 B | 2016-05-26 08:00 | 2016-05-30 17:00 | 3d |  | 0 | 3017 | 0 | 0 | 3017 | 2016-06-03 08:00 | 5d | 3017 | 0 | 0 | 616 | 0 | 3633 | 0 | 1 | Finished | 3017 | 3017 | C2016-33 Apartment Building Finishing Works (3).xlsx
23 | 17 | chape 1 B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 26153 | 0 | 0 | 26153 | 2016-06-10 08:00 | 5d | 26153 | 0 | 0 | 375 | 0 | 26528 | 0 | 1 | Finished | 26153 | 26153 | C2016-33 Apartment Building Finishing Works (3).xlsx
24 | 18 | plaatsen keramsiche tegels 1 B | 2016-06-21 08:00 | 2016-07-04 17:00 | 10d |  | 0 | 10964 | 0 | 0 | 10964 | 2016-07-01 08:00 | 10d | 10964 | 0 | 0 | 1096 | 0 | 12060 | 0 | 1 | Finished | 10964 | 10964 | C2016-33 Apartment Building Finishing Works (3).xlsx
25 | 19 | plaatsen faience 1 B | 2016-06-28 08:00 | 2016-07-11 17:00 | 10d |  | 0 | 10059 | 0 | 0 | 10059 | 2016-07-08 08:00 | 10d | 10059 | 0 | 0 | 558 | 0 | 10617 | 0 | 1 | Finished | 10059 | 10059 | C2016-33 Apartment Building Finishing Works (3).xlsx
26 | 20 | zachte vloerbekleding 1 B | 2016-07-19 08:00 | 2016-08-01 17:00 | 10d |  | 0 | 8047 | 0 | 0 | 8047 | 2016-07-29 08:00 | 10d | 8047 | 0 | 0 | -29 | 0 | 8018 | 0 | 1 | Finished | 8047 | 8047 | C2016-33 Apartment Building Finishing Works (3).xlsx
27 | 21 | binnenschrijnwerk 1B | 2016-08-02 08:00 | 2016-08-11 17:00 | 8d |  | 0 | 28165 | 0 | 0 | 28165 | 2016-08-12 08:00 | 10d | 28165 | 0 | 0 | 5130 | 0 | 33295 | 0 | 1 | Finished | 28165 | 28165 | C2016-33 Apartment Building Finishing Works (3).xlsx
28 | 22 | schilderwerken wanden en plafonds 1B | 2016-08-02 08:00 | 2016-08-29 17:00 | 20d |  | 0 | 24142 | 0 | 0 | 24142 | 2016-08-12 08:00 | 25d | 24142 | 0 | 0 | 4109 | 0 | 28251 | 0 | 1 | Finished | 24142 | 24142 | C2016-33 Apartment Building Finishing Works (3).xlsx
29 | 24 | binnenmeubilair 1B | 2016-08-02 08:00 | 2016-08-15 17:00 | 10d |  | 0 | 30177 | 0 | 0 | 30177 | 2016-08-12 08:00 | 10d | 30177 | 0 | 0 | -1287 | 0 | 28890 | 0 | 1 | Finished | 30177 | 30177 | C2016-33 Apartment Building Finishing Works (3).xlsx
4 | 0 | Apartment Building Finishing Works (4) | 2016-03-21 08:00 | 2016-07-13 17:00 | 83d |  |  | 362476 |  |  | 362476 |  | 92d | [5 empty] | 383871 |  | 1 |  | 362476 | 362476 | C2016-34 Apartment Building Finishing Works (4).xlsx
5 | 24 | nivo +2 blok B | 2016-03-21 08:00 | 2016-07-13 17:00 | 83d |  |  | 177539 |  |  | 177539 |  | 92d | [5 empty] | 187211 |  | 1 |  | 177539 | 177539 | C2016-34 Apartment Building Finishing Works (4).xlsx
6 | 1 | pleisterwerken wanden 2B | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 14082 | 0 | 0 | 14082 | 2016-03-21 08:00 | 17d | 14082 | 0 | 0 | 475 | 0 | 14557 | 0 | 1 | Finished | 14082 | 14082 | C2016-34 Apartment Building Finishing Works (4).xlsx
7 | 2 | pleisterwerken plafonds 2B | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 18106 | 0 | 0 | 18106 | 2016-03-21 08:00 | 12d | 18106 | 0 | 0 | 2859 | 0 | 20965 | 0 | 1 | Finished | 18106 | 18106 | C2016-34 Apartment Building Finishing Works (4).xlsx
8 | 3 | lichte scheidingswanden 2B | 2016-03-28 08:00 | 2016-04-08 17:00 | 10d |  | 0 | 4627 | 0 | 0 | 4627 | 2016-03-30 08:00 | 10d | 4627 | 0 | 0 | 222 | 0 | 4849 | 0 | 1 | Finished | 4627 | 4627 | C2016-34 Apartment Building Finishing Works (4).xlsx
9 | 4 | vloer uitvullingen 2B | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3017 | 0 | 0 | 3017 | 2016-04-13 08:00 | 5d | 3017 | 0 | 0 | 454 | 0 | 3471 | 0 | 1 | Finished | 3017 | 3017 | C2016-34 Apartment Building Finishing Works (4).xlsx
10 | 5 | chape 2B | 2016-04-14 08:00 | 2016-04-20 17:00 | 5d |  | 0 | 26153 | 0 | 0 | 26153 | 2016-04-20 08:00 | 5d | 26153 | 0 | 0 | 2433 | 0 | 28586 | 0 | 1 | Finished | 26153 | 26153 | C2016-34 Apartment Building Finishing Works (4).xlsx
11 | 6 | plaatsen keramische tegels 2B | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 10964 | 0 | 0 | 10964 | 2016-05-11 08:00 | 10d | 10964 | 0 | 0 | 825 | 0 | 11789 | 0 | 1 | Finished | 10964 | 10964 | C2016-34 Apartment Building Finishing Works (4).xlsx
12 | 7 | plaatsen faience 2B | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 10059 | 0 | 0 | 10059 | 2016-05-18 08:00 | 10d | 10059 | 0 | 0 | 37 | 0 | 10096 | 0 | 1 | Finished | 10059 | 10059 | C2016-34 Apartment Building Finishing Works (4).xlsx
13 | 8 | zachte vloerbekleding 2B | 2016-06-02 08:00 | 2016-06-15 17:00 | 10d |  | 0 | 8047 | 0 | 0 | 8047 | 2016-06-08 08:00 | 10d | 8047 | 0 | 0 | 224 | 0 | 8271 | 0 | 1 | Finished | 8047 | 8047 | C2016-34 Apartment Building Finishing Works (4).xlsx
14 | 9 | binnenschrijnwerk 2B | 2016-06-16 08:00 | 2016-06-27 17:00 | 8d |  | 0 | 28165 | 0 | 0 | 28165 | 2016-06-22 08:00 | 10d | 28165 | 0 | 0 | -372 | 0 | 27793 | 0 | 1 | Finished | 28165 | 28165 | C2016-34 Apartment Building Finishing Works (4).xlsx
15 | 10 | schilderwerken wanden en plafonds 2B | 2016-06-16 08:00 | 2016-07-13 17:00 | 20d |  | 0 | 24142 | 0 | 0 | 24142 | 2016-06-22 08:00 | 25d | 24142 | 0 | 0 | 4411 | 0 | 28553 | 0 | 1 | Finished | 24142 | 24142 | C2016-34 Apartment Building Finishing Works (4).xlsx
16 | 11 | binnenmeubilair 2B | 2016-06-16 08:00 | 2016-06-29 17:00 | 10d |  | 0 | 30177 | 0 | 0 | 30177 | 2016-06-22 08:00 | 10d | 30177 | 0 | 0 | -1896 | 0 | 28281 | 0 | 1 | Finished | 30177 | 30177 | C2016-34 Apartment Building Finishing Works (4).xlsx
17 | 25 | nivo +3 blok B | 2016-04-04 08:00 | 2016-07-04 17:00 | 66d |  |  | 184937 |  |  | 184937 |  | 70d | [5 empty] | 196660 |  | 1 |  | 184937 | 184937 | C2016-34 Apartment Building Finishing Works (4).xlsx
18 | 12 | pleisterwerken wanden 3B | 2016-04-04 08:00 | 2016-04-15 17:00 | 10d |  | 0 | 14596 | 0 | 0 | 14596 | 2016-04-06 08:00 | 10d | 14596 | 0 | 0 | 817 | 0 | 15413 | 0 | 1 | Finished | 14596 | 14596 | C2016-34 Apartment Building Finishing Works (4).xlsx
19 | 13 | pleisterwerken plafonds 3B | 2016-04-04 08:00 | 2016-04-08 17:00 | 5d |  | 0 | 18767 | 0 | 0 | 18767 | 2016-04-06 08:00 | 5d | 18767 | 0 | 0 | 457 | 0 | 19224 | 0 | 1 | Finished | 18767 | 18767 | C2016-34 Apartment Building Finishing Works (4).xlsx
20 | 14 | lichte scheidingswanden 3B | 2016-04-04 08:00 | 2016-04-08 17:00 | 5d |  | 0 | 4796 | 0 | 0 | 4796 | 2016-04-06 08:00 | 5d | 4796 | 0 | 0 | -455 | 0 | 4341 | 0 | 1 | Finished | 4796 | 4796 | C2016-34 Apartment Building Finishing Works (4).xlsx
21 | 15 | vloer uitvullingen 3B | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3127 | 0 | 0 | 3127 | 2016-04-13 08:00 | 5d | 3127 | 0 | 0 | 484 | 0 | 3611 | 0 | 1 | Finished | 3127 | 3127 | C2016-34 Apartment Building Finishing Works (4).xlsx
22 | 16 | chape 3B | 2016-04-14 08:00 | 2016-04-18 17:00 | 3d |  | 0 | 27108 | 0 | 0 | 27108 | 2016-04-20 08:00 | 5d | 27108 | 0 | 0 | 8248 | 0 | 35356 | 0 | 1 | Finished | 27108 | 27108 | C2016-34 Apartment Building Finishing Works (4).xlsx
23 | 17 | plaatsen keramische tegels 3B | 2016-05-03 08:00 | 2016-05-12 17:00 | 8d |  | 0 | 11364 | 0 | 0 | 11364 | 2016-05-11 08:00 | 10d | 11364 | 0 | 0 | 245 | 0 | 11609 | 0 | 1 | Finished | 11364 | 11364 | C2016-34 Apartment Building Finishing Works (4).xlsx
24 | 18 | plaatsen faience 3B | 2016-05-06 08:00 | 2016-05-17 17:00 | 8d |  | 0 | 10426 | 0 | 0 | 10426 | 2016-05-18 08:00 | 10d | 10426 | 0 | 0 | 1474 | 0 | 11900 | 0 | 1 | Finished | 10426 | 10426 | C2016-34 Apartment Building Finishing Works (4).xlsx
25 | 19 | zachte vloerbekleding 3B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 8340 | 0 | 0 | 8340 | 2016-06-08 08:00 | 5d | 8340 | 0 | 0 | 741 | 0 | 9081 | 0 | 1 | Finished | 8340 | 8340 | C2016-34 Apartment Building Finishing Works (4).xlsx
26 | 20 | binnenschrijnwerk 3B | 2016-06-07 08:00 | 2016-06-16 17:00 | 8d |  | 0 | 29193 | 0 | 0 | 29193 | 2016-06-15 08:00 | 10d | 29193 | 0 | 0 | 1977 | 0 | 31170 | 0 | 1 | Finished | 29193 | 29193 | C2016-34 Apartment Building Finishing Works (4).xlsx
27 | 21 | schilderwerken wanden en plafonds 3B | 2016-06-07 08:00 | 2016-06-27 17:00 | 15d |  | 0 | 25022 | 0 | 0 | 25022 | 2016-06-15 08:00 | 15d | 25022 | 0 | 0 | -2133 | 0 | 22889 | 0 | 1 | Finished | 25022 | 25022 | C2016-34 Apartment Building Finishing Works (4).xlsx
28 | 22 | binnenmeubilair 3B | 2016-06-07 08:00 | 2016-06-16 17:00 | 8d |  | 0 | 31278 | 0 | 0 | 31278 | 2016-06-15 08:00 | 10d | 31278 | 0 | 0 | -113 | 0 | 31165 | 0 | 1 | Finished | 31278 | 31278 | C2016-34 Apartment Building Finishing Works (4).xlsx
29 | 23 | opkuis voor oplevering blok B | 2016-06-28 08:00 | 2016-07-04 17:00 | 5d |  | 0 | 920 | 0 | 0 | 920 | 2016-07-06 08:00 | 5d | 920 | 0 | 0 | -19 | 0 | 901 | 0 | 1 | Finished | 920 | 920 | C2016-34 Apartment Building Finishing Works (4).xlsx
4 | 0 | PROJECT LEPELSTRAAT | 2015-07-30 | 2017-08-14 17:00 | 533d |  |  | 0 |  |  | 1292979 |  | 673d | [5 empty] | 1315819.86 |  | 1 |  | 1292979 | 1292979 | C2019-01 Lepelstraat.xlsx
5 | 1 | maken compromis aankoop grond met 1 of meerdere huizen | 2015-07-30 | 2015-07-30 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2015-07-30 08:00 | 67d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-01 Lepelstraat.xlsx
6 | 2 | Aanvraag plannen architect | 2015-07-31 | 2015-07-31 17:00 | 1d |  | 0 | 0 | 3375 | 27000 | 27000 | 2015-07-31 08:00 | 66d | 1782000 | 0 | 0 | -1755000 | 0 | 27000 | 0 | 1 | Finished | 27000 | 27000 | C2019-01 Lepelstraat.xlsx
7 | 3 | Wachten op plannen appartementen door architect | 2015-08-03 | 2015-08-14 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2015-08-03 08:00 | 65d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-01 Lepelstraat.xlsx
8 | 4 | aanvragen stedenbouwkundige vergunning | 2015-08-13 | 2015-08-13 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2015-08-13 08:00 | 57d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-01 Lepelstraat.xlsx
9 | 5 | Wachten op goedkeuring vergunning | 2015-08-14 | 2015-10-02 17:00 | 36d |  | 0 | 0 | 0 | 0 | 0 | 2015-08-14 08:00 | 56d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-01 Lepelstraat.xlsx
10 | 6 | aanstellen EPB verslaggever | 2015-10-20 | 2015-10-20 17:00 | 1d |  | 0 | 0 | 481.25 | 3850 | 3850 | 2015-10-20 08:00 | 9d | 34650 | 0 | 0 | -29650 | 0 | 5000 | 0 | 1 | Finished | 3850 | 3850 | C2019-01 Lepelstraat.xlsx
11 | 7 | aankoop grond | 2015-11-02 | 2015-11-02 17:00 | 1d |  | 0 | 0 | 38750 | 310000 | 310000 | 2015-11-02 08:00 | 51d | 15810000 | 0 | 0 | -15500000 | 0 | 310000 | 0 | 1 | Finished | 310000 | 310000 | C2019-01 Lepelstraat.xlsx
12 | 8 | betalen kosten notaris | 2015-11-16 | 2015-11-16 17:00 | 1d |  | 0 | 0 | 787.5 | 6300 | 6300 | 2015-11-16 08:00 | 41d | 258300 | 0 | 0 | -252800 | 0 | 5500 | 0 | 1 | Finished | 6300 | 6300 | C2019-01 Lepelstraat.xlsx
13 | 9 | afkoppelen nutsvoorzieningen (telefoon, elektriciteit, water, gas) | 2015-12-02 | 2015-12-03 17:00 | 2d |  | 0 | 0 | 273.125 | 4370 | 4370 | 2015-12-02 08:00 | 29d | 63365 | 0 | 0 | -58995 | 0 | 4370 | 0 | 1 | Finished | 4370 | 4370 | C2019-01 Lepelstraat.xlsx
14 | 10 | aanvragen verkeersverbod voor sloopwerken + akkoord | 2015-12-04 | 2015-12-04 17:00 | 1d |  | 0 | 0 | 125 | 1000 | 1000 | 2015-12-04 08:00 | 27d | 27000 | 0 | 0 | -26000 | 0 | 1000 | 0 | 1 | Finished | 1000 | 1000 | C2019-01 Lepelstraat.xlsx
15 | 11 | Inrichten werf | 2016-01-05 | 2016-01-06 17:00 | 2d |  | 0 | 0 | 218.75 | 3500 | 3500 | 2016-01-05 08:00 | 5d | 8750 | 0 | 0 | -5200 | 0 | 3550 | 0 | 1 | Finished | 3500 | 3500 | C2019-01 Lepelstraat.xlsx
16 | 12 | slopen gebouwen en bijgebouwen | 2016-01-07 | 2016-01-28 17:00 | 16d |  | 0 | 0 | 136.7188 | 17500 | 17500 | 2016-01-11 08:00 | 96d | 105000 | 0 | 0 | -87500 | 0 | 17500 | 0 | 1 | Finished | 17500 | 17500 | C2019-01 Lepelstraat.xlsx
17 | 13 | sondering bodem | 2016-01-28 | 2016-01-29 17:00 | 2d |  | 0 | 0 | 53.125 | 850 | 850 | 2016-01-28 08:00 | 83d | 35275 | 0 | 0 | -34425 | 0 | 850 | 0 | 1 | Finished | 850 | 850 | C2019-01 Lepelstraat.xlsx
18 | 14 | uitgraven funderingsgleuven voor appartement en garages + afvoer grond | 2016-02-01 | 2016-02-01 17:00 | 1d |  | 0 | 0 | 975 | 7800 | 7800 | 2016-02-01 08:00 | 81d | 631800 | 0 | 0 | -624000 | 0 | 7800 | 0 | 1 | Finished | 7800 | 7800 | C2019-01 Lepelstraat.xlsx
19 | 15 | plaatsen aardingslus | 2016-02-01 | 2016-02-01 17:00 | 1d |  | 0 | 0 | 68.75 | 550 | 550 | 2016-02-01 08:00 | 81d | 44550 | 0 | 0 | -44067.15 | 0 | 482.85 | 0 | 1 | Finished | 550 | 550 | C2019-01 Lepelstraat.xlsx
20 | 16 | storten betonnen funderingsgleuven | 2016-02-10 | 2016-02-10 17:00 | 1d |  | 0 | 0 | 281.25 | 2250 | 2250 | 2016-02-10 08:00 | 74d | 166500 | 0 | 0 | -164250 | 0 | 2250 | 0 | 1 | Finished | 2250 | 2250 | C2019-01 Lepelstraat.xlsx
21 | 17 | plaatsen pvc riolerings en afwateringsbuizen + buizen nutsvoorzieningen (app + garages)(rioleringswerken) | 2016-02-15 | 2016-02-16 17:00 | 2d |  | 0 | 0 | 268.75 | 4300 | 4300 | 2016-02-15 08:00 | 71d | 152650 | 0 | 0 | -148350 | 0 | 4300 | 0 | 1 | Finished | 4300 | 4300 | C2019-01 Lepelstraat.xlsx
22 | 18 | opmetselen vorstrand + aanvullen met gewassen zand | 2016-02-17 | 2016-02-23 17:00 | 5d |  | 0 | 0 | 102.5 | 4100 | 4100 | 2016-02-17 08:00 | 69d | 56580 | 0 | 0 | -52413.13 | 0 | 4166.87 | 0 | 1 | Finished | 4100 | 4100 | C2019-01 Lepelstraat.xlsx
23 | 19 | plaatsen van bewapeningsnetten | 2016-02-23 | 2016-02-24 17:00 | 2d |  | 0 | 0 | 403.125 | 6450 | 6450 | 2016-02-23 08:00 | 65d | 209625 | 0 | 0 | -203175 | 0 | 6450 | 0 | 1 | Finished | 6450 | 6450 | C2019-01 Lepelstraat.xlsx
24 | 20 | gieten van betonnen vloerplaat | 2016-02-25 | 2016-02-25 17:00 | 1d |  | 0 | 0 | 687.5 | 5500 | 5500 | 2016-02-25 08:00 | 63d | 346500 | 0 | 0 | -341000 | 0 | 5500 | 0 | 1 | Finished | 5500 | 5500 | C2019-01 Lepelstraat.xlsx
25 | 21 | opmetselen binnenmuren appartementen gelijkvloers en de garages | 2016-03-03 | 2016-03-18 17:00 | 12d |  | 0 | 0 | 87.5 | 8400 | 8400 | 2016-03-03 08:00 | 58d | 40600 | 0 | 0 | -32200 | 0 | 8400 | 0 | 1 | Finished | 8400 | 8400 | C2019-01 Lepelstraat.xlsx
26 | 22 | plaatsen gewelven gelijkvloers en garages | 2016-03-18 | 2016-03-21 17:00 | 2d |  | 0 | 0 | 456.25 | 7300 | 7300 | 2016-03-18 08:00 | 47d | 171550 | 0 | 0 | -164250 | 0 | 7300 | 0 | 1 | Finished | 7300 | 7300 | C2019-01 Lepelstraat.xlsx
27 | 23 | plaatsen bewapening vloerplaat eerste verdiep + gieten beton | 2016-03-22 | 2016-03-24 17:00 | 3d |  | 0 | 0 | 393.75 | 9450 | 9450 | 2016-03-22 08:00 | 45d | 141750 | 0 | 0 | -132300 | 0 | 9450 | 0 | 1 | Finished | 9450 | 9450 | C2019-01 Lepelstraat.xlsx
28 | 24 | metsen van binnenmuren eerste verdiep | 2016-04-01 | 2016-04-14 17:00 | 10d |  | 0 | 0 | 77.5 | 6200 | 6200 | 2016-04-01 08:00 | 99d | 61380 | 0 | 0 | -55180 | 0 | 6200 | 0 | 1 | Finished | 6200 | 6200 | C2019-01 Lepelstraat.xlsx
29 | 25 | plaatsen gewelven eerste verdiep | 2016-04-18 | 2016-04-21 17:00 | 4d |  | 0 | 0 | 228.125 | 7300 | 7300 | 2016-05-23 08:00 | 63d | 114975 | 0 | 0 | -107675 | 0 | 7300 | 0 | 1 | Finished | 7300 | 7300 | C2019-01 Lepelstraat.xlsx
30 | 26 | plaatsen van gevelelementen + dakbalkons met bovenbewapening | 2016-04-22 | 2016-05-12 17:00 | 15d |  | 0 | 0 | 600 | 72000 | 72000 | 2016-05-23 08:00 | 63d | 302400 | 0 | 0 | -230400 | 0 | 72000 | 0 | 1 | Finished | 72000 | 72000 | C2019-01 Lepelstraat.xlsx
31 | 27 | plaatsen bewapening en gieten betonnen gewelven tweede verdiep | 2016-05-18 | 2016-05-24 17:00 | 5d |  | 0 | 0 | 182.5 | 7300 | 7300 | 2016-05-23 08:00 | 63d | 91980 | 0 | 0 | -84680 | 0 | 7300 | 0 | 1 | Finished | 7300 | 7300 | C2019-01 Lepelstraat.xlsx
32 | 28 | inbinden balken | 2016-05-25 | 2016-05-25 17:00 | 1d |  | 0 | 0 | 718.75 | 5750 | 5750 | 2016-05-25 08:00 | 61d | 350750 | 0 | 0 | -345000 | 0 | 5750 | 0 | 1 | Finished | 5750 | 5750 | C2019-01 Lepelstraat.xlsx
33 | 29 | bekisting + bewapening betonnen trappen + storten beton voor trap | 2016-05-30 | 2016-05-31 17:00 | 2d |  | 0 | 0 | 281.25 | 4500 | 4500 | 2016-05-30 08:00 | 58d | 130500 | 0 | 0 | -126000 | 0 | 4500 | 0 | 1 | Finished | 4500 | 4500 | C2019-01 Lepelstraat.xlsx
34 | 30 | opmetsen borstwering tweede verdiep | 2016-06-06 | 2016-06-07 17:00 | 2d |  | 0 | 0 | 525 | 8400 | 8400 | 2016-06-06 08:00 | 53d | 222600 | 0 | 0 | -214200 | 0 | 8400 | 0 | 1 | Finished | 8400 | 8400 | C2019-01 Lepelstraat.xlsx
35 | 31 | gieten van bewapende ring balk | 2016-06-08 | 2016-06-09 17:00 | 2d |  | 0 | 0 | 237.5 | 3800 | 3800 | 2016-06-08 08:00 | 51d | 96900 | 0 | 0 | -93100 | 0 | 3800 | 0 | 1 | Finished | 3800 | 3800 | C2019-01 Lepelstraat.xlsx
36 | 32 | plaatsen van houten koppelkepers als modellen voor de binnenmuren en puntgevels (deel dakconstructie) | 2016-06-10 | 2016-06-13 17:00 | 2d |  | 0 | 0 | 140.625 | 2250 | 2250 | 2016-06-10 08:00 | 49d | 55125 | 0 | 0 | -52875 | 0 | 2250 | 0 | 1 | Finished | 2250 | 2250 | C2019-01 Lepelstraat.xlsx
37 | 33 | opmetsen resterende muren tweede verdiep en puntgevels | 2016-06-13 | 2016-06-24 17:00 | 10d |  | 0 | 0 | 109.375 | 8750 | 8750 | 2016-06-13 08:00 | 130d | 113750 | 0 | 0 | -105000 | 0 | 8750 | 0 | 1 | Finished | 8750 | 8750 | C2019-01 Lepelstraat.xlsx
38 | 34 | plaatsen metalen I-profielen (waar nodig) | 2016-06-27 | 2016-06-27 17:00 | 1d |  | 0 | 0 | 934.375 | 7475 | 7475 | 2016-08-17 08:00 | 83d | 620425 | 0 | 0 | -612950 | 0 | 7475 | 0 | 1 | Finished | 7475 | 7475 | C2019-01 Lepelstraat.xlsx
39 | 35 | plaatsen spouwisolatie 140mm aan buitenzijde gebouw tegen binnenmuren (voorzien van de nodige spouwankers) getaped | 2016-06-29 | 2016-07-08 17:00 | 8d |  | 0 | 0 | 75.9375 | 4860 | 4860 | 2016-08-17 08:00 | 83d | 50422.5 | 0 | 0 | -44422.5 | 0 | 6000 | 0 | 1 | Finished | 4860 | 4860 | C2019-01 Lepelstraat.xlsx
40 | 36 | dichtkleven van de isolatie | 2016-07-11 | 2016-07-11 17:00 | 1d |  | 0 | 0 | 35.625 | 285 | 285 | 2016-08-17 08:00 | 83d | 23655 | 0 | 0 | -23370 | 0 | 285 | 0 | 1 | Finished | 285 | 285 | C2019-01 Lepelstraat.xlsx
41 | 37 | plaatsen opgaand metselwerk aan buitenzijde gebouw | 2016-07-04 | 2016-07-18 17:00 | 11d |  | 0 | 0 | 625 | 55000 | 55000 | 2016-08-17 08:00 | 83d | 415000 | 0 | 0 | -354723 | 0 | 60277 | 0 | 1 | Finished | 55000 | 55000 | C2019-01 Lepelstraat.xlsx
42 | 38 | plaatsen opgaand metselwerk aan gebouw deel 2 en garages | 2016-08-08 | 2016-08-22 17:00 | 11d |  | 0 | 0 | 1136.3636 | 100000 | 100000 | 2016-08-17 08:00 | 83d | 754545.4545 | 0 | 0 | -659825.4545 | 0 | 94720 | 0 | 1 | Finished | 100000 | 100000 | C2019-01 Lepelstraat.xlsx
43 | 39 | aanbrengen van isolatieplaten op de platforms en platte daken van appartementen en de garages | 2016-08-30 | 2016-09-01 17:00 | 3d |  | 0 | 0 | 116.6667 | 2800 | 2800 | 2016-08-30 08:00 | 74d | 69066.6667 | 0 | 0 | -66266.6667 | 0 | 2800 | 0 | 1 | Finished | 2800 | 2800 | C2019-01 Lepelstraat.xlsx
44 | 40 | plaatsen van EPDM dakbedekking op de appartementen en de garages en platforms voorzien van de nodige dakranden | 2016-09-05 | 2016-09-09 17:00 | 5d |  | 0 | 0 | 77.475 | 3099 | 3099 | 2016-09-05 08:00 | 70d | 43386 | 0 | 0 | -40236 | 0 | 3150 | 0 | 1 | Finished | 3099 | 3099 | C2019-01 Lepelstraat.xlsx
45 | 41 | plaatsen dakconstructie | 2016-09-12 | 2016-09-23 17:00 | 10d |  | 0 | 0 | 267.5 | 21400 | 21400 | 2016-09-12 08:00 | 65d | 139100 | 0 | 0 | -116300 | 0 | 22800 | 0 | 1 | Finished | 21400 | 21400 | C2019-01 Lepelstraat.xlsx
46 | 42 | plaatsen van de reeds opgementen blauwe hardsteen (raamdorpels) | 2016-09-26 | 2016-09-26 17:00 | 1d |  | 0 | 0 | 500 | 4000 | 4000 | 2016-09-26 08:00 | 55d | 220000 | 0 | 0 | -215657.12 | 0 | 4342.88 | 0 | 1 | Finished | 4000 | 4000 | C2019-01 Lepelstraat.xlsx
47 | 43 | plaatsen dakgoten en aflopen | 2016-09-29 | 2016-09-30 17:00 | 2d |  | 0 | 0 | 136.25 | 2180 | 2180 | 2016-09-29 08:00 | 52d | 56680 | 0 | 0 | -54280 | 0 | 2400 | 0 | 1 | Finished | 2180 | 2180 | C2019-01 Lepelstraat.xlsx
48 | 44 | plaatsen onderdak + inwerken van dakvlakvensters | 2016-10-03 | 2016-10-04 17:00 | 2d |  | 0 | 0 | 350 | 5600 | 5600 | 2016-10-03 08:00 | 50d | 140000 | 0 | 0 | -132100 | 0 | 7900 | 0 | 1 | Finished | 5600 | 5600 | C2019-01 Lepelstraat.xlsx
49 | 45 | dichtleggen dakconstructie met nodige gevel- en nokpannen | 2016-10-05 | 2016-10-11 17:00 | 5d |  | 0 | 0 | 357.75 | 14310 | 14310 | 2016-10-05 08:00 | 139d | 397818 | 0 | 0 | -383508 | 0 | 14310 | 0 | 1 | Finished | 14310 | 14310 | C2019-01 Lepelstraat.xlsx
50 | 46 | dak doorvoeren (voor ventillatie, verluchting en liftkoker) | 2016-10-10 | 2016-10-11 17:00 | 2d |  | 0 | 0 | 59.375 | 950 | 950 | 2016-12-09 08:00 | 92d | 43700 | 0 | 0 | -42750 | 0 | 950 | 0 | 1 | Finished | 950 | 950 | C2019-01 Lepelstraat.xlsx
51 | 47 | CV doorvoer | 2016-10-10 | 2016-10-10 17:00 | 1d |  | 0 | 0 | 43.75 | 350 | 350 | 2016-12-09 08:00 | 92d | 32200 | 0 | 0 | -31850 | 0 | 350 | 0 | 1 | Finished | 350 | 350 | C2019-01 Lepelstraat.xlsx
52 | 48 | slijpen nutsvoorzieningen (water gas elektriciteit) in alle app | 2016-10-17 | 2016-10-19 17:00 | 3d |  | 0 | 0 | 75 | 1800 | 1800 | 2016-12-09 08:00 | 92d | 55200 | 0 | 0 | -53400 | 0 | 1800 | 0 | 1 | Finished | 1800 | 1800 | C2019-01 Lepelstraat.xlsx
53 | 49 | boren gaten in betonnen plafond voor plaatsen van spots (indien van toepassing) | 2016-10-18 | 2016-10-19 17:00 | 2d |  | 0 | 0 | 75 | 1200 | 1200 | 2016-09-12 08:00 | 156d | 93600 | 0 | 0 | -92400 | 0 | 1200 | 0 | 1 | Finished | 1200 | 1200 | C2019-01 Lepelstraat.xlsx
54 | 50 | leveren en plaatsen van buitenschrijnwerk (hout, alu of pvc) (ramen deuren) | 2016-11-04 | 2016-11-07 17:00 | 2d |  | 0 | 0 | 3200 | 51200 | 51200 | 2016-12-09 08:00 | 92d | 2355200 | 0 | 0 | -2304000 | 0 | 51200 | 0 | 1 | Finished | 51200 | 51200 | C2019-01 Lepelstraat.xlsx
55 | 51 | leggen sanitaire buizen, afwatering bad water en toilet | 2016-11-15 | 2016-11-30 17:00 | 12d |  | 0 | 0 | 190.1042 | 18250 | 18250 | 2016-12-09 08:00 | 92d | 139916.6667 | 0 | 0 | -121666.6667 | 0 | 18250 | 0 | 1 | Finished | 18250 | 18250 | C2019-01 Lepelstraat.xlsx
56 | 52 | leggen elektriciteit | 2016-11-21 | 2016-12-16 17:00 | 20d |  | 0 | 0 | 134.375 | 21500 | 21500 | 2016-12-09 08:00 | 92d | 98900 | 0 | 0 | -77400 | 0 | 21500 | 0 | 1 | Finished | 21500 | 21500 | C2019-01 Lepelstraat.xlsx
57 | 53 | leggen van ventillatiekanalen | 2016-11-22 | 2016-11-25 17:00 | 4d |  | 0 | 0 | 950 | 30400 | 30400 | 2016-12-09 08:00 | 92d | 699200 | 0 | 0 | -668794.74 | 0 | 30405.26 | 0 | 1 | Finished | 30400 | 30400 | C2019-01 Lepelstraat.xlsx
58 | 54 | plaasten van PUR (16cm) ondervloeren op het gelijkvloers en PUR(16cm) akoestiek op de verdiepen | 2017-01-16 | 2017-01-17 17:00 | 2d |  | 0 | 0 | 800 | 12800 | 12800 | 2017-01-16 08:00 | 66d | 422400 | 0 | 0 | -409600 | 0 | 12800 | 0 | 1 | Finished | 12800 | 12800 | C2019-01 Lepelstraat.xlsx
59 | 55 | plaatsen van leidingen voor vloerverwarming | 2017-01-23 | 2017-01-26 17:00 | 4d |  | 0 | 0 | 1198.4375 | 38350 | 38350 | 2017-01-23 08:00 | 61d | 584837.5 | 0 | 0 | -542737.5 | 0 | 42100 | 0 | 1 | Finished | 38350 | 38350 | C2019-01 Lepelstraat.xlsx
60 | 56 | aanbrengen chappe (80mm - bewapend en voorzien van bijpassend product voor vloerverwarming en randuitzettingsvoeg) | 2017-02-03 | 2017-02-07 17:00 | 3d |  | 0 | 0 | 447.9167 | 10750 | 10750 | 2017-02-03 08:00 | 52d | 186333.3333 | 0 | 0 | -177423.3333 | 0 | 8910 | 0 | 1 | Finished | 10750 | 10750 | C2019-01 Lepelstraat.xlsx
61 | 57 | plaatsen lift | 2017-02-10 | 2017-02-17 17:00 | 6d |  | 0 | 0 | 437.5 | 21000 | 21000 | 2017-02-10 08:00 | 107d | 374500 | 0 | 0 | -353500 | 0 | 21000 | 0 | 1 | Finished | 21000 | 21000 | C2019-01 Lepelstraat.xlsx
62 | 58 | distributienetwerk: ondergrondse aansluitingen (water gas elektriciteit) + plaatsen tellers | 2017-02-28 | 2017-02-28 17:00 | 1d |  | 0 | 0 | 922.5 | 7380 | 7380 | 2017-04-17 08:00 | 61d | 450180 | 0 | 0 | -441680 | 0 | 8500 | 0 | 1 | Finished | 7380 | 7380 | C2019-01 Lepelstraat.xlsx
63 | 59 | isoleren van het dakgebindte met 220 mm mineraalwol voorzien van dampscherm | 2017-03-01 | 2017-03-06 17:00 | 4d |  | 0 | 0 | 212.5 | 6800 | 6800 | 2017-04-17 08:00 | 61d | 103700 | 0 | 0 | -96200 | 0 | 7500 | 0 | 1 | Finished | 6800 | 6800 | C2019-01 Lepelstraat.xlsx
64 | 60 | aanbrengen van latwerk voor later aan te brengen G-plat | 2017-03-10 | 2017-03-13 17:00 | 2d |  | 0 | 0 | 123.4375 | 1975 | 1975 | 2017-04-17 08:00 | 61d | 60237.5 | 0 | 0 | -57987.5 | 0 | 2250 | 0 | 1 | Finished | 1975 | 1975 | C2019-01 Lepelstraat.xlsx
65 | 61 | plaatsen OSB platen op de zolder | 2017-03-13 | 2017-03-14 17:00 | 2d |  | 0 | 0 | 55 | 880 | 880 | 2017-04-17 08:00 | 61d | 26840 | 0 | 0 | -26090 | 0 | 750 | 0 | 1 | Finished | 880 | 880 | C2019-01 Lepelstraat.xlsx
66 | 62 | verder plaatsen van bedrading verlichting voor het dakgeheel | 2017-03-13 | 2017-03-16 17:00 | 4d |  | 0 | 0 | 35.9375 | 1150 | 1150 | 2017-04-17 08:00 | 61d | 17537.5 | 0 | 0 | -16637.5 | 0 | 900 | 0 | 1 | Finished | 1150 | 1150 | C2019-01 Lepelstraat.xlsx
67 | 63 | plaatsen G-plat op het bestaande latwerk | 2017-03-15 | 2017-03-16 17:00 | 2d |  | 0 | 0 | 35.9375 | 575 | 575 | 2017-04-17 08:00 | 61d | 17537.5 | 0 | 0 | -16962.5 | 0 | 575 | 0 | 1 | Finished | 575 | 575 | C2019-01 Lepelstraat.xlsx
68 | 64 | uitwerken velux | 2017-03-16 | 2017-03-17 17:00 | 2d |  | 0 | 0 | 62.5 | 1000 | 1000 | 2017-04-17 08:00 | 61d | 30500 | 0 | 0 | -29500 | 0 | 1000 | 0 | 1 | Finished | 1000 | 1000 | C2019-01 Lepelstraat.xlsx
69 | 65 | aftapen van de chappe in alle ruimtes | 2017-03-22 | 2017-03-22 17:00 | 1d |  | 0 | 0 | 31.25 | 250 | 250 | 2017-04-17 08:00 | 61d | 15250 | 0 | 0 | -15000 | 0 | 250 | 0 | 1 | Finished | 250 | 250 | C2019-01 Lepelstraat.xlsx
70 | 66 | pleisterwerken (binnenmuren) | 2017-03-27 | 2017-04-28 17:00 | 25d |  | 0 | 0 | 50 | 10000 | 10000 | 2017-04-17 08:00 | 61d | 24400 | 0 | 0 | -14087.5 | 0 | 10312.5 | 0 | 1 | Finished | 10000 | 10000 | C2019-01 Lepelstraat.xlsx
71 | 67 | pleisterwerken (plafonds and G-plat) | 2017-04-03 | 2017-05-05 17:00 | 25d |  | 0 | 0 | 175 | 35000 | 35000 | 2017-07-10 08:00 | 78d | 109200 | 0 | 0 | -70012.5 | 0 | 39187.5 | 0 | 1 | Finished | 35000 | 35000 | C2019-01 Lepelstraat.xlsx
72 | 68 | bevloeringswerken | 2017-04-18 | 2017-05-29 17:00 | 30d |  | 0 | 0 | 279.1667 | 67000 | 67000 | 2017-07-10 08:00 | 78d | 174200 | 0 | 0 | -101200 | 0 | 73000 | 0 | 1 | Finished | 67000 | 67000 | C2019-01 Lepelstraat.xlsx
73 | 69 | plaatsen douchebakken en/of ligbaden | 2017-05-05 | 2017-05-08 17:00 | 2d |  | 0 | 0 | 781.25 | 12500 | 12500 | 2017-07-10 08:00 | 78d | 487500 | 0 | 0 | -475000 | 0 | 12500 | 0 | 1 | Finished | 12500 | 12500 | C2019-01 Lepelstraat.xlsx
74 | 70 | plaatsen muurtegels in badkamers en toiletten | 2017-05-08 | 2017-05-12 17:00 | 5d |  | 0 | 0 | 93.75 | 3750 | 3750 | 2017-07-10 08:00 | 78d | 58500 | 0 | 0 | -54750 | 0 | 3750 | 0 | 1 | Finished | 3750 | 3750 | C2019-01 Lepelstraat.xlsx
75 | 71 | plaatsen sanitaire toestellen: CV ketel, toilet uitgietbakken | 2017-05-15 | 2017-06-02 17:00 | 15d |  | 0 | 0 | 38.25 | 4590 | 4590 | 2017-07-10 08:00 | 118d | 36108 | 0 | 0 | -30608 | 0 | 5500 | 0 | 1 | Finished | 4590 | 4590 | C2019-01 Lepelstraat.xlsx
76 | 72 | plaatsen schakelaars elektriciteit | 2017-05-22 | 2017-06-02 17:00 | 10d |  | 0 | 0 | 21.875 | 1750 | 1750 | 2017-07-10 08:00 | 118d | 20650 | 0 | 0 | -18900 | 0 | 1750 | 0 | 1 | Finished | 1750 | 1750 | C2019-01 Lepelstraat.xlsx
77 | 73 | plaatsen ventillatie-units | 2017-05-22 | 2017-05-24 17:00 | 3d |  | 0 | 0 | 1208.3333 | 29000 | 29000 | 2017-10-25 08:00 | 41d | 396333.3333 | 0 | 0 | -366333.3333 | 0 | 30000 | 0 | 1 | Finished | 29000 | 29000 | C2019-01 Lepelstraat.xlsx
78 | 74 | bekleden traptreden met keramische tegels | 2017-06-01 | 2017-06-02 17:00 | 2d |  | 0 | 0 | 343.75 | 5500 | 5500 | 2017-10-25 08:00 | 41d | 112750 | 0 | 0 | -107250 | 0 | 5500 | 0 | 1 | Finished | 5500 | 5500 | C2019-01 Lepelstraat.xlsx
79 | 75 | plaatsen keukens | 2017-06-20 | 2017-06-26 17:00 | 5d |  | 0 | 0 | 1050 | 42000 | 42000 | 2017-07-10 08:00 | 78d | 655200 | 0 | 0 | -613200 | 0 | 42000 | 0 | 1 | Finished | 42000 | 42000 | C2019-01 Lepelstraat.xlsx
80 | 76 | plaatsen badkamermeubels | 2017-06-26 | 2017-06-30 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 | 2017-07-10 08:00 | 78d | 292500 | 0 | 0 | -273750 | 0 | 18750 | 0 | 1 | Finished | 18750 | 18750 | C2019-01 Lepelstraat.xlsx
81 | 77 | plaatsen binnendeuren | 2017-06-21 | 2017-07-04 17:00 | 10d |  | 0 | 0 | 206.25 | 16500 | 16500 | 2017-10-25 08:00 | 41d | 67650 | 0 | 0 | -51150 | 0 | 16500 | 0 | 1 | Finished | 16500 | 16500 | C2019-01 Lepelstraat.xlsx
82 | 78 | aansluiten plinten tegen de binnendeuren en keuken | 2017-08-07 | 2017-08-08 17:00 | 2d |  | 0 | 0 | 21.875 | 350 | 350 | 2017-12-20 08:00 | 48d | 8400 | 0 | 0 | -8050 | 0 | 350 | 0 | 1 | Finished | 350 | 350 | C2019-01 Lepelstraat.xlsx
83 | 79 | plaatsen van balkonleuningen | 2017-08-07 | 2017-08-08 17:00 | 2d |  | 0 | 0 | 200 | 3200 | 3200 | 2017-12-20 08:00 | 48d | 76800 | 0 | 0 | -73800 | 0 | 3000 | 0 | 1 | Finished | 3200 | 3200 | C2019-01 Lepelstraat.xlsx
84 | 80 | plaatsen trapleuningen | 2017-08-09 | 2017-08-09 17:00 | 1d |  | 0 | 0 | 225 | 1800 | 1800 | 2017-12-20 08:00 | 48d | 86400 | 0 | 0 | -83900 | 0 | 2500 | 0 | 1 | Finished | 1800 | 1800 | C2019-01 Lepelstraat.xlsx
85 | 81 | schilderen gemeenschappelijke delen | 2017-08-10 | 2017-08-11 17:00 | 2d |  | 0 | 0 | 93.75 | 1500 | 1500 | 2017-12-20 08:00 | 48d | 36000 | 0 | 0 | -31000 | 0 | 5000 | 0 | 1 | Finished | 1500 | 1500 | C2019-01 Lepelstraat.xlsx
86 | 82 | voegwerken gevelsteen + elastische voeg tussen ramen en metselwerk | 2017-08-01 | 2017-08-14 17:00 | 10d |  | 0 | 0 | 100 | 8000 | 8000 | 2017-12-20 08:00 | 48d | 38400 | 0 | 0 | -30150 | 0 | 8250 | 0 | 1 | Finished | 8000 | 8000 | C2019-01 Lepelstraat.xlsx
87 | 83 | opkuis werf | 2017-08-10 | 2017-08-10 17:00 | 1d |  | 0 | 0 | 62.5 | 500 | 500 | 2017-12-20 08:00 | 48d | 24000 | 0 | 0 | -23500 | 0 | 500 | 0 | 1 | Finished | 500 | 500 | C2019-01 Lepelstraat.xlsx
88 | 84 | oplevering met architect | 2017-08-14 | 2017-08-14 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2018-02-25 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-01 Lepelstraat.xlsx
89 | 85 | afleveren ASS BUILD dossier van EPB verslaggever | 2017-08-14 | 2017-08-14 17:00 | 1d |  | 0 | 0 | 625 | 5000 | 5000 | 2018-02-25 08:00 | 1d | 5000 | 0 | 0 | -3300 | 0 | 1700 | 0 | 1 | Finished | 5000 | 5000 | C2019-01 Lepelstraat.xlsx
90 | 86 | heraanleg stoep (voetpad) +buitenaanleg | 2017-08-04 | 2017-08-04 17:00 | 1d |  | 0 | 0 | 2500 | 20000 | 20000 | 2017-12-20 08:00 | 48d | 960000 | 0 | 0 | -940000 | 0 | 20000 | 0 | 1 | Finished | 20000 | 20000 | C2019-01 Lepelstraat.xlsx
4 | 0 | PROJECT SOCIAL HOUSING | 2017-01-20 08:00 | 2018-05-28 17:00 | 352d |  |  | 0 |  |  | 734602.11 |  | 355d | [5 empty] | 748555.7982 |  | 1 |  | 734602.11 | 734602.11 | C2019-02 Social Housing.xlsx
5 | 1 | Ruwbouw | 2017-01-20 08:00 | 2017-09-15 17:00 | 171d |  | 0 | 0 | 186.107 | 254594.36 | 254594.36 | 2017-01-20 08:00 | 195d | 290326.9018 | 0 | 0 | -34826.5418 | 0 | 255500.36 | 0 | 1 | Finished | 254594.36 | 254594.36 | C2019-02 Social Housing.xlsx
6 | 2 | Buitenriolering | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 245.7083 | 29485 | 29485 | 2017-11-04 08:00 | 12d | 23588 | 0 | 0 | 11712.5 | 0 | 35300.5 | 0 | 1 | Finished | 29485 | 29485 | C2019-02 Social Housing.xlsx
7 | 3 | Daktimmer | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 276.7854 | 33214.25 | 33214.25 | 2017-09-11 08:00 | 29d | 64214.2167 | 0 | 0 | -30999.9667 | 0 | 33214.25 | 0 | 1 | Finished | 33214.25 | 33214.25 | C2019-02 Social Housing.xlsx
8 | 4 | Dakbedekking | 2017-10-02 08:00 | 2017-10-27 17:00 | 20d |  | 0 | 0 | 250.2914 | 40046.63 | 40046.63 | 2017-10-02 08:00 | 25d | 50058.2875 | 0 | 0 | -5002.9275 | 0 | 45055.36 | 0 | 1 | Finished | 40046.63 | 40046.63 | C2019-02 Social Housing.xlsx
9 | 5 | dakisolatie | 2017-11-20 08:00 | 2017-11-30 17:00 | 9d |  | 0 | 0 | 86.8056 | 6250 | 6250 | 2018-01-04 08:00 | 1d | 694.4444 | 0 | 0 | 5555.5556 | 0 | 6250 | 0 | 1 | Finished | 6250 | 6250 | C2019-02 Social Housing.xlsx
10 | 6 | Buitenschrijnwerk | 2017-11-20 08:00 | 2017-11-24 17:00 | 5d |  | 0 | 0 | 1277.386 | 51095.44 | 51095.44 | 2017-11-20 08:00 | 34d | 347448.992 | 0 | 0 | -292353.492 | 0 | 55095.5 | 0 | 1 | Finished | 51095.44 | 51095.44 | C2019-02 Social Housing.xlsx
11 | 7 | Aansluiting watermaatschappij | 2017-11-20 08:00 | 2017-11-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2017-11-21 08:00 | 33d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-02 Social Housing.xlsx
12 | 8 | Pleisterwerken | 2017-11-27 08:00 | 2018-01-26 17:00 | 45d |  | 0 | 0 | 74.697 | 26890.93 | 26890.93 | 2017-11-21 08:00 | 99d | 59160.046 | 0 | 0 | -34958.209 | 0 | 24201.837 | 0 | 1 | Finished | 26890.93 | 26890.93 | C2019-02 Social Housing.xlsx
13 | 9 | Chape fase1 (2woningen) | 2018-01-08 08:00 | 2018-01-12 17:00 | 5d |  | 0 | 0 | 193.4148 | 7736.592 | 7736.592 | 2018-01-08 08:00 | 9d | 13925.8656 | 0 | 0 | -6189.2736 | 0 | 7736.592 | 0 | 1 | Finished | 7736.592 | 7736.592 | C2019-02 Social Housing.xlsx
14 | 10 | Chape fase2 (3woningen) | 2018-02-05 08:00 | 2018-02-09 17:00 | 5d |  | 0 | 0 | 290.1222 | 11604.888 | 11604.888 | 2018-01-04 08:00 | 11d | 25530.7536 | 0 | 0 | -15086.3544 | 0 | 10444.3992 | 0 | 1 | Finished | 11604.888 | 11604.888 | C2019-02 Social Housing.xlsx
15 | 11 | Technieken voor chape fase1 | 2017-12-18 08:00 | 2017-12-22 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 | 2017-12-18 08:00 | 14d | 84000 | 0 | 0 | -54000 | 0 | 30000 | 0 | 1 | Finished | 30000 | 30000 | C2019-02 Social Housing.xlsx
16 | 12 | Technieken voor chape fase2 | 2018-01-09 08:00 | 2018-01-15 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 | 2018-01-09 08:00 | 8d | 48000 | 0 | 0 | -18000 | 0 | 30000 | 0 | 1 | Finished | 30000 | 30000 | C2019-02 Social Housing.xlsx
17 | 13 | afwerking technieken sanitair / elektriciteit | 2018-03-19 08:00 | 2018-04-30 17:00 | 31d |  | 0 | 0 | 173.0928 | 42927.02 | 42927.02 | 2018-04-06 08:00 | 19d | 26310.109 | 0 | 0 | 18689.891 | 0 | 45000 | 0 | 1 | Finished | 42927.02 | 42927.02 | C2019-02 Social Housing.xlsx
18 | 14 | vloer en tegelwerken | 2018-02-05 08:00 | 2018-03-30 17:00 | 40d |  | 0 | 0 | 109.1903 | 34940.91 | 34940.91 | 2018-02-05 08:00 | 63d | 55031.9333 | 0 | 0 | -20091.0232 | 0 | 34940.91 | 0 | 1 | Finished | 34940.91 | 34940.91 | C2019-02 Social Housing.xlsx
19 | 15 | binnenschrijnwerk (deuren, trappen, keukens) | 2018-04-02 08:00 | 2018-04-30 17:00 | 21d |  | 0 | 0 | 467.3524 | 78515.2 | 78515.2 | 2018-01-18 08:00 | 57d | 213112.6857 | 0 | 0 | -134597.4857 | 0 | 78515.2 | 0 | 1 | Finished | 78515.2 | 78515.2 | C2019-02 Social Housing.xlsx
20 | 16 | buitenaanleg | 2018-03-12 08:00 | 2018-04-13 17:00 | 25d |  | 0 | 0 | 110.9183 | 22183.65 | 22183.65 | 2018-03-12 08:00 | 20d | 17746.92 | 0 | 0 | 4436.73 | 0 | 22183.65 | 0 | 1 | Finished | 22183.65 | 22183.65 | C2019-02 Social Housing.xlsx
21 | 17 | afwerken diversen (fietsenstalling, afwerking buitenschrijnwerk, brievenbussen, …) | 2018-03-23 08:00 | 2018-04-18 17:00 | 19d |  | 0 | 0 | 231.0345 | 35117.24 | 35117.24 | 2018-03-23 08:00 | 11d | 20331.0337 | 0 | 0 | 14786.2063 | 0 | 35117.24 | 0 | 1 | Finished | 35117.24 | 35117.24 | C2019-02 Social Housing.xlsx
22 | 18 | oplevering | 2018-05-28 08:00 | 2018-05-28 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2018-05-31 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-02 Social Housing.xlsx
4 | 0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 520d | [5 empty] | 4232553.41 |  | 1 |  | 4318950 | 4318950 | C2019-04 Nuclear Healthcare.xlsx
5 | 1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 1 | Finished | 22050 | 22050 | C2019-04 Nuclear Healthcare.xlsx
6 | 2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 1 | Finished | 300000 | 300000 | C2019-04 Nuclear Healthcare.xlsx
7 | 3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-04 Nuclear Healthcare.xlsx
8 | 4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 1 | Finished | 6400 | 6400 | C2019-04 Nuclear Healthcare.xlsx
9 | 5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-04 Nuclear Healthcare.xlsx
10 | 6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 1 | Finished | 12000 | 12000 | C2019-04 Nuclear Healthcare.xlsx
11 | 7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 1 | Finished | 30700 | 30700 | C2019-04 Nuclear Healthcare.xlsx
12 | 8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-04 Nuclear Healthcare.xlsx
13 | 9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2019-04 Nuclear Healthcare.xlsx
14 | 10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-04 Nuclear Healthcare.xlsx
15 | 11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-04 Nuclear Healthcare.xlsx
16 | 12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 1 | Finished | 3200 | 3200 | C2019-04 Nuclear Healthcare.xlsx
17 | 13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 1 | Finished | 1600 | 1600 | C2019-04 Nuclear Healthcare.xlsx
18 | 14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-04 Nuclear Healthcare.xlsx
19 | 15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-04 Nuclear Healthcare.xlsx
20 | 16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-04 Nuclear Healthcare.xlsx
21 | 17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-04 Nuclear Healthcare.xlsx
22 | 18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 2016-11-07 08:00 | 21d | 693000 | 0 | 0 | -502239.9 | 0 | 190760.1 | 0 | 1 | Finished | 165000 | 165000 | C2019-04 Nuclear Healthcare.xlsx
23 | 38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 40d | [5 empty] | 430397.54 |  | 1 |  | 410000 | 410000 | C2019-04 Nuclear Healthcare.xlsx
24 | 19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 2016-11-07 08:00 | 40d | 1093333.3333 | 0 | 0 | -662935.7933 | 0 | 430397.54 | 0 | 1 | Finished | 410000 | 410000 | C2019-04 Nuclear Healthcare.xlsx
25 | 39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 1 |  | 195000 | 195000 | C2019-04 Nuclear Healthcare.xlsx
26 | 20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 1 | Finished | 193000 | 193000 | C2019-04 Nuclear Healthcare.xlsx
27 | 21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 1 | Finished | 2000 | 2000 | C2019-04 Nuclear Healthcare.xlsx
28 | 22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-04 Nuclear Healthcare.xlsx
29 | 40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 278d | [5 empty] | 1037447.3333 |  | 1 |  | 1056833.3333 | 1056833.3333 | C2019-04 Nuclear Healthcare.xlsx
30 | 23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 | 2016-12-05 08:00 | 215d | 7232553.7634 | 0 | 0 | -6207786.4301 | 0 | 1024767.3333 | 0 | 1 | Finished | 1042833.3333 | 1042833.3333 | C2019-04 Nuclear Healthcare.xlsx
31 | 24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 | 2017-08-01 08:00 | 44d | 52800 | 0 | 0 | -40120 | 0 | 12680 | 0 | 1 | Finished | 12000 | 12000 | C2019-04 Nuclear Healthcare.xlsx
32 | 25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 1 | Finished | 2000 | 2000 | C2019-04 Nuclear Healthcare.xlsx
33 | 26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-04 Nuclear Healthcare.xlsx
34 | 41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 67d | [5 empty] | 2074894.6667 |  | 1 |  | 2113666.6667 | 2113666.6667 | C2019-04 Nuclear Healthcare.xlsx
35 | 27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 | 2017-10-01 08:00 | 45d | 38571.4286 | 0 | 0 | -27584.4286 | 0 | 10987 | 0 | 1 | Finished | 12000 | 12000 | C2019-04 Nuclear Healthcare.xlsx
36 | 28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2017-11-01 08:00 | 45d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-04 Nuclear Healthcare.xlsx
37 | 29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 | 2017-10-01 08:00 | 23d | 198636.3636 | 0 | 0 | -108636.3636 | 0 | 90000 | 0 | 1 | Finished | 95000 | 95000 | C2019-04 Nuclear Healthcare.xlsx
38 | 30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 | 2017-10-01 08:00 | 66d | 1719184.2105 | 0 | 0 | 236223.4561 | 0 | 1955407.6667 | 0 | 1 | Finished | 1979666.6667 | 1979666.6667 | C2019-04 Nuclear Healthcare.xlsx
39 | 31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 | 2017-12-01 08:00 | 22d | 61111.1111 | 0 | 0 | -42611.1111 | 0 | 18500 | 0 | 1 | Finished | 25000 | 25000 | C2019-04 Nuclear Healthcare.xlsx
40 | 32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 | 2017-12-01 08:00 | 22d | 4000 | 0 | 0 | -4000 | 0 | 0 | 0 | 1 | Finished | 2000 | 2000 | C2019-04 Nuclear Healthcare.xlsx
41 | 33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2018-01-01 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-04 Nuclear Healthcare.xlsx
4 | 0 | PROJECT FUEL TANK FILTER | 2016-05-09 08:00 | 2018-04-20 17:00 | 510d |  |  | 0 |  |  | 1456000 |  | 515d | [5 empty] | 1476290 |  | 1 |  | 1456000 | 1456000 | C2019-05 Fuel Tank Filter.xlsx
5 | 1 | Research &amp; pre-design study P87 | 2016-05-09 08:00 | 2017-03-16 17:00 | 224d |  | 0 | 0 | 122.7679 | 220000 | 220000 | 2016-05-09 08:00 | 302d | 296607.1429 | 0 | 0 | -70877.1429 | 0 | 225730 | 0 | 1 | Finished | 220000 | 220000 | C2019-05 Fuel Tank Filter.xlsx
6 | 2 | Research &amp; pre-design study P84 /P1UO | 2016-05-30 08:00 | 2017-03-16 17:00 | 209d |  | 0 | 0 | 151.3158 | 253000 | 253000 | 2016-05-30 08:00 | 287d | 347421.0526 | 0 | 0 | -85921.0526 | 0 | 261500 | 0 | 1 | Finished | 253000 | 253000 | C2019-05 Fuel Tank Filter.xlsx
7 | 3 | Echange documentaire PSA (Responsibility matrix, CD price, Fete 43, 45 and 46) | 2016-11-14 08:00 | 2016-12-23 17:00 | 30d |  | 0 | 0 | 291.6667 | 70000 | 70000 | 2016-11-14 08:00 | 332d | 774666.6667 | 0 | 0 | -708526.6667 | 0 | 66140 | 0 | 1 | Finished | 70000 | 70000 | C2019-05 Fuel Tank Filter.xlsx
8 | 18 | P84/P1UO | 2016-10-13 08:00 | 2017-11-24 17:00 | 292d |  |  | 0 |  |  | 245000 |  | 291d | [5 empty] | 279200 |  | 1 |  | 245000 | 245000 | C2019-05 Fuel Tank Filter.xlsx
9 | 4 | Instal blow mold tool diesel | 2016-10-13 08:00 | 2017-10-20 17:00 | 267d |  | 0 | 0 | 67.8839 | 145000 | 145000 | 2017-01-10 08:00 | 291d | 158033.7079 | 0 | 0 | 10188.2254 | 0 | 168221.9332 | 0 | 1 | Finished | 145000 | 145000 | C2019-05 Fuel Tank Filter.xlsx
10 | 5 | Instal welding line P84 | 2016-12-22 08:00 | 2017-10-27 17:00 | 222d |  | 0 | 0 | 2.8153 | 5000 | 5000 | 2017-01-10 08:00 | 221d | 4977.4775 | 0 | 0 | -499.6275 | 0 | 4477.85 | 0 | 1 | Finished | 5000 | 5000 | C2019-05 Fuel Tank Filter.xlsx
11 | 6 | Assembly line Sochaux | 2016-12-22 08:00 | 2017-11-24 17:00 | 242d |  | 0 | 0 | 49.0702 | 95000 | 95000 | 2017-01-10 08:00 | 291d | 114235.5372 | 0 | 0 | -7735.3205 | 0 | 106500.2167 | 0 | 1 | Finished | 95000 | 95000 | C2019-05 Fuel Tank Filter.xlsx
12 | 19 | P87 | 2016-10-13 08:00 | 2017-12-01 17:00 | 297d |  |  | 0 |  |  | 234000 |  | 354d | [5 empty] | 225000 |  | 1 |  | 234000 | 234000 | C2019-05 Fuel Tank Filter.xlsx
13 | 7 | Blow mold tool diesel | 2016-10-13 08:00 | 2017-09-27 17:00 | 250d |  | 0 | 0 | 75 | 150000 | 150000 | 2016-10-13 08:00 | 284d | 170400 | 0 | 0 | -31372.2853 | 0 | 139027.7147 | 0 | 1 | Finished | 150000 | 150000 | C2019-05 Fuel Tank Filter.xlsx
14 | 8 | Instal welding line P87 | 2016-12-22 08:00 | 2017-09-29 17:00 | 202d |  | 0 | 0 | 6.1881 | 10000 | 10000 | 2016-12-22 08:00 | 234d | 11584.1584 | 0 | 0 | -4223.8676 | 0 | 7360.2908 | 0 | 1 | Finished | 10000 | 10000 | C2019-05 Fuel Tank Filter.xlsx
15 | 9 | Assembly line Rennes | 2016-12-22 08:00 | 2017-12-01 17:00 | 247d |  | 0 | 0 | 37.4494 | 74000 | 74000 | 2017-07-04 08:00 | 166d | 49732.7935 | 0 | 0 | 28879.201 | 0 | 78611.9945 | 0 | 1 | Finished | 74000 | 74000 | C2019-05 Fuel Tank Filter.xlsx
16 | 10 | Visual Design &amp; Engineer P84/P1UO | 2017-03-17 08:00 | 2018-03-28 17:00 | 269d |  | 0 | 0 | 7.8996 | 17000 | 17000 | 2017-03-17 08:00 | 275d | 17379.1822 | 0 | 0 | 4020.8178 | 0 | 21400 | 0 | 1 | Finished | 17000 | 17000 | C2019-05 Fuel Tank Filter.xlsx
17 | 11 | Visual Design &amp; Engineer P87 | 2017-03-20 08:00 | 2018-03-14 17:00 | 258d |  | 0 | 0 | 9.2054 | 19000 | 19000 | 2017-03-20 08:00 | 274d | 20178.2946 | 0 | 0 | -3858.2946 | 0 | 16320 | 0 | 1 | Finished | 19000 | 19000 | C2019-05 Fuel Tank Filter.xlsx
18 | 12 | Blow mold &amp; Welding line equipment for P84/P1UO | 2018-03-29 08:00 | 2018-04-19 17:00 | 16d |  | 0 | 0 | 1554.6875 | 199000 | 199000 | 2018-03-29 08:00 | 6d | 74625 | 0 | 0 | 116375 | 0 | 191000 | 0 | 1 | Finished | 199000 | 199000 | C2019-05 Fuel Tank Filter.xlsx
19 | 13 | PRSEL validation P84/P1UO | 2018-04-19 08:00 | 2018-04-19 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2018-04-28 | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-05 Fuel Tank Filter.xlsx
20 | 14 | Blow mold &amp; Welding line equipment for P87 | 2018-03-15 08:00 | 2018-04-20 17:00 | 27d |  | 0 | 0 | 921.2963 | 199000 | 199000 | 2018-03-15 08:00 | 16d | 117925.9259 | 0 | 0 | 72074.0741 | 0 | 190000 | 0 | 1 | Finished | 199000 | 199000 | C2019-05 Fuel Tank Filter.xlsx
21 | 15 | PRSEL validation P87 | 2018-04-20 08:00 | 2018-04-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2018-04-28 | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | C2019-05 Fuel Tank Filter.xlsx
4 | 0 | PROJECT Production Line Change | 2016-10-31 08:00 | 2018-08-31 17:00 | 480d |  |  | 0 |  |  | 1512000 |  | 501d | [5 empty] | 1534060 |  | 1 |  | 1512000 | 1512000 | C2019-06 Production Line Change.xlsx
5 | 1 | Design | 2016-10-31 08:00 | 2017-12-11 17:00 | 291d |  | 0 | 0 | 67.4399 | 157000 | 157000 | 2016-10-31 | 272d | 146749.1409 | 0 | 0 | 25350.8591 | 0 | 172100 | 0 | 1 | Finished | 157000 | 157000 | C2019-06 Production Line Change.xlsx
6 | 26 | Refueling Test P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  |  | 0 |  |  | 71000 |  | 38d | [5 empty] | 69070 |  | 1 |  | 71000 | 71000 | C2019-06 Production Line Change.xlsx
7 | 2 | Definition of 2D and 3D for prototypes for P8X | 2017-02-27 08:00 | 2017-02-27 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-02-27 | 38d | 570000 | 0 | 0 | -553600 | 0 | 16400 | 0 | 1 | Finished | 15000 | 15000 | C2019-06 Production Line Change.xlsx
8 | 3 | Prototype components assembly &amp; refueling test for P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  | 0 | 0 | 333.3333 | 56000 | 56000 | 2017-02-27 | 38d | 101333.3333 | 0 | 0 | -48663.3333 | 0 | 52670 | 0 | 1 | Finished | 56000 | 56000 | C2019-06 Production Line Change.xlsx
9 | 27 | Refueling Test P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  |  | 0 |  |  | 60000 |  | 56d | [5 empty] | 55350 |  | 1 |  | 60000 | 60000 | C2019-06 Production Line Change.xlsx
10 | 4 | Definition of 2D and 3D for prototypes for P1UO | 2017-07-06 08:00 | 2017-07-06 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-07-06 | 22d | 330000 | 0 | 0 | -315650 | 0 | 14350 | 0 | 1 | Finished | 15000 | 15000 | C2019-06 Production Line Change.xlsx
11 | 5 | Prototype components assembly &amp; refueling test for P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  | 0 | 0 | 267.8571 | 45000 | 45000 | 2017-07-06 | 56d | 120000 | 0 | 0 | -79000 | 0 | 41000 | 0 | 1 | Finished | 45000 | 45000 | C2019-06 Production Line Change.xlsx
12 | 6 | Produce Filler Pipe Blow molds P8x | 2017-03-27 08:00 | 2017-10-23 17:00 | 151d |  | 0 | 0 | 48.0132 | 58000 | 58000 | 2017-03-27 | 129d | 49549.6689 | 0 | 0 | 2450.3311 | 0 | 52000 | 0 | 1 | Finished | 58000 | 58000 | C2019-06 Production Line Change.xlsx
13 | 7 | Produce Filler Pipe Calibrations P8x | 2017-03-27 08:00 | 2017-10-30 17:00 | 156d |  | 0 | 0 | 17.6282 | 22000 | 22000 | 2017-03-27 | 129d | 18192.3077 | 0 | 0 | 5307.6923 | 0 | 23500 | 0 | 1 | Finished | 22000 | 22000 | C2019-06 Production Line Change.xlsx
14 | 8 | Produce Filler Pipe Blow mold P1UO | 2017-08-03 08:00 | 2018-01-12 17:00 | 117d |  | 0 | 0 | 58.7607 | 55000 | 55000 | 2017-08-04 | 143d | 67222.2222 | 0 | 0 | -16722.2222 | 0 | 50500 | 0 | 1 | Finished | 55000 | 55000 | C2019-06 Production Line Change.xlsx
15 | 9 | Produce Filler Pipe Calibration P1UO | 2017-08-03 08:00 | 2018-01-19 17:00 | 122d |  | 0 | 0 | 20.4918 | 20000 | 20000 | 2017-08-04 | 191d | 31311.4754 | 0 | 0 | -10311.4754 | 0 | 21000 | 0 | 1 | Finished | 20000 | 20000 | C2019-06 Production Line Change.xlsx
16 | 10 | Filler pipe Welding/assembly machine Liberec | 2017-07-28 08:00 | 2018-08-20 17:00 | 277d |  | 0 | 0 | 101.5343 | 225000 | 225000 | 2017-08-04 | 208d | 168953.0686 | 0 | 0 | 71046.9314 | 0 | 240000 | 0 | 1 | Finished | 225000 | 225000 | C2019-06 Production Line Change.xlsx
17 | 11 | Modification Welding lines Lokeren ‚6D | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 10 | 8000 | 8000 | 2017-10-23 | 87d | 6960 | 0 | 0 | 2240 | 0 | 9200 | 0 | 1 | Finished | 8000 | 8000 | C2019-06 Production Line Change.xlsx
18 | 12 | Modification ROV web assembly station Lokeren ‚6D (FETE 51) | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 43.75 | 35000 | 35000 | 2017-10-23 | 87d | 30450 | 0 | 0 | -650 | 0 | 29800 | 0 | 1 | Finished | 35000 | 35000 | C2019-06 Production Line Change.xlsx
19 | 13 | Mariage welder Rennes | 2017-08-21 08:00 | 2018-03-23 17:00 | 155d |  | 0 | 0 | 278.2258 | 345000 | 345000 | 2017-08-21 | 132d | 293806.4516 | 0 | 0 | 38193.5484 | 0 | 332000 | 0 | 1 | Finished | 345000 | 345000 | C2019-06 Production Line Change.xlsx
20 | 14 | Modification assembly line Rennes | 2017-08-21 08:00 | 2018-03-20 17:00 | 152d |  | 0 | 0 | 37.0066 | 45000 | 45000 | 2017-08-21 | 132d | 39078.9474 | 0 | 0 | 16621.0526 | 0 | 55700 | 0 | 1 | Finished | 45000 | 45000 | C2019-06 Production Line Change.xlsx
21 | 15 | Modification Leak Tester Rennes | 2017-09-25 08:00 | 2018-03-20 17:00 | 127d |  | 0 | 0 | 8.8583 | 9000 | 9000 | 2017-08-04 | 143d | 10133.8583 | 0 | 0 | -1133.8583 | 0 | 9000 | 0 | 1 | Finished | 9000 | 9000 | C2019-06 Production Line Change.xlsx
22 | 16 | Mariage welder Sochaux ‚6D | 2017-09-25 08:00 | 2018-07-16 17:00 | 211d |  | 0 | 0 | 52.7251 | 89000 | 89000 | 2017-09-25 | 266d | 112199.0521 | 0 | 0 | -8199.0521 | 0 | 104000 | 0 | 1 | Finished | 89000 | 89000 | C2019-06 Production Line Change.xlsx
23 | 17 | Modification assembly line Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 59.5238 | 50000 | 50000 | 2017-09-25 | 155d | 73809.5238 | 0 | 0 | -31359.5238 | 0 | 42450 | 0 | 1 | Finished | 50000 | 50000 | C2019-06 Production Line Change.xlsx
24 | 18 | Modification Leak Tester Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 35.7143 | 30000 | 30000 | 2017-09-25 | 155d | 44285.7143 | 0 | 0 | -28285.7143 | 0 | 16000 | 0 | 1 | Finished | 30000 | 30000 | C2019-06 Production Line Change.xlsx
25 | 19 | Modification Sequencer and conveyors Sochaux ‚6D | 2017-11-20 08:00 | 2018-05-18 17:00 | 130d |  | 0 | 0 | 38.4615 | 40000 | 40000 | 2017-09-21 | 247d | 76000 | 0 | 0 | -24000 | 0 | 52000 | 0 | 1 | Finished | 40000 | 40000 | C2019-06 Production Line Change.xlsx
26 | 20 | Production for VRS P8x | 2017-11-06 08:00 | 2017-12-01 17:00 | 20d |  | 0 | 0 | 156.25 | 25000 | 25000 | 2017-11-06 | 125d | 156250 | 0 | 0 | -128250 | 0 | 28000 | 0 | 1 | Finished | 25000 | 25000 | C2019-06 Production Line Change.xlsx
27 | 21 | Production for VRS P1UO | 2018-01-19 08:00 | 2018-04-17 17:00 | 63d |  | 0 | 0 | 49.6032 | 25000 | 25000 | 2018-02-20 | 49d | 19444.4444 | 0 | 0 | 13355.5556 | 0 | 32800 | 0 | 1 | Finished | 25000 | 25000 | C2019-06 Production Line Change.xlsx
28 | 22 | Production for homologation P8x | 2017-12-01 08:00 | 2017-12-29 17:00 | 21d |  | 0 | 0 | 107.1429 | 18000 | 18000 | 2017-11-14 | 71d | 60857.1429 | 0 | 0 | -45157.1429 | 0 | 15700 | 0 | 1 | Finished | 18000 | 18000 | C2019-06 Production Line Change.xlsx
29 | 23 | Finalization of all test runs, design systems and go life | 2018-08-20 08:00 | 2018-08-31 17:00 | 10d |  | 0 | 0 | 1562.5 | 125000 | 125000 | 2018-09-01 | 21d | 262500 | 0 | 0 | -138610 | 0 | 123890 | 0 | 1 | Finished | 125000 | 125000 | C2019-06 Production Line Change.xlsx
4 | 0 | PROJECT GLUING MACHINE | 2017-09-11 08:00 | 2018-04-06 17:00 | 150d |  |  | 0 |  |  | 107500 |  | 189d | [5 empty] | 116800 |  | 1 |  | 107500 | 107500 | C2019-07 Gluing Machine.xlsx
5 | 1 | test PU lijm | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-11 08:00 | 100d | 10000 | 0 | 0 | -6500 | 0 | 3500 | 0 | 1 | Finished | 1000 | 1000 | C2019-07 Gluing Machine.xlsx
6 | 2 | aankoop rollenwals + vatsmelter | 2017-09-25 08:00 | 2018-01-19 17:00 | 85d |  | 0 | 0 | 135.2941 | 92000 | 92000 | 2017-10-06 08:00 | 95d | 102823.5294 | 0 | 0 | -7823.5294 | 0 | 95000 | 0 | 1 | Finished | 92000 | 92000 | C2019-07 Gluing Machine.xlsx
7 | 3 | voorbereidende werken afzuiging | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2018-02-15 08:00 | 47d | 11750 | 0 | 0 | -9250 | 0 | 2500 | 0 | 1 | Finished | 2500 | 2500 | C2019-07 Gluing Machine.xlsx
8 | 4 | voorbereidende werken (elektrisch) | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2018-02-15 08:00 | 47d | 14100 | 0 | 0 | -10600 | 0 | 3500 | 0 | 1 | Finished | 3000 | 3000 | C2019-07 Gluing Machine.xlsx
9 | 5 | testfase productie, opleiding, eerste keer in MTO | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 25 | 3000 | 3000 | 2018-03-21 08:00 | 40d | 8000 | 0 | 0 | -4800 | 0 | 3200 | 0 | 1 | Finished | 3000 | 3000 | C2019-07 Gluing Machine.xlsx
10 | 6 | haalbaarheidsstudie | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 16.6667 | 2000 | 2000 | 2018-03-21 08:00 | 40d | 5333.3333 | 0 | 0 | -2833.3333 | 0 | 2500 | 0 | 1 | Finished | 2000 | 2000 | C2019-07 Gluing Machine.xlsx
11 | 7 | bijkomend onderzoek naar belijmde mdf panelen met release coat | 2018-03-09 08:00 | 2018-03-30 17:00 | 16d |  | 0 | 0 | 7.8125 | 1000 | 1000 | 2017-09-22 08:00 | 180d | 11250 | 0 | 0 | -9550 | 0 | 1700 | 0 | 1 | Finished | 1000 | 1000 | C2019-07 Gluing Machine.xlsx
12 | 8 | volledige implementatie en opstart in productie | 2018-03-21 08:00 | 2018-04-06 17:00 | 13d |  | 0 | 0 | 28.8462 | 3000 | 3000 | 2018-05-15 08:00 | 13d | 3000 | 0 | 0 | 1900 | 0 | 4900 | 0 | 1 | Finished | 3000 | 3000 | C2019-07 Gluing Machine.xlsx
4 | 0 | PROJECT Labeling MACHINE | 2017-09-04 08:00 | 2018-02-09 17:00 | 115d |  |  | 0 |  |  | 114700 |  | 182d | [5 empty] | 128200 |  | 1 |  | 114700 | 114700 | C2019-08 Labeling Machine.xlsx
5 | 1 | Vereenvoudigen huidige werkpost | 2017-09-04 08:00 | 2017-09-15 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-04 08:00 | 105d | 10500 | 0 | 0 | -9000 | 0 | 1500 | 0 | 1 | Finished | 1000 | 1000 | C2019-08 Labeling Machine.xlsx
6 | 2 | vastleggen instructies en procedures | 2017-09-21 08:00 | 2017-10-09 17:00 | 13d |  | 0 | 0 | 6.7308 | 700 | 700 | 2017-12-18 08:00 | 30d | 1615.3846 | 0 | 0 | -615.3846 | 0 | 1000 | 0 | 1 | Finished | 700 | 700 | C2019-08 Labeling Machine.xlsx
7 | 3 | ontwerp semi automatische applicatie unit | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2017-09-11 08:00 | 71d | 71000 | 0 | 0 | -61000 | 0 | 10000 | 0 | 1 | Finished | 10000 | 10000 | C2019-08 Labeling Machine.xlsx
8 | 4 | bestellen print &amp; apply | 2017-09-25 08:00 | 2017-12-11 17:00 | 56d |  | 0 | 0 | 200.8929 | 90000 | 90000 | 2017-09-25 08:00 | 90d | 144642.8571 | 0 | 0 | -44642.8571 | 0 | 100000 | 0 | 1 | Finished | 90000 | 90000 | C2019-08 Labeling Machine.xlsx
9 | 5 | voorbereiden werken (hardwarde, dataconnectie) | 2017-12-18 08:00 | 2018-01-05 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000 | 5000 | 2017-11-15 08:00 | 113d | 37666.6667 | 0 | 0 | -32066.6667 | 0 | 5600 | 0 | 1 | Finished | 5000 | 5000 | C2019-08 Labeling Machine.xlsx
10 | 6 | integratie met shopfloor software (printbaar maken) | 2018-01-08 08:00 | 2018-01-18 17:00 | 9d |  | 0 | 0 | 69.4444 | 5000 | 5000 | 2018-03-21 08:00 | 23d | 12777.7778 | 0 | 0 | -8077.7778 | 0 | 4700 | 0 | 1 | Finished | 5000 | 5000 | C2019-08 Labeling Machine.xlsx
11 | 7 | implementatie in productie, opstart en opleiding | 2018-01-23 08:00 | 2018-02-09 17:00 | 14d |  | 0 | 0 | 26.7857 | 3000 | 3000 | 2018-04-20 08:00 | 18d | 3857.1429 | 0 | 0 | 1542.8571 | 0 | 5400 | 0 | 1 | Finished | 3000 | 3000 | C2019-08 Labeling Machine.xlsx